## DESG PDC Allocation
Updated by: | Anuja | Updated on: |  | 2018-01-16 |  |  |  |  | Pole Data Cleansing | [8 empty] | AFR Load |  |  |  |  | PDC Cycle Time
SAM Name | SAM Code | Program | Gate | Category | Version | Overall Status | PDC Cleansing Type | PDC Input Date | PDC Allocated To? | Start Date | End Date | PDC QA Allocated To | Start Date | End Date | PDC Status | Actual Handover Date | Comments/ Issues/ Blockers | AFR Load Allocated to | Start Date | End Date | AFR Load Status | Comments/ Issues/ Blockers |  | Sr.No | Names |  | Dropdown Validation List
2CMO-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-03-27 | Swapna | 2017-03-27 | 2017-04-03 | Minu | 2017-04-03 | 2017-04-03 | Submitted | 2017-04-03 |  | Jainy | 2017-07-04 |  | OnHold |  |  | 1 | Jainy Joseph | Jainy Joseph
4MGA-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-03-27 | MYTHILY L | 2017-03-27 | 2017-04-03 | Anuja | 2017-04-03 | 2017-04-03 | Submitted | 2017-04-03 |  |  |  |  | Not Started |  |  | 2 | Asha Jacob | Asha Jacob
5EDW-67 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-03-21 | Zarinabegum | 2017-03-21 | 2017-04-03 | Minu | 2017-04-03 | 2017-04-03 | Submitted | 2017-04-03 |  |  |  |  | Not Started |  |  | 3 | Lisha Manuel | Lisha Manuel
4CPH-73 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-03-29 | Mythili S | 2017-03-29 | 2017-04-05 | Minu | 2017-04-05 | 2017-04-05 | Submitted | 2017-04-05 |  | Joshlee | 2017-07-07 |  | OnHold |  |  | 4 | Nina Sebastian | Nina Sebastian
2MEN-60 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-03-29 | Lisha | 2017-03-29 | 2017-04-05 | Minu | 2017-04-05 | 2017-04-05 | Submitted | 2017-04-05 |  | Joshlee | 2017-06-28 | 2017-07-06 | Posted |  |  | 5 | Sheeba C | Sheeba C
6MLO-65 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-03-31 | Zarinabegum | 2017-03-31 | 2017-04-06 | Minu | 2017-04-06 | 2017-04-06 | Submitted | 2017-04-06 |  | Jainy | 2017-07-05 | 2017-07-05 | Posted |  |  | 6 | Dhanya A | Dhanya A
2PET-67 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-03-29 | Jainy | 2017-03-29 | 2017-04-06 | Minu | 2017-04-06 | 2017-04-06 | Submitted | 2017-04-06 |  | Jainy | 2017-07-05 | 2017-07-06 | Posted |  |  | 7 | Jumana.M | Jumana.M
4CPH-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-03-28 | Fausia | 2017-03-28 | 2017-04-06 | Minu | 2017-04-06 | 2017-04-06 | Submitted | 2017-04-06 |  | Mythili S |  |  | OnHold |  |  | 8 | Brinson Bovas | Brinson Bovas
2SHA-60 | H-A-H | BAU | Pre-Design | Delta |  | Submitted |  | 2017-04-06 |  | 2017-04-06 | 2017-04-06 |  | 2017-04-06 | 2017-04-06 | Submitted | 2017-04-06 | [7 empty] | 9 | Varun | Varun
4MGA-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-05 | Sheeba | 2017-04-05 | 2017-04-07 | Minu | 2017-04-07 | 2017-04-07 | Submitted | 2017-04-07 |  |  |  |  | Not Started |  |  | 10 | Jyothish | Jyothish
3DNC-62 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-03-29 | Anila | 2017-03-29 | 2017-04-07 | Minu | 2017-04-07 | 2017-04-07 | Submitted | 2017-04-07 |  | Jainy | 2017-07-04 | 2017-07-04 | Posted |  |  | 11 | Fausia | Fausia
4SOP-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-03-29 | Asha | 2017-03-29 | 2017-04-07 | Minu | 2017-04-07 | 2017-04-07 | Submitted | 2017-04-07 |  |  |  |  | Not Started |  |  | 12 | Jyoti | Jyoti
2ASH-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-03-31 | Nina | 2017-03-31 | 2017-04-11 | Minu | 2017-04-11 | 2017-04-11 | Submitted | 2017-04-11 |  | Jainy | 2017-07-05 |  | OnHold |  |  | 13 | Joshlee | Joshlee
2PET-61 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-03 | Jainy | 2017-04-03 | 2017-04-11 | Minu | 2017-04-11 | 2017-04-11 | Submitted | 2017-04-11 |  | Jainy | 2017-07-06 | 2017-07-06 | Posted |  |  | 14 | Linda | Linda
2PET-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-03-31 | Sheeba | 2017-03-31 | 2017-04-11 | Minu | 2017-04-11 | 2017-04-11 | Submitted | 2017-04-11 |  |  |  |  | Not Started |  |  | 15 | Anila | Anila
5GLL-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-04 | Anila | 2017-04-04 | 2017-04-12 | Minu | 2017-04-12 | 2017-04-12 | Submitted | 2017-04-12 |  | Jainy | 2017-07-10 |  | OnHold |  |  | 16 | Mythili S | Mythili S
5HNL-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-03-31 | Mythily L | 2017-03-31 | 2017-04-12 | Anila | 2017-04-12 | 2017-04-12 | Submitted | 2017-04-12 |  | Mythili S | 2017-07-11 |  | OnHold |  |  | 17 | Minu | Minu
5BRI-68 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-03 | Mythili S | 2017-04-03 | 2017-04-13 | Minu | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13 |  | Jainy | 2017-06-30 | 2017-07-03 | Posted |  |  | 18 | Anuja | Anuja
3TYH-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-03-18 | Fausia | 2017-03-18 | 2017-04-13 | Minu | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13 |  | Joshlee | 2017-07-07 |  | OnHold |  |  | 19 | Mani | Mani
2CAS-61 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-03 | Lisha | 2017-04-03 | 2017-04-13 | Minu | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13 |  | Mythili S | 2017-07-06 | 2017-07-06 | Posted |  |  | 20 | Joju | Joju
3KGP-67 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-03-22 | Anila | 2017-03-22 | 2017-04-13 | Minu | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13 |  | Mythili S | 2017-07-05 |  | OnHold |  |  | 21 | Keerthi | Keerthi
5GLL-66 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2016-11-11 | Keerthi | 2016-11-11 | 2017-04-13 | Minu | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13 |  | Mythili S | 2017-07-10 | 2017-07-10 | Posted |  |  | 22 | Sree Lekshmi | Sree Lekshmi
5GNG-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-06 | Lisha | 2017-04-06 | 2017-04-13 | Minu | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13 |  |  |  |  | Not Started |  |  |  |  | NA
3SPL-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-13 |  | 2017-04-13 | 2017-04-13 |  | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13
3SCO-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-13 |  | 2017-04-13 | 2017-04-13 |  | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13
2NEW-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-13 |  | 2017-04-13 | 2017-04-13 |  | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13
3SOA-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-13 |  | 2017-04-13 | 2017-04-13 |  | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13 |  |  | 2017-07-10
3TYH-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-13 |  | 2017-04-13 | 2017-04-13 |  | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13
3BLB-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-13 |  | 2017-04-13 | 2017-04-13 |  | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13
2SEV-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-13 |  | 2017-04-13 | 2017-04-13 |  | 2017-04-13 | 2017-04-13 | Submitted | 2017-04-13
4FHL-20 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-06 | Asha | 2017-04-06 | 2017-04-18 | Anila | 2017-04-18 | 2017-04-18 | Submitted | 2017-04-18 |  |  |  |  | Not Started
2BON-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-06 | Sheeba | 2017-04-06 | 2017-04-18 | Minu | 2017-04-18 | 2017-04-18 | Submitted | 2017-04-18 |  |  |  |  | Not Started
2PNN-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-06 | Jainy | 2017-04-06 | 2017-04-19 | Minu | 2017-04-19 | 2017-04-19 | Submitted | 2017-04-19 |  |  |  |  | Not Started
2MIL-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-10 | Sheeba | 2017-04-10 | 2017-04-19 | Minu | 2017-04-19 | 2017-04-19 | Submitted | 2017-04-19 |  |  |  |  | Not Started
2FRE-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-06 | Zarinabegum | 2017-04-06 | 2017-04-19 | Minu | 2017-04-19 | 2017-04-19 | Submitted | 2017-04-19 |  |  |  |  | Not Started
2BON-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-10 | Nina | 2017-04-10 | 2017-04-19 | Anila | 2017-04-19 | 2017-04-19 | Submitted | 2017-04-19 |  |  |  |  | Not Started
4CHP-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-11 | Nina | 2017-04-11 | 2017-04-20 | Anila | 2017-04-20 | 2017-04-20 | Submitted | 2017-04-20 |  |  |  |  | Not Started
4ASH-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-11 | Lisha | 2017-04-11 | 2017-04-20 | Minu | 2017-04-20 | 2017-04-20 | Submitted | 2017-04-20 |  |  |  |  | Not Started
3NBA-68 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-04 | Fausia | 2017-04-04 | 2017-04-20 | Minu | 2017-04-20 | 2017-04-20 | Submitted | 2017-04-20 |  | Mythili S | 2017-07-06 |  | OnHold
4BLH-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-11 | Asha | 2017-04-11 | 2017-04-20 | Anila | 2017-04-20 | 2017-04-20 | Submitted | 2017-04-20 |  |  |  |  | Not Started
3BAY-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-03 | Swapna | 2017-04-03 | 2017-04-20 | Minu | 2017-04-20 | 2017-04-20 | Submitted | 2017-04-20 |  | Mythili S | 2017-07-11 |  | OnHold
2PNN-70 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-06 | Nina | 2017-04-06 | 2017-04-20 | Anila | 2017-04-20 | 2017-04-20 | Submitted | 2017-04-20 |  |  |  |  | Not Started
4SLA-68 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-10 | Mythili S | 2017-04-10 | 2017-04-20 | Minu | 2017-04-20 | 2017-04-20 | Submitted | 2017-04-20 |  |  |  |  | Not Started
4SLA-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-11 | Jainy | 2017-04-11 | 2017-04-21 | Anila | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21 |  |  |  |  | Not Started
3DAD-65 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-11 | FAUSIA | 2017-04-11 | 2017-04-21 | Jyothish | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21 |  | Jainy | 2017-07-12 | 2017-07-12 | Posted
4SLA-71 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-13 | Mythili S | 2017-04-13 | 2017-04-21 | Jyothish | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21 |  |  |  |  | Not Started
2BON-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-13 | Sheeba | 2017-04-13 | 2017-04-21 | Minu | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21 |  |  |  |  | Not Started
3TYH-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-21 |  | 2017-04-21 | 2017-04-21 |  | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21 |  |  | 2017-07-07
2PET-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-21 |  | 2017-04-21 | 2017-04-21 |  | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21
4BNP-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-21 |  | 2017-04-21 | 2017-04-21 |  | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21
2LIV-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-21 |  | 2017-04-21 | 2017-04-21 |  | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21
3DRP-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-21 |  | 2017-04-21 | 2017-04-21 |  | 2017-04-21 | 2017-04-21 | Submitted | 2017-04-21
3TNI-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-13 | Fausia | 2017-04-13 | 2017-04-24 | Anila | 2017-04-24 | 2017-04-24 | Submitted | 2017-04-24 |  |  |  |  | Not Started
2FRE-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-12 | Nina | 2017-04-12 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26 |  |  |  |  | Not Started
4BNP-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-26 |  | 2017-04-26 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26
4IAL-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-26 |  | 2017-04-26 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26 |  |  | 2017-06-30 | 2017-07-03
4CPH-70 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-26 |  | 2017-04-26 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26
5EDW-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-26 |  | 2017-04-26 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26
5GNG-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-26 |  | 2017-04-26 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26
5WES-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-26 |  | 2017-04-26 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26
5EDW-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-26 |  | 2017-04-26 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26
4MGA-71 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-26 |  | 2017-04-26 | 2017-04-26 |  | 2017-04-26 | 2017-04-26 | Submitted | 2017-04-26
2BAN-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-04 |  | 2017-04-04 | 2017-04-27 | Minu | 2017-04-27 | 2017-04-27 | Submitted | 2017-04-27 |  |  |  |  | Not Started
4SLA-74 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-27 |  | 2017-04-27 | 2017-04-27 |  | 2017-04-27 | 2017-04-27 | Submitted | 2017-04-27
3CLA-67 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-19 | Jainy | 2017-04-19 | 2017-04-28 | Anila | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  | Jainy | 2017-07-05 |  | OnHold
4SLA-70 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-17 | Jainy | 2017-04-17 | 2017-04-28 | Minu | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
3DAD-61 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-05 | Zarinabegum | 2017-04-05 | 2017-04-28 | Minu | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  | Jainy | 2017-07-11 | 2017-07-11 | Posted
2CRM-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-17 | Sheeba | 2017-04-17 | 2017-04-28 | Anila | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
5EDW-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-20 | Zarinabegum | 2017-04-20 | 2017-04-28 | Anila | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
2CRR-65 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2016-09-30 | Mythili S | 2016-09-30 | 2017-04-28 | Minu | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
3DAD-60 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-20 | MYTHILY L | 2017-04-20 | 2017-04-28 | Anila | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  | Mythili S | 2017-07-13 | 2017-07-13 | Posted
3SOA-62 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-20 | Nina | 2017-04-20 | 2017-04-28 | Anila | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  | Jainy | 2017-07-13 | 2017-07-13 | Posted
4SOP-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-22 | Lisha | 2017-04-22 | 2017-04-28 | Anila | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
2PNN-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-18 | MYTHILY L | 2017-04-18 | 2017-04-28 | Anila | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
3MIT-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-20 | Lisha | 2017-04-20 | 2017-04-28 | Minu | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  | Mythili S | 2017-07-12 |  | OnHold
4BLH-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-20 | Sheeba | 2017-04-20 | 2017-04-28 | Minu | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
3NAW-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-20 | FAUSIA | 2017-04-20 | 2017-04-28 | Minu | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started |  |  | 23 | NA
6CTO-61 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-24 | Jainy | 2017-04-24 | 2017-04-28 | Minu | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  | Mythili S | 2017-07-10 | 2017-07-10 | Posted
4OXE-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-18 | Asha | 2017-04-18 | 2017-04-28 | Minu | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
2CRM-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-17 | Lisha | 2017-04-17 | 2017-04-28 | Anila | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28 |  |  |  |  | Not Started
3SPL-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-04-28 |  | 2017-04-28 | 2017-04-28 |  | 2017-04-28 | 2017-04-28 | Submitted | 2017-04-28
2EAS-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-01 | Fausia | 2017-05-01 | 2017-05-01 | Brinson | 2017-05-01 | 2017-05-01 | Submitted | 2017-05-01
5HNL-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-19 | Swapna | 2017-04-19 | 2017-05-02 | Minu | 2017-05-02 | 2017-05-02 | Submitted | 2017-05-02 |  |  |  |  | Not Started
5HNL-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-21 | Mythili S | 2017-04-21 | 2017-05-02 | Anila | 2017-05-02 | 2017-05-02 | Submitted | 2017-05-02 |  |  |  |  | Not Started
2SHA-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-03 |  | 2017-05-03 | 2017-05-03 |  | 2017-05-03 | 2017-05-03 | Submitted | 2017-05-03 |  |  | 2017-06-30 | 2017-07-07
4CHP-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-21 | Asha | 2017-04-21 | 2017-05-04 | Minu | 2017-05-04 | 2017-05-04 | Submitted | 2017-05-04 |  |  |  |  | Not Started
3TYH-68 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-24 | Nina | 2017-04-24 | 2017-05-04 | Minu | 2017-05-04 | 2017-05-04 | Submitted | 2017-05-04 |  | Jainy | 2017-07-11 |  | OnHold
2MIL-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-27 | Swapna | 2017-04-27 | 2017-05-04 | Anila | 2017-05-04 | 2017-05-04 | Submitted | 2017-05-04 |  |  |  |  | Not Started
2CMO-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-24 | MYTHILY L | 2017-04-24 | 2017-05-05 | Anila | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Mythili S |  |  | OnHold
3SOA-64 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-27 | Jyoti | 2017-04-27 | 2017-05-05 | Anuja | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Joshlee | 2017-07-13 | 2017-07-13 | Posted
3ELT-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-22 | FAUSIA | 2017-04-22 | 2017-05-05 | Minu | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Mythili S | 2017-07-13 |  | OnHold
2PNN-68 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-26 | Asha | 2017-04-26 | 2017-05-05 | Minu | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  |  |  |  | Not Started
2EPP-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-27 | Sheeba | 2017-04-27 | 2017-05-05 | Anila | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Jainy | 2017-07-13 |  | OnHold
2SEV-60 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-27 | Lisha | 2017-04-27 | 2017-05-05 | Anuja | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Joshlee | 2017-07-13 |  | Posted
5BRI-71 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-24 | Jyoti | 2017-04-24 | 2017-05-05 | Minu | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  |  |  |  | Not Started
2ENG-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-03 | Swapna | 2017-05-03 | 2017-05-05 | Anila | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Mythili S | 2017-07-11 |  | OnHold
2ASH-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-03 | Nina | 2017-05-03 | 2017-05-05 | Minu | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  |  |  |  | Not Started
4SOP-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-21 | Sheeba | 2017-04-21 | 2017-05-05 | Minu | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  |  |  |  | Not Started
3KYG-65 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-26 | Minu | 2017-04-26 | 2017-05-05 | Minu | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  |  |  |  | Not Started
2BAN-69 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-05-02 | Jainy | 2017-05-02 | 2017-05-05 | Jyothish | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Jainy | 2017-07-06 | 2017-07-06 | Posted
6SUB-63 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-25 | Asha | 2017-04-25 | 2017-05-05 | Anila | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Joshlee | 2017-07-14 | 2017-07-14 | Posted
6CTO-64 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-25 | Sheeba | 2017-04-25 | 2017-05-05 | Anila | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  | Jainy | 2017-07-10 | 2017-07-10 | Posted
2CRM-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-03 | Jainy | 2017-05-03 | 2017-05-05 | Jyothish | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05 |  |  |  |  | Not Started
3ELT-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-05 |  | 2017-05-05 | 2017-05-05 |  | 2017-05-05 | 2017-05-05 | Submitted | 2017-05-05
4WRN-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-03 | Jyoti | 2017-05-03 | 2017-05-08 | Minu | 2017-05-08 | 2017-05-08 | Submitted | 2017-05-08 |  |  |  |  | Not Started
4BLH-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-27 | Zarinabegum | 2017-04-27 | 2017-05-08 | Minu | 2017-05-08 | 2017-05-08 | Submitted | 2017-05-08 |  |  |  |  | Not Started
4SOP-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-28 | Manikandan K | 2017-04-28 | 2017-05-08 | Anila | 2017-05-08 | 2017-05-08 | Submitted | 2017-05-08 |  |  |  |  | Not Started
4IAL-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-03 | FAUSIA | 2017-05-03 | 2017-05-08 | Minu | 2017-05-08 | 2017-05-08 | Submitted | 2017-05-08 |  |  |  |  | Not Started
3KGP-60 | H-A-H | HAC | Pre-Design | PDC |  | Posted |  | 2017-04-25 | Jainy | 2017-04-25 | 2017-05-08 | Anila | 2017-05-08 | 2017-05-08 | Submitted | 2017-05-08 |  | Mythili S | 2017-07-14 | 2017-07-17 | Posted
5EZB-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-08 |  | 2017-05-08 | 2017-05-08 |  | 2017-05-08 | 2017-05-08 | Submitted | 2017-05-08
5GLL-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-08 |  | 2017-05-08 | 2017-05-08 |  | 2017-05-08 | 2017-05-08 | Submitted | 2017-05-08 |  |  | 2017-07-10
3NBA-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-08 |  | 2017-05-08 | 2017-05-08 |  | 2017-05-08 | 2017-05-08 | Submitted | 2017-05-08 |  |  | 2017-07-06
4CPH-72 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-04 | Asha | 2017-05-04 | 2017-05-09 | Minu | 2017-05-09 | 2017-05-09 | Submitted | 2017-05-09 |  |  |  |  | Not Started
4WRN-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-04 | Sheeba | 2017-05-04 | 2017-05-09 | Minu | 2017-05-09 | 2017-05-09 | Submitted | 2017-05-09 |  |  |  |  | Not Started
4BLH-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-04-27 | Mythili S | 2017-04-27 | 2017-05-09 | Anila | 2017-05-09 | 2017-05-09 | Submitted | 2017-05-09 |  |  |  |  | Not Started
4ASH-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2016-07-25 | Praveen | 2016-07-25 | 2017-05-09 | Minu | 2017-05-09 | 2017-05-09 | Submitted | 2017-05-09 |  |  |  |  | Not Started
4MGA-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-04 | Swapna | 2017-05-04 | 2017-05-10 | Minu | 2017-05-10 | 2017-05-10 | Submitted | 2017-05-10 |  |  |  |  | Not Started
2UND-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-04 | Jainy | 2017-05-04 | 2017-05-10 | Anila | 2017-05-10 | 2017-05-10 | Submitted | 2017-05-10 |  |  |  |  | Not Started
2BAN-67 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-05 | Mythili S | 2017-05-05 | 2017-05-10 | Minu | 2017-05-10 | 2017-05-10 | Submitted | 2017-05-10 |  |  |  |  | Not Started
2MOS-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-08 | Minu | 2017-05-08 | 2017-05-10 | Minu | 2017-05-10 | 2017-05-10 | Submitted | 2017-05-10 |  |  |  |  | Not Started
4CHD-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-06 | Asha | 2017-05-06 | 2017-05-10 | Anila | 2017-05-10 | 2017-05-10 | Submitted | 2017-05-10 |  |  |  |  | Not Started
6SUB-65 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-04 | MYTHILY L | 2017-05-04 | 2017-05-10 | Anila | 2017-05-10 | 2017-05-10 | Submitted | 2017-05-10 |  |  |  |  | Not Started
2CRR-73 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-10 |  | 2017-05-10 | 2017-05-10 |  | 2017-05-10 | 2017-05-10 | Submitted | 2017-05-10
2BON-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-10 |  | 2017-05-10 | 2017-05-10 |  | 2017-05-10 | 2017-05-10 | Submitted | 2017-05-10
3SOA-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-06 | FAUSIA | 2017-05-06 | 2017-05-11 | Anila | 2017-05-11 | 2017-05-11 | Submitted | 2017-05-11 |  |  |  |  | Not Started
3GLI-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-08 | Asha | 2017-05-08 | 2017-05-11 |  | 2017-05-11 | 2017-05-11 | Submitted | 2017-05-11 |  |  |  |  | Not Started
3HGT-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-11 |  | 2017-05-11 | 2017-05-11 |  | 2017-05-11 | 2017-05-11 | Submitted | 2017-05-11
5BRI-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-11 |  | 2017-05-11 | 2017-05-11 |  | 2017-05-11 | 2017-05-11 | Submitted | 2017-05-11 |  |  | 2017-06-30 | 2017-07-03
4IAL-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-11 |  | 2017-05-11 | 2017-05-11 |  | 2017-05-11 | 2017-05-11 | Submitted | 2017-05-11 |  |  | 2017-06-30 | 2017-07-03
4BLH-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-11 |  | 2017-05-11 | 2017-05-11 |  | 2017-05-11 | 2017-05-11 | Submitted | 2017-05-11 |  |  | 2017-07-07 | 2017-07-07
2BAN-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-11 |  | 2017-05-11 | 2017-05-11 |  | 2017-05-11 | 2017-05-11 | Submitted | 2017-05-11 |  |  | 2017-06-30
3KGP-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-11 |  | 2017-05-11 | 2017-05-11 |  | 2017-05-11 | 2017-05-11 | Submitted | 2017-05-11 |  |  | 2017-07-05
5BRI-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-04 | Nina | 2017-05-04 | 2017-05-12 | Anila | 2017-05-12 | 2017-05-12 | Submitted | 2017-05-12 |  |  |  |  | Not Started
3NCO-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-06 | MYTHILY L | 2017-05-06 | 2017-05-12 | Minu | 2017-05-12 | 2017-05-12 | Submitted | 2017-05-12 |  |  |  |  | Not Started
2EPP-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-04 | Zarinabegum | 2017-05-04 | 2017-05-14 | Anila | 2017-05-14 | 2017-05-14 | Submitted | 2017-05-14 |  | Jainy | 2017-07-14 |  | OnHold
2BAN-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-06 | Asha | 2017-05-06 | 2017-05-15 | Anila | 2017-05-15 | 2017-05-15 | Submitted | 2017-05-15 |  |  |  |  | Not Started
2CAS-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-08 | Jyoti | 2017-05-08 | 2017-05-15 | Anuja | 2017-05-15 | 2017-05-15 | Submitted | 2017-05-15 |  |  |  |  | Not Started
2BAN-68 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-08 | Lisha | 2017-05-08 | 2017-05-15 | Anila | 2017-05-15 | 2017-05-15 | Submitted | 2017-05-15 |  |  |  |  | Not Started
2BAN-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-09 | Swapna | 2017-05-09 | 2017-05-15 | Anila | 2017-05-15 | 2017-05-15 | Submitted | 2017-05-15 |  |  |  |  | Not Started
2BAL-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-08 | Sheeba | 2017-05-08 | 2017-05-15 | Minu | 2017-05-15 | 2017-05-15 | Submitted | 2017-05-15 |  |  |  |  | Not Started
2ROS-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-11 | Nina | 2017-05-11 | 2017-05-15 | Minu | 2017-05-15 | 2017-05-15 | Submitted | 2017-05-15 |  |  |  |  | Not Started
6GIR-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-10 | LINDA | 2017-05-10 | 2017-05-15 | Minu | 2017-05-15 | 2017-05-15 | Submitted | 2017-05-15 |  |  |  |  | Not Started
2UND-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-11 | Jyoti | 2017-05-11 | 2017-05-16 | Anila | 2017-05-16 | 2017-05-16 | Submitted | 2017-05-16 |  |  |  |  | Not Started
2ASH-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-10 | Joshlee | 2017-05-10 | 2017-05-16 | Anila | 2017-05-16 | 2017-05-16 | Submitted | 2017-05-16 |  |  |  |  | Not Started
4SOP-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-16 |  | 2017-05-16 | 2017-05-16 |  | 2017-05-16 | 2017-05-16 | Submitted | 2017-05-16
2LIV-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-16 |  | 2017-05-16 | 2017-05-16 |  | 2017-05-16 | 2017-05-16 | Submitted | 2017-05-16
6SUB-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-15 | FAUSIA | 2017-05-15 | 2017-05-17 | Anila | 2017-05-17 | 2017-05-17 | Submitted | 2017-05-17 |  |  |  |  | Not Started
3NBA-69 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-06 | Mythili S | 2017-05-06 | 2017-05-17 | Anila | 2017-05-17 | 2017-05-17 | Submitted | 2017-05-17 |  |  |  |  | Not Started
2NEW-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-10 | SHEEBA | 2017-05-10 | 2017-05-17 | Anila | 2017-05-17 | 2017-05-17 | Submitted | 2017-05-17 |  |  |  |  | Not Started
3CAU-69 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-11 | Asha | 2017-05-11 | 2017-05-17 | Minu | 2017-05-17 | 2017-05-17 | Submitted | 2017-05-17 |  |  |  |  | Not Started
3TYH-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-17 |  | 2017-05-17 | 2017-05-17 |  | 2017-05-17 | 2017-05-17 | Submitted | 2017-05-17
2MIL-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-17 |  | 2017-05-17 | 2017-05-17 |  | 2017-05-17 | 2017-05-17 | Submitted | 2017-05-17
2SEV-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-15 | Mythili S | 2017-05-15 | 2017-05-18 | Minu | 2017-05-18 | 2017-05-18 | Submitted | 2017-05-18 |  |  |  |  | Not Started
3BGO-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-11 | Swapna | 2017-05-11 | 2017-05-18 | Anila | 2017-05-18 | 2017-05-18 | Submitted | 2017-05-18 |  |  |  |  | Not Started
5HNL-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-08 | Jainy | 2017-05-08 | 2017-05-18 | Minu | 2017-05-18 | 2017-05-18 | Submitted | 2017-05-18 |  |  |  |  | Not Started
3SOA-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-18 |  | 2017-05-18 | 2017-05-18 |  | 2017-05-18 | 2017-05-18 | Submitted | 2017-05-18 |  |  | 2017-07-13 | 2017-07-13
4BNP-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-18 |  | 2017-05-18 | 2017-05-18 |  | 2017-05-18 | 2017-05-18 | Submitted | 2017-05-18
3HGT-70 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-18 |  | 2017-05-18 | 2017-05-18 |  | 2017-05-18 | 2017-05-18 | Submitted | 2017-05-18
4CPH-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-18 |  | 2017-05-18 | 2017-05-18 |  | 2017-05-18 | 2017-05-18 | Submitted | 2017-05-18
3NBA-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-12 | Nina | 2017-05-12 | 2017-05-19 | Anila | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  |  |  | Not Started
3CTA-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2016-09-08 | Zarinabegum | 2016-09-08 | 2017-05-19 | Minu | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  |  |  | Not Started
3NCO-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2016-11-09 | Minu | 2016-11-09 | 2017-05-19 | Minu | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  |  |  | Not Started
3SCO-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-16 | Zarinabegum | 2017-05-16 | 2017-05-19 | Minu | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  |  |  | Not Started
3RWO-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-16 | Jainy | 2017-05-16 | 2017-05-19 | Minu | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  |  |  | Not Started
5HNL-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-16 | FAUSIA | 2017-05-16 | 2017-05-19 | Anila | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  |  |  | Not Started
3NCO-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2016-11-01 | Mythily L | 2016-11-01 | 2017-05-19 | Minu | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  |  |  | Not Started
3DNC-67 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-16 | Lisha | 2017-05-16 | 2017-05-19 | Minu | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  |  |  | Not Started
2LIV-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-19 |  | 2017-05-19 | 2017-05-19 |  | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19
5HNL-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-19 |  | 2017-05-19 | 2017-05-19 |  | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19
5HNL-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-19 |  | 2017-05-19 | 2017-05-19 |  | 2017-05-19 | 2017-05-19 | Submitted | 2017-05-19 |  |  | 2017-07-11
5BRI-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-11 | MYTHILY L | 2017-05-11 | 2017-05-22 | Anila | 2017-05-22 | 2017-05-22 | Submitted | 2017-05-22 |  |  |  |  | Not Started
3MLN-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-16 | Jyoti | 2017-05-16 | 2017-05-22 | Minu | 2017-05-22 | 2017-05-22 | Submitted | 2017-05-22 |  |  |  |  | Not Started
3KGP-65 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-17 | FAUSIA | 2017-05-17 | 2017-05-22 | Minu | 2017-05-22 | 2017-05-22 | Submitted | 2017-05-22 |  |  |  |  | Not Started
3BGO-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-17 | Sheeba | 2017-05-17 | 2017-05-22 | Anila | 2017-05-22 | 2017-05-22 | Submitted | 2017-05-22 |  |  |  |  | Not Started
3HGT-74 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2016-11-21 | Zarinabegum | 2016-11-21 | 2017-05-22 | Minu | 2017-05-22 | 2017-05-22 | Submitted | 2017-05-22 |  |  |  |  | Not Started
5SAL-69 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-17 | Swapna | 2017-05-17 | 2017-05-22 | Anila | 2017-05-22 | 2017-05-22 | Submitted | 2017-05-22 |  |  |  |  | Not Started
3GLI-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-17 | Joshlee | 2017-05-17 | 2017-05-22 | Anila | 2017-05-22 | 2017-05-22 | Submitted | 2017-05-22 |  |  |  |  | Not Started
3BLB-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-18 | Swapna | 2017-05-18 | 2017-05-23 | Anila | 2017-05-23 | 2017-05-23 | Submitted | 2017-05-23 |  |  |  |  | Not Started
3NCO-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-22 | Sheeba | 2017-05-22 | 2017-05-23 | Anila | 2017-05-23 | 2017-05-23 | Submitted | 2017-05-23 |  |  |  |  | Not Started
3BLB-67 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-18 | Mythili S | 2017-05-18 | 2017-05-24 | Minu | 2017-05-24 | 2017-05-24 | Submitted | 2017-05-24 |  |  |  |  | Not Started
3SOA-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-19 | Linda | 2017-05-19 | 2017-05-24 | Anila | 2017-05-24 | 2017-05-24 | Submitted | 2017-05-24 |  |  |  |  | Not Started
3MIT-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-19 | MYTHILY L | 2017-05-19 | 2017-05-24 | Minu | 2017-05-24 | 2017-05-24 | Submitted | 2017-05-24 |  |  |  |  | Not Started
2CAS-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-23 | Jyoti | 2017-05-23 | 2017-05-24 | Minu | 2017-05-24 | 2017-05-24 | Submitted | 2017-05-24 |  |  |  |  | Not Started
3ELT-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-24 |  | 2017-05-24 | 2017-05-24 |  | 2017-05-24 | 2017-05-24 | Submitted | 2017-05-24 |  |  | 2017-07-13
3NBA-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-24 |  | 2017-05-24 | 2017-05-24 |  | 2017-05-24 | 2017-05-24 | Submitted | 2017-05-24 |  |  | 2017-07-06
2SEF-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-24 |  | 2017-05-24 | 2017-05-24 |  | 2017-05-24 | 2017-05-24 | Submitted | 2017-05-24
4CPH-73 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-24 |  | 2017-05-24 | 2017-05-24 |  | 2017-05-24 | 2017-05-24 | Submitted | 2017-05-24 |  |  | 2017-07-07
3MIT-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-18 | Nina | 2017-05-18 | 2017-05-25 | Anila | 2017-05-25 | 2017-05-25 | Submitted | 2017-05-25 |  |  |  |  | Not Started
3RWO-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-19 | Zarinabegum | 2017-05-19 | 2017-05-25 | Minu | 2017-05-25 | 2017-05-25 | Submitted | 2017-05-25 |  |  |  |  | Not Started
4BLH-67 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-19 | Asha | 2017-05-19 | 2017-05-25 | Minu | 2017-05-25 | 2017-05-25 | Submitted | 2017-05-25 |  |  |  |  | Not Started
2CMO-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-20 | Sheeba | 2017-05-20 | 2017-05-25 | Anila | 2017-05-25 | 2017-05-25 | Submitted | 2017-05-25 |  |  |  |  | Not Started
2CAS-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-23 | Swapna | 2017-05-23 | 2017-05-25 | Anila | 2017-05-25 | 2017-05-25 | Submitted | 2017-05-25 |  |  |  |  | Not Started
6SUB-67 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-04-25 | Minu | 2017-04-25 | 2017-05-25 | Anila | 2017-05-25 | 2017-05-25 | Submitted | 2017-05-25 |  |  |  |  | Not Started
2BAL-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-23 | Joshlee | 2017-05-23 | 2017-05-25 | Anila | 2017-05-25 | 2017-05-25 | Submitted | 2017-05-25 |  |  |  |  | Not Started
6GIR-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-17 | Linda | 2017-05-17 | 2017-05-25 | Minu | 2017-05-25 | 2017-05-25 | Submitted | 2017-05-25 |  |  |  |  | Not Started
2BAN-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-23 | Mythili S | 2017-05-23 | 2017-05-29 | Anila | 2017-05-29 | 2017-05-29 | Submitted | 2017-05-29 |  |  |  |  | Not Started
2ING-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-24 | Swapna | 2017-05-24 | 2017-05-29 | Minu | 2017-05-29 | 2017-05-29 | Submitted | 2017-05-29 |  |  |  |  | Not Started
6KSL-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-18 | Linda | 2017-05-18 | 2017-05-29 | Minu | 2017-05-29 | 2017-05-29 | Submitted | 2017-05-29 |  |  |  |  | Not Started
6KSL-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-18 | Joshlee | 2017-05-18 | 2017-05-29 | Minu | 2017-05-29 | 2017-05-29 | Submitted | 2017-05-29 |  |  |  |  | Not Started
3BOX-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-24 | Zarinabegum | 2017-05-24 | 2017-05-30 | Anila | 2017-05-30 | 2017-05-30 | Submitted | 2017-05-30 |  |  |  |  | Not Started
2EPP-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-23 | Sheeba | 2017-05-23 | 2017-05-30 | Anila | 2017-05-30 | 2017-05-30 | Submitted | 2017-05-30 |  |  |  |  | Not Started
2BAL-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-24 | Linda | 2017-05-24 | 2017-05-30 | Minu | 2017-05-30 | 2017-05-30 | Submitted | 2017-05-30 |  |  |  |  | Not Started
6GIR-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-24 | Asha | 2017-05-24 | 2017-05-30 | Anila | 2017-05-30 | 2017-05-30 | Submitted | 2017-05-30 |  |  |  |  | Not Started
2ROS-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-24 | MYTHILY L | 2017-05-24 | 2017-05-30 | Minu | 2017-05-30 | 2017-05-30 | Submitted | 2017-05-30 |  |  |  |  | Not Started
2BAN-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-30 |  | 2017-05-30 | 2017-05-30 |  | 2017-05-30 | 2017-05-30 | Submitted | 2017-05-30
3RWO-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-24 | Jainy | 2017-05-24 | 2017-05-31 | Anila | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  |  |  | Not Started
3SOA-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-24 | Jyoti | 2017-05-24 | 2017-05-31 | Minu | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  |  |  | Not Started
2ENG-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-24 | FAUSIA | 2017-05-24 | 2017-05-31 | Minu | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  |  |  | Not Started
2PET-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-25 | Swapna | 2017-05-25 | 2017-05-31 | Minu | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  |  |  | Not Started
3NCO-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-25 | Nina | 2017-05-25 | 2017-05-31 | Minu | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  |  |  | Not Started
3CAU-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-30 | Minu | 2017-05-30 | 2017-05-31 | Minu | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  |  |  | Not Started
3KYG-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-25 | Jyoti | 2017-05-25 | 2017-05-31 | Minu | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  |  |  | Not Started
2NEW-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-31 |  | 2017-05-31 | 2017-05-31 |  | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31
2NEW-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-31 |  | 2017-05-31 | 2017-05-31 |  | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31
3KGP-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-31 |  | 2017-05-31 | 2017-05-31 |  | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  | 2017-07-14 | 2017-07-17
2SEV-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-05-31 |  | 2017-05-31 | 2017-05-31 |  | 2017-05-31 | 2017-05-31 | Submitted | 2017-05-31 |  |  | 2017-07-13
4SOP-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-02 |  | 2017-06-02 | 2017-06-02 |  | 2017-06-02 | 2017-06-02 | Submitted | 2017-06-02
5BRI-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-02 |  | 2017-06-02 | 2017-06-02 |  | 2017-06-02 | 2017-06-02 | Submitted | 2017-06-02
4WRN-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-02 |  | 2017-06-02 | 2017-06-02 |  | 2017-06-02 | 2017-06-02 | Submitted | 2017-06-02
3NBA-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-02 |  | 2017-06-02 | 2017-06-02 |  | 2017-06-02 | 2017-06-02 | Submitted | 2017-06-02
3RWO-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-02 |  | 2017-06-02 | 2017-06-02 |  | 2017-06-02 | 2017-06-02 | Submitted | 2017-06-02
3CTA-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-02 |  | 2017-06-02 | 2017-06-02 |  | 2017-06-02 | 2017-06-02 | Submitted | 2017-06-02
2EPP-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-02 |  | 2017-06-02 | 2017-06-02 |  | 2017-06-02 | 2017-06-02 | Submitted | 2017-06-02 |  |  | 2017-07-14
3NCO-68 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-26 | MYTHILY L | 2017-05-26 | 2017-06-05 | Minu | 2017-06-05 | 2017-06-05 | Submitted | 2017-06-05 |  |  |  |  | Not Started
4IAL-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-26 | Lisha | 2017-05-26 | 2017-06-05 | Minu | 2017-06-05 | 2017-06-05 | Submitted | 2017-06-05 |  |  |  |  | Not Started
4CHD-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-26 | Jyoti | 2017-05-26 | 2017-06-05 | Anila | 2017-06-05 | 2017-06-05 | Submitted | 2017-06-05 |  |  |  |  | Not Started
3BNT-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-29 | Swapna | 2017-05-29 | 2017-06-05 | Minu | 2017-06-05 | 2017-06-05 | Submitted | 2017-06-05 |  |  |  |  | Not Started
2CAS-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-05 |  | 2017-06-05 | 2017-06-05 |  | 2017-06-05 | 2017-06-05 | Submitted | 2017-06-05
4MGA-72 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Jyothish | 2017-06-06 | 2017-06-06 | Minu | 2017-06-06 | 2017-06-06 | Submitted | 2017-06-06 |  |  |  |  | Not Started
4MGA-70 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Jyothish | 2017-06-06 | 2017-06-06 | Minu | 2017-06-06 | 2017-06-06 | Submitted | 2017-06-06 |  |  |  |  | Not Started
4MGA-68 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Jyothish | 2017-06-06 | 2017-06-06 | Minu | 2017-06-06 | 2017-06-06 | Submitted | 2017-06-06 |  |  |  |  | Not Started
4CPH-69 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Jyothish | 2017-06-06 | 2017-06-06 | Anila | 2017-06-06 | 2017-06-06 | Submitted | 2017-06-06 |  |  |  |  | Not Started
4AGV-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-19 | Sheeba | 2017-06-19 | 2017-07-03 | Minu | 2017-07-03 | 2017-07-03 | Submitted | 2017-07-03 |  |  |  |  | Not Started
2ASH-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-06 |  | 2017-06-06 | 2017-06-06 |  | 2017-06-06 | 2017-06-06 | Submitted | 2017-06-06
2CRR-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-06 |  | 2017-06-06 | 2017-06-06 |  | 2017-06-06 | 2017-06-06 | Submitted | 2017-06-06
2ROS-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-06 |  | 2017-06-06 | 2017-06-06 |  | 2017-06-06 | 2017-06-06 | Submitted | 2017-06-06
4MGA-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-30 | Swapna | 2017-05-30 | 2017-06-07 | Minu | 2017-06-07 | 2017-06-07 | Submitted | 2017-06-07 |  |  |  |  | Not Started
4CHD-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-31 | Sheeba | 2017-05-31 | 2017-06-07 | Minu | 2017-06-07 | 2017-06-07 | Submitted | 2017-06-07 |  |  |  |  | Not Started
3KGP-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-07 |  | 2017-06-07 | 2017-06-07 |  | 2017-06-07 | 2017-06-07 | Submitted | 2017-06-07 |  |  | 2017-07-14 | 2017-07-17
4CHD-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-31 | FAUSIA | 2017-05-31 | 2017-06-08 | Anila | 2017-06-08 | 2017-06-08 | Submitted | 2017-06-08 |  |  |  |  | Not Started
4CHD-01 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-31 | Joshlee | 2017-05-31 | 2017-06-08 |  | 2017-06-08 | 2017-06-08 | Submitted | 2017-06-08 |  |  |  |  | Not Started
3NCO-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-08 |  | 2017-06-08 | 2017-06-08 |  | 2017-06-08 | 2017-06-08 | Submitted | 2017-06-08
4BLH-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-08 |  | 2017-06-08 | 2017-06-08 |  | 2017-06-08 | 2017-06-08 | Submitted | 2017-06-08
4SLA-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
4SLA-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
4SLA-73 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
5GNG-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
5GUG-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
3ELT-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
3KGP-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
3NBA-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
3NBA-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
3NBA-71 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
3OAK-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
3SPL-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-09 |  | 2017-06-09 | 2017-06-09 |  | 2017-06-09 | 2017-06-09 | Submitted | 2017-06-09
2SEV-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-05-31 | Linda | 2017-05-31 | 2017-06-13 | Anila | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13 |  |  |  |  | Not Started
2ASH-68 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-05-31 | Lisha | 2017-05-31 | 2017-06-13 | Anila | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13 |  |  |  |  | Not Started
5HNL-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-13 |  | 2017-06-13 | 2017-06-13 |  | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13
3BGO-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-13 |  | 2017-06-13 | 2017-06-13 |  | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13
2CMO-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-13 |  | 2017-06-13 | 2017-06-13 |  | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13
4BLH-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-13 |  | 2017-06-13 | 2017-06-13 |  | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13
4BLH-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-13 |  | 2017-06-13 | 2017-06-13 |  | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13
3NCO-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-13 |  | 2017-06-13 | 2017-06-13 |  | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13
3NBA-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-13 |  | 2017-06-13 | 2017-06-13 |  | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13
5HNL-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-13 |  | 2017-06-13 | 2017-06-13 |  | 2017-06-13 | 2017-06-13 | Submitted | 2017-06-13
4BLH-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-01 | Jainy | 2017-06-01 | 2017-06-14 | Anila | 2017-06-14 | 2017-06-14 | Submitted | 2017-06-14 |  |  |  |  | Not Started
2ROS-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-01 | Joshlee | 2017-06-01 | 2017-06-14 | Minu | 2017-06-14 | 2017-06-14 | Submitted | 2017-06-14 |  |  |  |  | Not Started
2ASH-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-14 |  | 2017-06-14 | 2017-06-14 |  | 2017-06-14 | 2017-06-14 | Submitted | 2017-06-14
2UND-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-14 |  | 2017-06-14 | 2017-06-14 |  | 2017-06-14 | 2017-06-14 | Submitted | 2017-06-14
6GIR-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-02 | Sheeba | 2017-06-02 | 2017-06-15 | Anila | 2017-06-15 | 2017-06-15 | Submitted | 2017-06-15 |  |  |  |  | Not Started
2SHA-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-01 | Zarinabegum | 2017-06-01 | 2017-06-15 | Anila | 2017-06-15 | 2017-06-15 | Submitted | 2017-06-15 |  |  |  |  | Not Started
2MOS-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-01 | Swapna | 2017-06-01 | 2017-06-15 | Anila | 2017-06-15 | 2017-06-15 | Submitted | 2017-06-15 |  |  |  |  | Not Started
4EMP-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-15 |  | 2017-06-15 | 2017-06-15 |  | 2017-06-15 | 2017-06-15 | Submitted | 2017-06-15
3NCO-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-15 |  | 2017-06-15 | 2017-06-15 |  | 2017-06-15 | 2017-06-15 | Submitted | 2017-06-15
6GIR-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-15 |  | 2017-06-15 | 2017-06-15 |  | 2017-06-15 | 2017-06-15 | Submitted | 2017-06-15
4MGA-67 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-02 | Swapna | 2017-06-02 | 2017-06-16 | Anila | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16 |  |  |  |  | Not Started
4CPH-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-02 | Jainy | 2017-06-02 | 2017-06-16 | Minu | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16 |  |  |  |  | Not Started
4BNP-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-02 | FAUSIA | 2017-06-02 | 2017-06-16 | Minu | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16 |  |  |  |  | Not Started
5SAL-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16
2EAS-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16
2BAN-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16 |  |  | 2017-06-30
2BON-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16
2CRM-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16
2ENG-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16
3SOA-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16
3OAK-70 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16 |  |  | 2017-07-04 | 2017-07-06
3CTA-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16
3HGT-74 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-16 |  | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 2017-06-16 | Submitted | 2017-06-16
6SUB-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-19 |  | 2017-06-19 | 2017-06-19 |  | 2017-06-19 | 2017-06-19 | Submitted | 2017-06-19
5HNL-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-19 |  | 2017-06-19 | 2017-06-19 |  | 2017-06-19 | 2017-06-19 | Submitted | 2017-06-19
4AGV-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | FAUSIA | 2017-06-06 | 2017-06-20 | Minu | 2017-06-20 | 2017-06-20 | Submitted | 2017-06-20 |  |  |  |  | Not Started
3SCO-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-20 |  | 2017-06-20 | 2017-06-20 |  | 2017-06-20 | 2017-06-20 | Submitted | 2017-06-20
3HGT-74 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-20 |  | 2017-06-20 | 2017-06-20 |  | 2017-06-20 | 2017-06-20 | Submitted | 2017-06-20
6SUB-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-20 |  | 2017-06-20 | 2017-06-20 |  | 2017-06-20 | 2017-06-20 | Submitted | 2017-06-20
5HNL-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-20 |  | 2017-06-20 | 2017-06-20 |  | 2017-06-20 | 2017-06-20 | Submitted | 2017-06-20
3DAD-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Zarinabegum | 2017-06-06 | 2017-06-21 | Anila | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21 |  |  |  |  | Not Started
3BOX-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-13 | Zarinabegum | 2017-06-13 | 2017-06-21 | Anila | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21 |  |  |  |  | Not Started
3WIR-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-08 | Linda | 2017-06-08 | 2017-06-21 | Anila | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21 |  |  |  |  | Not Started
3SSN-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-08 | Swapna | 2017-06-08 | 2017-06-21 | Anila | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21 |  |  |  |  | Not Started
3MLN-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-08 | Asha | 2017-06-08 | 2017-06-21 | Anila | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21 |  |  |  |  | Not Started
3DAD-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-13 | Jainy | 2017-06-13 | 2017-06-21 | Anila | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21 |  |  |  |  | Not Started
4CHD-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-21 |  | 2017-06-21 | 2017-06-21 |  | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21
5BRI-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-21 |  | 2017-06-21 | 2017-06-21 |  | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21
5BRI-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-21 |  | 2017-06-21 | 2017-06-21 |  | 2017-06-21 | 2017-06-21 | Submitted | 2017-06-21
3DAD-67 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-13 | Lisha | 2017-06-13 | 2017-06-22 | Minu | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22 |  |  |  |  | Not Started
2PET-69 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-08 | Lisha | 2017-06-08 | 2017-06-22 | Anila | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22 |  |  |  |  | Not Started
2EPP-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Mythili S | 2017-06-06 | 2017-06-22 | Anila | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22 |  |  |  |  | Not Started
2BAL-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-13 | Sheeba | 2017-06-13 | 2017-06-22 | Minu | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22 |  |  |  |  | Not Started
2FRE-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-22 |  | 2017-06-22 | 2017-06-22 |  | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22
2EAS-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-22 |  | 2017-06-22 | 2017-06-22 |  | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22
2CRM-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-22 |  | 2017-06-22 | 2017-06-22 |  | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22
2MIL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-22 |  | 2017-06-22 | 2017-06-22 |  | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22
3BNT-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-22 |  | 2017-06-22 | 2017-06-22 |  | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22 |  |  | 2017-06-23 | 2017-06-28
3SPL-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-22 |  | 2017-06-22 | 2017-06-22 |  | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22
3SPL-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-22 |  | 2017-06-22 | 2017-06-22 |  | 2017-06-22 | 2017-06-22 | Submitted | 2017-06-22
2MEN-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-02 | Mythili S | 2017-06-02 | 2017-06-23 | Anila | 2017-06-23 | 2017-06-23 | Submitted | 2017-06-23 |  |  |  |  | Not Started
2EAS-68 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-13 | Asha | 2017-06-13 | 2017-06-23 | Anila | 2017-06-23 | 2017-06-23 | Submitted | 2017-06-23 |  |  |  |  | Not Started
2BAN-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-13 | Mythili S | 2017-06-13 | 2017-06-23 | Minu | 2017-06-23 | 2017-06-23 | Submitted | 2017-06-23 |  |  |  |  | Not Started
3BOX-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-07 | Nina | 2017-06-07 | 2017-06-26 | Anila | 2017-06-26 | 2017-06-26 | Submitted | 2017-06-26 |  |  |  |  | Not Started
3BOX-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-15 | Mythili S | 2017-06-15 | 2017-06-26 | Anila | 2017-06-26 | 2017-06-26 | Submitted | 2017-06-26 |  |  |  |  | Not Started
2EPP-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-14 | Swapna | 2017-06-14 | 2017-06-26 | Minu | 2017-06-26 | 2017-06-26 | Submitted | 2017-06-26 |  |  |  |  | Not Started
2ASH-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-14 | FAUSIA | 2017-06-14 | 2017-06-26 | Anila | 2017-06-26 | 2017-06-26 | Submitted | 2017-06-26 |  |  |  |  | Not Started
5MOD-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-26 |  | 2017-06-26 | 2017-06-26 |  | 2017-06-26 | 2017-06-26 | Submitted | 2017-06-26
3RWO-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-26 |  | 2017-06-26 | 2017-06-26 |  | 2017-06-26 | 2017-06-26 | Submitted | 2017-06-26
6SUB-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-02 | Joshlee | 2017-06-02 | 2017-06-27 | Anila | 2017-06-27 | 2017-06-27 | Submitted | 2017-06-27 |  |  |  |  | Not Started
6GIR-68 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-02 | Linda | 2017-06-02 | 2017-06-27 | Anila | 2017-06-27 | 2017-06-27 | Submitted | 2017-06-27 |  |  |  |  | Not Started
6GIR-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-02 | Joshlee | 2017-06-02 | 2017-06-27 | Anila | 2017-06-27 | 2017-06-27 | Submitted | 2017-06-27 |  |  |  |  | Not Started
3BOX-65 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-15 | Asha | 2017-06-15 | 2017-06-27 | Minu | 2017-06-27 | 2017-06-27 | Submitted | 2017-06-27 |  |  |  |  | Not Started
3TYH-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-15 | FAUSIA | 2017-06-15 | 2017-06-28 | Minu | 2017-06-28 | 2017-06-28 | Submitted | 2017-06-28 |  |  |  |  | Not Started
3OAK-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-15 | Sheeba | 2017-06-15 | 2017-06-28 | Minu | 2017-06-28 | 2017-06-28 | Submitted | 2017-06-28 |  |  |  |  | Not Started
3DNC-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-16 | Nina | 2017-06-16 | 2017-06-28 | Anila | 2017-06-28 | 2017-06-28 | Submitted | 2017-06-28 |  |  |  |  | Not Started
3BAY-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-16 | Swapna | 2017-06-16 | 2017-06-28 | Minu | 2017-06-28 | 2017-06-28 | Submitted | 2017-06-28 |  |  |  |  | Not Started
3NBA-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-28 |  | 2017-06-28 | 2017-06-28 |  | 2017-06-28 | 2017-06-28 | Submitted | 2017-06-28
2PET-71 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-16 | Zarinabegum | 2017-06-16 | 2017-06-29 | Anila | 2017-06-29 | 2017-06-29 | Submitted | 2017-06-29 |  |  |  |  | Not Started
2PET-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-17 | Mythili S | 2017-06-17 | 2017-06-29 | Anila | 2017-06-29 | 2017-06-29 | Submitted | 2017-06-29 |  |  |  |  | Not Started
2CAS-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-19 | Joju | 2017-06-19 | 2017-06-29 | Anila | 2017-06-29 | 2017-06-29 | Submitted | 2017-06-29 |  |  |  |  | Not Started
5BRI-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-29 |  | 2017-06-29 | 2017-06-29 |  | 2017-06-29 | 2017-06-29 | Submitted | 2017-06-29
3NBA-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-30 |  | 2017-06-30 | 2017-06-30 |  | 2017-06-30 | 2017-06-30 | Submitted | 2017-06-30
5BRI-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-30 |  | 2017-06-30 | 2017-06-30 |  | 2017-06-30 | 2017-06-30 | Submitted | 2017-06-30
3BLB-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-30 |  | 2017-06-30 | 2017-06-30 |  | 2017-06-30 | 2017-06-30 | Submitted | 2017-06-30
4AGV-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-06-30 |  | 2017-06-30 | 2017-06-30 |  | 2017-06-30 | 2017-06-30 | Submitted | 2017-06-30
4AGV-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-19 | FAUSIA | 2017-06-19 | 2017-07-03 | Minu | 2017-07-03 | 2017-07-03 | Submitted | 2017-07-03 |  |  |  |  | Not Started
2LIV-67 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-19 | Jainy | 2017-06-19 | 2017-07-03 | Minu | 2017-07-03 | 2017-07-03 | Submitted | 2017-07-03 |  |  |  |  | Not Started
2LIV-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Swapna | 2017-06-06 | 2017-07-03 | Minu | 2017-07-03 | 2017-07-03 | Submitted | 2017-07-03 |  |  |  |  | Not Started
4CHD-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-19 | Linda | 2017-06-19 | 2017-07-04 | Minu | 2017-07-04 | 2017-07-04 | Submitted | 2017-07-04 |  |  |  |  | Not Started
6SUB-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-05 | Asha | 2017-06-05 | 2017-07-05 | Minu | 2017-07-05 | 2017-07-05 | Submitted | 2017-07-05 |  |  |  |  | Not Started
2BAN-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-04 |  | 2017-07-04 | 2017-07-04 |  | 2017-07-04 | 2017-07-04 | Submitted | 2017-07-04
4SSB-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-19 | Asha | 2017-06-19 | 2017-07-05 | Minu | 2017-07-05 | 2017-07-05 | Submitted | 2017-07-05 |  |  |  |  | Not Started
4CPR-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-19 | Zarinabegum | 2017-06-19 | 2017-07-05 | Minu | 2017-07-05 | 2017-07-05 | Submitted | 2017-07-05 |  |  |  |  | Not Started
6CTO-20 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-05 | Sheeba | 2017-06-05 | 2017-07-06 | Minu | 2017-07-06 | 2017-07-06 | Submitted | 2017-07-06 |  |  |  |  | Not Started
3BGO-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-05 |  | 2017-07-05 | 2017-07-05 |  | 2017-07-05 | 2017-07-05 | Submitted | 2017-07-05
6GIR-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-05 |  | 2017-07-05 | 2017-07-05 |  | 2017-07-05 | 2017-07-05 | Submitted | 2017-07-05
3NCO-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-05 |  | 2017-07-05 | 2017-07-05 |  | 2017-07-05 | 2017-07-05 | Submitted | 2017-07-05
4SRW-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-19 | Mythili S | 2017-06-19 | 2017-07-06 | Minu | 2017-07-06 | 2017-07-06 | Submitted | 2017-07-06 |  |  |  |  | Not Started
4SOP-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-20 | Swapna | 2017-06-20 | 2017-07-06 | Minu | 2017-07-06 | 2017-07-06 | Submitted | 2017-07-06 |  |  |  |  | Not Started
4SRW-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-20 | Lisha | 2017-06-20 | 2017-07-10 | Anila | 2017-07-10 | 2017-07-10 | Submitted | 2017-07-10 |  |  |  |  | Not Started
4BLH-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-06 |  | 2017-07-06 | 2017-07-06 |  | 2017-07-06 | 2017-07-06 | Submitted | 2017-07-06
2SEV-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-08 |  | 2017-07-08 | 2017-07-08 |  | 2017-07-08 | 2017-07-08 | Submitted | 2017-07-08
2BAL-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-08 |  | 2017-07-08 | 2017-07-08 |  | 2017-07-08 | 2017-07-08 | Submitted | 2017-07-08
3ELT-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-08 |  | 2017-07-08 | 2017-07-08 |  | 2017-07-08 | 2017-07-08 | Submitted | 2017-07-08
4CHD-21 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-20 | MYTHILY L | 2017-06-20 | 2017-07-10 | Anila | 2017-07-10 | 2017-07-10 | Submitted | 2017-07-10 |  |  |  |  | Not Started
4AGV-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-20 | Nina | 2017-06-20 | 2017-07-10 | Anila | 2017-07-10 | 2017-07-10 | Submitted | 2017-07-10 |  |  |  |  | Not Started
4ABC-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-22 | FAUSIA | 2017-06-22 | 2017-07-10 | Anila | 2017-07-10 | 2017-07-10 | Submitted | 2017-07-10 |  |  |  |  | Not Started
4WTF-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-22 | Swapna | 2017-06-22 | 2017-07-11 | Anila | 2017-07-11 | 2017-07-11 | Submitted | 2017-07-11 |  |  |  |  | Not Started
4OXE-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-23 | Sheeba | 2017-06-23 | 2017-07-11 | Anila | 2017-07-11 | 2017-07-11 | Submitted | 2017-07-11 |  |  |  |  | Not Started
4APL-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-28 | Joju | 2017-06-28 | 2017-07-11 | Anila | 2017-07-11 | 2017-07-11 | Submitted | 2017-07-11 |  |  |  |  | Not Started
4AAR-63 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-28 | Asha | 2017-06-28 | 2017-07-11 | Minu | 2017-07-11 | 2017-07-11 | Submitted | 2017-07-11 |  |  |  |  | Not Started
6MLO-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Nina | 2017-06-06 | 2017-07-12 | Anila | 2017-07-12 | 2017-07-12 | Submitted | 2017-07-12 |  |  |  |  | Not Started
3KYG-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-11 |  | 2017-07-11 | 2017-07-11 |  | 2017-07-11 | 2017-07-11 | Submitted | 2017-07-11
3OAK-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-11 |  | 2017-07-11 | 2017-07-11 |  | 2017-07-11 | 2017-07-11 | Submitted | 2017-07-11
4OXE-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-27 | Joju | 2017-06-27 | 2017-07-12 | Anila | 2017-07-12 | 2017-07-12 | Submitted | 2017-07-12 |  |  |  |  | Not Started
4CUR-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-27 | Zarinabegum | 2017-06-27 | 2017-07-12 | Anila | 2017-07-12 | 2017-07-12 | Submitted | 2017-07-12 |  |  |  |  | Not Started
4CPB-22 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-28 | Linda | 2017-06-28 | 2017-07-12 | Anila | 2017-07-12 | 2017-07-12 | Submitted | 2017-07-12 |  |  |  |  | Not Started
2NEW-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-29 | Lisha | 2017-06-29 | 2017-07-13 | Anila | 2017-07-13 | 2017-07-13 | Submitted | 2017-07-13 |  |  |  |  | Not Started
3BGO-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-12 |  | 2017-07-12 | 2017-07-12 |  | 2017-07-12 | 2017-07-12 | Submitted | 2017-07-12
3SPL-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-12 |  | 2017-07-12 | 2017-07-12 |  | 2017-07-12 | 2017-07-12 | Submitted | 2017-07-12
3CAU-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-12 |  | 2017-07-12 | 2017-07-12 |  | 2017-07-12 | 2017-07-12 | Submitted | 2017-07-12
2BON-67 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-29 | Nina | 2017-06-29 | 2017-07-13 | Anila | 2017-07-13 | 2017-07-13 | Submitted | 2017-07-13 |  |  |  |  | Not Started
2BON-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-30 | Sheeba | 2017-06-30 | 2017-07-13 | Anila | 2017-07-13 | 2017-07-13 | Submitted | 2017-07-13 |  |  |  |  | Not Started
3CAU-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-12 | Linda | 2017-07-24 | 2017-07-25 | Anila | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-14 |  |  |  |  | Not Started
2ING-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-13 |  | 2017-07-13 | 2017-07-13 |  | 2017-07-13 | 2017-07-13 | Submitted | 2017-07-13
3SSN-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-28 | Zarinabegum | 2017-06-28 | 2017-07-17 | Anila | 2017-07-17 | 2017-07-17 | Submitted | 2017-07-17 |  |  |  |  | Not Started
3NBA-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-14 |  | 2017-07-14 | 2017-07-14 |  | 2017-07-14 | 2017-07-14 | Submitted | 2017-07-14
3NCO-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-14 |  | 2017-07-14 | 2017-07-14 |  | 2017-07-14 | 2017-07-14 | Submitted | 2017-07-14
3SPL-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-14 |  | 2017-07-14 | 2017-07-14 |  | 2017-07-14 | 2017-07-14 | Submitted | 2017-07-14
3SSN-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-29 | Nina | 2017-06-29 | 2017-07-17 | Anila | 2017-07-17 | 2017-07-17 | Submitted | 2017-07-17 |  |  |  |  | Not Started
3OAK-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-29 | Linda | 2017-06-29 | 2017-07-17 | Anila | 2017-07-17 | 2017-07-17 | Submitted | 2017-07-17 |  |  |  |  | Not Started
2MEN-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-30 | Joju | 2017-06-30 | 2017-07-17 | Anila | 2017-07-17 | 2017-07-17 | Submitted | 2017-07-17 |  |  |  |  | Not Started
2PEN-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-12 | Joju | 2017-07-24 | 2017-07-25 | Minu | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-17 |  |  |  |  | Not Started
3OAK-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-06-30 | Sheeba | 2017-06-30 | 2017-07-18 | Minu | 2017-07-18 | 2017-07-18 | Submitted | 2017-07-18 |  |  |  |  | Not Started
3MLN-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-03 | Asha | 2017-07-03 | 2017-07-18 | Minu | 2017-07-18 | 2017-07-18 | Submitted | 2017-07-18 |  |  |  |  | Not Started
3MLN-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-03 | Linda | 2017-07-03 | 2017-07-18 | Minu | 2017-07-18 | 2017-07-18 | Submitted | 2017-07-18 |  |  |  |  | Not Started
3GLI-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-03 | Joju | 2017-07-03 | 2017-07-18 | Minu | 2017-07-18 | 2017-07-18 | Submitted | 2017-07-18 |  |  |  |  | Not Started
3NBA-67 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-17 | Linda | 2017-07-17 | 2017-07-18 | Anila | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-18 |  |  |  |  | Not Started
2HLS-61 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-13 | Dhanya | 2017-07-13 | 2017-07-18 | Anila | 2017-07-27 | 2017-07-27 | Submitted | 2017-07-18 |  |  |  |  | Not Started
5GLL-61 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-03 | Fausia | 2017-07-03 | 2017-07-19 | Anila | 2017-07-19 | 2017-07-19 | Submitted | 2017-07-19 |  |  |  |  | Not Started
3MLN-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-18 |  | 2017-07-18 | 2017-07-18 |  | 2017-07-18 | 2017-07-18 | Submitted | 2017-07-18
2ASH-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-18 |  | 2017-07-18 | 2017-07-18 |  | 2017-07-18 | 2017-07-18 | Submitted | 2017-07-18
2PEN-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-06 | Asha | 2017-07-06 | 2017-07-19 | Anila | 2017-07-19 | 2017-07-19 | Submitted | 2017-07-19 |  |  |  |  | Not Started
2PEN-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-05 | Sheeba | 2017-07-05 | 2017-07-19 | Anila | 2017-07-19 | 2017-07-19 | Submitted | 2017-07-19 |  |  |  |  | Not Started
5BRI-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-18 | Nina | 2017-07-18 | 2017-07-19 | Anila | 2017-07-25 | 2017-07-25 | Submitted | 2017-07-19 |  |  |  |  | Not Started
3TYH-69 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-07 | Nina | 2017-07-07 | 2017-07-20 | Anila | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20 |  |  |  |  | Not Started
3RWO-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-19 |  | 2017-07-19 | 2017-07-19 |  | 2017-07-19 | 2017-07-19 | Submitted | 2017-07-19
3CLA-66 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-06 | Linda | 2017-07-06 | 2017-07-20 | Anila | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20 |  |  |  |  | Not Started
3BLB-65 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-07 | Joju | 2017-07-07 | 2017-07-20 | Anila | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20 |  |  |  |  | Not Started
2PET-66 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-10 | Lisha | 2017-07-10 | 2017-07-20 | Anila | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20 |  |  |  |  | Not Started
2BAN-70 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-11 | Linda | 2017-07-11 | 2017-07-20 | Anila | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20 |  |  |  |  | Not Started
6GIR-22 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Asha | 2017-06-06 | 2017-07-20 | Anila | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20 |  |  |  |  | Not Started
2HLS-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-19 | Sheeba | 2017-07-19 | 2017-07-20 | Anila | 2017-07-27 | 2017-07-27 | Submitted | 2017-07-20 |  |  |  |  | Not Started
5BRI-64 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-20 | Asha | 2017-07-20 | 2017-07-20 | Anila | 2017-07-28 | 2017-07-28 | Submitted | 2017-07-20 |  |  |  |  | Not Started
4WTF-22 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-19 | Joju | 2017-07-19 | 2017-07-20 | Anila | 2017-07-25 | 2017-07-25 | Submitted | 2017-07-20 |  |  |  |  | Not Started
4IAL-64 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-20 | Sheeba | 2017-07-20 | 2017-07-20 | Anila | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20 |  |  |  |  | Not Started
2PYM-62 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-11 | Asha | 2017-07-11 | 2017-07-21 | Anila | 2017-07-21 |  | Submitted | 2017-07-21 |  |  |  |  | Not Started
6SUB-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-20 |  | 2017-07-20 | 2017-07-20 |  | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20
4CHP-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-20 |  | 2017-07-20 | 2017-07-20 |  | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20
3KGP-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-20 |  | 2017-07-20 | 2017-07-20 |  | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20
3NCO-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-20 |  | 2017-07-20 | 2017-07-20 |  | 2017-07-20 | 2017-07-20 | Submitted | 2017-07-20
2PYM-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-11 | Sheeba | 2017-07-11 | 2017-07-21 | Anila | 2017-07-21 | 2017-07-21 | Submitted | 2017-07-21 |  |  |  |  | Not Started
2ING-65 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-13 | Lisha | 2017-07-13 | 2017-07-21 | Anila | 2017-07-24 | 2017-07-24 | Submitted | 2017-07-21 |  |  |  |  | Not Started
2PYM-63 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-13 | Nina | 2017-07-13 | 2017-07-21 | Anila | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-21 |  |  |  |  | Not Started
2FRE-62 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-18 | Joju | 2017-07-18 | 2017-07-21 | Anila | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-21 |  |  |  |  | Not Started
4CUR-60 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-21 | Dhanya | 2017-07-21 | 2017-07-21 | Fausia | 2017-07-31 | 2017-07-31 | Submitted | 2017-07-21 |  |  |  |  | Not Started
4CHD-60 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-07-20 | Dhanya | 2017-07-20 | 2017-07-21 | Anila | 2017-07-27 | 2017-07-27 | Submitted | 2017-07-21 |  |  |  |  | Not Started
5EDW-68 | H-A-H | HAC | Pre-Design | PDC |  | Submitted |  | 2017-07-20 | Linda | 2017-07-20 | 2017-07-21 | Anila | 2017-07-28 | 2017-07-28 | Submitted | 2017-07-21 |  |  |  |  | Not Started
6GIR-21 | H-A-H | BAU | Pre-Design | PDC |  | Submitted |  | 2017-06-06 | Sheeba | 2017-07-24 | 2017-07-25 | Anila | 2017-07-25 | 2017-07-25 | Submitted | 2017-07-26 |  |  |  |  | Not Started
3TNI-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-20 | Lisha | 2017-07-20 | 2017-07-25 | Anila | 2017-07-25 | 2017-07-25 | Submitted | 2017-07-26 |  |  |  |  | Not Started
4CPR-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-25 | Lisha | 2017-07-25 | 2017-07-28 | Anila | 2017-07-28 | 2017-07-28 | Submitted | 2017-07-31 |  |  |  |  | Not Started
4ABC-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-18 | FAUSIA | 2017-07-18 | 2017-07-25 | Anila | 2017-07-28 | 2017-07-28 | Submitted | 2017-07-31 |  |  |  |  | Not Started
2CAS-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-24 | Joju | 2017-07-24 | 2017-07-24 | Anila | 2017-07-25 | 2017-07-25 | Submitted | 2017-07-31 |  |  |  |  | Not Started
3HDB-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-18 | Dhanya | 2017-07-18 | 2017-07-24 | Anila | 2017-07-25 | 2017-07-25 | Submitted | 2017-07-25 |  |  |  |  | Not Started
4AGV-20 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-26 | Nina | 2017-07-26 | 2017-07-31 | Anila | 2017-07-31 | 2017-07-31 | Submitted | 2017-08-01 |  |  |  |  | Not Started
4CPR-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-27 | Asha | 2017-07-27 | 2017-07-31 | Anila | 2017-07-31 | 2017-07-31 | Submitted | 2017-08-01 |  |  |  |  | Not Started
4NDG-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-31 | Asha | 2017-07-31 | 2017-08-01 | Anila | 2017-08-02 | 2017-08-02 | Submitted | 2017-08-02 |  |  |  |  | Not Started
4CPR-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-26 | FAUSIA | 2017-07-26 | 2017-08-01 | Anila | 2017-08-01 | 2017-08-01 | Submitted | 2017-08-02 |  |  |  |  | Not Started
4CHL-68 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-26 | Mythili S | 2017-07-26 | 2017-08-01 | Anila | 2017-08-01 | 2017-08-01 | Submitted | 2017-08-02 |  |  |  |  | Not Started
4SSB-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-27 | Joju | 2017-07-27 | 2017-08-02 | Anila | 2017-08-02 | 2017-08-02 | Submitted | 2017-08-03 |  |  |  |  | Not Started
4SRW-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-07-31 | Nina | 2017-07-31 | 2017-08-02 | Anila | 2017-08-02 | 2017-08-02 | Submitted | 2017-08-03 |  |  |  |  | Not Started
6GIR-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-01 | Sheeba | 2017-08-01 | 2017-08-02 | Anila | 2017-08-08 | 2017-08-08 | Submitted | 2017-08-08 |  |  |  |  | Not Started
5BRI-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-01 | Lisha | 2017-08-01 | 2017-08-04 | Anila | 2017-08-07 | 2017-08-07 | Submitted | 2017-08-07
4AAR-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-02 | Nina | 2017-08-02 | 2017-08-04 | Anila | 2017-08-07 | 2017-08-07 | Submitted | 2017-08-08
4FHL-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-05 | Mythili S | 2017-08-05 | 2017-08-05 | Anila | 2017-08-14 | 2017-08-14 | Submitted | 2017-08-14
5GLL-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-05 | Minu | 2017-08-05 | 2017-08-08 | Anila | 2017-08-10 | 2017-08-10 | Submitted | 2017-08-11
5GLL-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-02 | Sheeba | 2017-08-02 | 2017-08-08 | Anila | 2017-08-08 | 2017-08-08 | Submitted | 2017-08-10
2FRE-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-04 | Nina | 2017-08-04 | 2017-08-08 | Anila | 2017-08-08 | 2017-08-08 | Submitted | 2017-08-10
3KGP-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-04 | Lisha | 2017-08-04 | 2017-08-08 | Anila | 2017-08-08 | 2017-08-08 | Submitted | 2017-08-09
3CLA-68 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-03 | Dhanya | 2017-08-03 | 2017-08-08 | Anila | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
3CAU-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-07 | Joju | 2017-08-07 | 2017-08-08 | Anila | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
4WTF-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-07 | Asha | 2017-08-07 | 2017-08-08 | Anila | 2017-08-09 | 2017-08-10 | Submitted | 2017-08-10
3CAU-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-07 | Linda | 2017-08-07 | 2017-08-08 | Anila | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
4SUR-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-09 | Asha | 2017-08-09 | 2017-08-09 | Anila | 2017-08-14 | 2017-08-14 | Submitted | 2017-08-14
4SUR-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-09 | Dhanya | 2017-08-09 | 2017-08-10 | Anila | 2017-08-11 | 2017-08-11 | Submitted | 2017-08-11
4SRW-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-09 | Lisha | 2017-08-09 | 2017-08-10 | Anila | 2017-08-11 | 2017-08-11 | Submitted | 2017-08-11
4WTF-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-09 | Linda | 2017-08-09 | 2017-08-10 | Anila | 2017-08-10 | 2017-08-10 | Submitted | 2017-08-10
4CUR-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-09 | Joju | 2017-08-09 | 2017-08-10 | Anila | 2017-08-11 | 2017-08-11 | Submitted | 2017-08-11
2PEN-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-09 | Asha | 2017-08-09 | 2017-08-10 | Anila | 2017-08-14 | 2017-08-14 | Submitted | 2017-08-14
6GIR-20 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-10 | Asha | 2017-08-10 | 2017-08-10 | Anila | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-17
6WMB-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-10 | Asha | 2017-08-10 | 2017-08-11 | Anila | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
3SSN-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-09 | Sheeba | 2017-08-09 | 2017-08-11 | Anila | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
3TNI-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-09 | Nina | 2017-08-09 | 2017-08-11 | Anila | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-21
3TYH-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-10 | Linda | 2017-08-10 | 2017-08-11 | Anila | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
2PEN-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-10 | Dhanya | 2017-08-10 | 2017-08-14 | Anila | 2017-08-14 | 2017-08-14 | Submitted | 2017-08-14
5BRI-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-10 | Jainy | 2017-08-10 | 2017-08-14 | Anila | 2017-08-17 | 2017-08-17 | Submitted | 2017-08-17
3BLB-69 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-11 | Sheeba | 2017-08-11 | 2017-08-14 | Anila | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
5BRI-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-03 | Fausia | 2017-08-03 | 2017-08-14 | Anila | 2017-08-17 | 2017-08-17 | Submitted | 2017-08-17
2ROS-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-11 | Sheeba | 2017-08-11 | 2017-08-16 | Anila | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-18
2ROS-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-14 | Lisha | 2017-08-14 | 2017-08-16 | Anila | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-18
3CAU-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-16 | Sheeba | 2017-08-16 | 2017-08-16 | Anila | 2017-08-17 | 2017-08-17 | Submitted | 2017-08-17
2PET-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-16 | Joju | 2017-08-16 | 2017-08-16 | Anila | 2017-08-17 | 2017-08-17 | Submitted | 2017-08-18
2LIV-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-16 | Linda | 2017-08-16 | 2017-08-17 | Anila | 2017-08-18 | 2017-08-18 | Submitted | 2017-08-21
3TYH-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-14 | Jainy | 2017-08-14 | 2017-08-17 | Anila | 2017-08-18 | 2017-08-18 | Submitted | 2017-08-21
3BNT-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-17 | Lisha | 2017-08-17 | 2017-08-17 | Anila | 2017-08-22 | 2017-08-22 | Submitted | 2017-08-22
2LIV-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-14 | Dhanya | 2017-08-14 | 2017-08-18 | Anila | 2017-08-21 | 2017-08-21 | Submitted | 2017-08-21
3BLB-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-21 |  | 2017-07-21 | 2017-07-21 |  | 2017-07-21 | 2017-07-21 | Submitted | 2017-07-21
3DNC-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-26 |  | 2017-07-26 | 2017-07-26 |  | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-26
2EPP-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-26 |  | 2017-07-26 | 2017-07-26 |  | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-26
AGV-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-26 |  | 2017-07-26 | 2017-07-26 |  | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-26
3MLN-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-26 |  | 2017-07-26 | 2017-07-26 |  | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-26
4CHD-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-26 |  | 2017-07-26 | 2017-07-26 |  | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-26
4MGA-70 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-26 |  | 2017-07-26 | 2017-07-26 |  | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-26
4CPH-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-26 |  | 2017-07-26 | 2017-07-26 |  | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-26
2ROS-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-26 |  | 2017-07-26 | 2017-07-26 |  | 2017-07-26 | 2017-07-26 | Submitted | 2017-07-26
4CHD-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-28 |  | 2017-07-28 | 2017-07-28 |  | 2017-07-28 | 2017-07-28 | Submitted | 2017-07-28
3MIT-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-28 |  | 2017-07-28 | 2017-07-28 |  | 2017-07-28 | 2017-07-28 | Submitted | 2017-07-28
2PET-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-07-31 |  | 2017-07-31 | 2017-07-31 |  | 2017-07-31 | 2017-07-31 | Submitted | 2017-07-31
4WTF-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
2STL-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
6KSL-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
2PET-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
2ING-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
4IAL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
4CPH-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
4CHD-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
4MGB-01 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
5BRI-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
4CUR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-03 |  | 2017-08-03 | 2017-08-03 |  | 2017-08-03 | 2017-08-03 | Submitted | 2017-08-03
2BAN-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-09 |  | 2017-08-09 | 2017-08-09 |  | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
3DAD-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-09 |  | 2017-08-09 | 2017-08-09 |  | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
4CUR-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-09 |  | 2017-08-09 | 2017-08-09 |  | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
4CPR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-09 |  | 2017-08-09 | 2017-08-09 |  | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
2LIV-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-09 |  | 2017-08-09 | 2017-08-09 |  | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
5GLL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-09 |  | 2017-08-09 | 2017-08-09 |  | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
2BAN-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-09 |  | 2017-08-09 | 2017-08-09 |  | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
4CPR-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-09 |  | 2017-08-09 | 2017-08-09 |  | 2017-08-09 | 2017-08-09 | Submitted | 2017-08-09
3SSN-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-10 |  | 2017-08-10 | 2017-08-10 |  | 2017-08-10 | 2017-08-10 | Submitted | 2017-08-10
3RWO-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-10 |  | 2017-08-10 | 2017-08-10 |  | 2017-08-10 | 2017-08-10 | Submitted | 2017-08-10
2EPP-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-10 |  | 2017-08-10 | 2017-08-10 |  | 2017-08-10 | 2017-08-10 | Submitted | 2017-08-10
2PYM-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-10 |  | 2017-08-10 | 2017-08-10 |  | 2017-08-10 | 2017-08-10 | Submitted | 2017-08-10
2MOS-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-11 |  | 2017-08-11 | 2017-08-11 |  | 2017-08-11 | 2017-08-11 | Submitted | 2017-08-11
4MGA-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-11 |  | 2017-08-11 | 2017-08-11 |  | 2017-08-11 | 2017-08-11 | Submitted | 2017-08-11
5SAL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-11 |  | 2017-08-11 | 2017-08-11 |  | 2017-08-11 | 2017-08-11 | Submitted | 2017-08-11
2ASH-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-11 |  | 2017-08-11 | 2017-08-11 |  | 2017-08-11 | 2017-08-11 | Submitted | 2017-08-11
3GLI-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-08 |  | 2017-08-08 | 2017-08-08 |  | 2017-08-08 | 2017-08-08 | Submitted | 2017-08-08
2MOS-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-08 |  | 2017-08-08 | 2017-08-08 |  | 2017-08-08 | 2017-08-08 | Submitted | 2017-08-08
2PET-70 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-08 |  | 2017-08-08 | 2017-08-08 |  | 2017-08-08 | 2017-08-08 | Submitted | 2017-08-08
2PNN-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-14 |  | 2017-08-14 | 2017-08-14 |  | 2017-08-14 | 2017-08-14 | Submitted | 2017-08-14
3ELT-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-14 |  | 2017-08-14 | 2017-08-14 |  | 2017-08-14 | 2017-08-14 | Submitted | 2017-08-14
2ASH-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-14 |  | 2017-08-14 | 2017-08-14 |  | 2017-08-14 | 2017-08-14 | Submitted | 2017-08-14
2ASH-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-16 |  | 2017-08-16 | 2017-08-16 |  | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
3DAD-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-11 |  | 2017-08-11 | 2017-08-11 |  | 2017-08-11 | 2017-08-11 | Submitted | 2017-08-11
2STL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-16 |  | 2017-08-16 | 2017-08-16 |  | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
2EPP-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-16 |  | 2017-08-16 | 2017-08-16 |  | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
3SOA-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-16 |  | 2017-08-16 | 2017-08-16 |  | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
4AGV-20 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-16 |  | 2017-08-16 | 2017-08-16 |  | 2017-08-16 | 2017-08-16 | Submitted | 2017-08-16
3KGP-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-18 |  | 2017-08-18 | 2017-08-18 |  | 2017-08-18 | 2017-08-18 | Submitted | 2017-08-18
3RWO-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-18 |  | 2017-08-18 | 2017-08-18 |  | 2017-08-18 | 2017-08-18 | Submitted | 2017-08-18
2PEN-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-17 | Linda | 2017-08-17 | 2017-08-22 | Anila | 2017-08-22 | 2017-08-22 | Submitted | 2017-08-22
2PEN-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-21 | Linda | 2017-08-21 | 2017-08-21 | Anila | 2017-08-22 | 2017-08-22 | Submitted | 2017-08-22
2PEN-01 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-21 | Dhanya | 2017-08-21 | 2017-08-22 | Anila | 2017-08-22 | 2017-08-22 | Submitted | 2017-08-23
3NES-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-17 | Joju | 2017-08-17 | 2017-08-22 | Anila | 2017-08-22 | 2017-08-22 | Submitted | 2017-08-23
3KYG-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-22 | Asha | 2017-08-22 | 2017-08-22 | Anila | 2017-08-23 | 2017-08-23 | Submitted | 2017-08-23
3CAU-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-21 | Lisha | 2017-08-21 | 2017-08-21 | Anila | 2017-08-23 | 2017-08-23 | Submitted | 2017-08-23
2PYM-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-17 | Nina | 2017-08-17 | 2017-08-22 | Anila | 2017-08-23 | 2017-08-23 | Submitted | 2017-08-23
2PYM-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-18 | Sheeba | 2017-08-18 | 2017-08-22 | Anila | 2017-08-24 | 2017-08-24 | Submitted | 2017-08-24
2HUR-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-17 | Jainy | 2017-08-17 | 2017-08-24 | Anila | 2017-08-24 | 2017-08-24 | Submitted | 2017-08-24
2HUR-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-22 | Asha | 2017-08-22 | 2017-08-23 | Anila | 2017-08-24 | 2017-08-24 | Submitted | 2017-08-24
5GLL-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-21 | Nina | 2017-08-21 | 2017-08-24 | Anila | 2017-08-28 | 2017-08-28 | Submitted | 2017-08-28
5BRI-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-23 | Dhanya | 2017-08-23 | 2017-08-28 | Anila | 2017-08-28 | 2017-08-28 | Submitted | 2017-08-28
4NDG-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-23 | Asha | 2017-08-23 | 2017-08-24 | Anila | 2017-08-28 | 2017-08-28 | Submitted | 2017-08-28
4ABO-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-23 | Mythili S | 2017-08-23 | 2017-08-25 | Anila | 2017-08-28 | 2017-08-28 | Submitted | 2017-08-28
4WTF-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-25 | Nina | 2017-08-25 | 2017-08-29 | Anila | 2017-08-30 | 2017-08-30 | Submitted | 2017-08-30
4CHL-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-24 | Jainy | 2017-08-24 | 2017-08-29 | Anila | 2017-08-30 | 2017-08-30 | Submitted | 2017-08-30
4SRW-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-23 | Lisha | 2017-08-23 | 2017-08-28 | Anila | 2017-08-29 | 2017-08-29 | Submitted | 2017-08-29
4AAR-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-23 | Sheeba | 2017-08-23 | 2017-08-26 | Anila | 2017-08-29 | 2017-08-29 | Submitted | 2017-08-29
4CHL-70 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-25 | Asha | 2017-08-25 | 2017-08-29 | Anila | 2017-08-29 | 2017-08-29 | Submitted | 2017-08-29
4CHL-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-28 | Sheeba | 2017-08-28 | 2017-08-29 | Anila | 2017-08-30 | 2017-08-30 | Submitted | 2017-08-30
4OXE-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-28 | Joju | 2017-08-28 | 2017-08-29 | Anila | 2017-08-30 | 2017-08-30 | Submitted | 2017-08-31
4ORM-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-29 | Asha Jacob | 2017-08-29 | 2017-08-29 | Anila | 2017-08-30 | 2017-08-30 | Submitted | 2017-08-31
5WES-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-28 | Dhanya A | 2017-08-28 | 2017-09-01 | Anila | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-05
3RWO-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-29 | Lisha Manuel | 2017-08-29 | 2017-09-01 | Anuja | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-01
3MIT-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-29 | Joju | 2017-08-29 | 2017-09-01 | Anila | 2017-09-06 | 2017-09-06 | Submitted | 2017-09-06
3BNT-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-29 | Sheeba C | 2017-08-29 | 2017-08-30 | Anila | 2017-08-31 | 2017-08-31 | Submitted | 2017-09-05
3SOA-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-28 |  | 2017-08-28 | 2017-08-28 |  | 2017-08-28 | 2017-08-28 | Submitted | 2017-08-28
3BLB-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-28 |  | 2017-08-28 | 2017-08-28 |  | 2017-08-28 | 2017-08-28 | Submitted | 2017-08-28
3BLB-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-30 |  | 2017-08-30 | 2017-08-30 |  | 2017-08-30 | 2017-08-30 | Submitted | 2017-08-30
4CHL-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-30 | Jainy Joseph | 2017-08-30 | 2017-08-30 | Anila | 2017-08-31 | 2017-08-31 | Submitted | 2017-09-05
2NEW-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-30 | Asha Jacob | 2017-08-30 | 2017-09-01 | Anila | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-05
3WIR-69 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-30 | Nina Sebastian | 2017-08-30 | 2017-08-30 | Anila | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-05
3DAD-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-30 | Sheeba | 2017-08-30 | 2017-09-01 | Anila | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-05
4FHL-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-08-31 | Jainy Joseph | 2017-08-31 | 2017-09-06 | Anila | 2017-09-06 | 2017-09-06 | Submitted | 2017-09-07
3MIT-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-01 | Nina Sebastian | 2017-09-01 | 2017-09-06 | Anila | 2017-09-06 | 2017-09-06 | Submitted | 2017-09-06
2SEV-20 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-01 | Asha Jacob | 2017-09-01 | 2017-09-01 | Anila | 2017-09-06 | 2017-09-06 | Submitted | 2017-09-06
2PET-68 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-01 | Sheeba C | 2017-09-01 | 2017-09-01 | Anila | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-06
2PYM-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-06 | Joju | 2017-09-06 | 2017-09-11 | Anila | 2017-09-12 | 2017-09-12 | Submitted | 2017-09-12
4CPR-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-06 | Sheeba C | 2017-09-06 | 2017-09-08 | Anila | 2017-09-11 | 2017-09-11 | Submitted | 2017-09-11
4ABO-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-06 | Mythili S | 2017-09-06 | 2017-09-07 | Anila | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-21
4FHL-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-06 | Asha Jacob | 2017-09-06 | 2017-09-07 | Anila | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-14
6WMB-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-07 | Nina Sebastian | 2017-09-07 | 2017-09-07 | Anila | 2017-09-11 | 2017-09-11 | Submitted | 2017-09-12
6SUB-23 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-07 | Nina Sebastian | 2017-09-07 | 2017-09-07 | Anila | 2017-09-11 | 2017-09-11 | Submitted | 2017-09-12
2RYD-68 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-09-07 | Nina Sebastian | 2017-09-07 | 2017-09-07 | Mythili | 2017-09-26 | 2017-09-26 | PDC completed & AFR Submitted | 2017-12-12
4CUR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-31 |  | 2017-08-31 | 2017-08-31 |  | 2017-08-31 | 2017-08-31 | Submitted | 2017-08-31
2PET-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-01 |  | 2017-09-01 | 2017-09-01 |  | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-01
2PEN-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
2PYM-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
3BLB-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
2PET-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
2ASH-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
4CUR-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-07 | Asha Jacob | 2017-09-07 | 2017-09-08 | Anila | 2017-09-11 | 2017-09-11 | Submitted | 2017-09-11
5NRW-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-08 | Linda | 2017-09-08 | 2017-09-12 | Anila | 2017-09-13 | 2017-09-13 | Submitted | 2017-09-13
2PEN-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-08 | Sheeba C | 2017-09-08 | 2017-09-12 | Anila | 2017-09-12 | 2017-09-12 | Submitted | 2017-09-12
2CAS-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-11 | Asha Jacob | 2017-09-11 | 2017-09-12 | Anila | 2017-09-13 | 2017-09-13 | Submitted | 2017-09-13
2SHA-21 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-11 | Lisha Manuel | 2017-09-11 | 2017-09-11 | Anila | 2017-09-13 | 2017-09-13 | Submitted | 2017-09-13
5HNL-20 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-11 | Nina Sebastian | 2017-09-11 | 2017-09-11 | Anila | 2017-09-12 | 2017-09-12 | Submitted | 2017-09-14
4FHL-22 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-11 | Dhanya A | 2017-09-11 | 2017-09-11 | Anila | 2017-09-14 | 2017-09-14 | Submitted | 2017-09-18
3CTA-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-08-29 |  | 2017-08-29 | 2017-08-29 |  | 2017-08-29 | 2017-08-29 | Submitted | 2017-08-29
2CAS-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-01 |  | 2017-09-01 | 2017-09-01 |  | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-01
4CPR-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-01 |  | 2017-09-01 | 2017-09-01 |  | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-01
3MLN-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-01 |  | 2017-09-01 | 2017-09-01 |  | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-01
4SSB-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-01 |  | 2017-09-01 | 2017-09-01 |  | 2017-09-01 | 2017-09-01 | Submitted | 2017-09-01
2PEN-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
2PYM-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
3BLB-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
2PET-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
2ASH-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-07 |  | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | 2017-09-07 | Submitted | 2017-09-07
3DAD-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
3BLB-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
2HUR-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-12 | Sheeba C | 2017-09-12 | 2017-09-13 | Anila | 2017-09-14 | 2017-09-14 | Submitted | 2017-09-20
3HGT-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-12 | Dhanya A | 2017-09-12 | 2017-09-13 | Anila | 2017-09-14 | 2017-09-14 | Submitted | 2017-09-20
4SRW-69 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-12 | Nina Sebastian | 2017-09-12 | 2017-09-12 | Anila | 2017-09-14 | 2017-09-14 | Submitted | 2017-09-22
4CPR-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
2HUR-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-13 | Nina Sebastian | 2017-09-13 | 2017-09-18 | Mythili | 2017-09-19 | 2017-09-19 | Submitted | 2017-09-21
2PAR-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-13 | Sheeba C | 2017-09-13 | 2017-09-18 | Mythili | 2017-09-19 | 2017-09-19 | Submitted | 2017-09-21
2HUR-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-14 | Linda | 2017-09-14 | 2017-09-15 | Mythili | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-26
3DNC-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-14 | Dhanya A | 2017-09-14 | 2017-09-14 | Anila | 2017-09-15 | 2017-09-15 | Submitted | 2017-10-10
6SUB-20 | H-A-H |  | Pre-Design | PDC |  | QA Completed |  | 2017-09-14 | Jainy Joseph | 2017-09-14 | 2017-09-14 | Anila | 2017-09-15 | 2017-09-15 | QA Completed
3RES-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-07 | Lisha Manuel | 2017-09-07 | 2017-09-14 | Anila | 2017-09-15 | 2017-09-15 | Submitted | 2017-10-31
2NEW-20 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-15 | Dhanya A | 2017-09-15 | 2017-09-18 | Mythili | 2017-09-19 | 2017-09-19 | Submitted | 2017-10-10
5NRW-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-15 | Lisha Manuel | 2017-09-15 | 2017-09-25 | Mythili | 2017-09-26 | 2017-09-26 | Submitted | 2017-09-26
2PYM-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
2WET-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
3BAY-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
5BRI-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
4SSB-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
3KYG-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
3SOA-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
4CPR-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-08 |  | 2017-09-08 | 2017-09-08 |  | 2017-09-08 | 2017-09-08 | Submitted | 2017-09-08
3SSN-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-15 |  | 2017-09-15 | 2017-09-15 |  | 2017-09-15 | 2017-09-15 | Submitted | 2017-09-15
2EAS-69 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-18 | LInda | 2017-09-18 | 2017-09-18 | Mythili | 2017-09-20 | 2017-09-20 | Submitted | 2017-10-05
4ABO-68 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-07 | Asha Jacob | 2017-09-07 | 2017-09-14 | Mythili | 2017-09-18 | 2017-09-18 | Submitted | 2017-10-23
5NRW-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-18 | Linda | 2017-09-18 | 2017-09-23 | Mythili | 2017-09-25 | 2017-09-25 | Submitted | 2017-09-26
2NEW-21 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-09-18 | Dhanya A | 2017-09-18 | 2017-09-18 | Mythili | 2017-09-20 | 2017-09-20 | PDC completed & AFR Submitted | 2017-12-07
2FRE-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-15 |  | 2017-09-15 | 2017-09-15 |  | 2017-09-15 | 2017-09-15 | Submitted | 2017-09-15
4NDG-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-15 |  | 2017-09-15 | 2017-09-15 |  | 2017-09-15 | 2017-09-15 | Submitted | 2017-09-15
4CPR-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
2PEN-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
3CTA-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
4SUR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
3BNT-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
3BNT-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
2RYD-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-19 | Nina | 2017-09-19 | 2017-09-25 | Mythili | 2017-09-25 | 2017-09-25 | Submitted | 2017-09-26
2NEW-22 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-09-19 | Sheeba | 2017-09-19 | 2017-09-19 | Mythili | 2017-09-20 | 2017-09-20 | PDC completed & AFR Submitted | 2018-01-23
3OAK-69 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-19 | Dhanya | 2017-09-19 | 2017-09-21 | Mythili | 2017-09-21 | 2017-09-21 | Submitted | 2017-10-05
2NEW-23 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-19 | Sheeba | 2017-09-19 | 2017-09-19 | Mythili | 2017-09-20 | 2017-09-20 | Submitted | 2017-10-12
3SOA-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
3DAD-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
3TYH-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
3CLA-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | Submitted | 2017-09-18
2PEN-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-19 |  | 2017-09-19 | 2017-09-19 |  | 2017-09-19 | 2017-09-19 | Submitted | 2017-09-19
4CHL-70 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-19 |  | 2017-09-19 | 2017-09-19 |  | 2017-09-19 | 2017-09-19 | Submitted | 2017-09-19
2PEN-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-19 |  | 2017-09-19 | 2017-09-19 |  | 2017-09-19 | 2017-09-19 | Submitted | 2017-09-19
3OAK-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-19 |  | 2017-09-19 | 2017-09-19 |  | 2017-09-19 | 2017-09-19 | Submitted | 2017-09-19
3KYG-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-19 |  | 2017-09-19 | 2017-09-19 |  | 2017-09-19 | 2017-09-19 | Submitted | 2017-09-19
2RDL-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-20 | Fausia | 2017-09-20 | 2017-09-27 | Anila | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-20
2RDL-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-20 | Sheeba | 2017-09-20 | 2017-10-10 | Mythili | 2017-10-11 | 2017-10-11 | Submitted | 2017-10-20
3CTA-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2016-11-30 | Mythili L | 2016-11-30 | 2016-12-02 | Mythili | 2017-09-20 | 2017-09-20 | Submitted | 2017-10-25
6MLO-20 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-21 | Dhanya | 2017-09-21 | 2017-09-21 | Mythili | 2017-09-22 | 2017-09-22 | Submitted | 2017-10-10
3CAU-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-21 | Jumana.M | 2017-09-21 | 2017-09-22 | Mythili | 2017-09-25 | 2017-09-25 | Submitted | 2017-10-06
2PYM-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-20 |  | 2017-09-20 | 2017-09-20 |  | 2017-09-20 | 2017-09-20 | Submitted | 2017-09-20
3SOA-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-20 |  | 2017-09-20 | 2017-09-20 |  | 2017-09-20 | 2017-09-20 | Submitted | 2017-09-20
3BNT-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-20 |  | 2017-09-20 | 2017-09-20 |  | 2017-09-20 | 2017-09-20 | Submitted | 2017-09-20
4CPR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-20 |  | 2017-09-20 | 2017-09-20 |  | 2017-09-20 | 2017-09-20 | Submitted | 2017-09-20
5GLL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-20 |  | 2017-09-20 | 2017-09-20 |  | 2017-09-20 | 2017-09-20 | Submitted | 2017-09-20
5BRI-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-20 |  | 2017-09-20 | 2017-09-20 |  | 2017-09-20 | 2017-09-20 | Submitted | 2017-09-20
5GLL-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-20 |  | 2017-09-20 | 2017-09-20 |  | 2017-09-20 | 2017-09-20 | Submitted | 2017-09-20
3BOX-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-20 |  | 2017-09-20 | 2017-09-20 |  | 2017-09-20 | 2017-09-20 | Submitted | 2017-09-20
2LIV-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-21 |  | 2017-09-21 | 2017-09-21 |  | 2017-09-21 | 2017-09-21 | Submitted | 2017-09-21
2LIV-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-21 |  | 2017-09-21 | 2017-09-21 |  | 2017-09-21 | 2017-09-21 | Submitted | 2017-09-21
2PYM-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-21 |  | 2017-09-21 | 2017-09-21 |  | 2017-09-21 | 2017-09-21 | Submitted | 2017-09-21
2PAR-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-19 | Jumana.M | 2017-09-19 | 2017-09-21 | Mythili | 2017-09-22 | 2017-09-22 | Submitted | 2017-09-22
3HDB-68 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-22 | Dhanya | 2017-09-22 | 2017-09-28 | Mythili | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
5WES-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-22 |  | 2017-09-22 | 2017-09-22 |  | 2017-09-22 | 2017-09-22 | Submitted | 2017-09-22
2ROS-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-22 |  | 2017-09-22 | 2017-09-22 |  | 2017-09-22 | 2017-09-22 | Submitted | 2017-09-22
3CAU-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-22 |  | 2017-09-22 | 2017-09-22 |  | 2017-09-22 | 2017-09-22 | Submitted | 2017-09-22
2CAS-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-22 |  | 2017-09-22 | 2017-09-22 |  | 2017-09-22 | 2017-09-22 | Submitted | 2017-09-22
3RWO-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-22 |  | 2017-09-22 | 2017-09-22 |  | 2017-09-22 | 2017-09-22 | Submitted | 2017-09-22
2CAS-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-22 |  | 2017-09-22 | 2017-09-22 |  | 2017-09-22 | 2017-09-22 | Submitted | 2017-09-22
5EDW-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-23 |  | 2017-09-23 | 2017-09-23 |  | 2017-09-23 | 2017-09-23 | Submitted | 2017-09-23
2PYM-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-23 |  | 2017-09-23 | 2017-09-23 |  | 2017-09-23 | 2017-09-23 | Submitted | 2017-09-23
3BOX-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-23 |  | 2017-09-23 | 2017-09-23 |  | 2017-09-23 | 2017-09-23 | Submitted | 2017-09-23
3NCO-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-23 |  | 2017-09-23 | 2017-09-23 |  | 2017-09-23 | 2017-09-23 | Submitted | 2017-09-23
3BOX-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-23 |  | 2017-09-23 | 2017-09-23 |  | 2017-09-23 | 2017-09-23 | Submitted | 2017-09-23
4SRW-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-23 |  | 2017-09-23 | 2017-09-23 |  | 2017-09-23 | 2017-09-23 | Submitted | 2017-09-23
4CPR-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-25 |  | 2017-09-25 | 2017-09-25 |  | 2017-09-25 | 2017-09-25 | Submitted | 2017-09-25
4AGV-20 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-25 |  | 2017-09-25 | 2017-09-25 |  | 2017-09-25 | 2017-09-25 | Submitted | 2017-09-25
3OAK-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-25 |  | 2017-09-25 | 2017-09-25 |  | 2017-09-25 | 2017-09-25 | Submitted | 2017-09-25
4SUR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-25 |  | 2017-09-25 | 2017-09-25 |  | 2017-09-25 | 2017-09-25 | Submitted | 2017-09-25
2RYD-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-25 | Linda | 2017-09-25 | 2017-09-27 | Anila | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-28
6WMB-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-23 | Jumana.M | 2017-09-23 | 2017-09-23 | Mythili | 2017-09-25 | 2017-09-25 | Submitted | 2017-09-28
2RYD-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-25 | Nina | 2017-09-25 | 2017-09-28 | Mythili | 2017-09-28 | 2017-09-28 | Submitted | 2017-09-28
3CAN-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-22 | Mythili S | 2016-09-08 | 2016-09-08 | Brinson | 2016-10-31 | 2016-10-31 | Submitted | 2017-09-22
4SOP-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-25 | Keerthi | 2017-09-25 | 2017-09-25 | Mythili | 2017-09-26 | 2017-09-26 | Submitted | 2017-09-26
5NRW-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-26 | Lisha Manuel | 2017-09-26 | 2017-09-29 | Mythili | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
3MLN-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-25 |  | 2017-09-25 | 2017-09-25 |  | 2017-09-25 | 2017-09-25 | Submitted | 2017-09-25
3RWO-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-26 |  | 2017-09-26 | 2017-09-26 |  | 2017-09-26 | 2017-09-26 | Submitted | 2017-09-26
3TYH-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-26 |  | 2017-09-26 | 2017-09-26 |  | 2017-09-26 | 2017-09-26 | Submitted | 2017-09-26
3NCO-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-27 |  | 2017-09-27 | 2017-09-27 |  | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-27
3TNI-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-27 |  | 2017-09-27 | 2017-09-27 |  | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-27
4SSB-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-27 |  | 2017-09-27 | 2017-09-27 |  | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-27
5GLL-20 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-28 | Keerthi | 2017-09-28 | 2017-09-28 | Mythili | 2017-10-03 | 2017-10-03 | Submitted | 2017-10-13
2KNS-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-28 | Keerthi | 2017-09-28 | 2017-10-05 | Anila | 2017-10-06 | 2017-10-06 | Submitted | 2017-10-06
5NRW-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-25 | Jainy Joseph | 2017-09-25 | 2017-09-28 | Mythili | 2017-09-28 | 2017-09-28 | Submitted | 2017-09-28
4CPR-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-27 |  | 2017-09-27 | 2017-09-27 |  | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-27
2PYM-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-27 |  | 2017-09-27 | 2017-09-27 |  | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-27
4SRW-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-27 |  | 2017-09-27 | 2017-09-27 |  | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-27
3TYH-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-27 |  | 2017-09-27 | 2017-09-27 |  | 2017-09-27 | 2017-09-27 | Submitted | 2017-09-27
3WER-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-29 |  | 2017-09-29 | 2017-09-29 |  | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
3CLA-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-29 |  | 2017-09-29 | 2017-09-29 |  | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
4CHL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-29 |  | 2017-09-29 | 2017-09-29 |  | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
2PYM-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-29 |  | 2017-09-29 | 2017-09-29 |  | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
4CPR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-29 |  | 2017-09-29 | 2017-09-29 |  | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
4CHL-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-29 |  | 2017-09-29 | 2017-09-29 |  | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
2PYM-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-09-29 |  | 2017-09-29 | 2017-09-29 |  | 2017-09-29 | 2017-09-29 | Submitted | 2017-09-29
3KGP-20 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-09-29 | Dhanya A | 2017-09-29 | 2017-09-29 | Mythili | 2017-10-03 | 2017-10-03 | PDC completed & AFR Submitted | 2017-10-10 | SAM not available in ConnectMTM
2HUR-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-29 | Nina | 2017-09-29 | 2017-10-05 | Mythili | 2017-10-06 | 2017-10-06 | Submitted | 2017-10-10
3BLB-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-09-29 | Lisha Manuel | 2017-09-29 | 2017-10-06 | Mythili | 2017-10-09 | 2017-10-09 | Submitted | 2017-10-13
3KYG-69 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-03 | Dhanya A | 2017-10-03 | 2017-10-04 | Mythili | 2017-10-09 | 2017-10-09 | Submitted | 2017-10-13
2FRE-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-03 |  | 2017-10-03 | 2017-10-03 |  | 2017-10-03 | 2017-10-03 | Submitted | 2017-10-03
3KYG-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-03 |  | 2017-10-03 | 2017-10-03 |  | 2017-10-03 | 2017-10-03 | Submitted | 2017-10-03
3CAU-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-03 |  | 2017-10-03 | 2017-10-03 |  | 2017-10-03 | 2017-10-03 | Submitted | 2017-10-03
2HLS-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-04 |  | 2017-10-04 | 2017-10-04 |  | 2017-10-04 | 2017-10-04 | Submitted | 2017-10-04
2WRO-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-05 | Fausia | 2017-10-05 | 2017-10-13 | Mythili | 2017-10-13 | 2017-10-13 | Submitted | 2017-10-13
2GBE-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-05 | Dhanya A | 2017-10-05 | 2017-10-06 | Mythili | 2017-10-10 | 2017-10-10 | Submitted | 2017-10-13
2GBE-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-05 | Nina Sebastian | 2017-10-05 | 2017-10-05 | Mythili | 2017-10-09 | 2017-10-09 | Submitted | 2017-10-13
2CHA-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-06 | Nina Sebastian | 2017-10-06 | 2017-10-11 | Mythili | 2017-10-12 | 2017-10-12 | Submitted | 2017-10-13
2PYM-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-06 |  | 2017-10-06 | 2017-10-06 |  | 2017-10-06 | 2017-10-06 | Submitted | 2017-10-06
2PEN-01 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-06 |  | 2017-10-06 | 2017-10-06 |  | 2017-10-06 | 2017-10-06 | Submitted | 2017-10-06
5WES-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-06 |  | 2017-10-06 | 2017-10-06 |  | 2017-10-06 | 2017-10-06 | Submitted | 2017-10-06
3NCO-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-05 |  | 2017-10-05 | 2017-10-05 |  | 2017-10-05 | 2017-10-05 | Submitted | 2017-10-05
2PEN-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-06 |  | 2017-10-06 | 2017-10-06 |  | 2017-10-06 | 2017-10-06 | Submitted | 2017-10-06
5GLL-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-09 |  | 2017-10-09 | 2017-10-09 |  | 2017-10-09 | 2017-10-09 | Submitted | 2017-10-09
3MLN-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-09 |  | 2017-10-09 | 2017-10-09 |  | 2017-10-09 | 2017-10-09 | Submitted | 2017-10-09
2BAM-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-09 |  | 2017-10-09 | 2017-10-09 |  | 2017-10-09 | 2017-10-09 | Submitted | 2017-10-09
2HUR-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-09 | Dhanya A | 2017-10-09 | 2017-10-09 | Mythili | 2017-10-10 | 2017-10-10 | Submitted | 2017-10-20
2CAM-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-09 | Lisha Manuel | 2017-10-09 | 2017-10-11 | Mythili | 2017-10-13 | 2017-10-13 | Submitted | 2017-10-20
5GLL-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-10 |  | 2017-10-10 | 2017-10-10 |  | 2017-10-10 | 2017-10-10 | Submitted | 2017-10-10
2CAR-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-10 | Dhanya A | 2017-10-10 | 2017-10-17 | Anila | 2017-10-19 | 2017-10-19 | Submitted | 2017-10-20
4ALX-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-10 | Linda | 2017-10-10 | 2017-10-12 | Mythili | 2017-10-16 | 2017-10-16 | Submitted | 2017-10-20
4TGP-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-11 | Lisha Manuel | 2017-10-11 | 2017-10-20 | Anila | 2017-10-20 | 2017-10-20 | Submitted | 2017-10-20
2QUA-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-11 | Sree Lekshmi | 2017-10-11 | 2017-10-17 | Anila | 2017-10-19 | 2017-10-19 | Submitted | 2017-10-20
5BRI-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-11 |  | 2017-10-11 | 2017-10-11 |  | 2017-10-11 | 2017-10-11 | Submitted | 2017-10-11
3TYH-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-11 |  | 2017-10-11 | 2017-10-11 |  | 2017-10-11 | 2017-10-11 | Submitted | 2017-10-11
3HDB-66 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-12 | Nina Sebastian | 2017-10-12 | 2017-10-19 | Anila | 2017-10-20 | 2017-10-20 | Submitted | 2017-10-20
3DNC-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-11 |  | 2017-10-11 | 2017-10-11 |  | 2017-10-11 | 2017-10-11 | Submitted | 2017-10-11
3BNT-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-11 |  | 2017-10-11 | 2017-10-11 |  | 2017-10-11 | 2017-10-11 | Submitted | 2017-10-11
3BNT-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-11 |  | 2017-10-11 | 2017-10-11 |  | 2017-10-11 | 2017-10-11 | Submitted | 2017-10-11
4ABO-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-13 | Linda | 2017-10-13 | 2017-10-13 | Mythili | 2017-10-16 | 2017-10-16 | Submitted | 2017-10-20
2CHA-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-13 | Joju | 2017-10-13 | 2017-10-23 | Anila | 2017-10-23 | 2017-10-23 | Submitted | 2017-10-23
4PDP-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-13 | Fausia | 2017-10-13 | 2017-10-16 | Anila | 2017-10-19 | 2017-10-19 | Submitted | 2017-10-20
5NRW-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-16 | Linda | 2017-10-16 | 2017-10-20 | Mythili | 2017-10-23 | 2017-10-23 | Submitted | 2017-10-23
4TGP-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-16 | Keerthi | 2017-10-16 | 2017-10-17 | Anila | 2017-10-19 | 2017-10-19 | Submitted | 2017-10-20
3BLB-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-16 |  | 2017-10-16 | 2017-10-16 |  | 2017-10-16 | 2017-10-16 | Submitted | 2017-10-16
4RBN-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-17 | Sree Lekshmi | 2017-10-17 | 2017-10-17 | Anila | 2017-10-20 | 2017-10-20 | Submitted | 2017-10-23
4SSB-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-16 |  | 2017-10-16 | 2017-10-16 |  | 2017-10-16 | 2017-10-16 | Submitted | 2017-10-16
3CAU-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-16 |  | 2017-10-16 | 2017-10-16 |  | 2017-10-16 | 2017-10-16 | Submitted | 2017-10-16
4SRW-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-16 |  | 2017-10-16 | 2017-10-16 |  | 2017-10-16 | 2017-10-16 | Submitted | 2017-10-16
3CAU-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-17 |  | 2017-10-17 | 2017-10-17 |  | 2017-10-17 | 2017-10-17 | Submitted | 2017-10-17
4LNH-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-19 | Fausia | 2017-10-19 | 2017-10-20 | Mythili | 2017-10-23 | 2017-10-23 | Submitted | 2017-10-23
4FHL-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-19 | Nina Sebastian | 2017-10-19 | 2017-10-24 | Mythili | 2017-10-24 | 2017-10-24 | Submitted | 2017-10-25
3MLN-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-17 |  | 2017-10-19 | 2017-10-19 |  | 2017-10-19 | 2017-10-19 | Submitted | 2017-10-19
2HUR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-19 |  | 2017-10-19 | 2017-10-19 |  | 2017-10-19 | 2017-10-19 | Submitted | 2017-10-19
2PNN-68 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-19 |  | 2017-10-19 | 2017-10-19 |  | 2017-10-19 | 2017-10-19 | Submitted | 2017-10-19
4CPR-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-19 |  | 2017-10-19 | 2017-10-19 |  | 2017-10-19 | 2017-10-19 | Submitted | 2017-10-19
2CAR-63 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-23 | Lisha Manuel | 2017-10-23 | 2017-10-27 | Mythili | 2017-10-27 | 2017-10-27 | Submitted | 2017-10-27
3BAY-67 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-23 | Dhanya A | 2017-10-23 | 2017-10-24 | Mythili | 2017-10-24 | 2017-10-24 | Submitted | 2017-10-25
4TGP-68 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-24 | Nina Sebastian | 2017-10-24 | 2017-10-27 | Mythili | 2017-10-27 | 2017-10-27 | Submitted | 2017-10-27
6WMB-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-24 | Dhanya A | 2017-10-24 | 2017-10-24 | Mythili | 2017-10-25 | 2017-10-25 | Submitted | 2017-10-25
3NBA-70 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-24 | Asha Jacob | 2017-10-24 | 2017-10-24 | Mythili | 2017-10-25 | 2017-10-25 | Submitted | 2017-10-25
4ABO-60 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-24 | Keerthi | 2017-10-24 | 2017-10-24 | Mythili | 2017-10-25 | 2017-10-26 | Submitted | 2017-10-27
3TNB-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-24 | Joju | 2017-10-24 | 2017-10-26 | Mythili | 2017-10-27 | 2017-10-27 | Submitted | 2017-10-27
3WIR-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-24 | Sree Lekshmi | 2017-10-24 | 2017-10-26 | Mythili | 2017-10-26 | 2017-10-26 | Submitted | 2017-10-31
5NRW-61 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-25 | Fausia | 2017-10-25 | 2017-10-30 | Mythili | 2017-10-30 | 2017-10-30 | Submitted | 2017-10-31
4ABO-65 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-25 | Keerthi | 2017-10-25 | 2017-10-26 | Anila | 2017-10-27 | 2017-10-27 | Submitted | 2017-10-27
2CAM-62 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-25 | Dhanya A | 2017-10-25 | 2017-10-26 | Anila | 2017-10-27 | 2017-10-27 | Submitted | 2017-10-31
5EDW-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-25 |  | 2017-10-25 | 2017-10-25 |  | 2017-10-25 | 2017-10-25 | Submitted | 2017-10-25
4FHL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-26 |  | 2017-10-26 | 2017-10-26 |  | 2017-10-26 | 2017-10-26 | Submitted | 2017-10-26
3KYG-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-26 | Sree Lekshmi | 2017-10-26 | 2017-10-27 | Mythili | 2017-10-30 | 2017-10-30 | PDC completed & AFR Submitted | 2017-11-03
3CTA-64 | H-A-H |  | Pre-Design | PDC |  | Submitted |  | 2017-10-27 | Dhanya A | 2017-10-27 | 2017-10-30 | Mythili | 2017-10-30 | 2017-10-31 | Submitted | 2017-10-31
4ALX-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-27 | Joju | 2017-10-27 | 2017-10-31 | Mythili | 2017-11-02 | 2017-11-02 | PDC completed & AFR Submitted | 2017-11-08
3RES-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-27 | Nina Sebastian | 2017-10-27 | 2017-10-31 | Mythili | 2017-10-31 | 2017-11-01 | PDC completed & AFR Submitted | 2017-11-02
3BAY-71 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-27 | Lisha Manuel | 2017-10-27 | 2017-11-02 | Mythili | 2017-11-03 | 2017-11-03 | PDC completed & AFR Submitted | 2017-11-03
2RDL-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-28 | Linda | 2017-10-28 | 2017-11-01 | Mythili | 2017-11-02 | 2017-11-02 | PDC completed & AFR Submitted | 2017-11-06
3KYG-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-27 | Sree Lekshmi | 2017-10-27 | 2017-10-30 | Mythili | 2017-10-30 | 2017-10-31 | PDC completed & AFR Submitted | 2017-11-03
4TGP-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-27 | Keerthi | 2017-10-27 | 2017-11-06 | Mythili | 2017-11-06 | 2017-11-06 | PDC completed & AFR Submitted | 2017-11-08
3RWO-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-26 |  | 2017-10-26 | 2017-10-26 |  | 2017-10-26 | 2017-10-26 | Submitted | 2017-10-26
2PYM-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-27 |  | 2017-10-27 | 2017-10-27 |  | 2017-10-27 | 2017-10-27 | Submitted | 2017-10-27
3BAY-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-27 |  | 2017-10-27 | 2017-10-27 |  | 2017-10-27 | 2017-10-27 | Submitted | 2017-10-27
4FHL-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-28 |  | 2017-10-28 | 2017-10-28 |  | 2017-10-28 | 2017-10-28 | Submitted | 2017-10-28
5NRW-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-28 |  | 2017-10-28 | 2017-10-28 |  | 2017-10-28 | 2017-10-28 | Submitted | 2017-10-28
2PET-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-28 |  | 2017-10-28 | 2017-10-28 |  | 2017-10-28 | 2017-10-28 | Submitted | 2017-10-28
5NRW-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-28 |  | 2017-10-28 | 2017-10-28 |  | 2017-10-28 | 2017-10-28 | Submitted | 2017-10-28
5NRW-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-28 |  | 2017-10-28 | 2017-10-28 |  | 2017-10-28 | 2017-10-28 | Submitted | 2017-10-28
5NRW-64 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-28 |  | 2017-10-28 | 2017-10-28 |  | 2017-10-28 | 2017-10-28 | Submitted | 2017-10-28
4CPR-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-28 |  | 2017-10-28 | 2017-10-28 |  | 2017-10-28 | 2017-10-28 | Submitted | 2017-10-28
3CAU-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-30 |  | 2017-10-30 | 2017-10-30 |  | 2017-10-30 | 2017-10-30 | Submitted | 2017-10-30
5WES-66 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-30 |  | 2017-10-30 | 2017-10-30 |  | 2017-10-30 | 2017-10-30 | Submitted | 2017-10-30
5WES-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-30 |  | 2017-10-30 | 2017-10-30 |  | 2017-10-30 | 2017-10-30 | Submitted | 2017-10-30
4ABO-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-30 |  | 2017-10-30 | 2017-10-30 |  | 2017-10-30 | 2017-10-30 | Submitted | 2017-10-30
3KYG-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-31 | Keerthi | 2017-10-31 | 2017-11-01 | Mythili | 2017-11-02 | 2017-11-03 | PDC completed & AFR Submitted | 2017-11-03
2PET-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-30 | Dhanya A | 2017-10-30 | 2017-10-30 | Mythili S | 2017-10-31 | 2017-10-31 | PDC completed & AFR Submitted | 2017-11-08
4ARU-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-31 | Dhanya A | 2017-10-31 | 2017-11-02 | Mythili | 2017-11-03 | 2017-11-06 | PDC completed & AFR Submitted | 2017-11-08
2RYD-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-31 | Sree Lekshmi | 2017-10-31 | 2017-11-01 | Mythili | 2017-11-01 | 2017-11-01 | PDC completed & AFR Submitted | 2017-11-08
2QUA-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-01 | Sree Lekshmi | 2017-11-01 | 2017-11-02 | Mythili | 2017-11-03 | 2017-11-06 | PDC completed & AFR Submitted | 2017-11-08
3RES-70 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-02 | Fausia | 2017-11-02 | 2017-11-08 | Mythili | 2017-11-09 | 2017-11-09 | PDC completed & AFR Submitted | 2017-11-10
3SCO-67 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-02 | Sree Lekshmi | 2017-11-02 | 2017-11-03 | Mythili | 2017-11-06 | 2017-11-06 | PDC completed & AFR Submitted | 2017-11-10
2GBE-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-02 | Asha Jacob | 2017-11-02 | 2017-11-02 | Mythili | 2017-11-03 | 2017-11-03 | PDC completed & AFR Submitted | 2017-11-08
3RES-68 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-02 | Joju | 2017-11-02 | 2017-11-08 | Mythili | 2017-11-09 | 2017-11-09 | PDC completed & AFR Submitted | 2017-11-10
3RES-67 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-10-25 | Minu | 2017-10-25 | 2017-10-31 | Mythili S | 2017-10-31 | 2017-10-31 | PDC completed & AFR Submitted | 2017-11-02
4CUR-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-30 |  | 2017-10-30 | 2017-10-30 |  | 2017-10-30 | 2017-10-30 | Submitted | 2017-10-30
3WIR-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-30 |  | 2017-10-30 | 2017-10-30 |  | 2017-10-30 | 2017-10-30 | Submitted | 2017-10-30
2PEN-67 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-02 |  | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Submitted | 2017-11-02
2CAM-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-03 | Dhanya A | 2017-11-03 | 2017-11-09 | Mythili | 2017-11-10 | 2017-11-10 | PDC completed & AFR Submitted | 2017-11-10
4RBN-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-03 | Sree Lekshmi | 2017-11-03 | 2017-11-03 | Mythili | 2017-11-06 | 2017-11-06 | PDC completed & AFR Submitted | 2017-11-08
2WRO-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-03 | Nina Sebastian | 2017-11-03 | 2017-11-10 | Mythili | 2017-11-10 | 2017-11-10 | PDC completed & AFR Submitted | 2017-11-13
3BLB-68 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-06 | Linda | 2017-11-06 | 2017-11-14 | Mythili | 2017-11-15 | 2017-11-15 | PDC completed & AFR Submitted | 2017-11-24
4SRW-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-02 |  | 2017-11-02 | 2017-11-02 |  | 2017-11-02 | 2017-11-02 | Submitted | 2017-11-02
3CTA-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-03 |  | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Submitted | 2017-11-03
2STL-61 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-03 |  | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Submitted | 2017-11-03
3KGP-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-03 |  | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Submitted | 2017-11-03
4SSB-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-03 |  | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Submitted | 2017-11-03
6GIR-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-03 |  | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Submitted | 2017-11-03
2HUR-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-03 |  | 2017-11-03 | 2017-11-03 |  | 2017-11-03 | 2017-11-03 | Submitted | 2017-11-03
2QUA-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-07 | Lisha Manuel | 2017-11-07 | 2017-11-09 | Mythili | 2017-11-10 | 2017-11-10 | PDC completed & AFR Submitted | 2017-11-10
3RES-72 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-07 | Keerthi | 2017-11-07 | 2017-11-09 | Mythili | 2017-11-15 | 2017-11-15 | PDC completed & AFR Submitted | 2017-11-28
4NDG-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-09 | Vrindha | 2017-11-09 | 2017-11-14 | Mythili | 2017-11-15 | 2017-11-15 | PDC completed & AFR Submitted | 2017-11-24
3OAK-69 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-06 |  | 2017-11-06 | 2017-11-06 |  | 2017-11-06 | 2017-11-06 | Submitted | 2017-11-06
5BRI-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-07 |  | 2017-11-07 | 2017-11-07 |  | 2017-11-07 | 2017-11-07 | Submitted | 2017-11-07
4CPR-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-07 |  | 2017-11-07 | 2017-11-07 |  | 2017-11-07 | 2017-11-07 | Submitted | 2017-11-07
4FHL-62 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-10-31 |  | 2017-10-31 | 2017-10-31 |  | 2017-10-31 | 2017-10-31 | Submitted | 2017-10-31
2HUR-65 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-07 |  | 2017-11-07 | 2017-11-07 |  | 2017-11-07 | 2017-11-07 | Submitted | 2017-11-07
4FHL-60 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-07 |  | 2017-11-07 | 2017-11-07 |  | 2017-11-07 | 2017-11-07 | Submitted | 2017-11-07
2LIV-63 | H-A-H |  | Pre-Design | Delta |  | Submitted |  | 2017-11-08 |  | 2017-11-08 | 2017-11-08 |  | 2017-11-08 | 2017-11-08 | Submitted | 2017-11-08
4LNH-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-09 | Fausia | 2017-11-09 | 2017-11-14 | Mythili | 2017-11-15 | 2017-11-16 | PDC completed & AFR Submitted | 2017-11-28
5HNL-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-09 | Joju | 2017-11-09 | 2017-11-15 | Mythili | 2017-11-17 | 2017-11-20 | PDC completed & AFR Submitted | 2017-11-24
2RYD-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 | Jainy Joseph | 2017-11-09 | 2017-11-11 | Joshlee | 2017-11-15 | 2017-11-15 | Delta completed & AFR submitted | 2017-11-15
5BRI-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 | Asha Jacob | 2017-11-09 | 2017-11-09 | Joshlee | 2017-11-10 | 2017-11-10 | Delta completed & AFR submitted | 2017-11-10
5NRW-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 | Asha Jacob | 2017-11-09 | 2017-11-09 | Joshlee | 2017-11-10 | 2017-11-10 | Delta completed & AFR submitted | 2017-11-10
2PET-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-10 | Asha Jacob | 2017-11-10 | 2017-11-13 | Joshlee | 2017-11-16 | 2017-11-16 | Delta completed & AFR submitted | 2017-11-16
2RYD-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-10 | Asha Jacob | 2017-11-10 | 2017-11-13 | Joshlee | 2017-11-16 | 2017-11-16 | Delta completed & AFR submitted | 2017-11-16
2PAR-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-10 | Minu | 2017-11-10 | 2017-11-10 | Anuja | 2017-11-13 | 2017-11-13 | Delta completed & AFR submitted | 2017-11-13
2RYD-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-10 | Minu | 2017-11-10 | 2017-11-10 | Joshlee | 2017-11-16 | 2017-11-16 | Delta completed & AFR submitted | 2017-11-09
2WRO-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-10 | Lisha Manuel | 2017-11-10 | 2017-11-20 | Mythili | 2017-11-21 | 2017-11-22 | PDC completed & AFR Submitted | 2017-11-28
4TGP-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-10 | Dhanya A | 2017-11-10 | 2017-11-21 | Minu | 2017-11-22 | 2017-11-22 | PDC completed & AFR Submitted | 2017-11-28
5NRW-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 |  | 2017-11-09 | 2017-11-09 |  | 2017-11-09 | 2017-11-09 | Delta completed & AFR submitted | 2017-11-09
3SSN-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 |  | 2017-11-09 | 2017-11-09 |  | 2017-11-09 | 2017-11-09 | Delta completed & AFR submitted | 2017-11-09
5BRI-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-08 |  | 2017-11-08 | 2017-11-08 |  | 2017-11-09 | 2017-11-09 | Delta completed & AFR submitted | 2017-11-09
3KYG-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 |  | 2017-11-09 | 2017-11-09 |  | 2017-11-09 | 2017-11-09 | Delta completed & AFR submitted | 2017-11-09
3MLN-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 |  | 2017-11-09 | 2017-11-09 |  | 2017-11-09 | 2017-11-09 | Delta completed & AFR submitted | 2017-11-09
5NRW-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 |  | 2017-11-09 | 2017-11-09 |  | 2017-11-09 | 2017-11-09 | Delta completed & AFR submitted | 2017-11-09
2PYM-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-09 |  | 2017-11-09 | 2017-11-09 |  | 2017-11-09 | 2017-11-09 | Delta completed & AFR submitted | 2017-11-09
4NDG-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-13 | Minu | 2017-11-13 | 2017-11-13 | Anuja | 2017-11-13 | 2017-11-13 | Delta completed & AFR submitted | 2017-11-13
3CAU-67 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-13 | Jainy Joseph | 2017-11-13 | 2017-11-13 | Anuja | 2017-11-13 | 2017-11-13 | Delta completed & AFR submitted | 2017-11-13
3HDB-68 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-13 | Jainy Joseph | 2017-11-13 | 2017-11-13 | Anuja | 2017-11-17 | 2017-11-17 | Delta completed & AFR submitted | 2017-11-17
3RES-71 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-13 | Nina Sebastian | 2017-11-13 | 2017-11-20 | Mythili | 2017-11-21 | 2017-11-22 | PDC completed & AFR Submitted | 2017-11-29 | Keerthi also working on this SAM
5NRW-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-10 |  | 2017-11-10 | 2017-11-10 |  | 2017-11-10 | 2017-11-10 | Delta completed & AFR submitted | 2017-11-10
5BRI-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-10 |  | 2017-11-10 | 2017-11-10 |  | 2017-11-10 | 2017-11-10 | Delta completed & AFR submitted | 2017-11-10
3CAN-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-14 | Jainy Joseph | 2017-11-14 | 2017-11-14 | Anuja | 2017-11-15 | 2017-11-15 | Delta completed & AFR submitted | 2017-11-15
5NRW-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-14 | Jainy Joseph | 2017-11-14 | 2017-11-14 | Anuja | 2017-11-16 | 2017-11-16 | Delta completed & AFR submitted | 2017-11-16
5BRI-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-14 | Jainy Joseph | 2017-11-14 | 2017-11-14 | Anuja | 2017-11-17 | 2017-11-17 | Delta completed & AFR submitted | 2017-11-17
2RYD-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-13 | Asha Jacob | 2017-11-13 | 2017-11-13 | Joshlee | 2017-11-16 | 2017-11-16 | Delta completed & AFR submitted | 2017-11-16
2HUR-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-14 | Asha Jacob | 2017-11-14 | 2017-11-14 | Fausia | 2017-11-16 | 2017-11-16 | Delta completed & AFR submitted | 2017-11-17
2PET-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-14 | Sree Lekshmi | 2017-11-14 | 2017-11-14 | Joshlee | 2017-11-16 | 2017-11-16 | Delta completed & AFR submitted | 2017-11-16
6SUB-24 | H-A-H |  | Pre-Design | PDC |  | QA Completed - Ready for submission |  | 2017-11-15 | Vrindha | 2017-11-15 | 2017-11-15 | Mythili | 2017-11-17 | 2017-11-17 | QA Completed - Ready for submission
2HUR-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-07 | Minu | 2017-11-07 | 2017-11-07 | Anuja | 2017-11-13 | 2017-11-13 | Delta completed & AFR submitted | 2017-11-13
4CHL-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-08 | Jainy Joseph | 2017-11-08 | 2017-11-08 | Joshlee | 2017-11-09 | 2017-11-09 | Delta completed & AFR submitted | 2017-11-14
4SRW-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-15 | Sree Lekshmi | 2017-11-15 | 2017-11-15 | Anuja | 2017-11-20 | 2017-11-20 | Delta completed & AFR submitted | 2017-11-20
2WET-60 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-15 | 2017-11-15 | AFR Load Completed & Posted
3CAN-61 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-15 | 2017-11-15 | AFR Load Completed & Posted
4CPB-60 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-15 | 2017-11-15 | AFR Load Completed & Posted
2HUR-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-15 | Asha Jacob | 2017-11-15 | 2017-11-15 | Fausia | 2017-11-16 | 2017-11-16 | Delta completed & AFR submitted | 2017-11-17
3NES-64 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-16 | 2017-11-17 | AFR Load Completed & Posted
4TGP-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-16 | Asha Jacob | 2017-11-16 | 2017-11-16 | Joshlee | 2017-11-17 | 2017-11-17 | Delta completed & AFR submitted | 2017-11-17
2SEV-20 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-16 | Sree Lekshmi | 2017-11-16 | 2017-11-16 | Joshlee | 2017-11-20 | 2017-11-20 | Delta completed & AFR submitted | 2017-11-20
3KGP-66 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-16 | Vrindha | 2017-11-16 | 2017-11-21 | Mythili S | 2017-11-24 | 2017-11-24 | PDC completed & AFR Submitted | 2017-12-29
6GIR-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-16 | Asha Jacob | 2017-11-17 | 2017-11-17 | Joshlee | 2017-11-20 | 2017-11-20 | Delta completed & AFR submitted | 2017-11-20
2CAS-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-17 | Sree Lekshmi | 2017-11-17 | 2017-11-17 | Anuja | 2017-11-22 | 2017-11-22 | Delta completed & AFR submitted | 2017-11-22
4AGV-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-17 | Sree Lekshmi | 2017-11-17 | 2017-11-17 | Joshlee | 2017-11-21 | 2017-11-21 | Delta completed & AFR submitted | 2017-11-21
3SSN-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-20 | Joju | 2017-11-20 | 2017-11-24 | Mythili S | 2017-11-27 | 2017-11-29 | PDC completed & AFR Submitted | 2017-11-29
4BEE-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-20 | Keerthi | 2017-11-20 | 2017-11-27 | Mythili S | 2017-11-27 | 2017-11-28 | PDC completed & AFR Submitted | 2017-11-29
3MIT-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-20 | Minu | 2017-11-20 | 2017-11-20 | Joshlee | 2017-11-21 | 2017-11-21 | Delta completed & AFR submitted | 2017-11-21
2HUR-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-20 | Minu | 2017-11-20 | 2017-11-20 | Joshlee | 2017-11-21 | 2017-11-21 | Delta completed & AFR submitted | 2017-11-21
3KYG-69 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-20 | Sree Lekshmi | 2017-11-20 | 2017-11-20 | Anuja | 2017-11-21 | 2017-11-21 | Delta completed & AFR submitted | 2017-11-21
2RYD-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-20 | Sree Lekshmi | 2017-11-20 | 2017-11-20 | Joshlee | 2017-11-28 | 2017-11-28 | Delta completed & AFR submitted | 2017-11-28
2PEN-01 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-21 | Asha Jacob | 2017-11-21 | 2017-11-21 | Joshlee | 2017-11-21 | 2017-11-21 | Delta completed & AFR submitted | 2017-11-21
2HLS-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-22 | Asha Jacob | 2017-11-22 | 2017-11-22 | Joshlee | 2017-11-22 | 2017-11-22 | Delta completed & AFR submitted | 2017-11-22
3NES-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-07 | Minu | 2017-11-07 | 2017-11-07 | Mythili S | 2017-11-07 | 2017-11-07 | Delta completed & AFR submitted | 2017-11-17
2ING-62 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Mythili S | 2017-11-20 | 2017-11-21 | AFR Load Completed & Posted
2LIV-62 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-23 | 2017-12-05 | AFR Load Completed & Posted | 1. Records with status error in the report generated.
3NES-61 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Mythili S | 2017-11-20 | 2017-11-21 | AFR Load Completed & Posted
3HDB-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-21 | Lisha Manuel | 2017-11-21 | 2017-11-22 | Mythili S | 2017-11-27 | 2017-11-28 | PDC completed & AFR Submitted | 2017-11-29
3WIR-66 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-21 | Nina Sebastian | 2017-11-21 | 2017-11-21 | Minu | 2017-11-22 | 2017-11-22 | PDC completed & AFR Submitted | 2017-11-29
3OAK-69 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-20 | Minu | 2017-11-20 | 2017-11-20 | Joshlee | 2017-12-01 | 2017-12-01 | Delta completed & AFR submitted | 2017-12-01
2RDL-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-22 | Sree Lekshmi | 2017-11-22 | 2017-11-22 | Joshlee | 2017-11-23 | 2017-11-23 | Delta completed & AFR submitted | 2017-11-23
3TNB-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-21 | Minu | 2017-11-21 | 2017-11-21 | Anuja | 2017-12-04 | 2017-12-04 | Delta completed & AFR submitted | 2017-12-04
3DNC-66 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-22 | Dhanya A | 2017-11-22 | 2017-11-22 | Mythili S | 2017-11-27 | 2017-11-28 | PDC completed & AFR Submitted | 2017-11-28
3WIR-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-22 | Nina Sebastian | 2017-11-22 | 2017-11-22 | Mythili S | 2017-12-01 | 2017-12-04 | PDC completed & AFR Submitted | 2017-12-12
6ELB-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-22 | Vrindha | 2017-11-22 | 2017-11-22 | Mythili S | 2018-01-08 | 2018-01-08 | PDC completed & AFR Submitted | 2018-01-09
2WET-64 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-22 | 2017-11-23 | AFR Load Completed & Posted
4CHL-70 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-21 | Minu | 2017-11-21 | 2017-11-21 | Joshlee | 2017-11-22 | 2017-11-22 | Delta completed & AFR submitted | 2017-11-22
4CHP-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-21 | Minu | 2017-11-21 | 2017-11-21 | Anuja | 2017-12-05 | 2017-12-05 | Delta completed & AFR submitted | 2017-12-05
2PYM-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-24 | Fausia | 2017-11-24 | 2017-11-24 | Joshlee | 2017-11-27 | 2017-11-27 | Delta completed & AFR submitted | 2017-11-27
3WHL-65 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-22 | 2017-11-29 | AFR Load Completed & Posted | 1. Issue in PUR generation. Raised IT Central request. 2. PUR contains 3 PDB poles from near by SAM which is already posted.
3CTA-61 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Mythili S | 2017-11-23 | 2017-11-27 | AFR Load Completed & Posted | 1. Issue in TPNI poles drawings.Mailed Varun for confirmation.
4PDP-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-22 | Sree Lekshmi | 2017-11-22 | 2017-11-22 | Anuja | 2017-12-04 | 2017-12-04 | Delta completed & AFR submitted | 2017-12-04
2PET-68 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-22 | Sree Lekshmi | 2017-11-22 | 2017-11-22 | Joshlee | 2017-11-23 | 2017-11-23 | Delta completed & AFR submitted | 2017-11-23
5GUG-65 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Mythili S | 2017-11-23 | 2017-11-23 | AFR Load Completed & Posted
3RWO-67 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-23 | Vrindha | 2017-11-23 | 2017-11-28 | Mythili S | 2017-11-30 | 2017-12-01 | PDC completed & AFR Submitted | 2017-12-01
4BEE-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-23 | Lisha Manuel | 2017-11-23 | 2017-11-29 | Mythili S | 2017-11-30 | 2017-12-01 | PDC completed & AFR Submitted | 2017-12-01
4BEE-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-23 | Nina Sebastian | 2017-11-23 | 2017-11-29 | Mythili S | 2017-12-01 | 2017-12-01 | PDC completed & AFR Submitted | 2017-12-01
6MLO-21 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-23 | Dhanya A | 2017-11-23 | 2017-11-23 | Mythili S | 2018-01-12 | 2018-01-12 | PDC completed & AFR Submitted | 2018-01-19
3TNB-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-24 | Dhanya A | 2017-11-24 | 2017-11-29 | Mythili S | 2017-11-30 | 2017-12-01 | PDC completed & AFR Submitted | 2017-12-01
2HUR-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-24 | Sree Lekshmi | 2017-11-24 | 2017-11-24 | Joshlee | 2017-11-24 | 2017-11-24 | Delta completed & AFR submitted | 2017-11-24
2CHA-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-24 | Sree Lekshmi | 2017-11-24 | 2017-11-24 | Anuja | 2017-12-05 | 2017-12-05 | Delta completed & AFR submitted | 2017-12-05
2RYD-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-28 | Fausia | 2017-11-28 | 2017-11-28 | Joshlee | 2017-11-28 | 2017-11-28 | Delta completed & AFR submitted | 2017-11-28
2RYD-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-27 | Asha Jacob | 2017-11-27 | 2017-11-27 | Joshlee | 2017-11-28 | 2017-11-28 | Delta completed & AFR submitted | 2017-11-28
2CAM-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-27 | Sree Lekshmi | 2017-11-27 | 2017-11-27 | Anuja | 2017-12-05 | 2017-12-05 | Delta completed & AFR submitted | 2017-12-05
2CAR-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-27 | Joju | 2017-11-27 | 2017-11-30 | Mythili S | 2017-12-01 | 2017-12-01 | PDC completed & AFR Submitted | 2017-12-01 | Sreelekshmi helping Joju with this SAM.
3TNB-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-27 | Keerthi | 2017-11-27 | 2017-11-30 | Mythili S | 2017-12-04 | 2017-12-04 | PDC completed & AFR Submitted | 2017-12-04
2RDL-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-27 | Sree Lekshmi | 2017-11-27 | 2017-11-27 | Anuja | 2017-12-08 | 2017-12-08 | Delta completed & AFR submitted | 2017-12-08
5NRW-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-29 | Asha Jacob | 2017-11-29 | 2017-11-29 | Joshlee | 2017-11-30 | 2017-11-30 | Delta completed & AFR submitted | 2017-11-30
3RES-66 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-28 | Vrindha | 2017-11-28 | 2017-12-01 | Mythili S | 2017-12-04 | 2017-12-04 | PDC completed & AFR Submitted | 2017-12-05
3HDB-68 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-29 | Fausia | 2017-11-29 | 2017-11-29 | Joshlee | 2017-11-30 | 2017-11-30 | Delta completed & AFR submitted | 2017-11-30
3CAN-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-11-20 | Sree Lekshmi | 2017-11-20 | 2017-11-20 | Joshlee | 2017-11-29 | 2017-11-30 | Delta completed & AFR submitted | 2017-11-30
5WES-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-01 | Asha Jacob | 2017-12-01 | 2017-12-01 | Joshlee | 2017-12-06 | 2017-12-06 | Delta completed & AFR submitted | 2017-12-06
3RES-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-30 | Dhanya A | 2017-11-30 | 2017-12-05 | Mythili S | 2017-12-05 | 2017-12-05 | PDC completed & AFR Submitted | 2017-12-05 | Lisha helping Dhanya with this SAM
5SAL-64 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-30 | 2017-11-30 | AFR Load Completed & Posted
3RES-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-11-30 | Joju | 2017-11-30 | 2017-12-04 | Mythili S | 2017-12-05 | 2017-12-05 | PDC completed & AFR Submitted | 2017-12-05 | Keerthi helping Joju with this SAM.
3FNT-67 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-30 | 2017-12-04 | AFR Load Completed & Posted | Duplicates in PUR-B
3NAW-64 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-11-30 | 2017-12-01 | AFR Load Completed & Posted
3HDB-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-01 | Sree Lekshmi | 2017-12-01 | 2017-12-01 | Anuja | 2017-12-11 | 2017-12-11 | Delta completed & AFR submitted | 2017-12-11
2GBE-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-01 | Sree Lekshmi | 2017-12-01 | 2017-12-01 | Anuja | 2017-12-08 | 2017-12-08 | Delta completed & AFR submitted | 2017-12-08
3DAD-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-04 | Nina Sebastian | 2017-12-04 | 2017-12-04 | Anuja | 2017-12-06 | 2017-12-06 | PDC completed & AFR Submitted | 2017-12-06 | The name of the SAM 3DAD-62 changed to 3DAD-68 and the folder for 3DAD-68 was not avaialable in Connect MTM. Awaiting confirmation from ConnectMTM team for AFR submission.Hence delay in AFR submission.
2QUA-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-04 | Keerthi | 2017-12-04 | 2017-12-04 | Mythili S | 2017-12-05 | 2017-12-05 | PDC completed & AFR Submitted | 2017-12-06
3WIR-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-01 | Asha Jacob | 2017-12-01 | 2017-12-01 | Joshlee | 2017-12-05 | 2017-12-05 | Delta completed & AFR submitted | 2017-12-05
2WRO-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-04 | Asha Jacob | 2017-12-04 | 2017-12-05 | Joshlee | 2017-12-06 | 2017-12-06 | Delta completed & AFR submitted | 2017-12-06
2GBE-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-04 | Sree Lekshmi | 2017-12-04 | 2017-12-04 | Anuja | 2017-12-12 | 2017-12-12 | Delta completed & AFR submitted | 2017-12-12
5WES-62 | H-A-H |  | Pre-Design | Delta |  | In Progress-Delta |  | 2017-12-04 | Sree Lekshmi | 2017-12-04 | 2017-12-04 |  |  |  | In Progress-Delta completed
4ABO-69 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-05 | Vrindha | 2017-12-05 | 2017-12-07 | Mythili S | 2017-12-08 | 2017-12-08 | PDC completed & AFR Submitted | 2017-12-12
4CHL-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-05 | Keerthi | 2017-12-05 | 2017-12-08 | Mythili S | 2017-12-11 | 2017-12-11 | PDC completed & AFR Submitted | 2017-12-12
2GBE-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-05 | Nina Sebastian | 2017-12-05 | 2017-12-06 | Mythili S | 2017-12-08 | 2017-12-08 | PDC completed & AFR Submitted | 2017-12-12
2CHA-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-05 | Joju | 2017-12-05 | 2017-12-08 | Mythili S | 2017-12-11 | 2017-12-11 | PDC completed & AFR Submitted | 2017-12-12
2RYD-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-04 | Sree Lekshmi | 2017-12-04 | 2017-12-04 | Anuja | 2017-12-08 | 2017-12-08 | Delta completed & AFR submitted | 2017-12-08
4TGP-67 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-05 | Sree Lekshmi | 2017-12-05 | 2017-12-05 | Anuja | 2017-12-08 | 2017-12-08 | Delta completed & AFR submitted | 2017-12-08
3KYG-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-05 | Sree Lekshmi | 2017-12-05 | 2017-12-05 | Anuja | 2017-12-12 | 2017-12-12 | Delta completed & AFR submitted | 2017-12-12
5NRW-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-05 | Sree Lekshmi | 2017-12-05 | 2017-12-05 | Joshlee | 2017-12-12 | 2017-12-12 | Delta completed & AFR submitted | 2017-12-12
4LNH-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-05 | Sree Lekshmi | 2017-12-05 | 2017-12-05 | Anuja | 2017-12-08 | 2017-12-08 | Delta completed & AFR submitted | 2017-12-08
3RES-68 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-04 | Asha Jacob | 2017-12-04 | 2017-12-05 | Joshlee | 2017-12-06 | 2017-12-06 | Delta completed & AFR submitted | 2017-12-06
3WHL-60 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-06 | 2017-12-06 | AFR Load Completed & Posted
3CTA-67 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-06 | 2017-12-07 | AFR Load Completed & Posted
4PDP-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-06 | Linda | 2017-12-06 | 2017-12-07 | Mythili S | 2017-12-08 | 2017-12-08 | PDC completed & AFR Submitted | 2017-12-20
3TNB-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-06 | Lisha Manuel | 2017-12-06 | 2017-12-14 | Mythili S | 2017-12-18 | 2017-12-18 | PDC completed & AFR Submitted | 2017-12-19
4LNH-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-06 | Dhanya A | 2017-12-06 | 2017-12-12 | Mythili S | 2017-12-13 | 2017-12-14 | PDC completed & AFR Submitted | 2017-12-19
4CHL-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-06 | Asha Jacob | 2017-12-06 | 2017-12-06 | Joshlee | 2017-12-06 | 2017-12-06 | Delta completed & AFR submitted | 2017-12-06
4TGP-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-06 | Sree Lekshmi | 2017-12-06 | 2017-12-06 | Anuja | 2017-12-08 | 2017-12-08 | Delta completed & AFR submitted | 2017-12-08
4TGP-68 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-06 | Sree Lekshmi | 2017-12-06 | 2017-12-06 | Anuja | 2017-12-13 | 2017-12-13 | Delta completed & AFR submitted | 2017-12-13
3NBA-70 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-06 | Sree Lekshmi | 2017-12-06 | 2017-12-06 | Anuja | 2017-12-11 | 2017-12-11 | Delta completed & AFR submitted | 2017-12-11
2KNS-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-07 | Nina Sebastian | 2017-12-07 | 2017-12-08 | Mythili S | 2017-12-11 | 2017-12-11 | PDC completed & AFR Submitted | 2017-12-19
3BNT-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-07 | Linda | 2017-12-07 | 2017-12-08 | Mythili S | 2017-12-11 | 2017-12-11 | PDC completed & AFR Submitted | 2017-12-20
3MIT-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-07 | Sree Lekshmi | 2017-12-07 | 2017-12-07 | Anuja | 2017-12-11 | 2017-12-11 | Delta completed & AFR submitted | 2017-12-11
2GBE-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-07 | Sree Lekshmi | 2017-12-07 | 2017-12-07 | Anuja | 2017-12-08 | 2017-12-08 | Delta completed & AFR submitted | 2017-12-08
4FHL-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-08 | Sree Lekshmi | 2017-12-08 | 2017-12-08 | Anuja | 2017-12-14 | 2017-12-14 | Delta completed & AFR submitted | 2017-12-14
3RES-72 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-08 | Asha Jacob | 2017-12-08 | 2017-12-08 | Joshlee | 2017-12-11 | 2017-12-11 | Delta completed & AFR submitted | 2017-12-11
3RES-70 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-11 | Asha Jacob | 2017-12-11 | 2017-12-11 | Joshlee | 2017-12-12 | 2017-12-12 | Delta completed & AFR submitted | 2017-12-12
5WES-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-07 | Sree Lekshmi | 2017-12-07 | 2017-12-07 | Anuja | 2017-12-13 | 2017-12-13 | Delta completed & AFR submitted | 2017-12-13
4ABC-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-07 | Sree Lekshmi | 2017-12-07 | 2017-12-07 | Anuja | 2017-12-12 | 2017-12-12 | Delta completed & AFR submitted | 2017-12-12
3BNT-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-11 | Nina Sebastian | 2017-12-11 | 2017-12-13 | Mythili S | 2017-12-14 | 2017-12-15 | PDC completed & AFR Submitted | 2017-12-20
4ABO-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-11 | Joju | 2017-12-11 | 2017-12-12 | Mythili S | 2017-12-13 | 2017-12-14 | PDC completed & AFR Submitted | 2017-12-20
3STK-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-11 | Vrindha | 2017-12-11 | 2017-12-11 | Mythili S | 2017-12-12 | 2017-12-12 | PDC completed & AFR Submitted | 2017-12-20
3BGO-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-11 | Keerthi | 2017-12-11 | 2017-12-13 | Mythili S | 2017-12-14 | 2017-12-15 | PDC completed & AFR Submitted | 2017-12-20
2LAK-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-11 | Linda | 2017-12-11 | 2017-12-13 | Mythili S | 2017-12-14 | 2017-12-15 | PDC completed & AFR Submitted | 2017-12-20
3SPL-63 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-11 | 2017-12-11 | AFR Load Completed & Posted
3HGT-66 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-11 | 2017-12-11 | AFR Load Completed & Posted
3KEW-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-11 | Minu | 2017-12-11 | 2017-12-11 | Mythili S | 2017-12-12 | 2017-12-12 | PDC completed & AFR Submitted | 2017-12-29
4TWO-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-11 | Vrindha | 2017-12-11 | 2017-12-11 | Mythili S | 2017-12-12 | 2017-12-12 | PDC completed & AFR Submitted | 2017-12-20
2CRR-70 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-12 | 2017-12-12 | AFR Load Completed & Posted
3HGT-73 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-12 | 2017-12-12 | AFR Load Completed & Posted
5SAL-66 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-12 | 2017-12-13 | AFR Load Completed & Posted
5NRW-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-11 | Asha Jacob | 2017-12-11 | 2017-12-11 | Joshlee | 2017-12-12 | 2017-12-12 | Delta completed & AFR submitted | 2017-12-12
4BLH-01 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-12 | Vrindha | 2017-12-12 | 2017-12-13 | Mythili S | 2017-12-13 | 2017-12-14 | PDC completed & AFR Submitted | 2017-12-28
2RDL-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-12 | Asha Jacob | 2017-12-12 | 2017-12-12 | Joshlee | 2017-12-13 | 2017-12-13 | Delta completed & AFR submitted | 2017-12-13
4ALX-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-12 | Asha Jacob | 2017-12-12 | 2017-12-12 | Joshlee | 2017-12-13 | 2017-12-13 | Delta completed & AFR submitted | 2017-12-13
2CAM-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-12 | Asha Jacob | 2017-12-12 | 2017-12-12 | Joshlee | 2017-12-19 | 2017-12-19 | Delta completed & AFR submitted | 2017-12-19
5WES-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-12 | Asha Jacob | 2017-12-12 | 2017-12-12 | Joshlee | 2017-12-19 | 2017-12-19 | Delta completed & AFR submitted | 2017-12-19
2RYD-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-12 | Asha Jacob | 2017-12-12 | 2017-12-12 | Joshlee | 2017-12-13 | 2017-12-13 | Delta completed & AFR submitted | 2017-12-13
3TNB-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-13 | Joju | 2017-12-13 | 2017-12-21 | Mythili S | 2017-12-22 | 2017-12-22 | PDC completed & AFR Submitted | 2017-12-29
4SRW-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-13 | Dhanya A | 2017-12-13 | 2017-12-21 | Mythili S | 2017-12-21 | 2017-12-21 | PDC completed & AFR Submitted | 2017-12-29
2LAK-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-13 | Vrindha | 2017-12-13 | 2017-12-14 | Mythili S | 2017-12-18 | 2017-12-18 | PDC completed & AFR Submitted | 2017-12-29
5HPS-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-13 | Keerthi | 2017-12-13 | 2017-12-18 | Mythili S | 2017-12-19 | 2017-12-19 | PDC completed & AFR Submitted | 2017-12-19
3CTA-68 | H-A-H |  | Pre-Design | PDC |  | On Hold | [11 empty] | Jainy Joseph | 2017-12-14 |  | On Hold | 14/12/2017:Error in output report generated, Raised Incident for the same.
2CAR-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-14 | Sree Lekshmi | 2017-12-14 | 2017-12-14 | Joshlee | 2017-12-21 | 2017-12-22 | Delta completed & AFR submitted | 2017-12-22
3RES-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-14 | Nina Sebastian | 2017-12-14 | 2017-12-14 | Anuja | 2018-01-03 | 2018-01-03 | Delta completed & AFR submitted | 2018-01-03
2RYD-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-13 | Asha Jacob | 2017-12-13 | 2017-12-13 | Anuja | 2017-12-18 | 2017-12-18 | Delta completed & AFR submitted | 2017-12-18
5NRW-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-14 | Asha Jacob | 2017-12-14 | 2017-12-14 | Joshlee | 2017-12-20 | 2017-12-20 | Delta completed & AFR submitted | 2017-12-20
2RDL-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-13 | Sree Lekshmi | 2017-12-13 | 2017-12-13 | Joshlee | 2017-12-20 | 2017-12-20 | Delta completed & AFR submitted | 2017-12-20
3BAY-67 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-13 | Sree Lekshmi | 2017-12-13 | 2017-12-13 | Anuja | 2017-12-15 | 2017-12-15 | Delta completed & AFR submitted | 2017-12-15
4TWO-21 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-15 | Nina Sebastian | 2017-12-15 | 2017-12-21 | Mythili S | 2017-12-22 | 2017-12-22 | PDC completed & AFR Submitted | 2017-12-29 | Sree helping with this SAM from 20-Dec-2017
2LAK-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-15 | Lisha Manuel | 2017-12-15 | 2017-12-21 | Mythili S | 2017-12-21 | 2017-12-21 | PDC completed & AFR Submitted | 2017-12-29
2CHA-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-15 | Sree Lekshmi | 2017-12-15 | 2017-12-15 | Anuja | 2017-12-19 | 2017-12-19 | Delta completed & AFR submitted | 2017-12-19
2EPP-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-19 | Asha Jacob | 2017-12-19 | 2017-12-19 | Joshlee | 2017-12-20 | 2017-12-20 | Delta completed & AFR submitted | 2017-12-20
4ABC-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-14 | Sree Lekshmi | 2017-12-14 | 2017-12-14 | Anuja | 2017-12-18 | 2017-12-18 | Delta completed & AFR submitted | 2017-12-18
2ERP-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-15 | Vrindha | 2017-12-15 | 2017-12-15 | Mythili S | 2017-12-19 | 2017-12-19 | PDC completed & AFR Submitted | 2017-12-29
2RAM-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-18 | Minu | 2017-12-18 | 2017-12-21 | Mythili S | 2017-12-22 | 2017-12-22 | PDC completed & AFR Submitted | 2017-12-29
2CHA-20 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-18 | Vrindha | 2017-12-18 | 2017-12-18 | Mythili S | 2017-12-19 | 2017-12-19 | PDC completed & AFR Submitted | 2017-12-29
3RES-68 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-18 | Sree Lekshmi | 2017-12-18 | 2017-12-18 | Mythili S | 2017-12-20 | 2017-12-20 | Delta completed & AFR submitted | 2017-12-20
3KYG-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-18 | Sree Lekshmi | 2017-12-18 | 2017-12-18 | Anuja | 2017-12-21 | 2017-12-21 | Delta completed & AFR submitted | 2017-12-21
5NRW-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-18 | Sree Lekshmi | 2017-12-18 | 2017-12-18 | Anuja | 2017-12-20 | 2017-12-20 | Delta completed & AFR submitted | 2017-12-20
5BRI-20 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-18 | Vrindha | 2017-12-18 | 2017-12-19 | Mythili S | 2017-12-20 | 2017-12-20 | PDC completed & AFR Submitted | 2018-01-04
2WET-62 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-19 | 2017-12-19 | AFR Load Completed & Posted
4SLA-60 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-19 | 2017-12-26 | AFR Load Completed & Posted | 19/12/2017: Error faced. Incident raised 26/12/2017:Issue resolved
2RYD-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-19 | Sree Lekshmi | 2017-12-19 | 2017-12-19 | Anuja | 2017-12-22 | 2017-12-22 | Delta completed & AFR submitted | 2017-12-22
4ARU-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-19 | Sree Lekshmi | 2017-12-19 | 2017-12-19 | Anuja | 2017-12-21 | 2017-12-21 | Delta completed & AFR submitted | 2017-12-21
3BAY-71 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-19 | Sree Lekshmi | 2017-12-19 | 2017-12-19 | Anuja | 2017-12-19 | 2017-12-19 | Delta completed & AFR submitted | 2017-12-19
3NBA-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-20 | Vrindha | 2017-12-20 | 2017-12-26 | Mythili S | 2018-01-02 | 2018-01-02 | PDC completed & AFR Submitted | 2018-01-05
5GLL-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-20 | Asha Jacob | 2017-12-20 | 2017-12-20 | Joshlee | 2017-12-20 | 2017-12-20 | Delta completed & AFR submitted | 2017-12-20
2CAR-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-20 | Asha Jacob | 2017-12-20 | 2017-12-20 | Joshlee | 2017-12-21 | 2017-12-22 | Delta completed & AFR submitted | 2017-12-22
3RES-71 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-21 | Asha Jacob | 2017-12-21 | 2017-12-21 | Joshlee | 2017-12-22 | 2017-12-22 | Delta completed & AFR submitted | 2017-12-22
5HNL-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-22 | Sree Lekshmi | 2017-12-22 | 2017-12-22 | Anuja | 2017-12-22 | 2017-12-22 | Delta completed & AFR submitted | 2017-12-22
2PET-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-22 | Sree Lekshmi | 2017-12-22 | 2017-12-22 | Anuja | 2017-12-26 | 2017-12-27 | Delta completed & AFR submitted | 2017-12-27
5WES-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-21 | Asha Jacob | 2017-12-21 | 2017-12-21 | Joshlee | 2017-12-22 | 2017-12-22 | Delta completed & AFR submitted | 2017-12-22
2CAR-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-22 | Asha Jacob | 2017-12-22 | 2017-12-22 | Joshlee | 2017-12-22 | 2017-12-22 | Delta completed & AFR submitted | 2017-12-22
2QUA-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-22 | Asha Jacob | 2017-12-22 | 2017-12-22 | Joshlee | 2017-12-22 | 2017-12-22 | Delta completed & AFR submitted | 2017-12-22
4SLA-69 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-22 | 2017-12-22 | AFR Load Completed & Posted
4BEE-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-22 | Lisha | 2017-12-22 | 2018-01-02 | Mythili S | 2018-01-03 | 2018-01-03 | PDC completed & AFR Submitted | 2018-01-04
2LAK-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-22 | Dhanya | 2017-12-22 | 2018-01-02 | Mythili S | 2018-01-03 | 2018-01-04 | PDC completed & AFR Submitted | 2018-01-04
4TWO-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-22 | Minu | 2017-12-22 | 2018-01-04 | Mythili S | 2018-01-04 | 2018-01-05 | PDC completed & AFR Submitted | 2018-01-05
4SRW-67 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-22 | Keerthi | 2017-12-22 | 2018-01-03 | Mythili S | 2018-01-04 | 2018-01-05 | PDC completed & AFR Submitted | 2018-01-05
2RAM-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-26 | Vrindha | 2017-12-26 | 2018-01-03 | Mythili S | 2018-01-03 | 2018-01-05 | PDC completed & AFR Submitted | 2018-01-05
4ABC-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-26 | Sree Lekshmi | 2017-12-26 | 2017-12-26 | Anuja | 2017-12-27 | 2017-12-27 | Delta completed & AFR submitted | 2017-12-27
4TWO-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-26 | Sree Lekshmi | 2017-12-26 | 2018-01-03 | Mythili S | 2018-01-04 | 2018-01-05 | PDC completed & AFR Submitted | 2018-01-05
5SAL-68 | H-A-H |  | Pre-Design | PDC |  | AFR Load Completed & Posted | [11 empty] | Jainy Joseph | 2017-12-26 | 2017-12-28 | AFR Load Completed & Posted
3RES-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-26 | Asha Jacob | 2017-12-26 | 2017-12-26 | Joshlee | 2017-12-28 | 2017-12-28 | Delta completed & AFR submitted | 2017-12-28
4TGP-67 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-26 | Asha Jacob | 2017-12-26 | 2017-12-26 | Joshlee | 2017-12-28 | 2017-12-28 | Delta completed & AFR submitted | 2017-12-28
3DPD-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2017-12-27 | Joju | 2017-12-27 | 2017-12-29 | Mythili S | 2018-01-02 | 2018-01-02 | PDC completed & AFR Submitted | 2018-01-05
3CTA-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-28 | Nina | 2017-12-28 | 2017-12-28 | Anuja | 2017-12-28 | 2017-12-28 | Delta completed & AFR submitted | 2017-12-28
4TGP-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-29 | Joshlee | 2017-12-29 | 2017-12-29 | Sree Lekshmi | 2017-12-29 | 2017-12-29 | Delta completed & AFR submitted | 2018-01-10
3KYG-68 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-01 | Linda | 2018-01-01 | 2018-01-01 | Mythili S | 2018-01-02 | 2018-01-03 | PDC completed & AFR Submitted | 2018-01-05
2QUA-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-01 | Joju | 2018-01-01 | 2018-01-04 | Mythili S | 2018-01-05 | 2018-01-05 | PDC completed & AFR Submitted | 2018-01-05
3TNB-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2017-12-29 | Asha Jacob | 2017-12-29 | 2017-12-29 | Joshlee | 2018-01-01 | 2018-01-01 | Delta completed & AFR submitted | 2018-01-01
2QUA-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-01 | Nina | 2018-01-01 | 2018-01-02 | Anuja | 2018-01-02 | 2018-01-02 | Delta completed & AFR submitted | 2018-01-02
3BNT-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-02 | Linda | 2018-01-02 | 2018-01-03 | Mythili S | 2018-01-04 | 2018-01-05 | PDC completed & AFR Submitted | 2018-01-05
3KEW-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-01 | Jumana | 2018-01-01 | 2018-01-02 | Mythili S | 2018-01-05 | 2018-01-05 | PDC completed & AFR Submitted | 2018-01-05
3RES-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-03 | Linda | 2018-01-04 | 2018-01-08 | Mythili S | 2018-01-08 | 2018-01-09 | PDC completed & AFR Submitted | 2018-01-09
2CAM-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-03 | Sree Lekshmi | 2018-01-03 | 2018-01-03 | Anuja | 2018-01-24 | 2018-01-24 | Delta completed & AFR submitted | 2018-01-24
2BOT-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-03 | Lisha | 2018-01-03 | 2018-01-05 | Mythili S | 2018-01-05 | 2018-01-05 | PDC completed & AFR Submitted | 2018-01-05
2WRO-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-03 | Nina | 2018-01-03 | 2018-01-03 | Anuja | 2018-01-10 | 2018-01-10 | Delta completed & AFR submitted | 2018-01-10
3HDB-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-03 | Asha Jacob | 2018-01-03 | 2018-01-03 | Minu | 2018-01-04 | 2018-01-04 | Delta completed & AFR submitted | 2018-01-05
3SSN-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-03 | Asha Jacob | 2018-01-03 | 2018-01-03 | Minu | 2018-01-04 | 2018-01-04 | Delta completed & AFR submitted | 2018-01-10
4TGP-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-03 | Asha Jacob | 2018-01-03 | 2018-01-03 | Minu | 2018-01-08 | 2018-01-08 | Delta completed & AFR submitted | 2018-01-08
2PEN-01 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-03 | Asha Jacob | 2018-01-03 | 2018-01-03 | Anuja | 2018-01-08 | 2018-01-08 | Delta completed & AFR submitted | 2018-01-08
2PET-71 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-04 | Sree Lekshmi | 2018-01-04 | 2018-01-04 | Anuja | 2018-01-12 | 2018-01-12 | Delta completed & AFR submitted | 2018-01-12
4AGV-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-04 | Sree Lekshmi | 2018-01-04 | 2018-01-04 | Anuja | 2018-01-12 | 2018-01-12 | Delta completed & AFR submitted | 2018-01-12
2WRO-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-04 | Sree Lekshmi | 2018-01-04 | 2018-01-04 | Anuja | 2018-01-15 | 2018-01-15 | Delta completed & AFR submitted | 2018-01-15
4RBN-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-04 | Nina | 2018-01-04 | 2018-01-08 | Mythili S | 2018-01-08 | 2018-01-09 | PDC completed & AFR Submitted | 2018-01-09
4TGP-69 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-04 | Dhanya | 2018-01-04 | 2018-01-08 | Mythili S | 2018-01-08 | 2018-01-09 | PDC completed & AFR Submitted | 2018-01-09
3STK-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-04 | Keerthi | 2018-01-04 | 2018-01-04 | Mythili S | 2018-01-08 | 2018-01-08 | PDC completed & AFR Submitted | 2018-01-09
4NWF-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-05 | Joju | 2018-01-05 | 2018-01-08 | Mythili S | 2018-01-09 | 2018-01-09 | PDC completed & AFR Submitted | 2018-01-12
4SRW-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-05 | Keerthi | 2018-01-05 | 2018-01-12 | Mythili S | 2018-01-12 | 2018-01-12 | PDC completed & AFR Submitted | 2018-01-12
5NRW-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-05 | Sree Lekshmi | 2018-01-05 | 2018-01-05 | Anuja | 2018-01-15 | 2018-01-15 | Delta completed & AFR submitted | 2018-01-15
4ABO-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-05 | Lisha | 2018-01-05 | 2018-01-08 | Mythili S | 2018-01-08 | 2018-01-08 | PDC completed & AFR Submitted | 2018-01-12
2ASH-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-08 | Sree Lekshmi | 2018-01-08 | 2018-01-08 | Anuja | 2018-01-16 | 2018-01-16 | Delta completed & AFR submitted | 2018-01-16
2CAR-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-08 | Sree Lekshmi | 2018-01-08 | 2018-01-08 | Anuja | 2018-01-16 | 2018-01-16 | Delta completed & AFR submitted | 2018-01-16
2BLK-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-08 | Nina | 2018-01-08 | 2018-01-09 | Mythili S | 2018-01-10 | 2018-01-10 | PDC completed & AFR Submitted | 2018-01-12
2CAM-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-08 | Sree Lekshmi | 2018-01-08 | 2018-01-09 | Mythili S | 2018-01-10 | 2018-01-10 | PDC completed & AFR Submitted | 2018-01-12
2NSY-66 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-08 | Linda | 2018-01-08 | 2018-01-09 | Mythili S | 2018-01-10 | 2018-01-10 | PDC completed & AFR Submitted | 2018-01-12
3RES-72 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-03 | Sree Lekshmi | 2018-01-03 | 2018-01-03 | Anuja | 2018-01-03 | 2018-01-03 | Delta completed & AFR submitted | 2018-01-03
3TNB-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-04 | Asha Jacob | 2018-01-04 | 2018-01-04 | Anuja | 2018-01-04 | 2018-01-04 | Delta completed & AFR submitted | 2018-01-04
2CHA-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-09 | Joju | 2018-01-09 | 2018-01-09 | Mythili S | 2018-01-10 | 2018-01-10 | PDC completed & AFR Submitted | 2018-01-12
2GRA-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-09 | Lisha | 2018-01-09 | 2018-01-10 | Mythili S | 2018-01-11 | 2018-01-11 | PDC completed & AFR Submitted | 2018-01-12
3STK-67 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-09 | Dhanya | 2018-01-09 | 2018-01-09 | Mythili S | 2018-01-10 | 2018-01-10 | PDC completed & AFR Submitted | 2018-01-12
3BAY-71 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-09 | Asha Jacob | 2018-01-08 | 2018-01-08 | Minu | 2018-01-09 | 2018-01-09 | Delta completed & AFR submitted | 2018-01-15
3BGO-65 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-10 | Joju | 2018-01-10 | 2018-01-15 | Mythili S | 2018-01-16 | 2018-01-16 | PDC completed & AFR Submitted | 2018-01-18
3NES-68 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-10 | Nina | 2018-01-10 | 2018-01-11 | Mythili S | 2018-01-12 | 2018-01-12 | PDC completed & AFR Submitted | 2018-01-19
3BGO-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-10 | Linda | 2018-01-10 | 2018-01-16 | Minu | 2018-01-18 | 2018-01-18 | PDC completed & AFR Submitted | 2018-01-19
2PAR-01 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-10 | Dhanya | 2018-01-10 | 2018-01-10 | Mythili S | 2018-01-11 | 2018-01-11 | PDC completed & AFR Submitted | 2018-01-19
2RDL-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-09 | Asha Jacob | 2018-01-09 | 2018-01-09 | Minu | 2018-01-10 | 2018-01-10 | Delta completed & AFR submitted | 2018-01-15
5NRW-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-09 | Asha Jacob | 2018-01-09 | 2018-01-09 | Minu | 2018-01-10 | 2018-01-10 | Delta completed & AFR submitted | 2018-01-15
4BEE-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-10 | Sree Lekshmi | 2018-01-10 | 2018-01-10 | Anuja | 2018-01-24 | 2018-01-24 | Delta completed & AFR submitted | 2018-01-24
4TGP-64 | H-A-H |  | Pre-Design | Delta |  | In Progress-Delta |  | 2018-01-10 | Sree Lekshmi | 2018-01-10 | 2018-01-10 |  |  |  | In Progress-Delta completed
3RES-71 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-10 | Sree Lekshmi | 2018-01-10 | 2018-01-10 | Anuja | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-17
2BAU-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-11 | Dhanya | 2018-01-11 | 2018-01-22 | Mythili S | 2018-01-22 | 2018-01-22 | PDC completed & AFR Submitted | 2018-01-23
2GRA-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-11 | Lisha | 2018-01-11 | 2018-01-17 | Mythili S | 2018-01-18 | 2018-01-18 | PDC completed & AFR Submitted | 2018-01-19
2PAR-04 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-09 | Linda | 2018-01-09 | 2018-01-09 | Mythili S | 2018-01-11 | 2018-01-11 | PDC completed & AFR Submitted | 2018-01-18
5SAL-70 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-09 | Sree Lekshmi | 2018-01-09 | 2018-01-09 | Mythili S | 2018-01-11 | 2018-01-11 | PDC completed & AFR Submitted | 2018-01-18
6HAM-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-11 | Sree Lekshmi | 2018-01-11 | 2018-01-11 | Mythili S | 2018-01-15 | 2018-01-15 | PDC completed & AFR Submitted | 2018-01-25
4ALX-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-08 | Asha Jacob | 2018-01-08 | 2018-01-08 | Minu | 2018-01-08 | 2018-01-08 | Delta completed & AFR submitted | 2018-01-11
2CAR-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-08 | Asha Jacob | 2018-01-08 | 2018-01-08 | Minu | 2018-01-08 | 2018-01-08 | Delta completed & AFR submitted | 2018-01-11
3HDB-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-12 | Sree Lekshmi | 2018-01-12 | 2018-01-12 | Anuja | 2018-01-29 | 2018-01-29 | Delta completed & AFR submitted | 2018-01-29
2BOT-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-12 | Nina | 2018-01-12 | 2018-01-12 | Mythili S | 2018-01-15 | 2018-01-15 | PDC completed & AFR Submitted | 2018-01-19
2BOT-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-12 | Sree Lekshmi | 2018-01-12 | 2018-01-15 | Minu | 2018-01-18 | 2018-01-18 | PDC completed & AFR Submitted | 2018-01-19
4PDP-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-15 | Nina | 2018-01-15 | 2018-01-16 | Minu | 2018-01-18 | 2018-01-18 | PDC completed & AFR Submitted | 2018-01-19
4BEE-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-15 | Sree Lekshmi | 2018-01-15 | 2018-01-15 | Anuja | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-17
2CAR-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-15 | Sree Lekshmi | 2018-01-15 | 2018-01-15 | Anuja | 2018-01-16 | 2018-01-16 | Delta completed & AFR submitted | 2018-01-16
4BEE-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-15 | Sree Lekshmi | 2018-01-15 | 2018-01-15 | Anuja | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-17
3BAY-71 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-11 | Asha Jacob | 2018-01-11 | 2018-01-11 | Anuja | 2018-01-15 | 2018-01-15 | Delta completed & AFR submitted | 2018-01-15
2RDL-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-11 | Asha Jacob | 2018-01-11 | 2018-01-11 | Anuja | 2018-01-15 | 2018-01-15 | Delta completed & AFR submitted | 2018-01-15
5NRW-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-11 | Asha Jacob | 2018-01-11 | 2018-01-11 | Anuja | 2018-01-15 | 2018-01-15 | Delta completed & AFR submitted | 2018-01-15
2RYD-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-16 | Asha Jacob | 2018-01-16 | 2018-01-16 | Minu | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-18
3BAY-67 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-16 | Asha Jacob | 2018-01-16 | 2018-01-16 | Minu | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-18
5SAL-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-16 | Asha Jacob | 2018-01-16 | 2018-01-16 | Minu | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-18
2QUA-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-16 | Asha Jacob | 2018-01-16 | 2018-01-16 | Minu | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-18
5HPS-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-15 | Nina | 2018-01-15 | 2018-01-23 | Mythili S | 2018-01-24 | 2018-01-24 | PDC completed & AFR Submitted | 2018-01-25
2WRO-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-18 | Lisha Manuel | 2018-01-18 | 2018-01-23 | Mythili S | 2018-01-24 | 2018-01-24 | PDC completed & AFR Submitted | 2018-01-25
2ERP-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-18 | Sree Lekshmi | 2018-01-18 | 2018-01-19 | Mythili S | 2018-01-24 | 2018-01-25 | PDC completed & AFR Submitted | 2018-01-25
2ERP-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-18 | Linda | 2018-01-18 | 2018-01-23 | Mythili S | 2018-01-24 | 2018-01-24 | PDC completed & AFR Submitted | 2018-01-25
3KYG-70 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-17 | Lisha Manuel | 2018-01-17 | 2018-01-17 | Mythili S | 2018-01-22 | 2018-01-22 | PDC completed & AFR Submitted | 2018-01-25
4RBN-63 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-17 | Sree Lekshmi | 2018-01-17 | 2018-01-18 | Mythili S | 2018-01-22 | 2018-01-22 | PDC completed & AFR Submitted | 2018-01-31
3BDW-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-16 | Keerthi | 2018-01-16 | 2018-01-25 | Minu | 2018-01-25 | 2018-01-25 | PDC completed & AFR Submitted | 2018-01-25
2QUA-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-17 | Asha Jacob | 2018-01-17 | 2018-01-17 | Minu | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-22
2WRO-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-17 | Asha Jacob | 2018-01-17 | 2018-01-17 | Minu | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-22
3TNB-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-17 | Asha Jacob | 2018-01-17 | 2018-01-17 | Minu | 2018-01-17 | 2018-01-17 | Delta completed & AFR submitted | 2018-01-22
5WES-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-18 | Asha Jacob | 2018-01-18 | 2018-01-18 | Minu | 2018-01-19 | 2018-01-19 | Delta completed & AFR submitted | 2018-01-25
3RES-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-18 | Asha Jacob | 2018-01-18 | 2018-01-18 | Minu | 2018-01-19 | 2018-01-19 | Delta completed & AFR submitted | 2018-01-24
4BEE-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-18 | Asha Jacob | 2018-01-18 | 2018-01-18 | Minu | 2018-01-19 | 2018-01-19 | Delta completed & AFR submitted | 2018-01-25
2ERP-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-22 | Sree Lekshmi | 2018-01-22 | 2018-01-22 | Mythili S | 2018-01-23 | 2018-01-23 | PDC completed & AFR Submitted | 2018-01-24
4FHL-21 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-22 | Dhanya | 2018-01-22 | 2018-01-25 | Mythili S | 2018-01-29 | 2018-01-29 | PDC completed & AFR Submitted | 2018-01-31
2ASH-67 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-16 | Joju | 2018-01-16 | 2018-01-18 | Mythili S | 2018-01-22 | 2018-01-22 | PDC completed & AFR Submitted | 2018-01-31
2BAU-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-23 | Lisha Manuel | 2018-01-23 | 2018-01-31 | Mythili S | 2018-01-31 | 2018-01-31 | PDC completed & AFR Submitted | 2018-01-31
6GIR-67 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-24 | Joju | 2018-01-24 | 2018-01-24 | Mythili S | 2018-01-29 | 2018-01-29 | PDC completed & AFR Submitted | 2018-02-01
2CHA-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-24 | Sree Lekshmi | 2018-01-24 | 2018-01-24 | Anuja | 2018-02-05 | 2018-02-05 | Delta completed & AFR submitted | 2018-02-05
3RES-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-24 | Sree Lekshmi | 2018-01-24 | 2018-01-24 | Anuja | 2018-02-01 | 2018-02-01 | Delta completed & AFR submitted | 2018-02-01
5BRI-70 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-16 | Linda | 2018-01-16 | 2018-01-18 | Mythili S | 2018-01-18 | 2018-01-18 | PDC completed & AFR Submitted | 2018-01-24
3GBR-62 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-25 | Joju | 2018-01-25 | 2018-01-25 | Mythili S | 2018-01-29 | 2018-01-29 | PDC completed & AFR Submitted | 2018-02-02
4SRW-68 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-25 | Dhanya | 2018-01-25 | 2018-02-01 | Mythili S | 2018-02-02 | 2018-02-02 | PDC completed & AFR Submitted | 2018-02-02
3RES-67 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-23 | Asha Jacob | 2018-01-23 | 2018-01-23 | Minu | 2018-01-24 | 2018-01-24 | Delta completed & AFR submitted | 2018-01-25
3RES-70 | H-A-H |  | Pre-Design | Delta |  | Delta completed-Ready for submission |  | 2018-01-23 | Asha Jacob | 2018-01-23 | 2018-01-23 | Minu | 2018-01-24 | 2018-01-24 | Delta completed-Ready for Submission
2HUR-60 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-24 | Asha Jacob | 2018-01-24 | 2018-01-24 | Minu | 2018-01-24 | 2018-01-24 | Delta completed & AFR submitted | 2018-01-25
3KYG-67 | H-A-H |  | Pre-Design | Delta |  | Delta completed-Ready for submission |  | 2018-01-24 | Asha Jacob | 2018-01-24 | 2018-01-24 | Minu | 2018-01-24 | 2018-01-24 | Delta completed-Ready for Submission
3DAD-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed-Ready for submission |  | 2018-01-24 | Asha Jacob | 2018-01-24 | 2018-01-24 | Minu | 2018-01-24 | 2018-01-24 | Delta completed-Ready for Submission
2PNN-68 | H-A-H |  | Pre-Design | Delta |  | Delta completed-Ready for submission |  | 2018-01-24 | Asha Jacob | 2018-01-24 | 2018-01-24 | Minu | 2018-01-24 | 2018-01-24 | Delta completed-Ready for Submission
5NRW-63 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-25 | Asha Jacob | 2018-01-25 | 2018-01-25 | Minu | 2018-01-25 | 2018-01-25 | Delta completed & AFR submitted | 2018-01-31
3RES-72 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-25 | Sree Lekshmi | 2018-01-25 | 2018-01-25 | Anuja | 2018-01-29 | 2018-01-29 | Delta completed & AFR submitted | 2018-01-29
3BNT-62 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-25 | Sree Lekshmi | 2018-01-25 | 2018-01-25 | Anuja | 2018-01-29 | 2018-01-29 | Delta completed & AFR submitted | 2018-01-29
2RYD-61 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-29 | Sree Lekshmi | 2018-01-29 | 2018-02-01 | Mythili S | 2018-02-02 | 2018-02-02 | PDC completed & AFR Submitted | 2018-02-02 | Linda and Keerthi also working on the SAM
2ESP-66 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-01-31 | Nina Sebastian | 2018-01-31 | 2018-02-02 | Mythili S | 2018-02-02 | 2018-02-02 | PDC completed & AFR Submitted | 2018-02-02
2PAR-61 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-01-31 | Jumana.M | 2018-01-31 | 2018-02-02 |  |  |  | In Progress - Self QA Completed
2BUR-64 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-01-30 | Joju | 2018-01-30 | 2018-02-05 |  |  |  | In Progress - Self QA Completed
3TYH-69 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-30 | Mythili S | 2018-01-30 | 2018-01-30 | Anuja | 2018-01-31 | 2018-01-31 | Delta completed & AFR submitted | 2018-01-31
4ABO-70 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-02-01 | Keerthi | 2018-02-01 |  |  |  |  | In Progress - Buffering
4CHL-66 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-18 | Sree Lekshmi | 2018-01-18 | 2018-01-18 | Anuja | 2018-02-01 | 2018-02-01 | Delta completed & AFR submitted | 2018-02-01
2PAR-64 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-02-02 | Jumana.M | 2018-02-02 | 2018-02-05 |  |  |  | In Progress - Self QA Completed
2BUR-63 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-02-02 | Nina Sebastian | 2018-02-02 |  |  |  |  | In Progress - Buffering
2PAR-60 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-02-02 | Dhanya | 2018-02-02 | 2018-02-05 |  |  |  | In Progress - Self QA Completed
6HAM-60 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-02-01 | Lisha Manuel | 2018-02-01 | 2018-02-01 | Mythili S | 2018-02-02 | 2018-02-02 | PDC completed & AFR Submitted | 2018-02-02
4CHL-61 | H-A-H |  | Pre-Design | Delta |  | Delta completed-Ready for submission |  | 2018-02-01 | Asha Jacob | 2018-02-01 | 2018-02-01 | Minu | 2018-02-02 | 2018-02-02 | Delta completed-Ready for Submission
3TNB-64 | H-A-H |  | Pre-Design | Delta |  | Delta completed-Ready for submission |  | 2018-02-01 | Asha Jacob | 2018-02-01 | 2018-02-01 | Minu | 2018-02-02 | 2018-02-02 | Delta completed-Ready for Submission
3GBR-64 | H-A-H |  | Pre-Design | PDC |  | PDC completed & AFR Submitted |  | 2018-02-01 | Lisha Manuel | 2018-02-01 | 2018-02-01 | Mythili S | 2018-02-02 | 2018-02-02 | PDC completed & AFR Submitted | 2018-02-02
4ABO-69 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-31 | Mythili S | 2018-01-31 | 2018-01-31 | Mythili S | 2018-02-05 | 2018-02-05 | Delta completed & AFR submitted | 2018-02-05
5HPS-65 | H-A-H |  | Pre-Design | Delta |  | Delta completed & AFR submitted |  | 2018-01-25 | Sree Lekshmi | 2018-01-25 | 2018-01-25 | Mythili S | 2018-02-04 | 2018-02-04 | Delta completed & AFR submitted | 2018-02-06
2COO-66 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-02-05 | Linda | 2018-02-05 |  |  |  |  | In Progress - Buffering
3CRO-64 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-02-05 | Lisha Manuel | 2018-02-05 |  |  |  |  | In Progress - Buffering
2BUR-65 | H-A-H |  | Pre-Design | PDC |  | In Progress - PDC |  | 2018-02-05 | Joju | 2018-02-05 |  |  |  |  | In Progress - Buffering

## LDM Allocation
Updated by : |  | Updated on : | [6 empty] | Temp ID Creation |  |  |  |  | Address Alignment and Validations
SAM | RFS Group | SAM Code | Program | Gate | Version | Overall Status | Comments | T18 Input date | Assigned to | Start date | End date | Dummy LocID count | Cycle Time (FBR & Temp ID) | Start date | End date | Actual LMS Handover Date | EUP Count in Handover | Cycle Time (Address Alignment) | Rejection Date | On Hold Start Date | Recommencement Date | LDM Queue Time (Internal waiting time) | LDM Waiting Time (External waiting time) | LDM Overall Cycle time | LDM Overall Processing Time | Sr.No | Names | Dropdowns Validation
2MOS-64 | RFS.75 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-03-28 | Eldhose | 2017-03-29 | 2017-03-31 | 37 | 4 | 2017-03-31 | 2017-04-01 | 2017-04-01 | 885 | 1 |  |  |  |  | 0 | 5 | 5 | 1 | Eldhose Joy | Eldhose Joy
3RWO-69 | RFS.83 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-03-29 | Gifty | 2017-03-29 | 2017-03-31 | 79 | 3 | 2017-03-31 | 2017-04-01 | 2017-04-01 | 4026 | 1 |  |  |  |  | 0 | 4 | 4 | 2 | Arunika Joy | Arunika Joy
2ASH-64 | RFS.75 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-03-29 | Gifty | 2017-03-29 | 2017-04-03 | 275 | 4 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 3994 | 1 |  |  |  |  | 0 | 5 | 5 | 3 | S Shilpa | S Shilpa
3SCO-69 | RFS.77 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-03-31 | Revathy/Eldhose | 2017-04-03 | 2017-04-05 | 18 | 4 | 2017-04-05 | 2017-04-06 | 2017-04-06 | 1326 | 2 |  |  |  |  | 0 | 6 | 6 | 4 | Devika Kala | Devika Kala
3SOA-61 | RFS.83 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-03 | Anet/Gifty | 2017-04-03 | 2017-04-05 | 46 | 3 | 2017-04-05 | 2017-04-06 | 2017-04-06 | 1916 | 2 |  |  |  |  | 0 | 5 | 5 | 5 | SanjanaKrishnan | SanjanaKrishnan
2BAN-66 | RFS.77 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-03 | Saiju/Eldhose | 2017-04-03 | 2017-04-06 | 123 | 4 | 2017-04-06 | 2017-04-07 | 2017-04-07 | 1029 | 2 |  |  |  |  | 0 | 6 | 6 | 6 | Reenu Treesa Peter | Reenu Treesa Peter
2EAS-66 | RFS.76 | H-A-Q | HAC | Pre-AT | 1 | Completed | v2 received on 04-Apr | 2017-04-04 | Revathy | 2017-03-29 | 2017-04-02 | 151 | -2 | 2017-04-02 | 2017-04-03 | 2017-04-03 | 2942 | 1 |  |  |  |  | 0 | -1 | -1 | 7 | Shambhavi Chandra | Shambhavi Chandra
2SHA-63 | RFS.76 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-04 | Jumana | 2017-04-05 | 2017-04-10 | 52 | 5 | 2017-04-10 | 2017-04-13 | 2017-04-13 | 3438 | 4 |  |  |  |  | 0 | 9 | 9 | 8 | Renjini R | Renjini R
5BRI-68 | RFS.80 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-04 | Revathy | 2017-04-05 | 2017-04-07 | 52 | 4 | 2017-04-07 | 2017-04-10 | 2017-04-10 | 2102 | 2 |  |  |  |  | 0 | 6 | 6 | 9 | Saranya Geetha | Saranya Geetha
4IAL-63 | RFS.76 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-06 | Anet | 2017-04-06 | 2017-04-11 | 49 | 4 | 2017-04-11 | 2017-04-12 | 2017-04-12 | 2581 | 2 |  |  |  |  | 0 | 6 | 6 | 10 | Kishore KI | Kishore KI
3OAK-70 | RFS.77 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-10 | Saiju | 2017-04-10 | 2017-04-13 | 159 | 4 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2220 | 1 |  |  |  |  | 0 | 5 | 5 | 11 | Revathy A | Revathy A
3BAY-69 | RFS.77 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-11 | Gifty | 2017-04-11 | 2017-12-04 | 126 | 157 | 2017-12-04 | 2017-04-18 | 2017-04-18 | 1752 | -154 |  |  |  |  | 0 | 3 | 3 | 12 | Anet Jose | Anet Jose
5EZB-60 | RFS.78 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-11 | Gautham | 2017-04-11 | 2017-04-20 | 39 | 6 | 2017-04-20 | 2017-04-21 | 2017-04-21 | 3472 | 2 |  |  |  |  | 0 | 8 | 8 | 13 | Saiju Xavier | Saiju Xavier
3DNC-62 | RFS.79 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-11 | Jumana/revathy | 2017-04-11 | 2017-04-19 | 44 | 5 | 2017-04-19 | 2017-04-21 | 2017-04-21 | 1498 | 3 |  |  |  |  | 0 | 8 | 8 | 14 | Jumana.M | Jumana.M
5EDW-64 | RFS.77 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-12 | Anet | 2017-04-12 | 2017-04-13 | 107 | 2 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2628 | 1 |  |  |  |  | 0 | 3 | 3 | 15 | Manjusha M | Manjusha M
3KGP-62 | RFS.79 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-12 | Saiju | 2017-04-13 | 2017-04-19 | 17 | 4 | 2017-04-19 | 2017-04-21 | 2017-04-21 | 1894 | 3 |  |  |  |  | 0 | 7 | 7 | 16 | Jowharulla.M | Jowharulla.M
2CMO-61 | RFS.79 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-13 | Anet | 2017-04-18 | 2017-04-19 | 10 | 3 | 2017-04-19 | 2017-04-21 | 2017-04-21 | 850 | 3 |  |  |  |  | 0 | 6 | 6 | 17 | Swathy Mohandas | Swathy Mohandas
3NAW-62 | RFS.87 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-04-13 | Tajinder Kaur | 2017-04-13 |  | 182 | -30584 |  | 2017-04-13 | 2017-04-13 | 1510 | 30584 |  |  |  |  | 0 | 0 | 0 | 18 | Tajinder Kaur | Tajinder Kaur
2MEN-60 | RFS.79 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-18 | Revathy/saiju | 2017-04-18 | 2017-04-24 | 82 | 5 | 2017-04-24 | 2017-04-26 | 2017-04-26 | 2847 | 2 |  |  |  |  | 0 | 7 | 7 | 19 | Goutham A S | Goutham A S
4CPH-73 | RFS.79 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-18 | jumana | 2017-04-20 | 2017-04-27 | 159 | 7 | 2017-04-27 | 2017-04-27 | 2017-04-27 | 2564 | 1 |  |  |  |  | 0 | 8 | 8 | 20 | ShabeenaShamsudin | ShabeenaShamsudin
2ASH-61 | RFS.80 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-18 | Revathy | 2017-04-21 | 2017-04-25 | 60 | 5 | 2017-04-25 | 2017-04-26 | 2017-04-26 | 1715 | 1 |  |  |  |  | 0 | 6 | 6 | 21 | VishnuS | VishnuS
2CMO-60 | RFS.82 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-18 | Revathy | 2017-04-28 | 2017-05-02 | 85 | 9 | 2017-05-02 | 2017-05-03 | 2017-05-03 | 3069 | 2 |  |  |  |  | 0 | 11 | 11 | 22 | ChristieThomas | ChristieThomas
2CRR-67 | RFS.80 | H-B-H | BAU | Design | 1 | Completed |  | 2017-04-18 | Tajinder Kaur | 2017-04-18 |  | 26 | -30585 |  | 2017-04-19 | 2017-04-19 | 1598 | 30586 |  |  |  |  | 0 | 1 | 1 | 23 | JadeeraKT | JadeeraKT
2PET-61 | RFS.84 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-19 | Saiju | 2017-04-25 | 2017-04-27 | 51 | 6 | 2017-04-27 | 2017-04-28 | 2017-04-28 | 952 | 2 |  |  |  |  | 0 | 8 | 8 | 24 | George | George
6MLO-65 | RFS.80 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-19 | Anet | 2017-04-27 | 2017-04-28 | 24 | 7 | 2017-04-28 | 2017-05-01 | 2017-05-01 | 3533 | 1 |  |  |  |  | 0 | 8 | 8 | 25 | Reshma Rajan | Reshma Rajan
3CLA-67 | RFS.82 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-19 | Jumana/Anet/Eldhose | 2017-04-27 | 2017-05-03 | 34 | 9 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2413 | 1 |  |  |  |  | 0 | 10 | 10 | 26 | Aleena Johny | Aleena Johny
2SEF-61 | RFS.80 | H-B-H | BAU | Design | 1 | Completed |  | 2017-04-19 | Tajinder Kaur | 2017-04-20 |  | 76 | -30586 |  | 2017-04-20 | 2017-04-20 | 3160 | 30587 |  |  |  |  | 0 | 1 | 1 | 27 | Kavya Methil | Kavya Methil
2ROC-60 | RFS.79 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-20 | anet | 2017-04-20 | 2017-04-25 | 194 | 3 | 2017-04-25 | 2017-04-26 | 2017-04-26 | 2838 | 1 |  |  |  |  | 0 | 4 | 4 |  |  | NA
2CRR-60 | RFS.99 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-04-20 | Tajinder Kaur | 2017-04-21 |  | 178 | -30587 |  | 2017-04-24 | 2017-04-24 | 4278 | 30589 |  |  |  |  | 0 | 2 | 2
2PET-67 | RFS.80 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-21 | Saiju/Gifty | 2017-04-27 | 2017-05-03 | 138 | 7 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 3271 | 1 |  |  |  |  | 0 | 8 | 8
4BUR-60 | RFS.95 | M-M-H | BAU | Design | 1 | Completed |  | 2017-04-21 | Tajinder Kaur | 2017-04-24 |  | 498 | -30588 |  | 2017-04-26 | 2017-04-26 | 5832 | 30590 |  |  |  |  | 0 | 2 | 2
3TYH-65 | RFS.79 | H-A-Q | HAC | Pre-AT | 1 | Rejected | v1 Rejected to TLS | 2017-04-24 | Revathy | 2017-04-26 | 2017-04-26 | NA | 2 | 2017-04-26 | 2017-04-26 | NA | NA | #VALUE! |  |  |  |  | 0 | #VALUE! | #VALUE!
3TYH-65 | RFS.79 | H-A-Q | HAC | Pre-AT | 2 | Completed | v2 received on 27-Apr | 2017-04-24 | Revathy | 2017-04-27 | 2017-04-27 | 45 | 3 | 2017-04-27 | 2017-05-01 | 2017-05-01 | 3159 | 2 |  |  |  |  | 0 | 5 | 5
3CTA-66 | RFS.82 | H-M-H | BAU | Design | 1 | Completed |  | 2017-04-28 | Tajinder Kaur | 2017-05-01 |  | 66 | -30592 |  | 2017-05-01 | 2017-05-01 | 3821 | 30592 |  |  |  |  | 0 | 0 | 0
3NBA-68 | RFS.79 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-29 | Gifty | 2017-05-01 | 2017-05-02 | 80 | 1 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 3315 | 1 |  |  |  |  | 0 | 2 | 2
4CPH-62 | RFS.80 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-29 | Manjusha/Jowhar/Anet/Eldhose | 2017-05-02 | 2017-05-05 | 191 | 4 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 3320 | 1 |  |  |  |  | 0 | 5 | 5
3KGP-67 | RFS.85 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-04-29 | Revathy/Eldhose | 2017-05-03 | 2017-05-05 | 126 | 4 | 2017-05-05 | 2017-05-08 | 2017-05-08 | 4132 | 2 |  |  |  |  | 0 | 6 | 6
2CAS-61 | RFS.81 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2-May-2017: ON HOLD due to Duplicate addresses 5-May-2017: Received new T18 | 2017-05-01 | Eldhose/Anet | 2017-05-01 | 2017-05-09 | 39 | 6 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 3893 | 1 |  |  |  |  | 0 | 7 | 7
4BLH-64 | RFS.80 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-01 | Eldhose | 2017-05-02 | 2017-05-02 | 9 | 1 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 914 | 1 |  |  |  |  | 0 | 2 | 2
5GLL-66 | RFS.84 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-02 | Saiju | 2017-05-03 | 2017-05-05 | 55 | 4 | 2017-05-05 | 2017-05-08 | 2017-05-08 | 1631 | 2 |  |  |  |  | 0 | 6 | 6
2NSY-64 | RFS.83 | H-A-Q | HAC | Pre-AT | 2 | Rejected | 4-May-2017: ON HOLD due to AP issue 16-May-2017: v3 received 17-May-2017: ON HOLD as we have PCDs present in equipment_hfc table but not present in SL table 23-May-2017: v4 received | 2017-05-02 | NA | 2017-05-02 | 2017-05-02 | NA | 1 | 2017-05-02 | 2017-05-02 | NA | NA | #VALUE! |  |  |  |  | 0 | #VALUE! | #VALUE!
5GLL-63 | RFS.80 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-03 | Gifty/Revathy/Eldhose | 2017-05-04 | 2017-05-09 | 100 | 5 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 3402 | 1 |  |  |  |  | 0 | 6 | 6
5HNL-66 | RFS.81 | M-A-Q | HAC | Pre-AT | 1 | Completed | 4-May-2017: ON HOLD for clarification from TLS on FTTB site 5-May-2017: Got clarification as a hospital site. | 2017-05-03 | Saiju | 2017-05-08 | 2017-05-12 | 286 | 8 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 4165 | 1 |  |  |  |  | 0 | 9 | 9
4SLA-62 | RFS.99 | H-M-H | BAU | Design | 1 | Completed |  | 2017-05-03 | Tajinder Kaur | 2017-05-04 |  | 222 | -30594 |  | 2017-05-05 | 2017-05-05 | 1006 | 30596 |  |  |  |  | 0 | 2 | 2
3BAY-64 | RFS.84 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-04 | Manjusha/Revathy | 2017-05-08 | 2017-05-12 | 56 | 7 | 2017-05-12 | 2017-05-15 | 2017-05-15 | 2363 | 2 |  |  |  |  | 0 | 9 | 9
4MGA-61 | RFS.88 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-05-04 | Swathy Mohandas | 2017-05-04 |  | 82 | -30595 |  | 2017-05-08 | 2017-05-08 | 4781 | 30597 |  |  |  |  | 0 | 2 | 2
6CTO-61 | RFS.82 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-05 | Jumana | 2017-05-08 | 2017-05-11 | 27 | 5 | 2017-05-11 | 2017-05-12 | 2017-05-12 | 1369 | 2 |  |  |  |  | 0 | 7 | 7
2FRE-64 | RFS.106 | M-B-H | BAU | Design | 1 | Completed |  | 2017-05-07 | George John Panikulam | 2017-05-08 |  | 1 | -30596 |  | 2017-05-10 | 2017-05-10 | 726 | 30599 |  |  |  |  | 0 | 3 | 3
3NCO-63 | RFS.80 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-08 | Gifty | 2017-05-08 | 2017-05-09 | 248 | 2 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2397 | 1 |  |  |  |  | 0 | 3 | 3
2SEV-60 | RFS.83 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-08 | Jowhar/Revathy | 2017-05-08 | 2017-05-11 | 49 | 4 | 2017-05-11 | 2017-05-12 | 2017-05-12 | 3585 | 2 |  |  |  |  | 0 | 6 | 6
4BLH-63 | RFS.138 | H-B-H | BAU | Design | 1 | Completed |  | 2017-05-08 | Swathy Mohandas | 2017-05-10 |  | 25 | -30597 |  | 2017-05-12 | 2017-05-12 | 2539 | 30601 |  |  |  |  | 0 | 4 | 4
5GNG-60 | RFS.113 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-09 | Goutham A S | 2017-05-09 |  | 192 | -30598 |  | 2017-05-16 | 2017-05-16 | 3446 | 30603 |  |  |  |  | 0 | 5 | 5
6SUB-60 | RFS.81 | H-A-Q | HAC | Pre-AT | 1 | Completed | 5-May-2017: ON HOLD due to equipments without NBN naming convention 10-May-2017: Received v2 T18 11-May-2017: Duplicate addresses for 2 records and need clrification from TLS 12-May-2017: Got confirmation to delete the dummy address | 2017-05-10 | Anet/Eldhose | 2017-05-04 | 2017-05-15 | 129 | 4 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 3040 | 1 |  |  |  |  | 0 | 5 | 5
3DAD-61 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-10 | Revathy | 2017-05-15 | 2017-05-16 | 98 | 5 | 2017-05-16 | 2017-05-17 | 2017-05-17 | 2555 | 2 |  |  |  |  | 0 | 7 | 7
2CRR-68 | RFS.56 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-05-10 | Tajinder Kaur | 2017-05-10 |  | 0 | -30599 |  | 2017-05-10 | 2017-05-10 | 704 | 30599 |  |  |  |  | 0 | 0 | 0
2BON-61 | RFS.101 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-10 | Swathy Mohandas | 2017-05-11 |  | 685 | -30599 |  | 2017-05-16 | 2017-05-16 | 4719 | 30603 |  |  |  |  | 0 | 4 | 4
2BON-64 | RFS.101 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-10 | Tajinder Kaur | 2017-05-11 |  | 115 | -30599 |  | 2017-05-15 | 2017-05-15 | 2947 | 30602 |  |  |  |  | 0 | 3 | 3
3DAD-65 | RFS.85 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-12 | Anet | 2017-05-15 | 2017-05-19 | 35 | 6 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2567 | 1 |  |  |  |  | 0 | 7 | 7
3DAD-60 | RFS.88 | H-A-Q | HAC | Pre-AT | 1 | Completed | 17-May-2017: Duplicate addresses for 2 records 22-May-2017: Received updated sl with UNIT numbers assigned for the 2 locations | 2017-05-15 | Jumana/Anet | 2017-05-15 | 2017-05-22 | 88 | 6 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 1888 | 1 |  |  |  |  | 0 | 7 | 7
3FNT-66 | RFS.85 | H-A-Q | HAC | Pre-AT | 1 | Completed | IAB File. 5 ELMS locations was missing in PNI | 2017-05-15 | Anet | 2017-05-17 | 2017-05-18 | 157 | 4 | 2017-05-18 | 2017-05-19 | 2017-05-19 | 2139 | 2 |  |  |  |  | 0 | 6 | 6
3SPL-62 | RFS.87 | H-M-H | BAU | Design | 1 | Rejected |  | 2017-05-15 | Tajinder Kaur | 2017-05-15 |  | 478 | -30602 |  | 2017-05-17 | 2017-05-17 | 5858 | 30604 | 2017-06-21 |  |  |  | 0 | 2 | 2
4MGA-63 | RFS.0 | M-B-H | BAU | Design | 1 | Completed |  | 2017-05-15 | Swathy Mohandas | 2017-05-16 |  | 338 | -30602 |  | 2017-05-17 | 2017-05-17 | 4295 | 30604 |  |  |  |  | 0 | 2 | 2
4BUR-67 | RFS.112 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-15 | George John Panikulam | 2017-05-15 |  | 181 | -30602 |  | 2017-05-26 | 2017-05-26 | 3982 | 30611 |  |  |  |  | 0 | 9 | 9
3TNI-62 | RFS.103 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-15 | Goutham A S | 2017-05-17 |  | 121 | -30602 |  | 2017-05-24 | 2017-05-24 | 3733 | 30609 |  |  |  |  | 0 | 7 | 7
2NSY-64 | RFS.83 | H-A-Q | HAC | Pre-AT | 3 | Completed | 4-May-2017: ON HOLD due to AP issue 16-May-2017: v3 received 17-May-2017: ON HOLD as we have PCDs present in equipment_hfc table but not present in SL table 23-May-2017: v4 received | 2017-05-16 | Sara/Anet | 2017-05-16 | 2017-05-16 | 164 | 1 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 3004 | 1 |  |  |  |  | 0 | 2 | 2
6SUB-68 | RFS.82 | H-A-Q | HAC | Pre-AT | 1 | Completed | v2 T18 | 2017-05-16 | Gifty/Eldhose | 2017-05-17 | 2017-05-18 | 6 | 3 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 1253 | 1 |  |  |  |  | 0 | 4 | 4
2BAM-62 | RFS.84 | M-B-H | BAU | Design | 1 | Completed |  | 2017-05-16 | Swathy Mohandas | 2017-05-16 |  | 82 | -30603 |  | 2017-05-19 | 2017-05-19 | 785 | 30606 |  |  |  |  | 0 | 3 | 3
3SOA-64 | RFS.83 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-17 | Revathy | 2017-05-17 | 2017-05-19 | 102 | 3 | 2017-05-19 | 2017-05-22 | 2017-05-22 | 2775 | 2 |  |  |  |  | 0 | 5 | 5
2EPP-63 | RFS.88 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-18 | Sara/Eldhose | 2017-05-18 | 2017-05-24 | 35 | 5 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 1929 | 1 |  |  |  |  | 0 | 6 | 6
3MIT-61 | RFS.83 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-18 | Renjini/Saiju | 2017-05-19 | 2017-05-22 | 6 | 3 | 2017-05-22 | 2017-05-23 | 2017-05-23 | 709 | 2 |  |  |  |  | 0 | 5 | 5
6CTO-64 | RFS.83 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-18 | Jumana/Jowhar/Gifty | 2017-05-19 | 2017-05-25 | 93 | 6 | 2017-05-25 | 2017-05-26 | 2017-05-26 | 2510 | 2 |  |  |  |  | 0 | 8 | 8
4MRA-64 | RFS.95 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-18 | Tajinder Kaur | 2017-05-19 |  | 382 | -30605 |  | 2017-05-19 | 2017-05-19 | 4464 | 30606 |  |  |  |  | 0 | 1 | 1
4BUR-20 | RFS.91 | M-B-H | BAU | Design | 1 | Completed |  | 2017-05-19 | Swathy Mohandas | 2017-05-22 |  | 4 | -30606 |  | 2017-05-22 | 2017-05-22 | 195 | 30607 |  |  |  |  | 0 | 1 | 1
3SOA-62 | RFS.85 | H-A-Q | HAC | Pre-AT | 1 | Completed | 22-May-2017: LOC000073574274 is located in 3SOA-61 and included in its design also. Need confirmation to remove/add a new location to SL table. 23-May-2017: Created a new SL for that in 3SOA-61 and included this location in 3SOA-62 | 2017-05-22 | Eldhose | 2017-05-22 | 2017-05-24 | 11 | 3 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 1017 | 1 |  |  |  |  | 0 | 4 | 4
2BAN-64 | RFS.89 | H-A-Q | HAC | Pre-AT | 1 | Completed | 23-May-2017: 2 HVMDU are present but one residing outside the SAM | 2017-05-22 | Manjusha | 2017-05-23 | 2017-05-30 | 362 | 7 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 3086 | 1 |  |  |  |  | 0 | 8 | 8
3SOA-63 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-22 | Renjini | 2017-06-12 | 2017-06-15 | 98 | 18 | 2017-06-15 | 2017-06-16 | 2017-06-16 | 3222 | 2 |  |  |  |  | 0 | 20 | 20
3NCO-64 | RFS.87 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-22 | Jowhar | 2017-06-13 | 2017-06-14 | 17 | 17 | 2017-06-14 | 2017-06-15 | 2017-06-15 | 1605 | 2 |  |  |  |  | 0 | 19 | 19 | 28 | NA
4CHP-67 | RFS.68 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-05-22 | Tajinder Kaur | 2017-05-22 |  | 0 | -30607 |  | 2017-05-22 | 2017-05-22 | 311 | 30607 |  |  |  |  | 0 | 0 | 0
2MIL-60 | RFS.103 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-22 | Swathy Mohandas | 2017-05-22 |  | 202 | -30607 |  | 2017-05-23 | 2017-05-23 | 5088 | 30608 |  |  |  |  | 0 | 1 | 1
4OXE-61 | RFS.108 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-22 | Tajinder Kaur | 2017-05-22 |  | 31 | -30607 |  | 2017-05-23 | 2017-05-23 | 2676 | 30608 |  |  |  |  | 0 | 1 | 1
4WRN-61 | RFS.90 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-05-22 | Tajinder Kaur | 2017-05-22 |  | 135 | -30607 |  | 2017-05-24 | 2017-05-24 | 4869 | 30609 |  |  |  |  | 0 | 2 | 2
3TYH-68 | RFS.85 | H-A-Q | HAC | Pre-AT | 1 | Rejected | 16-May-2017: ON HOLD due to 950 dummy locations 23-May-2017: v2 received but still has 950 dummy locations | 2017-05-23 | NA | 2017-05-10 | 2017-05-10 | NA | -10 | 2017-05-10 | 2017-05-10 | NA | NA | #VALUE! |  |  |  |  | 0 | #VALUE! | #VALUE!
3TYH-68 | RFS.85 | H-A-Q | HAC | Pre-AT | 2 | Completed | 23-May-2017: v2 received but still has 950 dummy locations | 2017-05-23 | Saiju/Gifty | 2017-05-23 | 2017-06-12 | 950 | 14 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 4009 | 0 |  |  |  |  | 0 | 14 | 14
2ENG-65 | RFS.88 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-24 | Jumana | 2017-05-24 | 2017-05-25 | 10 | 2 | 2017-05-25 | 2017-05-26 | 2017-05-26 | 175 | 2 |  |  |  |  | 0 | 4 | 4
5EDW-66 | RFS.113 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-24 | Swathy Mohandas | 2017-05-25 |  | 130 | -30609 |  | 2017-05-25 | 2017-05-25 | 2391 | 30610 |  |  |  |  | 0 | 1 | 1
4SLA-63 | RFS.86 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-05-24 | Tajinder Kaur | 2017-05-24 |  | 522 | -30609 |  | 2017-05-25 | 2017-05-25 | 3267 | 30610 |  |  |  |  | 0 | 1 | 1
3ELT-60 | RFS.85 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-25 | Revathy/Anet/Jowhar | 2017-05-25 | 2017-06-06 | 168 | 9 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 3415 | 1 |  |  |  |  | 0 | 10 | 10
2SEV-62 | RFS.90 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-25 | Saiju/Jumana | 2017-05-25 | 2017-06-01 | 77 | 6 | 2017-06-01 | 2017-06-06 | 2017-06-06 | 2762 | 4 |  |  |  |  | 0 | 10 | 10
5WES-65 | RFS.108 | H-M-H | BAU | Design | 1 | Completed |  | 2017-05-26 | Swathy Mohandas | 2017-05-26 |  | 252 | -30611 |  | 2017-05-30 | 2017-05-30 | 4856 | 30613 |  |  |  |  | 0 | 2 | 2
2CRR-20 | RFS.86 | H-B-H | BAU | Post RFS | 0.1 | Completed |  | 2017-05-26 | Tajinder Kaur | 2017-05-29 |  | 175 | -30611 |  | 2017-05-30 | 2017-05-30 | 1223 | 30613 |  |  |  |  | 0 | 2 | 2
4BLH-66 | RFS.94 | H-A-H | BAU | Pre-AT | 1 | Rejected | 28-Jun-2017 :On Hold defect from DESG 13-Jul-2017 : V2 arrived | 2017-05-26 | George John Panikulam | 2017-05-31 | 2017-05-31 | 27 | 4 | 2017-05-31 | 2017-05-31 | NA | 3820 | #VALUE! |  |  |  |  | 0 | #VALUE! | #VALUE!
2PNN-63 | RFS.130 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-05-29 | Goutham A S | 2017-05-29 |  | 110 | -30612 |  | 2017-06-01 | 2017-06-01 | 1484 | 30615 |  |  |  |  | 0 | 3 | 3
5HNL-62 | RFS.89 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-05-29 | Tajinder Kaur | 2017-05-30 |  | 233 | -30612 |  | 2017-06-01 | 2017-06-01 | 4637 | 30615 |  |  |  |  | 0 | 3 | 3
6SUB-63 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-30 | Manjusha | 2017-05-30 | 2017-06-01 | 48 | 3 | 2017-06-01 | 2017-06-02 | 2017-06-02 | 3474 | 2 |  |  |  |  | 0 | 5 | 5
2EPP-60 | RFS.89 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-05-30 | Manjusha | 2017-06-02 | 2017-06-07 | 57 | 7 | 2017-06-07 | 2017-06-08 | 2017-06-08 | 3935 | 2 |  |  |  |  | 0 | 9 | 9
3FNT-63 | RFS.87 | M-M-H | BAU | Design | 1 | Completed |  | 2017-05-30 | Swathy Mohandas | 2017-05-30 |  | 236 | -30613 |  | 2017-06-02 | 2017-06-02 | 1926 | 30616 |  |  |  |  | 0 | 3 | 3
4ASH-65 | RFS.57 | H-A-J | BAU | Pre-AT | 1 | Completed |  | 2017-05-30 | Swathy Mohandas | 2017-05-30 |  | 141 | -30613 |  | 2017-06-02 | 2017-06-02 | 4880 | 30616 |  |  |  |  | 0 | 3 | 3
3KGP-60 | RFS.85 | H-A-Q | HAC | Pre-AT | 1 | Rejected | 31-May-2017: ON HOLD as 237 SL located outside the NAT Boundary 01-Jun-2017: SAM got rejected due to AP issue | 2017-05-31 | NA | 2017-05-31 | 2017-05-31 | NA | 1 | 2017-05-31 | 2017-05-31 | NA | NA | #VALUE! |  |  |  |  | 0 | #VALUE! | #VALUE!
3DRP-64 | RFS.58 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-05-31 | Tajinder Kaur | 2017-06-01 |  | 7 | -30614 |  | 2017-06-05 | 2017-06-05 | 736 | 30617 |  |  |  |  | 0 | 3 | 3
4ASH-67 | RFS.70 | M-M-J | BAU | Post RFS | 1 | Completed |  | 2017-05-31 | Tajinder Kaur | 2017-06-05 |  | 164 | -30614 |  | 2017-06-06 | 2017-06-06 | 1568 | 30618 |  |  |  |  | 0 | 4 | 4
2CRM-65 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-01 | Gifty | 2017-06-01 | 2017-06-05 | 551 | 3 | 2017-06-05 | 2017-06-07 | 2017-06-07 | 3561 | 3 |  |  |  |  | 0 | 6 | 6
2STL-62 | RFS.104 | H-B-H | BAU | Post RFS | 1 | Completed |  | 2017-06-01 | Swathy Mohandas | 2017-06-02 |  | 0 | -30615 |  | 2017-06-05 | 2017-06-05 | 1243 | 30617 |  |  |  |  | 0 | 2 | 2
4SOP-60 | RFS.90 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-01 | Swathy Mohandas | 2017-06-05 |  | 211 | -30615 |  | 2017-06-06 | 2017-06-06 | 3058 | 30618 |  |  |  |  | 0 | 3 | 3
2UND-62 | RFS.116 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-06-01 | Goutham A S | 2017-06-05 |  | 246 | -30615 |  | 2017-06-06 | 2017-06-06 | 3176 | 30618 |  |  |  |  | 0 | 3 | 3
4SLA-63 | RFS.86 | H-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-06-01 | Tajinder Kaur | 2017-06-02 |  | 507 | -30615 |  | 2017-06-05 | 2017-06-05 | 3257 | 30617 |  |  |  |  | 0 | 2 | 2
2ASH-63 | RFS.116 | H-M-Q | BAU | Design | 1 | Completed | 07-Jun-2017 : On Hold critical defects from DSG 03-Jul-2017 : V4 arrived. 04-Jul-2017 : Assigned to Tajinder Kaur 05-Jul-2017 : Completed | 2017-06-01 | George John Panikulam | 2017-07-04 |  | 216 | -30615 |  | 2017-07-05 | 2017-07-05 | 3132 | 30637 |  |  |  |  | 0 | 22 | 22
4MGA-68 | RFS.114 | M-M-H | BAU | Design | 1 | Completed |  | 2017-06-02 | Swathy Mohandas | 2017-06-05 |  | 39 | -30616 |  | 2017-06-07 | 2017-06-07 | 1046 | 30619 |  |  |  |  | 0 | 3 | 3
3DAN-62 | RFS.57 | H-A-Q | BAU | Post RFS | 1 | Completed |  | 2017-06-04 | Goutham A S | 2017-06-04 |  | 20 | -30616 |  | 2017-06-09 | 2017-06-09 | 1700 | 30621 |  |  |  |  | 0 | 5 | 5
6GIR-61 | RFS.87 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-05 | Revathy | 2017-06-06 | 2017-06-07 | 22 | 3 | 2017-06-07 | 2017-06-08 | 2017-06-08 | 2321 | 2 |  |  |  |  | 0 | 5 | 5
4BUR-64 | RFS.95 | M-M-H | BAU | Design | 1 | Completed |  | 2017-06-05 | Tajinder Kaur | 2017-06-07 |  | 82 | -30617 |  | 2017-06-07 | 2017-06-07 | 5489 | 30619 |  |  |  |  | 0 | 2 | 2
6GIR-66 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-06 | Jumana | 2017-06-07 | 2017-06-08 | 29 | 3 | 2017-06-08 | 2017-06-09 | 2017-06-09 | 3136 | 2 |  |  |  |  | 0 | 5 | 5
5HNL-63 | RFS.111 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-06 | Goutham A S | 2017-06-06 |  | 121 | -30618 |  | 2017-06-09 | 2017-06-09 | 3531 | 30621 |  |  |  |  | 0 | 3 | 3
5HNL-63 | RFS.111 | H-M-Q | BAU | Design | 2 | Completed |  | 2017-06-06 | Goutham A S | 2017-06-06 |  | 119 | -30618 |  | 2017-06-09 | 2017-06-09 | 3531 | 30621 |  |  |  |  | 0 | 3 | 3
4BLH-67 | RFS.87 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-07 | Jowhar | 2017-06-07 | 2017-06-09 | 98 | 3 | 2017-06-09 | 2017-06-13 | 2017-06-13 | 1461 | 2 |  |  |  |  | 0 | 5 | 5
3GLI-64 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-07 | Saiju | 2017-06-12 | 2017-06-14 | 81 | 5 | 2017-06-14 | 2017-06-15 | 2017-06-15 | 2523 | 2 |  |  |  |  | 0 | 7 | 7
2BAL-64 | RFS.0 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-07 | George John Panikulam | 2017-06-07 |  | 32 | -30619 |  | 2017-06-08 | 2017-06-08 | 1573 | 30620 |  |  |  |  | 0 | 1 | 1
3CAN-60 | RFS.63 | H-M-H | BAU | Design | 1 | Completed |  | 2017-06-07 | Tajinder Kaur | 2017-06-08 |  | 123 | -30619 |  | 2017-06-08 | 2017-06-08 | 3695 | 30620 |  |  |  |  | 0 | 1 | 1
5EDW-66 | RFS.113 | M-M-H | BAU | Design | 2 | Completed |  | 2017-06-07 | Tajinder Kaur | 2017-06-08 |  | 130 | -30619 |  | 2017-06-09 | 2017-06-09 | 2895 | 30621 |  |  |  |  | 0 | 2 | 2
2ESP-60 | RFS.53 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-07 | Tajinder Kaur | 2017-06-09 |  | 0 | -30619 |  | 2017-06-09 | 2017-06-09 | 3961 | 30621 |  |  |  |  | 0 | 2 | 2
2ESP-61 | RFS.58 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-07 | Tajinder Kaur | 2017-06-09 |  | 0 | -30619 |  | 2017-06-09 | 2017-06-09 | 3472 | 30621 |  |  |  |  | 0 | 2 | 2
2NEW-60 | RFS.92 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-07 | Swathy Mohandas | 2017-06-07 |  | 277 | -30619 |  | 2017-06-09 | 2017-06-09 | 3263 | 30621 |  |  |  |  | 0 | 2 | 2
2CAS-62 | RFS.89 | H-A-Q | HAC | Pre-AT | 1 | Completed | 09-Jun-2017: Put ON HOLD due to Boundary mismatch 14-Jun-2017: Released the SAM mentioning the pending action with AP | 2017-06-08 | Manjusha/Anet | 2017-06-08 | 2017-06-13 | 101 | 3 | 2017-06-13 | 2017-06-14 | 2017-06-14 | 4096 | 2 |  |  |  |  | 0 | 5 | 5
4SUR-61 | RFS.134 | M-B-H | BAU | Design | 1 | Completed |  | 2017-06-08 | Tajinder Kaur | 2017-06-14 |  | 243 | -30620 |  | 2017-06-14 | 2017-06-14 | 3706 | 30623 |  |  |  |  | 0 | 3 | 3
3DNC-67 | RFS.93 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-09 | Jumana | 2017-06-12 | 2017-06-14 | 50 | 3 | 2017-06-14 | 2017-06-15 | 2017-06-15 | 2363 | 2 |  |  |  |  | 0 | 5 | 5
5HNL-61 | RFS.88 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-06-09 | Swathy Mohandas | 2017-06-13 |  | 83 | -30621 |  | 2017-06-13 | 2017-06-13 | 2958 | 30622 |  |  |  |  | 0 | 1 | 1
5GUG-63 | RFS.48 | H-M-J | BAU | Post RFS | 1 | Completed |  | 2017-06-09 | Goutham A S | 2017-06-12 |  | 1 | -30621 |  | 2017-06-14 | 2017-06-14 | 4759 | 30623 |  |  |  |  | 0 | 2 | 2
2CRR-20 | RFS.86 | H-B-H | BAU | Post RFS | 0.2 | Completed |  | 2017-06-09 | Tajinder Kaur | 2017-06-13 |  | 175 | -30621 |  | 2017-06-13 | 2017-06-13 | 1169 | 30622 |  |  |  |  | 0 | 1 | 1
3CAN-61 | RFS.65 | H-M-J | BAU | Post RFS | 1 | Completed |  | 2017-06-12 | Swathy Mohandas | 2017-06-13 |  | 219 | -30621 |  | 2017-06-15 | 2017-06-15 | 2828 | 30624 |  |  |  |  | 0 | 3 | 3
3CTA-62 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-13 | Anet | 2017-05-31 | 2017-06-07 | 143 | -4 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 3186 | 1 |  |  |  |  | 0 | -3 | -3
3HGT-74 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-13 | Revathy | 2017-06-13 | 2017-06-14 | 17 | 2 | 2017-06-14 | 2017-06-15 | 2017-06-15 | 859 | 2 |  |  |  |  | 0 | 4 | 4
5SAL-69 | RFS.87 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-13 | Gifty | 2017-06-13 | 2017-06-14 | 18 | 2 | 2017-06-14 | 2017-06-16 | 2017-06-16 | 339 | 3 |  |  |  |  | 0 | 5 | 5
3RWO-65 | RFS.87 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-13 | Saiju | 2017-06-15 | 2017-06-16 | 81 | 4 | 2017-06-16 | 2017-06-20 | 2017-06-20 | 976 | 3 |  |  |  |  | 0 | 7 | 7
3SCO-65 | RFS.121 | H-M-H | BAU | Design | 1 | Completed |  | 2017-06-13 | Tajinder Kaur | 2017-06-15 |  | 88 | -30622 |  | 2017-06-15 | 2017-06-15 | 3124 | 30624 |  |  |  |  | 0 | 2 | 2
2CAS-60 | RFS.91 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-13 | Jumana | 2017-06-15 | 2017-06-19 | 14 | 5 | 2017-06-19 | 2017-06-20 | 2017-06-20 | 1464 | 2 |  |  |  |  | 0 | 7 | 7
2BON-64 | RFS.101 | M-M-H | BAU | Design | 2 | Completed |  | 2017-06-14 | Swathy Mohandas | 2017-06-14 |  | 116 | -30623 |  | 2017-06-15 | 2017-06-15 | 2915 | 30624 |  |  |  |  | 0 | 1 | 1
2CRR-65 | RFS.102 | M-M-H | BAU | Design | 1 | Completed |  | 2017-06-14 | Goutham A S | 2017-06-14 |  | 159 | -30623 |  | 2017-06-16 | 2017-06-16 | 3121 | 30625 |  |  |  |  | 0 | 2 | 2
3KGP-60 | RFS.85 | H-A-Q | HAC | Pre-AT | 2 | Completed | 14-Jun-2017: Received v2 T18 15-Jun-2017: Started with v2 T18 19-Jun-2017: SLs outside NAT. Sent a follow-up mail to AP Team 21-Jun-2017: AP Team updated the boundary | 2017-06-15 | Revathy/Anet | 2017-06-15 | 2017-06-19 | 149 | 3 | 2017-06-19 | 2017-06-22 | 2017-06-22 | 3138 | 4 |  |  |  |  | 0 | 7 | 7
4AGV-63 | RFS.118 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-16 | Tajinder Kaur | 2017-06-19 |  | 66 | -30625 |  | 2017-06-20 | 2017-06-20 | 3217 | 30627 |  |  |  |  | 0 | 2 | 2
6SUB-65 | RFS.90 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-16 | Swathy Mohandas | 2017-06-16 |  | 48 | -30625 |  | 2017-06-20 | 2017-06-20 | 773 | 30627 |  |  |  |  | 0 | 2 | 2
3FNT-65 | RFS.63 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-06-16 | Swathy Mohandas | 2017-06-19 |  | 0 | -30625 |  | 2017-06-19 | 2017-06-19 | 1240 | 30626 |  |  |  |  | 0 | 1 | 1
5WES-61 | RFS.108 | M-M-H | BAU | Pre-AT | 1 | Rejected |  | 2017-06-16 | Swathy Mohandas | 2017-06-19 |  | 136 | -30625 |  | 2017-06-20 | 2017-06-20 | 3547 | 30627 |  |  |  |  | 0 | 2 | 2
5HNL-64 | RFS.103 | H-M-H | BAU | Design | 1 | Completed |  | 2017-06-16 | Goutham A S | 2017-06-16 |  | 34 | -30625 |  | 2017-06-19 | 2017-06-19 | 1147 | 30626 |  |  |  |  | 0 | 1 | 1
5BRI-66 | RFS.105 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-16 | Revathy Babu | 2017-06-19 |  | 289 | -30625 |  | 2017-06-22 | 2017-06-22 | 3886 | 30629 |  |  |  |  | 0 | 4 | 4
3NBA-64 | RFS.87 | H-A-Q | HAC | Pre-AT | 1 | Completed | 20-Jun-2017: Issue raised for valid SL outisde SAM Boundary 23-Jun-2017: Update received to inlcude the location outside SAM | 2017-06-19 | Saiju/Eldhose | 2017-06-20 | 2017-06-27 | 29 | 6 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2617 | 1 |  |  |  |  | 0 | 7 | 7
2BAN-68 | RFS.89 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-19 | Renjini | 2017-06-19 | 2017-06-23 | 513 | 5 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 3933 | 1 |  |  |  |  | 0 | 6 | 6
3BOX-66 | RFS.90 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-19 | Jowhar | 2017-06-19 | 2017-06-20 | 154 | 2 | 2017-06-20 | 2017-06-22 | 2017-06-22 | 4136 | 3 |  |  |  |  | 0 | 5 | 5
2CAS-63 | RFS.90 | H-A-Q | HAC | Pre-AT | 1 | Completed | 21-Jun-2017: ON HOLD. Rejected to TLS due to DESG Issue 23-Jun-2017: Update received to delete the extra PCDs in Equipment_hfc table | 2017-06-19 | Gifty/Jumana | 2017-06-19 | 2017-06-23 | 75 | 5 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 3778 | 1 |  |  |  |  | 0 | 6 | 6
3NCO-65 | RFS.86 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-21 | Kishore | 2017-06-15 | 2017-06-20 | 46 | -2 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 3935 | 1 |  |  |  |  | 0 | -1 | -1
2ROS-60 | RFS.89 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-21 | Jowhar/Revathy | 2017-06-22 | 2017-07-03 | 257 | 8 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 3828 | 1 |  |  |  |  | 0 | 9 | 9
4IAL-62 | RFS.87 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-21 | Gifty/Jumana | 2017-06-21 | 2017-06-28 | 86 | 5 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 3695 | 1 |  |  |  |  | 0 | 6 | 6
2BAN-67 | RFS.97 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-06-21 | George John Panikulam | 2017-06-21 |  | 992 | -30628 |  | 2017-06-23 | 2017-06-23 | 4933 | 30630 |  |  |  |  | 0 | 2 | 2
4SLA-68 | RFS.91 | H-A-H | BAU | Pre-AT | 2 | Rejected | On Hold because D&NA would like to investigate part of the payload before other teams begin their process. | 2017-06-21 | Goutham A S | 2017-06-21 | 2017-06-21 | 352 | 1 | 2017-06-21 | 2017-06-21 |  | 3627 | -30628 |  |  |  |  | 0 | -30627 | -30627
4AGV-61 | RFS.121 | M-M-H | BAU | Design | 1 | Completed |  | 2017-06-22 | Tajinder Kaur | 2017-06-22 |  | 17 | -30629 |  | 2017-06-23 | 2017-06-23 | 1478 | 30630 |  |  |  |  | 0 | 1 | 1
4CPB-22 | RFS.122 | M-M-H | BAU | Design | 1 | Completed |  | 2017-06-22 | Swathy Mohandas | 2017-06-23 |  | 63 | -30629 |  | 2017-06-26 | 2017-06-26 | 1044 | 30630 |  |  |  |  | 0 | 1 | 1
4BUR-67 | RFS.112 | M-M-H | BAU | Design | 2 | Completed |  | 2017-06-23 | Tajinder Kaur | 2017-06-26 |  | 181 | -30630 |  | 2017-06-26 | 2017-06-26 | 3982 | 30630 |  |  |  |  | 0 | 0 | 0
5FLN-62 | RFS.99 | H-B-J | BAU | Pre-AT | 1 | Completed |  | 2017-06-23 | Swathy Mohandas | 2017-06-26 |  | 360 | -30630 |  | 2017-06-27 | 2017-06-27 | 3559 | 30631 |  |  |  |  | 0 | 1 | 1
5GPC-60 | RFS.90 | H-A-Q | HAC | Post RFS | 1 | Completed | 27-Jun-2017: SL outside SAM boundary. CRITICAL defect 29-Jun-2017: Got confirmation to remove the SL outside SAM | 2017-06-26 | Revathy | 2017-06-27 | 2017-06-28 | 1 | 2 | 2017-06-28 | 2017-06-30 | 2017-06-30 | 602 | 3 |  |  |  |  | 0 | 5 | 5
3CAU-69 | RFS.91 | H-A-Q | HAC | Pre-AT | 1 | Completed | 28-Jun-2017: Duplicate addresses for 2 records 29-Jun-2017: Got update from TLS | 2017-06-26 | Renjini | 2017-06-27 | 2017-06-30 | 136 | 4 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 3456 | 1 |  |  |  |  | 0 | 5 | 5
2MOS-63 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Completed | 28-Jun-2017: Duplicate addresses for 24 records 30-Jun-2017: Got update from TLS | 2017-06-26 | Manjusha/Jumana | 2017-06-27 | 2017-07-08 | 552 | 9 | 2017-07-08 | 2017-07-10 | 2017-07-10 | 2884 | 1 |  |  |  |  | 0 | 10 | 10
4BLH-60 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-26 | Kishore | 2017-06-28 | 2017-07-04 | 244 | 6 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 3564 | 1 |  |  |  |  | 0 | 7 | 7
3BGO-60 | RFS.91 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-06-28 | Anet/Gifty | 2017-06-28 | 2017-07-04 | 221 | 5 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 3782 | 1 |  |  |  |  | 0 | 6 | 6
3DAN-60 | RFS.53 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-06-28 | George John Panikulam | 2017-06-28 |  | 0 | -30632 |  | 2017-06-29 | 2017-06-29 | 3086 | 30633 |  |  |  |  | 0 | 1 | 1
2UND-61 | RFS.90 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-06-28 | Swathy Mohandas | 2017-06-29 |  | 389 | -30632 |  | 2017-06-30 | 2017-06-30 | 4808 | 30634 |  |  |  |  | 0 | 2 | 2
4IAL-61 | RFS.114 | M-M-H | BAU | Design | 1 | ON HOLD | On Hold Missing SLs | 2017-06-28 | Goutham A S | 2017-06-28 | 2017-06-28 | 3 | 1 | 2017-06-28 | 2017-06-28 |  | 1068 | -30632 |  |  |  |  | 0 | -30631 | -30631
3NBA-69 | RFS.91 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-29 | Swathy Mohandas | 2017-06-30 |  | 116 | -30633 |  | 2017-07-04 | 2017-07-04 | 4273 | 30636 |  |  |  |  | 0 | 3 | 3
2BON-64 | RFS.101 | M-M-H | BAU | Design | 3 | Completed |  | 2017-06-29 | Tajinder Kaur | 2017-06-29 |  | 116 | -30633 |  | 2017-07-04 | 2017-07-04 | 2915 | 30636 |  |  |  |  | 0 | 3 | 3
5GNG-61 | RFS.95 | M-M-H | BAU | Pre-AT | 1 | Completed |  | 2017-06-30 | Revathy Babu | 2017-07-03 | 2017-07-04 | 0 | 3 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2392 | 1 |  |  |  |  | 0 | 4 | 4
2CRR-69 | RFS.90 | M-M-H | BAU | Pre-AT | 1 | Rejected | Design has identified Critical defects and this T18 requires a resubmission from Telstra. | 2017-06-30 | George John Panikulam | 2017-06-30 | 2017-06-30 | 551 | 1 | 2017-06-30 | 2017-06-30 |  | 4657 | -30634 |  |  |  |  | 0 | -30633 | -30633
5MOD-63 | RFS.96 | M-A-J | BAU | Pre-AT | 4 | Rejected | On Hold Critical defects identified by DESG | 2017-06-30 | Goutham A S | 2017-06-30 | 2017-06-30 | 130 | 1 | 2017-06-30 | 2017-06-30 |  | 8774 | -30634 |  |  |  |  | 0 | -30633 | -30633
4OXE-61 | RFS.108 | M-M-H | BAU | Design | 2 | Completed |  | 2017-07-03 | George John Panikulam | 2017-07-04 | 2017-07-05 | 31 | 3 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2676 | 1 |  |  |  |  | 0 | 4 | 4
4SOP-61 | RFS.94 | H-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-07-03 | Revathy Babu | 2017-07-04 | 2017-07-06 | 130 | 4 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 3160 | 1 |  |  |  |  | 0 | 5 | 5
2CRM-61 | RFS.89 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-04 | Saiju | 2017-07-04 | 2017-07-07 | 195 | 4 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 1105 | 1 |  |  |  |  | 0 | 5 | 5
4CHD-21 | RFS.122 | M-M-H | BAU | Design | 1 | Completed |  | 2017-07-04 | Tajinder Kaur | 2017-07-05 | 2017-07-06 | 6 | 3 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 1734 | 1 |  |  |  |  | 0 | 4 | 4
3SPL-67 | RFS.93 | M-M-H | BAU | Pre-AT | 1 | Rejected |  | 2017-07-04 | George John Panikulam | 2017-07-05 | 2017-07-05 | 156 | 2 | 2017-07-05 | 2017-07-05 |  | 4688 | -30637 |  |  |  |  | 0 | -30635 | -30635
2SEV-61 | RFS.115 | M-M-H | BAU | Design | 1 | Completed |  | 2017-07-04 | Goutham A S | 2017-07-04 | 2017-07-05 | 57 | 2 | 2017-07-05 | 2017-07-06 | 2017-07-06 | 2210 | 2 |  |  |  |  | 0 | 4 | 4
2UND-62 | RFS.116 | H-M-Q | BAU | Design | 3 | Completed |  | 2017-07-04 | Goutham A S | 2017-07-05 | 2017-07-07 | 245 | 4 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 3176 | 1 |  |  |  |  | 0 | 5 | 5
5BRI-69 | RFS.80 | H-M-H | BAU | Post RFS | 1 | Completed |  | 2017-07-05 | Swathy Mohandas | 2017-07-05 | 2017-07-07 | 0 | 3 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 446 | 1 |  |  |  |  | 0 | 4 | 4
2CMO-63 | RFS.93 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-06 | Shilpa/Arunika | 2017-07-10 | 2017-07-11 | 119 | 4 | 2017-07-11 | 2017-07-12 | 2017-07-12 | 1003 | 2 |  |  |  |  | 0 | 6 | 6
3SPL-64 | RFS.100 | M-B-H | BAU | Design | 3 | Completed |  | 2017-07-06 | George John Panikulam | 2017-07-06 | 2017-07-07 | 23 | 2 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 1002 | 1 |  |  |  |  | 0 | 3 | 3
4CHD-62 | RFS.97 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-07-06 | Tajinder Kaur | 2017-07-06 | 2017-07-07 | 145 | 2 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2619 | 1 |  |  |  |  | 0 | 3 | 3
3BLB-67 | RFS.98 | M-A-H | BAU | Pre-AT | 1 | Rejected |  | 2017-07-06 | Tajinder Kaur | 2017-07-07 | 2017-07-10 | 97 | 3 | 2017-07-10 | 2017-07-11 | 2017-07-11 | 4346 | 2 |  |  |  |  | 0 | 5 | 5
5FLN-62 | RFS.99 | H-B-J | BAU | Pre-AT | 1.2 | Rejected |  | 2017-07-06 | Swathy Mohandas | 2017-07-06 | 2017-07-06 | 360 | 1 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 3559 | 1 |  |  |  |  | 0 | 2 | 2
3END-62 | RFS.81 | M-A-J | BAU | Post RFS | 1 | Completed |  | 2017-07-06 | Swathy Mohandas | 2017-07-06 | 2017-07-07 | 85 | 2 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2670 | 1 |  |  |  |  | 0 | 3 | 3
4MGA-70 | RFS.114 | M-M-H | BAU | Design | 1 | Completed |  | 2017-07-06 | Goutham A S | 2017-07-07 | 2017-07-11 | 44 | 4 | 2017-07-11 | 2017-07-11 | 2017-07-11 | 2181 | 1 |  |  |  |  | 0 | 5 | 5
4OXE-62 | RFS.0 | H-A-H | BAU | Pre-AT | 1 | Rejected | 07-Jul-2017: Issue raise for NAT boundary mismatch with Area Planning team. 17-Jul-2017 : 4OXE-62 T18 is being sent back to Telstra due to critical issues identified by Area Planning. The NAT Boundary issued identified will not be fixed until the resubmission is processed at a later date. | 2017-07-06 | George John Panikulam | 2017-07-07 | 2017-07-07 | 199 | 2 | 2017-07-07 | 2017-07-07 |  | 3536 | -30639 |  |  |  |  | 0 | -30637 | -30637
3MLN-63 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed | 14-Jul-2017: Pending Action with AP Team. One SL located outisde SAM | 2017-07-07 | Revathy/Sanjana | 2017-07-07 | 2017-07-12 | 97 | 4 | 2017-07-12 | 2017-07-14 | 2017-07-14 | 3815 | 3 |  |  |  |  | 0 | 7 | 7
4SOP-64 | RFS.0 | M-M-H | BAU | Design | 1 | Completed |  | 2017-07-10 | Swathy Mohandas | 2017-07-10 | 2017-07-11 | 315 | 2 | 2017-07-11 | 2017-07-11 | 2017-07-11 | 3101 | 1 |  |  |  |  | 0 | 3 | 3
2MOS-62 | RFS.95 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-07-10 | Saiju Xavier | 2017-07-11 | 2017-07-12 | 6 | 3 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 724 | 1 |  |  |  |  | 0 | 4 | 4
3BGO-62 | RFS.93 | M-M-H | BAU | Design | 1 | Completed |  | 2017-07-10 | Goutham A S | 2017-07-11 | 2017-07-12 | 213 | 3 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 3391 | 1 |  |  |  |  | 0 | 4 | 4
5BRI-60 | RFS.140 | H-M-H | BAU | Design | 1 | Completed |  | 2017-07-10 | George John Panikulam | 2017-07-11 | 2017-07-12 | 11 | 3 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 576 | 1 |  |  |  |  | 0 | 4 | 4
2EAS-65 | RFS.89 | M-M-H | BAU | Pre-AT | 1 | Completed |  | 2017-07-12 | Goutham A S | 2017-07-13 | 2017-07-14 | 349 | 3 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 1199 | 1 |  |  |  |  | 0 | 4 | 4
3SPL-62 | RFS.107 | M-M-H | BAU | Design | 3 | Completed |  | 2017-07-13 | George John Panikulam | 2017-07-13 | 2017-07-17 | 478 | 3 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 5858 | 1 |  |  |  |  | 0 | 4 | 4
2LIV-62 | RFS.65 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-07-13 | Sanjana | 2017-07-13 | 2017-07-17 | 0 | 3 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 877 | 1 |  |  |  |  | 0 | 4 | 4
2ASH-62 | RFS.89 | H-M-Q | BAU | Design | 1 | ON HOLD | 18-Jul-2017 : On Hold. Critical defect identified by Area Planning. | 2017-07-13 | Arunika | 2017-07-13 | 2017-07-13 | 431 | 1 | 2017-07-13 | 2017-07-13 |  | 3593 | -30643 |  |  |  |  | 0 | -30642 | -30642
4BLH-66 | RFS.94 | H-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-07-13 | Reenu | 2017-07-13 | 2017-07-17 | 23 | 3 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 3816 | 1 |  |  |  |  | 0 | 4 | 4
3WER-64 | RFS.100 | M-B-H | BAU | Post RFS | 1 | Rejected | 17-Jul-17 : Update pending with TLS for the next payload. Withdrawn from Appian | 2017-07-13 | Jumana | 2017-07-13 | 2017-07-13 | 0 | 1 | 2017-07-13 | 2017-07-13 |  | 2610 | -30643 |  |  |  |  | 0 | -30642 | -30642
3FNT-67 | RFS.66 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-07-13 | Revathy | 2017-07-13 | 2017-07-17 | 0 | 3 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 823 | 1 |  |  |  |  | 0 | 4 | 4
2BAL-65 | RFS.93 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-13 | Shilpa | 2017-07-13 | 2017-07-18 | 137 | 4 | 2017-07-18 | 2017-07-19 | 2017-07-19 | 3825 | 2 |  |  |  |  | 0 | 6 | 6
4MRA-62 | RFS.58 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-07-14 | Goutham A S | 2017-07-17 | 2017-07-18 | 0 | 3 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 1091 | 1 |  |  |  |  | 0 | 4 | 4
2STL-63 | RFS.104 | H-B-H | BAU | Design | 1 | Completed |  | 2017-07-14 | Tajinder Kaur | 2017-07-14 | 2017-07-14 | 139 | 1 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2206 | 1 |  |  |  |  | 0 | 2 | 2
2ENG-62 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-14 | Jumana | 2017-07-14 | 2017-07-19 | 144 | 4 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 1742 | 1 |  |  |  |  | 0 | 5 | 5
2EPP-61 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-14 | Sanjana | 2017-07-14 | 2017-07-19 | 334 | 4 | 2017-07-19 | 2017-07-20 | 2017-07-20 | 4591 | 2 |  |  |  |  | 0 | 6 | 6
2ROS-65 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-14 | Anet/Reenu | 2017-07-14 | 2017-07-19 | 120 | 4 | 2017-07-19 | 2017-07-20 | 2017-07-20 | 3606 | 2 |  |  |  |  | 0 | 6 | 6
4OXE-63 | RFS.0 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-14 | Gifty/Kavya | 2017-07-14 | 2017-07-18 | 5 | 3 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 381 | 1 |  |  |  |  | 0 | 4 | 4
4APL-60 | RFS.122 | M-M-H | BAU | Design | 1 | ON HOLD | 19-Jul-2017 : on Hold. Critical defect identified by AP and design team. | 2017-07-17 | George John Panikulam | 2017-07-17 | 2017-07-17 | 106 | 1 | 2017-07-17 | 2017-07-17 |  | 2939 | -30645 |  |  |  |  | 0 | -30644 | -30644
4MGB-01 | RFS.100 | M-B-H | BAU | Design | 1 | ON HOLD | 19-Jul-2017 : on Hold. Critical defect identified by AP and design team. | 2017-07-17 | Tajinder Kaur | 2017-07-17 | 2017-07-17 | 1171 | 1 | 2017-07-17 | 2017-07-17 |  | 1228 | -30645 |  |  |  |  | 0 | -30644 | -30644
4CPH-69 | RFS.93 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-18 | Saiju | 2017-07-18 | 2017-07-19 | 150 | 2 | 2017-07-19 | 2017-07-21 | 2017-07-21 | 3173 | 3 |  |  |  |  | 0 | 5 | 5
2ING-64 | RFS.112 | M-M-H | BAU | Design | 1 | Completed |  | 2017-07-18 | Arunika | 2017-07-18 | 2017-07-20 | 334 | 3 | 2017-07-20 | 2017-07-20 | 2017-07-20 | 2964 | 1 |  |  |  |  | 0 | 4 | 4
4IAL-61 | RFS.114 | M-M-H | BAU | Design | 2 | Completed |  | 2017-07-18 | Goutham A S | 2017-07-18 | 2017-07-19 | 3 | 2 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 1154 | 1 |  |  |  |  | 0 | 3 | 3
4CHD-60 | RFS.126 | M-M-H | BAU | Design | 1 | ON HOLD | 19-Jul-2017 : on Hold. Critical defect identified by AP and design team. | 2017-07-18 | Tajinder Kaur | 2017-07-18 |  | 4 | -30646 |  |  |  | 1720 | 0 |  |  |  |  | 0 | -30646 | -30646
3BLB-67 | RFS.98 | M-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-07-18 | Shilpa/Revathy | 2017-07-18 | 2017-07-19 | 97 | 2 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 3914 | 1 |  |  |  |  | 0 | 3 | 3
2PET-60 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed | 24-Jul-2017: ON HOLD as 65/40 is not met 17-Aug-2017: Taken from HOLD as confirmed by NA team | 2017-07-19 | Jowharulla.M | 2017-08-17 | 2017-08-21 | 7 | 23 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 4078 | 1 |  |  |  |  | 0 | 24 | 24
4CHD-01 | RFS.117 | M-M-H | BAU | Design | 1 | ON HOLD | Critical defect identified by AP and design team. | 2017-07-19 | Shilpa | 2017-07-19 | 2017-07-19 | 241 | 1 | 2017-07-19 | 2017-07-19 |  | 4977 | -30647 |  |  |  |  | 0 | -30646 | -30646
4MGA-66 | RFS.114 | M-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-19 | Kavya | 2017-07-19 | 2017-07-21 | 23 | 3 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 3911 | 1 |  |  |  |  | 0 | 4 | 4
3NCO-60 | RFS.97 | M-A-H | BAU | Pre-AT | 1 | ON HOLD | Critical defect identified by AP and design team. | 2017-07-19 | Jumana | 2017-07-19 | 2017-07-19 | 125 | 1 | 2017-07-19 | 2017-07-19 |  | 3640 | -30647 |  |  |  |  | 0 | -30646 | -30646
2BAM-64 | RFS.93 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-07-19 | George John Panikulam | 2017-07-19 | 2017-07-21 | 130 | 3 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 3786 | 1 |  |  |  |  | 0 | 4 | 4
4SLA-75 | RFS.94 | M-B-H | BAU | Pre-AT | 2 | Rejected | Critical defect identified by design team. | 2017-07-19 | Goutham A S | 2017-07-19 | 2017-07-21 | 0 | 3 | 2017-07-21 | 2017-07-21 |  | 906 | -30649 |  |  |  |  | 0 | -30646 | -30646
2LIV-68 | RFS.93 | M-M-H | BAU | Pre-AT | 2 | Completed |  | 2017-07-20 | Saiju Xavier | 2017-07-20 | 2017-07-24 | 163 | 3 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 1911 | 1 |  |  |  |  | 0 | 4 | 4
4CHD-64 | RFS.97 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-07-20 | Sanjana Krishnan | 2017-07-20 | 2017-07-24 | 26 | 3 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 3822 | 1 |  |  |  |  | 0 | 4 | 4
4BUR-68 | RFS.91 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-20 | Revathy | 2017-07-20 | 2017-07-21 | 65 | 2 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 1328 | 1 |  |  |  |  | 0 | 3 | 3
3GLI-61 | RFS.91 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-20 | Kavya/revathy | 2017-07-20 | 2017-07-24 | 115 | 3 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 3095 | 1 |  |  |  |  | 0 | 4 | 4
3NCO-68 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Rejected | 24-Jul-2017: ON HOLD as 65/40 is not met | 2017-07-20 | Reenu | 2017-07-20 | 2017-07-20 |  | 1 | 2017-07-20 | 2017-07-20 | NA |  | #VALUE! |  |  |  |  | 0 | #VALUE! | #VALUE!
3SPL-63 | RFS.66 | H-A-H | BAU | Post RFS | 3 | Completed |  | 2017-07-21 | George John Panikulam | 2017-07-21 | 2017-07-24 | 0 | 2 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 1749 | 1 |  |  |  |  | 0 | 3 | 3
2BAN-63 | RFS.112 | M-M-H | BAU | Design | 1 | Completed |  | 2017-07-21 | Aleena Johny | 2017-07-21 | 2017-07-27 | 1405 | 5 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 5947 | 1 |  |  |  |  | 0 | 6 | 6
3CAU-62 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed | 24-Jul-2017: ON HOLD as 65/40 is not met 17-Aug-2017: Taken from HOLD as confirmed by NA team | 2017-07-21 | Manjusha M | 2017-08-17 | 2017-08-23 | 293 | 23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 4568 | 1 |  |  |  |  | 0 | 24 | 24
4CHD-65 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-24 | Arunika | 2017-07-24 | 2017-07-26 | 87 | 3 | 2017-07-26 | 2017-07-27 | 2017-07-27 | 3735 | 2 |  |  |  |  | 0 | 5 | 5
3MIT-64 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-24 | Jumana | 2017-07-24 | 2017-07-26 | 69 | 3 | 2017-07-26 | 2017-07-27 | 2017-07-27 | 3426 | 2 |  |  |  |  | 0 | 5 | 5
3HGT-68 | RFS.74 | M-M-J | BAU | Post RFS | 0.2 | Completed |  | 2017-07-24 | Goutham A S | 2017-07-24 | 2017-07-25 | 137 | 2 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2605 | 1 |  |  |  |  | 0 | 3 | 3
3KGP-65 | RFS.93 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-07-24 | Swathy Mohandas | 2017-07-24 | 2017-07-25 | 163 | 2 | 2017-07-25 | 2017-07-26 | 2017-07-26 | 5157 | 2 |  |  |  |  | 0 | 4 | 4
4CPB-61 | RFS.63 | M-A-J | BAU | Post RFS | 0.5 | Rejected | Critical defect identified by AP and design team. | 2017-07-24 | Jowhar | 2017-07-24 | 2017-07-24 | 71 | 1 | 2017-07-24 | 2017-07-24 |  | 3684 | -30650 |  |  |  |  | 0 | -30649 | -30649
5FLN-60 | RFS.104 | H-B-J | BAU | Post RFS | 2.1 | Completed |  | 2017-07-24 | Kavya | 2017-07-24 | 2017-07-26 | 43 | 3 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 1578 | 1 |  |  |  |  | 0 | 4 | 4
4ASH-67 | RFS.70 | M-M-J | BAU | Post RFS | 1.4 | Completed |  | 2017-07-24 | Shilpa | 2017-07-24 | 2017-07-27 | 155 | 4 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 1559 | 1 |  |  |  |  | 0 | 5 | 5
3BGO-62 | RFS.93 | M-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-07-25 | Goutham A S | 2017-07-25 | 2017-07-27 | 261 | 3 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 3391 | 1 |  |  |  |  | 0 | 4 | 4
4SLA-69 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-07-25 | Sanjana Krishnan | 2017-07-25 | 2017-07-27 | 0 | 3 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 4688 | 1 |  |  |  |  | 0 | 4 | 4
3SPL-67 | RFS.93 | M-M-H | BAU | Pre-AT | 0.2 | Completed |  | 2017-07-25 | George John Panikulam | 2017-07-25 | 2017-07-27 | 0 | 3 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 609 | 1 |  |  |  |  | 0 | 4 | 4
2ASH-68 | RFS.0 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-25 | Saiju | 2017-07-25 | 2017-07-27 | 103 | 3 | 2017-07-27 | 2017-07-28 | 2017-07-28 | 2876 | 2 |  |  |  |  | 0 | 5 | 5
2ROS-62 | RFS.94 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-25 | Jowhar | 2017-07-25 | 2017-07-27 | 53 | 3 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 1382 | 1 |  |  |  |  | 0 | 4 | 4
2SHA-62 | RFS.94 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-25 | Manjusha | 2017-07-25 | 2017-07-27 | 113 | 3 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2840 | 1 |  |  |  |  | 0 | 4 | 4
2ASH-62 | RFS.89 | H-M-Q | BAU | Design | 4 | ON HOLD | Critical defect identified by design team. | 2017-07-26 | Saranya Geetha | 2017-07-26 | 2017-07-26 | 431 | 1 | 2017-07-26 | 2017-07-26 |  | 3593 | -30652 |  |  |  |  | 0 | -30651 | -30651
4MGA-68 | RFS.114 | M-M-H | BAU | Design | 2 | Completed |  | 2017-07-27 | Goutham A S | 2017-07-27 | 2017-07-28 | 41 | 2 | 2017-07-28 | 2017-07-28 | 2017-07-28 | 1048 | 1 |  |  |  |  | 0 | 3 | 3
2CRR-70 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-07-27 | George John Panikulam | 2017-07-27 | 2017-07-28 | 0 | 2 | 2017-07-28 | 2017-07-28 | 2017-07-28 | 1460 | 1 |  |  |  |  | 0 | 3 | 3
2EDG-65 | RFS.65 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-07-27 | Shilpa | 2017-07-27 | 2017-07-31 | 100 | 3 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 1237 | 1 |  |  |  |  | 0 | 4 | 4
4SLA-75 | RFS.96 | M-B-H | BAU | Pre-AT | 3 | Completed |  | 2017-07-27 | Goutham/Swathy | 2017-07-27 | 2017-08-01 | 0 | 4 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 906 | 1 |  |  |  |  | 0 | 5 | 5
4BUR-21 | RFS.94 | M-B-H | BAU | Post RFS | 0.1 | Completed |  | 2017-07-28 | Reenu | 2017-07-28 | 2017-07-31 | 0 | 2 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 1676 | 1 |  |  |  |  | 0 | 3 | 3
2MEN-63 | RFS.117 | M-M-H | BAU | Design | 1 | Completed |  | 2017-07-28 | Jowharulla M | 2017-07-28 | 2017-08-01 | 111 | 3 | 2017-08-01 | 2017-08-02 | 2017-08-02 | 858 | 2 |  |  |  |  | 0 | 5 | 5
4SLA-66 | RFS.94 | M-B-H | BAU | Post RFS | 0.1 | Completed |  | 2017-07-28 | Jowharulla M | 2017-07-28 | 2017-07-31 | 0 | 2 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 339 | 1 |  |  |  |  | 0 | 3 | 3
5HNL-60 | RFS.77 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-07-28 | Jumana M | 2017-07-28 | 2017-08-01 | 0 | 3 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 561 | 1 |  |  |  |  | 0 | 4 | 4
4CHD-63 | RFS.107 | M-M-Q | BAU | Design | 2 | On Hold |  | 2017-07-28 | Kavya Methil | 2017-07-28 | 2017-08-01 | 243 | 3 | 2017-08-01 | 2017-08-02 | 2017-08-02 | 4978 | 2 |  |  |  |  | 0 | 5 | 5
4SOP-64 | RFS.0 | M-M-H | BAU | Design | 2 | Completed |  | 2017-07-28 | Sanjana Krishnan | 2017-07-28 | 2017-07-31 | 315 | 2 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 3101 | 1 |  |  |  |  | 0 | 3 | 3
3BLB-64 | RFS.93 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-28 | Goutham A S | 2017-07-28 | 2017-07-31 | 72 | 2 | 2017-07-31 | 2017-08-01 | 2017-08-01 | 4132 | 2 |  |  |  |  | 0 | 4 | 4
6GIR-62 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-28 | Manjusha | 2017-07-28 | 2017-07-31 | 3 | 2 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 1204 | 1 |  |  |  |  | 0 | 3 | 3
5BRI-67 | RFS.100 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-28 | George John Panikulam | 2017-07-28 | 2017-07-31 | 155 | 2 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 1147 | 1 |  |  |  |  | 0 | 3 | 3
2STL-61 | RFS.104 | M-M-H | BAU | Design | 3 | Completed |  | 2017-07-31 | Shilpa | 2017-07-31 | 2017-08-02 | 440 | 3 | 2017-08-02 | 2017-08-02 | 2017-08-02 | 3404 | 1 |  |  |  |  | 0 | 4 | 4
4SLA-68 | RFS.68 | H-A-H | BAU | Pre-AT | 0.1 | Completed | The internal nbn fix T18 and artefacts | 2017-07-31 | Saiju Xavier | 2017-07-31 | 2017-08-03 | 350 | 4 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 3627 | 1 |  |  |  |  | 0 | 5 | 5
2PET-63 | RFS.96 | H-M-Q | HAC | Pre-AT | 1 | Completed | 02-Aug-2017: 65/40 NOT MET but takes this as H-M-Q 02-Aug-2017 : Will be completed as BAU SAM. 17-Aug-2017: Got Confirmation to take as H-A-Q sam | 2017-07-31 | Revathy A | 2017-08-17 | 2017-08-21 | 181 | 15 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 1441 | 1 |  |  |  |  | 0 | 16 | 16
3DNC-61 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Rejected |  | 2017-07-31 | Saranya Geetha | 2017-07-31 | 2017-08-02 | 76 | 3 | 2017-08-02 | 2017-08-02 | 2017-08-02 | 1936 | 1 |  |  |  |  | 0 | 4 | 4
3RWO-60 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-31 | Saiju | 2017-07-31 | 2017-08-03 | 154 | 4 | 2017-08-03 | 2017-08-04 | 2017-08-04 | 3515 | 2 |  |  |  |  | 0 | 6 | 6
6KSL-60 | RFS.95 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-07-31 | Manjusha | 2017-07-31 | 2017-08-01 | 8 | 2 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 3936 | 1 |  |  |  |  | 0 | 3 | 3
2SEF-67 | RFS.95 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-01 | Goutham A S | 2017-08-01 | 2017-08-02 | 66 | 2 | 2017-08-02 | 2017-08-02 | 2017-08-02 | 1046 | 1 |  |  |  |  | 0 | 3 | 3
2EPP-62 | RFS.117 | M-M-H | BAU | Design | 1 | Completed |  | 2017-08-01 | Reenu Treesa | 2017-08-01 | 2017-08-03 | 124 | 3 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2301 | 1 |  |  |  |  | 0 | 4 | 4
2PET-63 | RFS.96 | H-M-H | BAU | Design | 1 | Completed | 02-Aug-2017: Came into BAU queue as H-M-H | 2017-08-02 | Aleena Johny | 2017-08-02 | 2017-08-03 | 181 | 2 | 2017-08-03 | 2017-08-04 | 2017-08-04 | 1789 | 2 |  |  |  |  | 0 | 4 | 4
4CHP-60 | RFS.95 | M-M-H | BAU | Design | 1 | Completed |  | 2017-08-02 | George John Panikulam | 2017-08-02 | 2017-08-03 | 122 | 2 | 2017-08-03 | 2017-08-04 | 2017-08-04 | 3913 | 2 |  |  |  |  | 0 | 4 | 4
4MGB-61 | RFS.95 | H-A-H | BAU | Pre-AT | 0.1 | Completed | 03-Aug-2017 : LocID_TempID file sent. | 2017-08-02 | Jowharulla M | 2017-08-02 | 2017-08-03 | 0 | 2 | 2017-08-03 | 2017-08-04 | 2017-08-04 | 614 | 2 |  |  |  |  | 0 | 4 | 4
3END-62 | RFS.81 | M-A-J | BAU | Post RFS | 1.1 | Completed |  | 2017-08-02 | Manjusha | 2017-08-02 | 2017-08-04 | 85 | 3 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2840 | 1 |  |  |  |  | 0 | 4 | 4
2EAS-62 | RFS.95 | M-M-H | BAU | Design | 4 | ON HOLD | Critical defect identified by AP and design team. | 2017-08-02 | Sanjana Krishnan | 2017-08-02 | 2017-08-07 | 541 | 4 | 2017-08-07 | 2017-08-07 |  | 5548 | -30660 |  |  |  |  | 0 | -30656 | -30656
4CPB-60 | RFS.65 | M-M-J | BAU | Post RFS | 0.4 | Rejected | Put on hold as LDM’s IAB activities haven’t been incorporated in the FAB payload | 2017-08-02 | Tajinder Kaur | 2017-08-02 | 2017-08-02 | 123 | 1 | 2017-08-02 | 2017-08-02 |  | 2506 | -30657 |  |  |  |  | 0 | -30656 | -30656
6SUB-66 | RFS.0 | M-M-H | BAU | Design | 1 | Completed |  | 2017-08-02 | Devika Kala | 2017-08-02 | 2017-08-04 | 48 | 3 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2454 | 1 |  |  |  |  | 0 | 4 | 4
3MIT-63 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-02 | Jumana | 2017-08-02 | 2017-08-04 | 102 | 3 | 2017-08-04 | 2017-08-07 | 2017-08-07 | 3445 | 2 |  |  |  |  | 0 | 5 | 5
5EDW-68 | RFS.120 | H-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-08-03 | Shilpa | 2017-08-03 | 2017-08-04 | 278 | 2 | 2017-08-04 | 2017-08-05 | 2017-08-05 | 1073 | 1 |  |  |  |  | 0 | 3 | 3
4OXE-62 | RFS.0 | H-A-H | BAU | Pre-AT | 2 | Rejected | Address Obsoletion and reinstating task on hold as waiting for Area Planning to respond on the boundary issues. 08-Aug-17 : Sent reminder to AP team regarding the boundary mismatch. 23-Aug-17 : Decided to Reject due to Area Planning Issues | 2017-08-03 | Revathy | 2017-08-03 | 2017-08-07 | 199 | 3 | 2017-08-07 | 2017-08-07 |  | 3536 | -30660 |  |  |  |  | 0 | -30657 | -30657
4BUR-64 | RFS.95 | M-M-H | BAU | Design | 2 | Completed |  | 2017-08-03 | Saranya Geetha | 2017-08-03 | 2017-08-04 | 81 | 2 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 5489 | 1 |  |  |  |  | 0 | 3 | 3
5MOD-63 | RFS.96 | M-A-J | BAU | Pre-AT | 5 | Rejected | Address Obsoletion and reinstating task on hold due to NAT Boundary issue. 15-Aug-2017 On hold due to Area Planning issues | 2017-08-03 | Goutham A S | 2017-08-03 | 2017-08-08 | 136 | 4 | 2017-08-08 | 2017-08-08 |  | 8777 | -30661 |  |  |  |  | 0 | -30657 | -30657
4MGA-67 | RFS.117 | M-M-H | BAU | Design | 0.1 | Completed |  | 2017-08-04 | Jowharulla M | 2017-08-04 | 2017-08-07 | 25 | 2 | 2017-08-07 | 2017-08-08 | 2017-08-08 | 1619 | 2 |  |  |  |  | 0 | 4 | 4
4BUR-62 | RFS.94 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-04 | Saiju Xavier | 2017-08-04 | 2017-08-07 | 107 | 2 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 990 | 1 |  |  |  |  | 0 | 3 | 3
3WIR-62 | RFS.96 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-07 | Arunika | 2017-08-07 | 2017-08-09 | 243 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2487 | 1 |  |  |  |  | 0 | 4 | 4
2CRR-69 | RFS.93 | M-M-H | BAU | Pre-AT | 1.1 | Completed |  | 2017-08-07 | George John Panikulam | 2017-08-07 | 2017-08-09 | 542 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 4648 | 1 |  |  |  |  | 0 | 4 | 4
3WER-64 | RFS.100 | M-B-H [P] | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-07 | Devika Kala | 2017-08-07 | 2017-08-09 | 0 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2610 | 1 |  |  |  |  | 0 | 4 | 4
4SLA-73 | RFS.73 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-07 | Reenu | 2017-08-07 | 2017-08-09 | 2 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 610 | 1 |  |  |  |  | 0 | 4 | 4
3NCO-60 | RFS.97 | M-M-H | BAU | Design | 2 | Completed |  | 2017-08-07 | Shilpa | 2017-08-07 | 2017-08-08 | 125 | 2 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 3640 | 1 |  |  |  |  | 0 | 3 | 3
3DRP-63 | RFS.80 | M-M-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-07 | Aleena Johny | 2017-08-07 | 2017-08-09 | 0 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2115 | 1 |  |  |  |  | 0 | 4 | 4
4EMP-61 | RFS.75 | M-M-H | BAU | Post RFS | 0.1 | Rejected |  | 2017-08-07 | Saranya Geetha | 2017-08-07 | 2017-08-09 | 0 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 1475 | 1 |  |  |  |  | 0 | 4 | 4
2BAL-66 | RFS.97 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-08-07 | Saiju | 2017-08-07 | 2017-08-09 | 340 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 3478 | 1 |  |  |  |  | 0 | 4 | 4
4BNP-64 | RFS.115 | M-M-H | BAU | Design | 1 | Completed |  | 2017-08-07 | Goutham A S | 2017-08-07 | 2017-08-10 | 75 | 4 | 2017-08-10 | 2017-08-10 | 2017-08-10 | 2750 | 1 |  |  |  |  | 0 | 5 | 5
2CRR-72 | RFS.95 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-07 | Jowaharulla | 2017-08-07 | 2017-08-09 | 291 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 4347 | 1 |  |  |  |  | 0 | 4 | 4
3NCO-66 | RFS.97 | M-M-H | BAU | Design | 2 | Completed |  | 2017-08-07 | Manjusha | 2017-08-07 | 2017-08-10 | 377 | 4 | 2017-08-11 | 2017-08-11 | 2017-08-11 | 5002 | 1 |  |  |  |  | 0 | 5 | 5
4MGB-66 | RFS.95 | H-M-Q | BAU | Pre-AT | 0.1 | Completed | Completed on the payload DESG provided. Task not appeared in APPIAN due to some issues. | 2017-08-07 | George John Panikulam | 2017-08-09 | 2017-08-09 | 44 | 3 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 1372 | 1 |  |  |  |  | 0 | 4 | 4
2ASH-62 | RFS.89 | H-M-Q | BAU | Design | 5 | Completed | Due to AP and Design issues. 14-Aug-17 : Sam released from hold | 2017-08-08 | Reenu | 2017-08-08 | 2017-08-14 | 428 | 5 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 3590 | 1 |  |  |  |  | 0 | 6 | 6
4MGB-01 | RFS.100 | M-B-H | BAU | Design | 2 | Completed |  | 2017-08-08 | Devika Kala | 2017-08-08 | 2017-08-10 | 1048 | 3 | 2017-08-10 | 2017-08-10 | 2017-08-10 | 1048 | 1 |  |  |  |  | 0 | 4 | 4
5FLN-62 | RFS.99 | H-B-J | BAU | Pre-AT | 1.4 | Rejected |  | 2017-08-08 | George John Panikulam | 2017-08-08 | 2017-08-10 | 0 | 3 | 2017-08-11 | 2017-08-11 | 2017-08-11 | 3559 | 1 |  |  |  |  | 0 | 4 | 4
4SLA-64 | RFS.104 | M-M-H | BAU | Design | 1 | Rejected |  | 2017-08-08 | Shilpa | 2017-08-09 | 2017-08-11 | 349 | 4 | 2017-08-11 | 2017-08-11 | 2017-08-11 | 3300 | 1 | 2017-08-17 |  |  |  | 0 | 5 | 5
2BAN-61 | RFS.113 | H-M-H | BAU | Design | 1 | Completed | Due to AP and Design issues. 11-Aug-17 : Sam released from hold | 2017-08-08 | Saranya/Swathy | 2017-08-11 | 2017-08-15 | 1873 | 5 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 5722 | 0 |  |  |  |  | 0 | 5 | 5
3SOA-60 | RFS.96 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-08-08 | Saiju | 2017-08-08 | 2017-08-10 | 204 | 3 | 2017-08-10 | 2017-08-10 | 2017-08-10 | 3559 | 1 |  |  |  |  | 0 | 4 | 4
2PET-69 | RFS.96 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-08-08 | Revathy/Sanjana | 2017-08-08 | 2017-08-11 | 381 | 4 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 3975 | 1 |  |  |  |  | 0 | 5 | 5
4BUR-65 | RFS.77 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-08 | Goutham A S | 2017-08-09 | 2017-08-10 | 0 | 3 | 2017-08-10 | 2017-08-10 | 2017-08-10 | 1271 | 1 |  |  |  |  | 0 | 4 | 4
3HGT-66 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 | Rejected |  | 2017-08-09 | Jowaharulla | 2017-08-09 | 2017-08-10 | 0 | 2 | 2017-08-10 | 2017-08-10 | 2017-08-10 | 665 | 1 |  |  |  |  | 0 | 3 | 3
3HGT-73 | RFS.66 | H-A-H | BAU | Post RFS | 0.2 | Completed |  | 2017-08-09 | Shambhavi | 2017-08-09 | 2017-08-10 | 0 | 2 | 2017-08-10 | 2017-08-10 | 2017-08-10 | 457 | 1 |  |  |  |  | 0 | 3 | 3
4MGB-63 | RFS.95 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-09 | Jumana | 2017-08-09 | 2017-08-11 | 34 | 3 | 2017-08-09 | 2017-08-11 | 2017-08-11 | 2993 | 3 |  |  |  |  | 0 | 6 | 6
4ASH-62 | RFS.95 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-09 | Revathy | 2017-08-09 | 2017-08-10 | 5 | 2 | 2017-08-09 | 2017-08-10 | 2017-08-10 | 1290 | 2 |  |  |  |  | 0 | 4 | 4
2EAS-67 | RFS.96 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-11 | Goutham A S/Revathy | 2017-08-11 | 2017-08-14 | 473 | 2 | 2017-08-11 | 2017-08-14 | 2017-08-14 | 3839 | 2 |  |  |  |  | 0 | 4 | 4
2EAS-68 | RFS.0 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-08-11 | Devika Kala | 2017-08-11 | 2017-08-14 | 343 | 2 | 2017-08-11 | 2017-08-14 | 2017-08-14 | 3899 | 2 |  |  |  |  | 0 | 4 | 4
3FNT-63 | RFS.87 | M-M-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-11 | Saiju/Tajinder | 2017-08-11 | 2017-08-15 | 0 | 2 | 2017-08-11 | 2017-08-15 | 2017-08-15 | 1926 | 2 |  |  |  |  | 0 | 4 | 4
5SAL-62 | RFS.82 | M-M-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-11 | Manjusha | 2017-08-11 | 2017-08-15 | 0 | 2 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 665 | 0 |  |  |  |  | 0 | 2 | 2
4SLA-72 | RFS.68 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-14 | Shambhavi | 2017-08-14 | 2017-08-16 | 0 | 2 | 2017-08-14 | 2017-08-16 | 2017-08-16 | 595 | 2 |  |  |  |  | 0 | 4 | 4
4CHP-60 | RFS.95 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-14 | Sanjana | 2017-08-14 | 2017-08-16 | 121 | 2 | 2017-08-21 | 2017-08-21 | 2017-08-21 | 3912 | 1 |  |  |  |  | 0 | 3 | 3
5BRI-64 | RFS.123 | H-M-H | BAU | Design | 1 | Completed |  | 2017-08-14 | Shilpa | 2017-08-14 | 2017-08-14 | 169 | 1 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 3454 | 1 |  |  |  |  | 0 | 2 | 2
2EAS-65 | RFS.93 | M-M-H | BAU | Pre-AT | 0.2 | Completed |  | 2017-08-14 | Manjhusa | 2017-08-14 | 2017-08-15 | 349 | 1 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 1199 | 1 |  |  |  |  | 0 | 2 | 2
2BON-65 | RFS.99 | H-A-Q | HAC | Pre-AT | 0.1 | Completed |  | 2017-08-14 | Jumana M | 2017-08-14 | 2017-08-16 | 175 | 2 | 2017-08-14 | 2017-08-16 | 2017-08-16 | 2512 | 2 |  |  |  |  | 0 | 4 | 4
3SOA-65 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-14 | Reenu | 2017-08-14 | 2017-08-16 | 112 | 2 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2453 | 1 |  |  |  |  | 0 | 3 | 3
2EDG-62 | RFS.96 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-15 | Saranya Geetha | 2017-08-15 | 2017-08-17 | 341 | 2 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 3188 | 1 |  |  |  |  | 0 | 3 | 3
2EAS-62 | RFS.96 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-16 | George John Panikulam | 2017-08-16 | 2017-08-17 | 436 | 2 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 4241 | 1 |  |  |  |  | 0 | 3 | 3
3DNC-65 | RFS.69 | H-A-H | BAU | Post RFS | 0.1 | Rejected | Critical defect identified by design team. | 2017-08-16 | Goutham | 2017-08-16 | 2017-08-16 | 14 | 1 | 2017-08-16 | 2017-08-16 |  | 2036 | -30666 |  |  |  |  | 0 | -30665 | -30665
2PEN-63 |  | H-A-Q | HAC | Pre-AT |  | Completed |  | 2017-08-14 | Eldhose Joy | 2017-08-14 | 2017-08-16 |  | 2 | 2017-08-16 | 2017-08-16 | 2017-08-16 |  | 1 |  |  |  |  | 0 | 3 | 3
4WTF-22 | RFS.22 | M-B-H | BAU | Design | 1 | Completed | Boundary issue identified by LDM and DESG | 2017-08-16 | Revathy | 2017-08-16 | 2017-08-21 | 9 | 4 | 2017-08-21 | 2017-08-22 | 2017-08-22 | 1651 | 2 |  |  |  |  | 0 | 6 | 6
3NAW-64 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-17 |  | 2017-08-17 | 2017-08-17 | 0 | 1 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 856 | 1 |  |  |  |  | 0 | 2 | 2
2SEF-65 | RFS.57 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-17 | Saranya | 2017-08-17 | 2017-08-18 | 0 | 2 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 3162 | 1 |  |  |  |  | 0 | 3 | 3
2BON-67 | RFS.67 | H-A-Q | HAC | Pre-AT | 1 | Completed | 18-Aug-17 : Approval to change SAM type from H-M-H by Project Controls and Network Acceptance. The SAM has been relaunched in Appian as H-A-Q | 2017-08-17 | Arunika | 2017-08-17 | 2017-08-21 | 620 | 3 | 2017-08-21 | 2017-08-21 | 2017-08-21 | 2602 | 1 |  |  |  |  | 0 | 4 | 4
4CPB-20 | RFS.96 | M-B-H | BAU | Design | 1 | Completed | SAM from the previous year. Got missed by the LDM team.Has been delivered based on the mail got from Telstra in HAD mailbox. | 2017-08-17 | Swathy Mohandas | 2017-08-18 | 2017-08-18 | 1654 | 2 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 1730 | 1 |  |  |  |  | 0 | 3 | 3
4EMP-63 | RFS.98 | M-B-H | BAU | Pre-AT | 0.2 | Completed |  | 2017-08-18 | Manjusha M | 2017-08-18 | 2017-08-21 | 0 | 2 | 2017-08-21 | 2017-08-21 | 2017-08-21 | 2978 | 1 |  |  |  |  | 0 | 3 | 3
2STL-64 | RFS.104 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-18 | Jowharulla M | 2017-08-18 | 2017-08-22 | 72 | 3 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 2155 | 1 |  |  |  |  | 0 | 4 | 4
4CUR-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | Completed |  | 2017-08-18 | Reenu | 2017-08-18 | 2017-08-22 | 168 | 3 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 3008 | 1 |  |  |  |  | 0 | 4 | 4
4SRW-62 | RFS.121 | M-M-H | BAU | Design | 1 | Rejected | No action required from LDM, only Area planning will placed the FBR and SAM will be rejected. 25-Aug-17 : On Hold 29:Aug-17 : FBR needs to placed | 2017-08-18 |  | 2017-08-18 | 2017-08-21 | 237 | 2 | 2017-08-21 | 2017-08-21 |  | 3542 | -30669 |  |  |  |  | 0 | -30667 | -30667
5MOD-63 | RFS.63 | M-A-J | BAU | Pre-AT | 6 | Completed | 24-Aug-17 : Valid locations in partial ONSA without PCD and tech choice FTTX . Raised in triage and fixed on 25-Aug-17 24-Aug-17 :Raised issue for valid LocID with Area planning and with LMS for the LocIDs inserted. 28-Aug-17 : Area Planning and LMS issues fixed. | 2017-08-21 | Shilpa | 2017-08-21 | 2017-08-23 | 136 | 3 | 2017-08-23 | 2017-08-28 | 2017-08-28 | 8777 | 4 |  |  |  |  | 0 | 7 | 7
4CPR-62 | RFS.121 | H-M-H | BAU | Design | 1 | ON HOLD | Will be relaunched in APPIAN, after the Design team review. 23-Aug-17 : Decided to be rejected valid SLs outside the bounadry, as it's a early T18 it will be rejected. | 2017-08-21 | Revathy | 2017-08-21 | 2017-08-21 | 178 | 1 | 2017-08-21 | 2017-08-21 |  | 4871 | -30669 |  |  |  |  | 0 | -30668 | -30668
4AAR-63 | RFS.122 | M-M-H | BAU | Design | 1 | ON HOLD | Decided to be rejected due to Design issue, only FBR needs to be placed. 24-Aug-17 : Resub Requested | 2017-08-21 | Tajinder Kaur | 2017-08-21 | 2017-08-21 | 110 | 1 | 2017-08-21 | 2017-08-21 |  | 3442 | -30669 |  |  |  |  | 0 | -30668 | -30668
4MRA-63 | RFS.63 | H-M-H | BAU | Post RFS | 0.1 | Rejected |  | 2017-08-21 | Manjusha | 2017-08-21 | 2017-08-22 | 0 | 2 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 1704 | 1 |  |  |  |  | 0 | 3 | 3
4AGV-64 | RFS.122 | M-M-H | BAU | Design | 1 | Completed |  | 2017-08-21 | George John Panikulam | 2017-08-21 | 2017-08-22 | 33 | 2 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 2383 | 1 |  |  |  |  | 0 | 3 | 3
4MGA-63 | RFS.0 | M-B-H | BAU | Design | 4 | Completed |  | 2017-08-21 | Saranya | 2017-08-21 | 2017-08-23 | 292 | 3 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 4248 | 1 |  |  |  |  | 0 | 4 | 4
4SRW-62 | RFS.121 | M-M-H | BAU | Design | 1 | Rejected | No action required from LDM, only Area planning will placed the FBR and SAM will be rejected. 25-Aug-17 : On Hold 29:Aug-17 : FBR needs to placed | 2017-08-18 | Tajinder Kaur | 2017-08-18 | 2017-08-21 | 237 | 2 | 2017-08-21 | 2017-08-21 |  | 3542 | -30669 |  |  |  |  | 0 | -30667 | -30667
3BOX-65 | RFS.98 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-08-22 | George John Panikulam | 2017-08-22 | 2017-08-24 | 270 | 3 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 4307 | 1 |  |  |  |  | 0 | 4 | 4
6MLO-64 | RFS.99 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-22 | Shambhavi | 2017-08-22 | 2017-08-23 | 19 | 2 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2220 | 1 |  |  |  |  | 0 | 3 | 3
3BLB-65 | RFS.0 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-08-23 | Jowharullah | 2017-08-23 | 2017-08-25 | 57 | 3 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 1602 | 1 |  |  |  |  | 0 | 4 | 4
4BUR-67 | RFS.112 | M-M-H | BAU | Design | 3 | Completed |  | 2017-08-23 | Aleena | 2017-08-23 | 2017-08-25 | 193 | 3 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 3968 | 1 |  |  |  |  | 0 | 4 | 4
2WET-65 | RFS.100 | M-M-H | BAU | Pre-AT | 0.1 | Rejected |  | 2017-08-24 | Goutham | 2017-08-24 | 2017-08-25 | 170 | 2 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 3765 | 0 |  |  |  |  | 0 | 2 | 2
4CPB-20 | RFS.98 | M-B-H | BAU | Pre-AT | 0.1 | Completed | On Hold due to missing artefacts for Design Team. 01-Sep-17 : SAM needs to processed with same payload | 2017-08-24 | Tajinder Kaur | 2017-09-05 | 2017-09-05 | 0 | 7 | 2017-09-05 | 2017-09-05 | 2017-09-05 | 1715 | 0 |  |  |  |  | 0 | 7 | 7
3DNC-61 | RFS.95 | H-A-Q | HAC | Pre-AT | 2 | Completed |  | 2017-08-24 | Arunika Joy | 2017-08-24 | 2017-08-28 | 76 | 3 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 1936 | 1 |  |  |  |  | 0 | 4 | 4
4NDG-60 | RFS.143 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-08-24 | Reenu | 2017-08-24 | 2017-08-28 | 30 | 3 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 3283 | 1 |  |  |  |  | 0 | 4 | 4
4BUR-21 | RFS.94 | M-B-H | BAU | Pre-AT | 0.2 | Completed |  | 2017-08-24 | Aleena | 2017-08-25 | 2017-08-28 | 0 | 3 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 1676 | 1 |  |  |  |  | 0 | 4 | 4
2NSY-60 | RFS.82 | H-M-H | BAU | Post RFS | 0.1 | Rejected |  | 2017-08-25 | Manjusha | 2017-08-25 | 2017-08-29 | 0 | 3 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 1888 | 1 |  |  |  |  | 0 | 4 | 4
4MGA-62 | RFS.80 | M-A-H | BAU | Post RFS | 2 | Completed |  | 2017-08-25 | Reshma | 2017-08-25 | 2017-08-29 | 68 | 3 | 2017-08-29 | 2017-08-31 | 2017-08-31 | 2934 | 3 |  |  |  |  | 0 | 6 | 6
2EPP-65 | RFS.118 | H-M-Q | BAU | Design | 2 | Completed |  | 2017-08-25 | Devika Kala | 2017-08-25 | 2017-08-29 | 337 | 3 | 2017-08-29 | 2017-08-31 | 2017-08-31 | 3914 | 3 |  |  |  |  | 0 | 6 | 6
2CRR-60 | RFS.100 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-08-25 | Reenu | 2017-08-25 | 2017-08-29 | 182 | 3 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 4982 | 1 |  |  |  |  | 0 | 4 | 4
4BUR-69 | RFS.77 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-08-28 | George | 2017-08-28 | 2017-08-30 | 0 | 3 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 1138 | 1 |  |  |  |  | 0 | 4 | 4
3BNT-63 | RFS.96 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-28 | Reenu | 2017-08-28 | 2017-08-29 | 189 | 2 | 2017-08-29 | 2017-08-30 | 2017-09-01 | 4161 | 4 |  |  |  |  | 0 | 6 | 6
4SRW-61 | RFS.103 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-28 | Saranya Geetha | 2017-08-28 | 2017-08-30 | 154 | 3 | 2017-08-30 | 2017-08-31 | 2017-08-31 | 3779 | 2 |  |  |  |  | 0 | 5 | 5
3DAD-67 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-28 | Revathy A | 2017-08-28 | 2017-08-30 | 46 | 3 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2579 | 3 |  |  |  |  | 0 | 6 | 6
4AGV-62 | RFS.118 | M-M-H | BAU | Design | 1 | Completed |  | 2017-08-28 | Shabeena Shamsudin | 2017-08-28 | 2017-08-29 | 25 | 2 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 4310 | 1 |  |  |  |  | 0 | 3 | 3
2BAN-70 | RFS.124 | M-B-H | BAU | Design | 1 | ON HOLD | 31-Aug-17 : Rejected due to critical defects in DESG. | 2017-08-28 | Goutham A S | 2017-08-28 | 2017-08-28 | 229 | 1 | 2017-08-28 | 2017-08-28 |  | 2415 | -30674 |  |  |  |  | 0 | -30673 | -30673
2CRR-66 | RFS.105 | M-M-H | BAU | Design | 3 | Rejected | 31-Aug-17 : Rejected due to critical defects in DESG. | 2017-08-28 | Devika Kala | 2017-08-29 | 2017-08-29 | 214 | 2 | 2017-08-29 | 2017-08-31 |  | 4862 | -30675 |  |  |  |  | 0 | -30673 | -30673
4BLH-62 | RFS.118 | M-B-H | BAU | Design | 1 | Completed |  | 2017-08-28 | Jumana.M | 2017-08-28 | 2017-08-30 | 0 | 3 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 859 | 1 |  |  |  |  | 0 | 4 | 4
4WTF-60 | RFS.122 | M-M-H | BAU | Design | 1 | Completed |  | 2017-08-28 | Jowharulla.M | 2017-08-29 | 2017-08-31 | 272 | 4 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 5578 | 1 |  |  |  |  | 0 | 5 | 5
2BAN-63 | RFS.112 | M-M-H | BAU | Design | 2 | Completed - Handover done | 04-Aug-17 : Waiting AP team to confirm for one location 11-Aug-17 : Awaiting response from Telstra. 18-Aug-17 : Critical Area Planning issues 01-Dec-17 : Resumed in APPIAN. | 2017-08-28 | Swathy Mohandas | 2017-08-29 | 2017-09-01 | 1405 | 5 | 2017-12-01 | 2017-12-05 | 2017-12-05 |  | 3 |  |  |  |  | 0 | 8 | 8
4CPR-62 | RFS.121 | M-M-H | BAU | Design | 2 | ON HOLD | 01-Sep-17 : Rejected due to defects found by DESG, LDM and Area Planning team. | 2017-08-28 | Saiju Xavier | 2017-08-28 | 2017-08-28 | 178 | 1 | 2017-08-28 | 2017-08-28 |  | 4871 | -30674 |  |  |  |  | 0 | -30673 | -30673
4EMP-02 | RFS.99 | M-B-H | BAU | Pre-AT | 0.2 | Rejected | 30-Aug-2017 : Decided to be rejected as FDDD repurposed cases are not incorporated in FAB phase for LDM and as well critical from DESG and AP team. | 2017-08-28 | George | 2017-08-28 | 2017-08-28 | 0 | 1 | 2017-08-28 | 2017-08-28 |  | 2569 | -30674 |  |  |  |  | 0 | -30673 | -30673
2STL-63 | RFS.103 | H-B-Q | HAC | Pre-AT | 0.1 | Completed | 12-Sep-2017: Resent the release mail of BAU as it changed from BAU to HAC but T18 is same | 2017-08-28 | George | 2017-08-29 | 2017-08-30 | 139 | 3 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2206 | 1 |  |  |  |  | 0 | 4 | 4
3RWO-61 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-28 | S Shilpa | 2017-08-28 | 2017-08-30 | 119 | 3 | 2017-08-30 | 2017-08-31 | 2017-08-31 | 2816 | 2 |  |  |  |  | 0 | 5 | 5
3DAD-66 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-28 | Arunika Joy | 2017-08-28 | 2017-08-30 | 158 | 3 | 2017-08-30 | 2017-09-01 | 2017-09-01 | 3364 | 3 |  |  |  |  | 0 | 6 | 6
3DAD-63 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-28 | Sanjana | 2017-08-29 | 2017-09-01 | 187 | 5 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 3111 | 1 |  |  |  |  | 0 | 6 | 6
4CPH-66 | RFS.115 | M-M-H | BAU | Design | 2 | Completed |  | 2017-08-29 | Aleena Johny | 2017-08-29 | 2017-08-31 | 204 | 3 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2688 | 1 |  |  |  |  | 0 | 4 | 4
4AAR-63 | RFS.122 | M-M-H | BAU | Design | 2 | Completed |  | 2017-08-29 | Swathy Mohandas | 2017-08-29 | 2017-08-31 | 110 | 3 | 2017-09-05 | 2017-09-05 | 2017-09-05 | 3442 | 0 |  |  |  |  | 0 | 3 | 3
4APL-60 | RFS.122 | M-M-H | BAU | Design | 2 | ON HOLD | 05-Sep-17 : Rejected due to defects found by DESG, LDM and Area Planning team. | 2017-08-29 | Manjusha M | 2017-08-30 | 2017-09-01 | 106 | 4 | 2017-09-01 | 2017-09-01 |  | 2939 | -30678 |  |  |  |  | 0 | -30674 | -30674
4CPB-60 | RFS.65 | M-M-J | BAU | Post RFS | 0.5 | Rejected | 31-Aug-2017 : Decided to be rejected as IAB repurposed cases are not incorporated in FAB phase. | 2017-08-30 | George | 2017-08-30 | 2017-08-30 | 123 | 1 | 2017-08-30 | 2017-08-30 |  | 2506 | -30676 |  |  |  |  | 0 | -30675 | -30675
6GIR-68 | RFS.118 | M-M-H | BAU | Design | 2 | Completed |  | 2017-08-30 | Saranya Geetha | 2017-08-30 | 2017-08-31 | 23 | 2 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 4634 | 1 |  |  |  |  | 0 | 3 | 3
2STL-61 | RFS.104 | M-M-H | BAU | Design | 4 | Completed |  | 2017-08-30 | Shabeena Shamsudin | 2017-08-30 | 2017-08-31 | 440 | 2 | 2017-09-06 | 2017-09-06 | 2017-09-06 | 3404 | 1 |  |  |  |  | 0 | 3 | 3
5WES-64 | RFS.108 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-30 | Reenu | 2017-08-30 | 2017-09-01 | 482 | 3 | 2017-09-01 | 2017-09-04 | 2017-09-04 | 2168 | 1 |  |  |  |  | 0 | 4 | 4
2MIL-60 | RFS.103 | M-M-H | BAU | Pre-AT | 0.1 | Completed | 04-Sep-17 : Waiting AP team to confirm for one location | 2017-08-31 | Tajinder Kaur | 2017-08-31 | 2017-09-04 | 202 | 2 | 2017-09-04 | 2017-09-05 | 2017-09-05 | 5042 | 0 |  |  |  |  | 0 | 2 | 2
2PYM-60 | RFS.99 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-08-31 | Goutham A S | 2017-08-31 | 2017-09-01 | 75 | 2 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 3142 | 1 |  |  |  |  | 0 | 3 | 3
3SSN-62 | RFS.121 | M-M-H | BAU | Design | 2 | Completed |  | 2017-09-01 | Aleena Johny | 2017-09-01 | 2017-09-06 | 146 | 2 | 2017-09-08 | 2017-09-08 | 2017-09-08 | 3962 | 1 |  |  |  |  | 0 | 3 | 3
3WER-65 | RFS.99 | M-A-H | BAU | Pre-AT | 1 | Completed | Same payload received again need confirmation. 04-Sep-17 : Already delivered in march.As per Nathan English mail task has been completed. | 2017-09-01 | Tajinder Kaur | 2017-09-01 | 2017-09-01 | 29 | 1 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2918 | 1 |  |  |  |  | 0 | 2 | 2
4MGB-62 | RFS.99 | M-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-09-01 | Swathy Mohandas | 2017-09-05 | 2017-09-05 | 94 | 1 | 2017-09-05 | 2017-09-05 | 2017-09-05 | 1673 | 0 |  |  |  |  | 0 | 1 | 1
3GLI-62 | RFS.100 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-09-01 | Reenu | 2017-09-06 | 2017-09-07 | 228 | 3 | 2017-09-07 | 2017-09-07 | 2017-09-07 | 3361 | 1 |  |  |  |  | 0 | 4 | 4
4EMP-61 | RFS.75 | M-M-H | BAU | Post RFS | 0.2 | Completed |  | 2017-09-01 | George | 2017-09-01 | 2017-09-06 | 0 | 2 | 2017-09-06 | 2017-09-06 | 2017-09-06 | 1497 | 1 |  |  |  |  | 0 | 3 | 3
3KYG-64 | RFS.100 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-09-01 | Anet | 2017-09-06 | 2017-09-11 | 501 | 5 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 5217 | 1 |  |  |  |  | 0 | 6 | 6
6GIR-22 | RFS.0 | M-B-H | BAU | Design | 1 | Completed |  | 2017-09-01 | Devika | 2017-09-11 | 2017-09-12 | 47 | 6 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 3457 | 1 |  |  |  |  | 0 | 7 | 7
5WES-63 | RFS.108 | M-M-H | BAU | Pre-AT | 0.1 | Rejected | 08-Sep-17 : On Hold due to Design critical defects 28-Sep-17 : Rejected due to Design issues | 2017-09-01 | Saranya/Reenu | 2017-09-06 | 2017-09-06 | 104 | 2 | 2017-09-06 | 2017-09-28 |  | 3250 | -30679 |  |  |  |  | 0 | -30677 | -30677
4CUR-60 | RFS.126 | M-M-H | BAU | Design | 1 | Completed | 07-Sep-17 : On hold due to missing artefacts for Design Team. 13-Sep-17: Relaunched in APPIAN 20-Sep-17: Awaiting AP response for 3 locations | 2017-09-01 | Manjusha M | 2017-09-13 | 2017-09-19 | 398 | 11 | 2017-09-19 | 2017-09-22 | 2017-09-22 | 3821 | 4 |  |  |  |  | 0 | 15 | 15
2FRE-62 | RFS.102 | M-M-H | BAU | Design | 1 | ON HOLD | 08-Sep-17 : On Hold due to Design and DESG critical defects | 2017-09-01 | Jowhar | 2017-09-06 | 2017-09-08 | 135 | 4 | 2017-09-08 | 2017-09-08 |  | 1109 | -30681 |  |  |  |  | 0 | -30677 | -30677
2PEN-66 | RFS.99 | H-A-Q | HAC | Pre-AT | 1 | Completed | 20-Sep-17: Awaiting AP response for 3 locations | 2017-09-01 | Revathy A | 2017-09-01 | 2017-09-04 | 86 | 1 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2491 | 0 |  |  |  |  | 0 | 1 | 1
3BOX-61 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-01 | Saranya Geetha | 2017-09-01 | 2017-09-05 |  | 1 | 2017-09-05 | 2017-09-05 | 2017-09-05 |  | 0 |  |  |  |  | 0 | 1 | 1
3SSN-66 | RFS.99 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-09-01 | Sanjana | 2017-09-06 | 2017-09-06 | 94 | 2 | 2017-09-06 | 2017-09-12 | 2017-09-12 | 4669 | 5 |  |  |  |  | 0 | 7 | 7
6GIR-21 | RFS.0 | M-B-H | BAU | Design | 1 | Completed |  | 2017-09-04 | Arunika | 2017-09-08 | 2017-09-12 | 22 | 5 | 2017-09-12 | 2017-09-13 | 2017-09-13 | 3892 | 2 |  |  |  |  | 0 | 7 | 7
6JDL-21 | RFS.78 | M-M-J | BAU | Post RFS | 0.3 | Rejected | 08-Sep-17: Waiting for NA to provide the decision 26-Sep-17 : Critical issues identified by LDM and Area planning. | 2017-09-04 | Devika | 2017-09-07 |  | 176 | -30678 |  |  |  | 2656 | 0 |  |  |  |  | 0 | -30678 | -30678
3WHL-65 | RFS.63 | M-A-J | BAU | Post RFS | 0.2 | Rejected | 08-Sep-17: Crritical defect raised by Area Planning and LDM teams | 2017-09-04 |  | 2017-09-04 | 2017-09-07 | 89 | 2 | 2017-09-07 | 2017-09-07 |  | 3488 | -30680 |  |  |  |  | 0 | -30678 | -30678
4ASH-66 | RFS.70 | M-M-J | BAU | Post RFS | 0.3 | Rejected | 08-Sep-17: Waiting for NA to provide the decision 26-Sep-17 : Critical issues identified by LDM and Design. | 2017-09-04 | Saiju | 2017-09-07 | 2017-09-07 | 22 | 2 | 2017-09-07 | 2017-09-07 |  | 4682 | -30680 |  |  |  |  | 0 | -30678 | -30678
3HGT-60 | RFS.63 | M-A-J | BAU | Post RFS | 1 | Rejected | 06-Sep-17: On Hold to reluanch with correct payload | 2017-09-04 |  | 2017-09-04 | 2017-09-07 | 133 | 2 | 2017-09-07 | 2017-09-07 |  | 3918 | -30680 |  |  |  |  | 0 | -30678 | -30678
5FLN-62 | RFS.99 | H-M-J | BAU | Post RFS | 1.5 | Rejected | 06-Sep-17 : Rejected due to Design And LDM team issues | 2017-09-04 |  | 2017-09-04 | 2017-09-07 | 0 | 2 | 2017-09-07 | 2017-09-07 |  | 3546 | -30680 |  |  |  |  | 0 | -30678 | -30678
2CRR-20 | RFS.101 | M-B-H | BAU | Pre-AT | 1.1 | Completed |  | 2017-09-04 | George | 2017-09-06 | 2017-09-07 | 0 | 2 | 2017-09-07 | 2017-09-07 | 2017-09-07 | 1154 | 1 |  |  |  |  | 0 | 3 | 3
2PET-71 | RFS.118 | M-M-H | BAU | Design | 1 | Completed | 13-Sep-17 : Awaiting AP response and Telstra input. | 2017-09-04 | Saranya | 2017-09-08 | 2017-09-12 | 115 | 5 | 2017-09-12 | 2017-09-20 | 2017-09-20 | 2940 | 7 |  |  |  |  | 0 | 12 | 12
4BUR-61 | RFS.77 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-09-04 | Manjusha | 2017-09-07 | 2017-09-11 | 0 | 4 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2275 | 1 |  |  |  |  | 0 | 5 | 5
6GIR-64 | RFS.115 | M-M-H | BAU | Design | 1 | Completed |  | 2017-09-04 | Sanjana | 2017-09-08 | 2017-09-12 | 114 | 5 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 3039 | 1 |  |  |  |  | 0 | 6 | 6
6CTO-20 | RFS.121 | M-M-H | BAU | Design | 1 | Rejected | 13-Sep-17 : Awaiting AP response. | 2017-09-04 |  | 2017-09-11 | 2017-09-15 | 197 | 8 | 2017-09-15 | 2017-09-15 | 2017-09-15 | 2165 | 1 |  |  |  |  | 0 | 9 | 9
2PEN-62 | RFS.100 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-05 | Eldhose Joy | 2017-09-06 | 2017-09-07 |  | 2 | 2017-09-07 | 2017-09-08 | 2017-09-08 |  | 2 |  |  |  |  | 0 | 4 | 4
5GLL-61 | RFS.101 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-05 | Revathy | 2017-09-06 | 2017-09-08 | 214 | 3 | 2017-09-08 | 2017-09-08 | 2017-09-08 | 2949 | 1 |  |  |  |  | 0 | 4 | 4
4AAR-64 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 | Rejected | 06-Sep-17: Rejected due to Design and LDM issues | 2017-09-05 |  | 2017-09-05 | 2017-09-07 | 0 | 2 | 2017-09-07 | 2017-09-07 |  | 1376 | -30680 |  |  |  |  | 0 | -30678 | -30678
2BAN-61 | RFS.113 | H-M-H | BAU | Design | 3 | Completed | 13-Sep-17 : Awaiting AP response. | 2017-09-05 | Manjusha M | 2017-09-07 | 2017-09-13 | 1873 | 6 | 2017-09-15 | 2017-09-15 | 2017-09-15 | 5722 | 1 |  |  |  |  | 0 | 7 | 7
4BUR-60 | RFS.103 | M-A-Q | HAC | Pre-AT | 2 | Completed |  | 2017-09-05 | George | 2017-09-06 | 2017-09-08 | 489 | 3 | 2017-09-08 | 2017-09-08 | 2017-09-08 | 4813 | 1 |  |  |  |  | 0 | 4 | 4
2LIV-63 | RFS.118 | M-M-H | BAU | Design | 1 | Rejected |  | 2017-09-05 | George | 2017-09-07 | 2017-09-11 | 405 | 4 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 3454 | 1 |  |  |  |  | 0 | 5 | 5
2CAS-66 | RFS.118 | M-M-H | BAU | Design | 1 | Completed |  | 2017-09-05 | Saiju Xavier | 2017-09-08 | 2017-09-13 | 151 | 6 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 3834 | 1 |  |  |  |  | 0 | 7 | 7
4MGB-20 | RFS.100 | M-B-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-09-06 | Saranya | 2017-09-06 | 2017-09-06 | 0 | 1 | 2017-09-06 | 2017-09-06 | 2017-09-06 | 1346 | 1 |  |  |  |  | 0 | 2 | 2
2SEF-61 | RFS.80 | M-M-H | BAU | Post RFS | 1.1 | Rejected | 11-Sep-17: 7 locations outside SAM boundary, Awaiting confirmatio from AP team 22-Jan: Awaiting documentation from Telstra from september, as there was no response it is rejected officially now. | 2017-09-06 | Shabeena Shamsudin | 2017-09-07 | 2017-09-13 | 0 | 6 | 2017-09-13 | 2017-09-13 | 2017-09-13 | 3027 | 1 | 2018-01-22 |  |  |  | 0 | 7 | 7
4AAR-61 | RFS.103 | M-A-H | BAU | Pre-AT | 1 | Rejected |  | 2017-09-07 | Revathy | 2017-09-07 | 2017-09-08 | 94 | 2 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 4476 | 1 |  |  |  |  | 0 | 3 | 3
4ASH-61 | RFS.100 | M-B-H | BAU | Pre-AT | 1 | Rejected | 12-Sep-17: Critical Issue identified by Design Team | 2017-09-07 | Shilpa | 2017-09-07 | 2017-09-07 | 0 | 1 | 2017-09-07 | 2017-09-07 |  | 1651 | -30680 |  |  |  |  | 0 | -30679 | -30679
3CTA-67 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-09-07 | Aleena | 2017-09-07 | 2017-09-11 | 0 | 3 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 1140 | 1 |  |  |  |  | 0 | 4 | 4
2BAN-70 | RFS.124 | M-B-H | BAU | Design | 2 | Completed |  | 2017-09-07 | Shilpa | 2017-09-11 | 2017-09-13 | 229 | 5 | 2017-09-13 | 2017-09-13 | 2017-09-13 | 2414 | 1 |  |  |  |  | 0 | 6 | 6
5WES-61 | RFS.108 | M-M-H | BAU | Pre-AT | 0.2 | Rejected | 12-Sep-17: Waiting for Telstra Input 15-Sep-2017: Critical defects identified by Design team | 2017-09-07 | Reenu Treesa Peter | 2017-09-07 | 2017-09-11 | 136 | 3 | 2017-09-11 | 2017-09-11 |  | 3547 | -30682 |  |  |  |  | 0 | -30679 | -30679
4ASH-63 | RFS.134 | H-M-H | BAU | Pre-AT | 0.1 | Completed |  | 2017-09-07 | Devika | 2017-09-08 | 2017-09-08 | 151 | 2 | 2017-09-08 | 2017-09-08 | 2017-09-08 | 4009 | 1 |  |  |  |  | 0 | 3 | 3
4CPR-62 | RFS.121 | M-M-H | BAU | Design | 3 | Completed |  | 2017-09-08 | Shabeena Shamsudin | 2017-09-08 | 2017-09-12 | 178 | 3 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 4864 | 1 |  |  |  |  | 0 | 4 | 4
2SEV-61 | RFS.106 | M-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-09-08 | Jowharullah | 2017-09-08 | 2017-09-11 | 132 | 2 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2285 | 1 |  |  |  |  | 0 | 3 | 3
2WET-61 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-09-08 | Goutham | 2017-09-08 | 2017-09-11 | 0 | 2 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 1141 | 1 |  |  |  |  | 0 | 3 | 3
3NCO-66 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-05 | Reenu | 2017-09-06 | 2017-09-08 | 381 | 3 | 2017-09-08 | 2017-09-08 | 2017-09-08 | 3749 | 1 |  |  |  |  | 0 | 4 | 4
3CAU-60 | RFS.101 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-08 | Aleena | 2017-09-08 | 2017-09-12 | 93 | 3 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 1925 | 1 |  |  |  |  | 0 | 4 | 4
4CPR-61 | RFS.101 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-08 | Reenu | 2017-09-08 | 2017-09-11 |  | 2 | 2017-09-11 | 2017-09-12 | 2017-09-12 |  | 2 |  |  |  |  | 0 | 4 | 4
2PYM-63 | RFS.125 | M-M-H | BAU | Design | 1 | Completed |  | 2017-09-11 | Jumana | 2017-09-11 | 2017-09-13 | 179 | 3 | 2017-09-13 | 2017-09-14 | 2017-09-14 | 3946 | 2 |  |  |  |  | 0 | 5 | 5
2LIV-67 | RFS.117 | M-M-H | BAU | Design | 2 | Completed |  | 2017-09-12 | Saranya | 2017-09-13 | 2017-09-15 | 120 | 4 | 2017-09-15 | 2017-09-15 | 2017-09-15 | 2598 | 1 |  |  |  |  | 0 | 5 | 5
4AGV-20 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | Completed | 13-Sep-2017: Awaiting AP response | 2017-09-12 | Reenu | 2017-09-12 | 2017-09-14 | 98 | 3 | 2017-09-15 | 2017-09-15 | 2017-09-15 | 3762 | 1 |  |  |  |  | 0 | 4 | 4
2FRE-60 | RFS.126 | M-M-H | BAU | Design | 1 | Completed |  | 2017-09-12 | Sanjana | 2017-09-13 | 2017-09-15 | 49 | 4 | 2017-09-15 | 2017-09-15 | 2017-09-15 | 2785 | 1 |  |  |  |  | 0 | 5 | 5
4SUR-62 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-09-12 | Jowhar | 2017-09-12 | 2017-09-14 | 103 | 3 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 3422 | 1 |  |  |  |  | 0 | 4 | 4
3TNI-64 | RFS.103 | M-A-H | BAU | Pre-AT | 1 | Completed | 14-Sep-2017: Awaiting AP response | 2017-09-12 | Goutham | 2017-09-12 | 2017-09-14 | 47 | 3 | 2017-09-18 | 2017-09-18 | 2017-09-18 |  | 1 |  |  |  |  | 0 | 4 | 4
3MLN-65 | RFS.100 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-12 | Arunika | 2017-09-12 | 2017-09-15 |  | 4 | 2017-09-15 | 2017-09-15 | 2017-09-15 |  | 1 |  |  |  |  | 0 | 5 | 5
4MGA-70 | RFS.101 | H-A-Q | HAC | Pre-AT | 1 | Completed | 13-Sep-2017: The same T18 which we processed as BAU | 2017-09-13 | Goutham | 2017-09-13 | 2017-09-15 |  | 3 | 2017-09-15 | 2017-09-15 | 2017-09-15 |  | 1 |  |  |  |  | 0 | 4 | 4
4MGA-72 | RFS.101 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-13 | Anet | 2017-09-13 | 2017-09-13 | 17 | 1 | 2017-09-13 | 2017-09-14 | 2017-09-14 | 1154 | 2 |  |  |  |  | 0 | 3 | 3
3HGT-66 | RFS.66 | H-A-H | BAU | Post RFS | 0.2 | Completed |  | 2017-09-13 | Shabeena Shamsudin | 2017-09-13 | 2017-09-14 | 0 | 2 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 666 | 1 |  |  |  |  | 0 | 3 | 3
4SLA-64 | RFS.104 | M-M-H | BAU | Design | 2 | Rejected | 15-Sep-2017: Critical Issue identified by Design team | 2017-09-13 | Aleena | 2017-09-13 | 2017-09-13 | 606 | 1 | 2017-09-13 | 2017-09-13 |  | 3301 | -30684 | 2018-09-18 |  |  |  | 0 | -30683 | -30683
5WES-65 | RFS.108 | H-M-H | BAU | Design | 3 | Rejected | 13-Sep-17 : Awaiting AP response. 18-Sep-17 : Issues raised by Area Planning. | 2017-09-13 | Devika | 2017-09-13 | 2017-09-15 | 252 | 3 | 2017-09-15 | 2017-09-18 |  | 4856 | -30686 |  |  |  |  | 0 | -30683 | -30683
2ASH-66 | RFS.118 | M-M-H | BAU | Design | 1 | Completed | 20-Sep-17: 2 locations outside SAM boundary, Awaiting AP response. 26-Sep-17: Area Planning provided input. | 2017-09-13 | Saiju Xavier | 2017-09-14 | 2017-09-19 | 461 | 5 | 2017-09-20 | 2017-09-28 | 2017-09-28 | 3432 | 7 |  |  |  |  | 0 | 12 | 12
2PET-66 | RFS.123 | M-M-H | BAU | Design | 1 | Rejected | 13-Sep-17 : Awaiting Telstra Input. 25-Sep-17 : Rejected due to LDM issue B[24] and B[26] and Design issues. | 2017-09-13 | Shabeena Shamsudin | 2017-09-14 | 2017-09-18 | 170 | 4 |  | 2017-09-26 |  | 4479 | 0 | 2017-09-25 |  |  |  | 0 | 4 | 4
2CAS-66 | RFS.101 | M-A-H | BAU | Pre-AT | 1 | Completed | 15-Sep-17 : SAM phase changed from Design to Pre-AT. Relaunched in APPIAN as Pre-AT with same T18 payload | 2017-09-15 | Saiju Xavier | 2017-09-15 | 2017-09-15 | 151 | 1 | 2017-09-15 | 2017-09-15 | 2017-09-15 | 3834 | 1 |  |  |  |  | 0 | 2 | 2
3CAU-61 | RFS.78 | H-A-H | BAU | Post RFS | 0.1 | Completed |  | 2017-09-15 | Reenu Treesa Peter | 2017-09-15 | 2017-09-18 | 0 | 2 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 312 | 1 |  |  |  |  | 0 | 3 | 3
5GLL-62 | RFS.125 | M-M-H | BAU | Design | 1 | Completed |  | 2017-09-15 | Jowharulla.M | 2017-09-18 | 2017-09-20 | 340 | 4 | 2017-09-20 | 2017-09-21 | 2017-09-21 | 2873 | 2 |  |  |  |  | 0 | 6 | 6
2WET-65 | RFS.100 | M-M-H | BAU | Pre-AT | 0.2 | Completed |  | 2017-09-18 |  | 2017-09-18 | 2017-09-19 | 170 | 2 | 2017-09-19 | 2017-09-20 | 2017-09-20 | 3765 | 2 |  |  |  |  | 0 | 4 | 4
4CPR-65 | RFS.105 | M-A-H | BAU | Pre-AT | 1 | Completed | 19-Sep-17 : 1 location is outside SAM boundary. Awaiting confirmation from AP team 22-Sep-17: Area Planning provided inputs | 2017-09-18 | Saranya Geetha | 2017-09-18 | 2017-09-22 | 54 | 5 | 2017-09-22 | 2017-09-22 | 2017-09-22 | 3298 | 1 |  |  |  |  | 0 | 6 | 6
4AGV-64 | RFS.122 | M-M-H | BAU | Design | 3 | Completed |  | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | 36 | 1 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2386 | 1 |  |  |  |  | 0 | 2 | 2
4CPR-62 | RFS.121 | M-A-H | BAU | Pre-AT | 4 | Completed |  | 2017-09-18 | George | 2017-09-18 | 2017-09-20 | 178 | 3 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 4852 | 1 |  |  |  |  | 0 | 4 | 4
4CHL-68 | RFS.143 | M-M-H | BAU | Design | 2 | Completed |  | 2017-09-18 | Arunika Joy | 2017-09-18 | 2017-09-20 | 98 | 3 | 2017-09-20 | 2017-09-22 | 2017-09-22 | 4251 | 3 |  |  |  |  | 0 | 6 | 6
2PYM-62 | RFS.124 | M-M-H | BAU | Design | 2 | Completed |  | 2017-09-18 | Goutham A S | 2017-09-18 | 2017-09-20 | 178 | 3 | 2017-09-21 | 2017-09-21 | 2017-09-21 | 4555 | 1 |  |  |  |  | 0 | 4 | 4
4APL-60 | RFS.122 | M-M-H | BAU | Design | 3 | Rejected | 19-Sep-17 : On Hold Design Review in progress 28-Sep-17 : Rejected due to Design and LDM issues | 2017-09-18 | ShabeenaShamsudin | 2017-09-19 | 2017-09-28 | 225 | 9 |  | 2017-09-28 |  | 3058 | 0 |  |  |  |  | 0 | 9 | 9
2CAS-65 | RFS.124 | M-M-H | BAU | Design | 1 | Completed |  | 2017-09-19 | Shabeena Shamsudin | 2017-09-19 | 2017-09-20 | 15 | 2 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 684 | 1 |  |  |  |  | 0 | 3 | 3
4ABC-63 | RFS.121 | M-M-H | BAU | Design | 1 | Completed | 20-Sep-17 : Boundary mismatch issue.Awaiting response from AP team 21-Sep-17 : Rejected due to critical Area Planning issues. 25-Sep-17: Relaunched in Appian | 2017-09-19 | Reenu Treesa Peter | 2017-09-19 | 2017-09-25 | 6 | 5 | 2017-09-25 | 2017-09-25 | 2017-09-25 | 2039 | 1 |  |  |  |  | 0 | 6 | 6
4IAL-64 | RFS.122 | M-M-H | BAU | Design | 1 | Completed | 19-Sep-17 : 1 location is outside SAM boundary. Awaiting confirmation from AP team | 2017-09-19 | Aleena Johny | 2017-09-19 | 2017-09-21 | 41 | 3 | 2017-09-21 | 2017-09-21 | 2017-09-21 | 2025 | 1 |  |  |  |  | 0 | 4 | 4
4SUR-60 | RFS.128 | M-B-H | BAU | Design | 2 | Completed |  | 2017-09-19 |  | 2017-09-19 | 2017-09-22 | 382 | 4 | 2017-09-22 | 2017-09-22 | 2017-09-22 | 2861 | 1 |  |  |  |  | 0 | 5 | 5
2HLS-61 | RFS.118 | M-M-H | BAU | Design | 2 | Completed | 21-Sep-17: Awaiting response from Area Planning | 2017-09-19 | Manjusha M | 2017-09-19 | 2017-09-21 | 8 | 3 | 2017-09-21 | 2017-09-25 | 2017-09-25 | 2680 | 3 |  |  |  |  | 0 | 6 | 6
2HLS-60 | RFS.124 | M-M-H | BAU | Design | 1 | Completed |  | 2017-09-19 | Revathy A | 2017-09-19 | 2017-09-21 | 104 | 3 | 2017-09-21 | 2017-09-21 | 2017-09-21 | 3251 | 1 |  |  |  |  | 0 | 4 | 4
3OAK-60 | RFS.99 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-09-19 |  | 2017-09-20 | 2017-09-22 | 219 | 4 | 2017-09-22 | 2017-09-22 | 2017-09-22 | 3720 | 1 |  |  |  |  | 0 | 5 | 5
3DAN-61 | RFS.49 | M-A-H | BAU | Post RFS | 1 | Rejected | 26-Sep-17 : Critical issues identified by Design | 2017-09-20 | George | 2017-09-20 | 2017-09-20 | 0 | 1 | 2017-09-21 | 2017-09-21 | 2017-09-21 | 3865 | 1 |  |  |  |  | 0 | 2 | 2
3CTA-61 | RFS.64 | M-A-H | BAU | Post RFS | 0.1 | Completed | 26-Sep-17 : Critical issues identified by Design 29-Sep-17 : Relaunched in appian as feedback placed by design was invalid | 2017-09-20 | Jowharulla.M | 2017-09-21 | 2017-10-04 | 0 | 9 | 2017-10-04 | 2017-10-04 | 2017-10-04 | 2019 | 1 |  |  |  |  | 0 | 10 | 10
3BOX-64 | RFS.100 | H-A-Q | HAC | Pre-AT | 1 | Completed | 20-Sep-17: Awaiting response from Area Planning | 2017-09-20 | Reenu Treesa Peter | 2017-09-20 | 2017-09-28 |  | 7 | 2017-09-28 | 2017-09-28 | 2017-09-28 |  | 1 |  |  |  |  | 0 | 8 | 8
5BRI-61 | RFS.104 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-09-21 | ShabeenaShamsudin | 2017-09-21 | 2017-09-25 |  | 3 | 2017-09-25 | 2017-09-25 | 2017-09-25 |  | 1 |  |  |  |  | 0 | 4 | 4
4BNP-64 | RFS.115 | M-M-H | BAU | Design | 2 | Completed | 26-Sep-17: Awaiting response from Telstra | 2017-09-21 | Arunika Joy | 2017-09-21 | 2017-09-25 | 75 | 3 | 2017-09-25 | 2017-09-27 | 2017-09-27 | 2750 | 3 |  |  |  |  | 0 | 6 | 6
4MGB-01 | RFS.102 | M-B-H | BAU | Pre-AT | 1 | Rejected |  | 2017-09-21 | Goutham A S | 2017-09-21 | 2017-09-25 | 0 | 3 | 2017-09-25 | 2017-09-25 | 2017-09-25 | 1048 | 1 |  |  |  |  | 0 | 4 | 4
2FRE-64 | RFS.106 | M-B-H | BAU | Design | 2 | Completed - Handover to LMS | 22-Sep-17: Awaiting inputs from Area Planning | 2017-09-22 | George | 2017-09-22 | 2017-09-22 | 1 | 1 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 724 | 1 |  |  |  |  | 0 | 2 | 2
6SUB-66 | RFS.113 | M-M-H | BAU | Design | 2 | Completed - Handover to LMS | 9-Oct-17: Rejected due to critical raised by Design | 2017-09-22 | SanjanaKrishnan | 2017-09-25 | 2017-09-26 | 48 | 3 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2454 | 1 |  |  |  |  | 0 | 4 | 4
4ABC-60 | RFS.113 | H-A-Q | HAC | Pre-AT | 2 | Completed - Handover to LMS |  | 2017-09-20 | Saiju Xavier | 2017-09-20 | 2017-09-22 |  | 3 | 2017-09-22 | 2017-09-22 | 2017-09-22 |  | 1 |  |  |  |  | 0 | 4 | 4
4SRW-64 | RFS.105 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-22 | Manjusha M | 2017-09-22 | 2017-09-26 |  | 3 | 2017-09-26 | 2017-09-27 | 2017-09-27 |  | 2 |  |  |  |  | 0 | 5 | 5
4CUR-61 | RFS.120 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-25 | Saranya Geetha | 2017-09-25 | 2017-09-27 | 349 | 3 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 3813 | 1 |  |  |  |  | 0 | 4 | 4
3TYH-60 | RFS.101 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-25 | Goutham A S | 2017-09-26 | 2017-09-28 |  | 4 | 2017-09-28 | 2017-09-28 | 2017-09-28 |  | 1 |  |  |  |  | 0 | 5 | 5
2PEN-60 | RFS.101 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS | 28-Sep-17: Awaiting inputs from Area Planning | 2017-09-25 | George | 2017-09-26 | 2017-09-29 |  | 4 | 2017-09-29 | 2017-09-29 | 2017-09-29 |  | 0 |  |  |  |  | 0 | 4 | 4
3CLA-66 | RFS.101 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS | 28-Sep-17: Awaiting inputs from Area Planning | 2017-09-25 | Devika Kala | 2017-09-26 | 2017-10-03 |  | 5 | 2017-10-03 | 2017-10-03 | 2017-10-03 |  | 1 |  |  |  |  | 0 | 6 | 6
5GLL-65 | RFS.102 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-25 | Jumana.M | 2017-09-26 | 2017-09-29 |  | 4 | 2017-10-03 | 2017-10-03 | 2017-10-03 |  | 1 |  |  |  |  | 0 | 5 | 5
4WTF-63 | RFS.102 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-25 | Reenu Treesa Peter | 2017-09-26 | 2017-09-28 |  | 4 | 2017-09-28 | 2017-09-28 | 2017-09-28 |  | 1 |  |  |  |  | 0 | 5 | 5
4AAR-62 | RFS.103 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-25 | S Shilpa | 2017-09-26 | 2017-09-28 |  | 4 | 2017-09-28 | 2017-09-29 | 2017-09-29 |  | 1 |  |  |  |  | 0 | 5 | 5
3BNT-66 | RFS.106 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-25 | Jowharulla.M | 2017-09-26 | 2017-09-28 |  | 4 | 2017-09-28 | 2017-09-28 | 2017-09-28 |  | 1 |  |  |  |  | 0 | 5 | 5
2ROS-67 | RFS.135 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-25 | ChristieThomas | 2017-09-26 | 2017-09-28 |  | 4 | 2017-09-28 | 2017-09-28 | 2017-09-28 |  | 1 |  |  |  |  | 0 | 5 | 5
6GIR-21 | RFS.150 | M-M-H | BAU | Design | 2 | Completed - Handover to LMS |  | 2017-09-26 | Manjusha M | 2017-09-26 | 2017-09-27 | 22 | 2 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 3840 | 1 |  |  |  |  | 0 | 3 | 3
3CAU-65 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover to LMS |  | 2017-09-27 | SanjanaKrishnan | 2017-09-27 | 2017-09-28 | 0 | 2 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 890 | 1 |  |  |  |  | 0 | 3 | 3
6GIR-20 | RFS.151 | M-M-H | BAU | Design | 1 | Completed - Handover to LMS |  | 2017-09-27 | Arunika Joy | 2017-09-27 | 2017-09-29 | 31 | 2 | 2017-09-29 | 2017-09-29 | 2017-09-29 | 2087 | 0 |  |  |  |  | 0 | 2 | 2
2ING-65 | RFS.131 | M-M-H | BAU | Design | 1 | Rejected |  | 2017-09-27 | Saranya Geetha | 2017-09-28 | 2017-09-29 | 42 | 2 | 2017-09-29 | 2017-09-29 | 2017-09-29 | 2304 | 0 |  |  |  |  | 0 | 2 | 2
5BRI-63 | RFS.104 | M-A-H | BAU | Pre-AT |  | Completed - Handover to LMS |  | 2017-09-25 | Devika Kala | 2017-09-27 | 2017-10-04 |  | 6 | 2017-10-04 | 2017-10-04 | 2017-10-04 |  | 1 |  |  |  |  | 0 | 7 | 7
4WTF-61 | RFS.106 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-28 | Revathy A | 2017-09-28 | 2017-10-04 | 156 | 3 | 2017-10-04 | 2017-10-04 | 2017-10-04 | 4968 | 1 |  |  |  |  | 0 | 4 | 4
4SRW-60 | RFS.105 | M-M-H | BAU | Design | 1 | Rejected | 23-Nov: Rejecting due to FTTX concern. | 2017-09-28 | SanjanaKrishnan | 2017-09-28 | 2017-10-03 | 228 | 2 | 2017-10-04 | 2017-10-04 | 2017-10-04 | 4703 | 1 | 2017-11-23 |  |  |  | 0 | 3 | 3
4ORM-60 | RFS.109 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-29 | ChristieThomas | 2017-09-29 | 2017-10-06 | 58 | 4 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 877 | 1 |  |  |  |  | 0 | 5 | 5
3CAU-63 | RFS.105 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-29 | JadeeraKT | 2017-09-29 | 2017-10-04 | 140 | 2 | 2017-10-04 | 2017-10-04 | 2017-10-04 | 2095 | 1 |  |  |  |  | 0 | 3 | 3
3NBA-67 | RFS.104 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-29 | Goutham A S | 2017-09-29 | 2017-10-03 | 34 | 1 | 2017-10-04 | 2017-10-04 | 2017-10-04 | 802 | 1 |  |  |  |  | 0 | 2 | 2
2STL-60 | RFS.104 | H-A-Q | HAC | Pre-AT | 3 | Completed - Handover to LMS |  | 2017-09-29 | Jowharulla.M | 2017-09-29 | 2017-10-05 | 235 | 3 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2671 | 1 |  |  |  |  | 0 | 4 | 4
4BUR-66 | RFS.87 | M-M-H | BAU | Post RFS | 1 | Completed - Handover to LMS |  | 2017-09-29 | Reenu Treesa Peter | 2017-09-29 | 2017-10-03 | 0 | 1 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 380 | 1 |  |  |  |  | 0 | 2 | 2
4BUR-68 | RFS.91 | H-M-Q | BAU | Post RFS | 1 | Completed - Handover to LMS |  | 2017-09-29 | ShabeenaShamsudin | 2017-09-29 | 2017-10-03 | 0 | 1 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 1872 | 1 |  |  |  |  | 0 | 2 | 2
2ING-61 | RFS.63 | H-A-H | BAU | Post RFS | 1 | Rejected |  | 2017-09-29 | S Shilpa | 2017-09-29 | 2017-10-03 | 0 | 1 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 3550 | 1 |  |  |  |  | 0 | 2 | 2
2PNN-67 | RFS.76 | H-A-H | BAU | Post RFS | 1 | Rejected |  | 2017-09-29 | Arunika Joy | 2017-09-29 | 2017-10-03 | 0 | 1 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 655 | 1 |  |  |  |  | 0 | 2 | 2
3TNI-63 | RFS.103 | M-A-Q | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-29 | Manjusha M | 2017-10-03 | 2017-10-04 | 50 | 2 | 2017-10-04 | 2017-10-04 | 2017-10-04 | 2322 | 1 |  |  |  |  | 0 | 3 | 3
4EMP-25 | RFS.103 | M-B-H | BAU | Pre-AT | 1 | Rejected to Telstra | 5-Oct-17: Rejected due to the critical issues raised by AP & Design | 2017-10-02 | Saranya Geetha | 2017-10-03 | 2017-10-05 | 0 | 3 |  |  |  | 519 | 0 |  |  |  |  | 0 | 3 | 3
2CRR-71 | RFS.58 | H-A-H | BAU | Post RFS | 1 | Completed - Handover to LMS |  | 2017-10-03 | Reenu Treesa Peter | 2017-10-04 | 2017-10-09 | 0 | 5 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 3455 | 1 |  |  |  |  | 0 | 6 | 6
3TYH-61 | RFS.118 | M-M-H | BAU | Design | 1 | Rejected to Telstra | 9-Oct-17: Rejected due to critical raised by Design | 2017-10-03 | George | 2017-10-03 | 2017-10-09 | 592 | 5 |  |  |  | 4533 | 0 |  |  |  |  | 0 | 5 | 5
3DRP-62 | RFS.63 | H-A-H | BAU | Post RFS | 1 | Completed - Handover to LMS |  | 2017-10-03 | ShabeenaShamsudin | 2017-10-03 | 2017-10-05 | 0 | 3 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 1561 | 1 |  |  |  |  | 0 | 4 | 4
4MRA-63 | RFS.78 | H-M-H | BAU | Post RFS | 0.2 | Completed - Handover to LMS |  | 2017-10-03 | Devika Kala | 2017-10-03 | 2017-10-05 | 0 | 3 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 1704 | 1 |  |  |  |  | 0 | 4 | 4
6WMB-63 | RFS.120 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-10-03 | Saranya Geetha | 2017-10-05 | 2017-10-09 | 116 | 5 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 3115 | 1 |  |  |  |  | 0 | 6 | 6
2MIL-63 | RFS.103 | M-M-H | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-10-03 | Reenu Treesa Peter | 2017-10-04 | 2017-10-05 | 0 | 3 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 1137 | 1 |  |  |  |  | 0 | 4 | 4
2LIV-60 | RFS.130 | M-M-H(P) | BAU | Design | 1 | Completed - Handover done | 5-Oct-17: Duplicate address issue raised, waiting input from Telstra 9-Oct: SLs outside the SAM, Awaiting input from AP 25-Oct : Telstra provided input 27-Oct : AP provided input | 2017-10-03 | ChristieThomas | 2017-10-05 | 2017-10-27 | 108 | 18 | 2017-10-27 | 2017-10-27 | 2017-10-27 | 1687 | 1 |  |  |  | 14 | 0 | 19 | 5
3BOX-63 | RFS.105 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-10-03 | Jumana.M | 2017-10-03 | 2017-10-06 | 93 | 4 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 4896 | 1 |  |  |  |  | 0 | 5 | 5
3HDB-62 | RFS.102 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-10-03 | S Shilpa | 2017-10-03 | 2017-10-05 |  | 3 | 2017-10-05 | 2017-10-05 | 2017-10-05 |  | 1 |  |  |  |  | 0 | 4 | 4
2PNN-64 | RFS.80 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-09-29 | Arunika Joy | 2017-10-03 | 2017-10-04 | 0 | 2 | 2017-10-04 | 2017-10-04 | 2017-10-04 | 558 | 1 |  |  |  |  | 0 | 3 | 3
4SLA-67 | RFS.81 | M-A-H | BAU | Post RFS | 1 | Rejected |  | 2017-10-03 | Jumana.M | 2017-10-06 | 2017-10-10 | 0 | 6 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 1473 | 1 |  |  |  |  | 0 | 7 | 7
6CTO-20 | RFS.133 | M-M-H | BAU | Design | 2 | Rejected | 5-Oct-17: SLs outside SAM, Critical issues reported to AP | 2017-10-03 | Arunika Joy | 2017-10-04 | 2017-10-06 | 232 | 4 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2307 | 1 |  |  |  |  | 0 | 5 | 5
2EDG-61 | RFS.55 | H-A-H | BAU | Post RFS | 1 | Completed - Handover to LMS |  | 2017-10-03 | Jowharulla.M | 2017-10-06 | 2017-10-09 | 0 | 5 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 1319 | 1 |  |  |  |  | 0 | 6 | 6
2BAN-69 | RFS.104 | H-M-Q | HAC | Pre-AT |  | Completed |  | 2017-10-03 | Anet Jose | 2017-10-03 | 2017-10-11 |  | 7 | 2017-10-11 | 2017-10-12 | 2017-10-12 |  | 2 |  |  |  |  | 0 | 9 | 9
2LIV-68 | RFS.97 | M-M-H | BAU | Post RFS | 1 | Completed - Handover to LMS |  | 2017-10-03 | Reenu Treesa Peter | 2017-10-04 | 2017-10-06 | 0 | 4 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 1911 | 1 |  |  |  |  | 0 | 5 | 5
4AAR-63 | RFS.122 | M-M-H | BAU | Design | 3 | Completed | 5-Oct-17: Duplicate address issue raised, waiting input from Telstra 25-Oct : Telstra provided input | 2017-10-04 | VishnuS | 2017-10-05 | 2017-10-25 | 110 | 15 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 3440 | 1 |  |  |  | 14 | 0 | 16 | 2
2PEN-61 | RFS.105 | M-M-H | BAU | Design | 1 | Completed - Handover to LMS |  | 2017-10-04 | JadeeraKT | 2017-10-05 | 2017-10-10 | 420 | 5 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 4846 | 1 |  |  |  |  | 0 | 6 | 6
4ASH-62 | RFS.95 | H-A-Q | BAU | Post RFS | 1 | Completed - Handover to LMS |  | 2017-10-04 | Devika Kala | 2017-10-05 | 2017-10-06 | 0 | 3 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 1269 | 1 |  |  |  |  | 0 | 4 | 4
3BNT-60 | RFS.102 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-10-04 | Revathy A | 2017-10-04 | 2017-10-05 | 12 | 2 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 1298 | 1 |  |  |  |  | 0 | 3 | 3
3BLB-69 | RFS.102 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-04 | Revathy A | 2017-10-04 | 2017-10-04 |  | 1 | 2017-10-04 | 2017-10-05 | 2017-10-05 |  | 2 |  |  |  |  | 0 | 3 | 3
2PEN-64 | RFS.104 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-10-04 | Manjusha M | 2017-10-05 | 2017-10-09 |  | 4 | 2017-10-10 | 2017-10-10 | 2017-10-10 |  | 1 |  |  |  |  | 0 | 5 | 5
4FHL-66 | RFS.78 | M-M-H | BAU | Post RFS | 1 | Rejected | 13-Nov: Rejected due to missing artifacts | 2017-10-05 | George | 2017-10-09 | 2017-10-09 | 0 | 3 | 2017-10-09 | 2017-10-13 | 2017-10-13 | 3339 | 5 | 2017-11-13 |  |  |  | 0 | 8 | 8
3WHL-65 | RFS.63 | M-A-J | BAU | Post RFS | 0.3 | Completed |  | 2017-10-05 | Saiju Xavier | 2017-10-09 | 2017-10-09 | 0 | 3 | 2017-10-09 | 2017-10-16 | 2017-10-16 | 3486 | 6 |  |  |  |  | 0 | 9 | 9
4FHL-64 | RFS.83 | M-M-H | BAU | Post RFS | 0.2 | Rejected | 18 Oct: T18 not updated correctly | 2017-10-05 | Reenu Treesa Peter | 2017-10-10 | 2017-10-10 | 0 | 4 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 3228 | 1 |  |  |  |  | 0 | 5 | 5
2WET-64 | RFS.65 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-05 | Manjusha M | 2017-10-09 | 2017-10-10 | 0 | 4 | 2017-10-11 | 2017-10-16 | 2017-10-16 | 2300 | 4 |  |  |  |  | 0 | 8 | 8
4APL-60 | RFS.125 | M-A-H | BAU | Pre-AT | 4 | Completed | 6-Oct-17: Duplicate addresses. Awaiting input | 2017-10-05 | Reenu Treesa Peter | 2017-10-05 | 2017-10-23 | 225 | 12 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 3058 | 1 |  |  |  |  | 0 | 13 | 13
2LIV-67 | RFS.125 | M-M-H(P) | BAU | Design | 3 | Completed |  | 2017-10-05 | VishnuS | 2017-10-10 | 2017-10-11 | 120 | 5 | 2017-10-11 | 2017-10-12 | 2017-10-12 | 2598 | 2 |  |  |  |  | 0 | 7 | 7
4MGA-63 | RFS.103 | M-A-Q | HAC | Pre-AT | 1.1 | Completed |  | 2017-10-05 | SanjanaKrishnan | 2017-10-06 | 2017-10-09 | 292 | 3 | 2017-10-09 | 2017-10-10 | 2017-10-10 | 4248 | 2 |  |  |  |  | 0 | 5 | 5
4SSB-61 | RFS.121 | M-M-H | BAU | Design | 1 | Rejected | 11-Oct-17: Rejected due to servicibility issues | 2017-10-05 | Devika Kala | 2017-10-10 |  |  | -30698 |  |  |  |  | 0 |  |  |  |  | 0 | -30698 | -30698
2PNN-66 | RFS.80 | H-A-H | BAU | Post RFS | 1 | Completed - Handover to LMS |  | 2017-10-06 | Devika Kala | 2017-10-06 | 2017-10-09 |  | 2 | 2017-10-09 | 2017-10-09 | 2017-10-09 |  | 1 |  |  |  |  | 0 | 3 | 3
4EMP-66 | RFS.56 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-06 | ShabeenaShamsudin | 2017-10-06 | 2017-10-06 |  | 1 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 1821 | 1 |  |  |  |  | 0 | 2 | 2
2PNN-68 | RFS.104 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-10-06 | Goutham A S | 2017-10-06 | 2017-10-09 |  | 2 | 2017-10-10 | 2017-10-10 | 2017-10-10 |  | 1 |  |  |  |  | 0 | 3 | 3
4CPR-63 | RFS.106 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover to LMS |  | 2017-10-06 | S Shilpa | 2017-10-06 | 2017-10-09 |  | 2 | 2017-10-10 | 2017-10-10 | 2017-10-10 |  | 1 |  |  |  |  | 0 | 3 | 3
4WTF-60 | RFS.130 | M-M-H | BAU | Design | 2 | Completed |  | 2017-10-09 | Reenu Treesa Peter | 2017-10-10 | 2017-10-11 |  | 3 | 2017-10-11 | 2017-10-12 | 2017-10-12 |  | 2 |  |  |  |  | 0 | 5 | 5
4SRW-66 | RFS.106 | M-A-H | BAU | Pre-AT | 1 | Rejected |  | 2017-10-09 | Revathy A | 2017-10-10 | 2017-10-11 |  | 3 | 2017-10-11 | 2017-10-12 | 2017-10-10 |  | -2 |  |  |  |  | 0 | 1 | 1
2PET-68 | RFS.131 | M-M-H | BAU | Design | 1 | Rejected | 11-Oct-17: SLs outside SAM, Awaiting AP's response 13-Oct: Rejected | 2017-10-09 | ShabeenaShamsudin | 2017-10-10 | 2017-10-13 |  | 5 |  |  |  |  | 0 |  |  |  |  | 0 | 5 | 5
3DRP-61 | RFS.63 | M-A-H | BAU | Post RFS | 1 | Rejected | 18 Oct: Rejected due to design issues | 2017-10-09 | ShabeenaShamsudin | 2017-10-10 | 2017-10-10 |  | 2 | 2017-10-10 | 2017-10-11 | 2017-10-11 |  | 2 | 2017-10-18 |  |  |  | 0 | 4 | 4
3NES-61 | RFS.65 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done | 18 Oct: Rejected due to design issues. TVT error on HFC part 24 Oct : Resumed version 1: Corrected tables sent to Midhun through email. Ahmed Ezatpanahlatifi updated duct & structure point tables to reflect the corrections | 2017-10-09 | Jowharulla.M | 2017-10-10 | 2017-10-10 |  | 2 | 2017-10-10 | 2017-10-11 | 2017-10-11 |  | 2 | 2017-10-18 |  |  |  | 0 | 4 | 4
4SSB-60 | RFS.106 | M-A-Q | HAC | Pre-AT | 1 | Rejected to Telstra | 9-Oct-17: Rejected due to critical raised by Design&LDM | 2017-10-05 | ShabeenaShamsudin | 2017-10-05 | 2017-10-09 | 228 | 3 |  |  |  | 4366 | 0 |  |  |  |  | 0 | 3 | 3
2STL-61 | RFS.104 | M-M-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-10 | JadeeraKT | 2017-10-10 | 2017-10-10 |  | 1 | 2017-10-10 | 2017-10-11 | 2017-10-11 |  | 2 |  |  |  |  | 0 | 3 | 3
3OAK-61 | RFS.105 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-10-10 | Jumana.M | 2017-10-10 | 2017-10-11 |  | 2 | 2017-10-11 | 2017-10-12 | 2017-10-12 |  | 2 |  |  |  |  | 0 | 4 | 4
2PYM-61 | RFS.125 | M-M-H | BAU | Design | 1 | Completed |  | 2017-10-11 | ShabeenaShamsudin | 2017-10-11 | 2017-10-12 |  | 2 | 2017-10-12 | 2017-10-13 | 2017-10-13 |  | 2 |  |  |  |  | 0 | 4 | 4
3CTA-60 | RFS.58 | H-A-H | BAU | Post RFS | 1 | Rejected | 6-Nov-17 : Rejected due to critical Design issues. | 2017-10-11 | JadeeraKT | 2017-10-12 | 2017-10-12 |  | 2 | 2017-10-12 | 2017-10-13 | 2017-10-13 |  | 2 | 2017-11-06 |  |  |  | 0 | 4 | 4
3CAU-64 | RFS.103 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-11 | Goutham A S | 2017-10-11 | 2017-10-12 |  | 2 | 2017-10-12 | 2017-10-13 | 2017-10-13 |  | 2 |  |  |  |  | 0 | 4 | 4
5BRI-65 | RFS.104 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-11 | Jumana.M | 2017-10-11 | 2017-10-12 |  | 2 | 2017-10-12 | 2017-10-13 | 2017-10-13 |  | 2 |  |  |  |  | 0 | 4 | 4
2ROS-66 | RFS.134 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-11 | Saiju Xavier | 2017-10-11 | 2017-10-12 |  | 2 | 2017-10-13 | 2017-10-16 | 2017-10-16 |  | 2 |  |  |  |  | 0 | 4 | 4
2PET-64 | RFS.108 | M-M-H | BAU | Design | 3 | Completed | 12-Oct-17: T18 payload wasn’t received till EoD | 2017-10-13 | S Shilpa | 2017-10-13 | 2017-10-17 |  | 3 | 2017-10-19 | 2017-10-19 | 2017-10-19 |  | 1 |  |  |  |  | 0 | 4 | 4
3BAY-65 | RFS.126 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-12 | Arunika Joy | 2017-10-12 | 2017-10-13 |  | 2 | 2017-10-13 | 2017-10-16 | 2017-10-16 |  | 2 |  |  |  |  | 0 | 4 | 4
4SSB-62 | RFS.126 | H-A-Q | HAC | Pre-AT |  | Completed |  | 2017-10-13 | ChristieThomas | 2017-10-13 | 2017-10-17 |  | 3 | 2017-10-17 | 2017-10-17 | 2017-10-17 |  | 1 |  |  |  |  | 0 | 4 | 4
5WES-63 | RFS.125 | M-M-H | BAU | Pre-AT | 1 | Rejected | 31-Oct : Critical Design issues | 2017-10-13 | VishnuS | 2017-10-13 | 2017-10-17 |  | 3 | 2017-10-17 | 2017-10-17 | 2017-10-17 |  | 1 | 2017-10-31 |  |  |  | 0 | 4 | 4
2EDG-65 | RFS.95 | M-M-H | BAU | Post RFS | 1 | Completed |  | 2017-10-13 | Saiju Xavier | 2017-10-16 | 2017-10-20 |  | 5 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 6 | 6
5GUG-63 | RFS.48 | H-M-J | BAU | Post RFS | 1.2 | Completed |  | 2017-10-13 | Jowharulla.M | 2017-10-16 | 2017-10-17 |  | 3 | 2017-10-17 | 2017-10-17 | 2017-10-17 |  | 1 |  |  |  |  | 0 | 4 | 4
2PET-62 | RFS.124 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-10-16 | JadeeraKT | 2017-10-16 | 2017-10-17 |  | 2 | 2017-10-17 | 2017-10-17 | 2017-10-17 |  | 1 |  |  |  |  | 0 | 3 | 3
2ING-61 | RFS.63 | H-A-H | BAU | Post RFS | 2 | Completed |  | 2017-10-16 | Manjusha M | 2017-10-16 | 2017-10-17 |  | 2 | 2017-10-17 | 2017-10-17 | 2017-10-17 |  | 1 |  |  |  |  | 0 | 3 | 3
2PNN-67 | RFS.80 | H-A-H | BAU | Post RFS | 2 | Completed |  | 2017-10-16 | Saranya Geetha | 2017-10-16 | 2017-10-17 |  | 2 | 2017-10-17 | 2017-10-17 | 2017-10-17 |  | 1 |  |  |  |  | 0 | 3 | 3
4ABO-67 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 17-Oct-17: Location issue reported to AP | 2017-10-16 | ShabeenaShamsudin | 2017-10-16 | 2017-10-20 |  | 4 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 5 | 5
4SSB-60 | RFS.126 | M-A-Q | HAC | Pre-AT | 2 | On Hold | 19-Oct-17: Relaunched as BAU | 2017-10-16 | Jumana.M | 2017-10-16 |  |  | -30705 |  |  |  |  | 0 |  |  |  |  | 0 | -30705 | -30705
3OAK-64 | RFS.104 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-17 | Arunika Joy | 2017-10-17 | 2017-10-20 |  | 3 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 4 | 4
4SLA-70 | RFS.108 | M-B-H | BAU | Pre-AT | 1 | Completed |  | 2017-10-17 | Saranya Geetha | 2017-10-17 | 2017-10-17 |  | 1 | 2017-10-17 | 2017-10-17 | 2017-10-17 |  | 1 |  |  |  |  | 0 | 2 | 2
3NBA-67 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-10-17 | George | 2017-10-17 | 2017-10-19 |  | 2 | 2017-10-19 | 2017-10-19 | 2017-10-19 |  | 1 |  |  |  |  | 0 | 3 | 3
3SSN-63 | RFS.102 | H-M-Q | BAU | Design | 1 | Completed |  | 2017-10-17 | Reenu Treesa Peter | 2017-10-17 | 2017-10-19 |  | 2 | 2017-10-19 | 2017-10-19 | 2017-10-19 |  | 1 |  |  |  |  | 0 | 3 | 3
3MLN-61 | RFS.103 | M-M-Q | BAU | Design | 1 | Rejected | 20-Oct-17: Duplicate address issue 24-Oct: Awaiting input from Telstra 31-Oct: Received input from telstra | 2017-10-17 | Revathy A | 2017-10-17 | 2017-10-24 |  | 5 | 2017-10-31 | 2017-10-31 | 2017-10-31 |  | 1 |  |  |  |  | 0 | 6 | 6
3CAU-66 | RFS.103 | H-M-Q | BAU | Design | 1 | Completed | 19-Oct-17: Relaunched in Appian as RFS.104 | 2017-10-17 | SanjanaKrishnan | 2017-10-17 | 2017-10-19 |  | 2 | 2017-10-19 | 2017-10-19 | 2017-10-19 |  | 1 |  |  |  |  | 0 | 3 | 3
3MLN-62 | RFS.125 | M-M-Q | BAU | Design | 1 | Completed |  | 2017-10-17 | Goutham A S | 2017-10-17 | 2017-10-23 |  | 4 | 2017-10-23 | 2017-10-23 | 2017-10-23 |  | 1 |  |  |  |  | 0 | 5 | 5
2CRR-65 | RFS.105 | M-M-H | BAU | Pre-AT | 1 | Completed |  | 2017-10-17 | JadeeraKT | 2017-10-17 | 2017-10-19 |  | 2 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 3 | 3
4BUR-63 | RFS.80 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-18 | ChristieThomas | 2017-10-19 | 2017-10-20 |  | 2 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 3 | 3
5FLN-62 | RFS.105 | H-B-J | BAU | Pre-AT | 1 | Completed | 19-Oct-17:previous phase changes not incorporated | 2017-10-18 | Jowharulla.M | 2017-10-19 | 2017-10-20 |  | 2 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 3 | 3
5GNG-61 | RFS.99 | M-M-H | BAU | Post RFS | 1 | Completed |  | 2017-10-18 | VishnuS | 2017-10-19 | 2017-10-20 |  | 2 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 3 | 3
2BON-64 | RFS.104 | M-A-Q | BAU | Pre-AT | 4 | Completed | 19-Oct-17: Processed out of appian | 2017-10-18 | Saiju Xavier | 2017-10-19 | 2017-10-20 |  | 2 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 3 | 3
2PNN-62 | RFS.108 | H-M-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-18 | Saranya Geetha | 2017-10-18 | 2017-10-20 |  | 2 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 3 | 3
2UND-62 | RFS.108 | H-M-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-18 | Manjusha M | 2017-10-19 | 2017-10-23 |  | 3 | 2017-10-23 | 2017-10-23 | 2017-10-23 |  | 1 |  |  |  |  | 0 | 4 | 4
5SAL-63 | RFS.51 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-18 | ShabeenaShamsudin | 2017-10-19 | 2017-10-20 |  | 2 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | 1 |  |  |  |  | 0 | 3 | 3
2WET-63 | RFS.58 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-18 | Jumana.M | 2017-10-19 | 2017-10-23 |  | 3 | 2017-10-23 | 2017-10-23 | 2017-10-23 |  | 1 |  |  |  |  | 0 | 4 | 4
2ENG-63 | RFS.72 | H-A-Q | BAU | Post RFS | 1 | Completed |  | 2017-10-18 | Saiju Xavier | 2017-10-23 | 2017-10-23 |  | 3 | 2017-10-23 | 2017-10-24 | 2017-10-24 |  | 2 |  |  |  |  | 0 | 5 | 5
4SSB-60 | RFS.106 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-10-18 | Devika Kala | 2017-10-20 | 2017-10-23 |  | 3 | 2017-10-24 | 2017-10-24 | 2017-10-24 |  | 1 |  |  |  |  | 0 | 4 | 4
2PAR-63 | RFS.125 | H-A-Q | HAC | Pre-AT | 1 | Completed | 24-Oct-17 : Awaiting input from AP 26-Oct-17 : AP provided input | 2017-10-19 | Saranya Geetha | 2017-10-20 | 2017-10-23 |  | 3 | 2017-10-31 | 2017-10-31 | 2017-11-01 |  | 2 |  |  |  |  | 0 | 5 | 5
3RWO-66 | RFS.107 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-10-20 | Jowharulla.M | 2017-10-23 | 2017-10-25 |  | 4 | 43033 | 2017-10-26 | 2017-10-26 |  | 2 |  |  |  |  | 0 | 6 | 6
2PNN-64 | RFS.80 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-20 | Arunika Joy | 2017-10-23 | 2017-10-23 |  | 2 | 2017-10-23 | 2017-10-24 | 2017-10-24 |  | 2 |  |  |  |  | 0 | 4 | 4
3DAD-64 | RFS.107 | M-M-H | BAU | Design | 1 | Completed | 23-Oct: Awaiting input from AP 25-Oct: Area planning responded. One more location correctly found outside boundary, Reported to AP Team 26-Oct: Awaiting input from AP 27-Oct: Area Planning provided input | 2017-10-20 | VishnuS | 2017-10-20 | 2017-10-27 |  | 6 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 |  |  |  |  | 0 | 7 | 7
6GIR-60 | RFS.104 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-20 | Sanjana Krishnan | 2017-10-20 | 2017-10-23 |  | 2 | 2017-10-23 | 2017-10-24 | 2017-10-24 |  | 2 |  |  |  |  | 0 | 4 | 4
6KSL-61 | RFS.104 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-20 | JadeeraKT | 2017-10-20 | 2017-10-23 |  | 2 | 2017-10-23 | 2017-10-23 | 2017-10-23 |  | 1 |  |  |  |  | 0 | 3 | 3
3KYG-66 | RFS.106 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-20 | George | 2017-10-20 | 2017-10-25 |  | 4 | 2017-10-25 | 2017-10-25 | 2017-10-25 |  | 1 |  |  |  |  | 0 | 5 | 5
4SRW-66 | RFS.106 | M-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-10-20 | ChristieThomas | 2017-10-20 | 2017-10-24 |  | 3 | 2017-10-24 | 2017-10-24 | 2017-10-24 |  | 1 |  |  |  |  | 0 | 4 | 4
4EMP-02 | RFS.106 | M-B-H | BAU | Pre-AT | 0.3 | Rejected |  | 2017-10-24 | JadeeraKT | 2017-10-24 | 2017-10-26 |  | 3 |  |  |  |  | 0 | 2017-10-27 |  |  |  | 0 | 3 | 3
3SPL-62 | RFS.120 | M-M-Q | HAC | Pre-AT | 1 | Completed - Handover done | 01-Feb : Critical Design issues,Acknowledged IAB load - post-PNI update of corrected artefacts. | 2017-10-24 | Manjusha M | 2017-10-24 | 2017-10-25 |  | 2 | 2017-10-25 | 2017-10-25 | 2017-10-25 |  | 1 |  |  |  |  | 0 | 3 | 3
4SRW-62 | RFS.108 | M-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-24 | Goutham A S | 2017-10-24 | 2017-10-25 |  | 2 | 2017-10-25 | 2017-10-25 | 2017-10-25 |  | 1 |  |  |  |  | 0 | 3 | 3
4SSB-61 | RFS.106 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-10-24 | Shabeena Shamsudin | 2017-10-24 | 2017-10-24 |  | 1 | 2017-10-24 | 2027-10-24 | 2017-10-24 |  | 1 |  |  |  |  | 0 | 2 | 2
4MGB-01 | RFS.106 | M-B-H | BAU | Pre-AT | 1.1 | Completed |  | 2017-10-24 | Revathy Babu | 2017-10-24 | 2017-10-25 |  | 2 | 2017-10-25 | 2017-10-25 | 2017-10-25 |  | 1 |  |  |  |  | 0 | 3 | 3
2LIV-63 | RFS.118 | M-M-H [P] | BAU | Design | 2 | Rejected | 24-Oct: Partial ONSA SAM.NAT Boundary mismatch reported to AP team 30-Oct: Area Planning provided input | 2017-10-24 | Jumana M | 2017-10-24 | 2017-10-27 |  | 4 | 2017-10-27 | 2017-10-31 | 2017-10-31 |  | 3 |  |  |  |  | 0 | 7 | 7
6GIR-68 | RFS.116 | M-A-H | BAU | Pre-AT | 3 | Completed |  | 2017-10-24 | Sanjana Krishnan | 2017-10-24 | 2017-10-25 |  | 2 | 2017-10-25 | 2017-10-25 | 2017-10-25 |  | 1 |  |  |  |  | 0 | 3 | 3
2FRE-61 | RFS.104 | M-A-H | BAU | Pre-AT | 1 | Completed |  | 2017-10-16 | Goutham A S | 2017-10-16 | 2017-10-16 |  | 1 | 2017-10-16 | 2017-10-17 | 2017-10-17 |  | 2 |  |  |  |  | 0 | 3 | 3
3HGT-60 | RFS.63 | M-A-J | BAU | Post RFS | 2 | Rejected | 25-Oct: Boundary mismatch reported to AP team 26-Oct: Input received ,but not reflected , mail sent again 27-oct : Boundary is not properly updated by AP Team, Awaiting input 30-oct: Boundary not properly updated by AP team Awaiting AP input 31-Oct: Awaiting AP response 01-Nov : Awaiting AP response 02-Nov :Awaiting LMS response 10-Nov : [REJECT] splicing within the SLD is incorrect as Fibres have been reallocated and therefore would not align with the integration or construction plans. | 2017-10-25 | Devika Kala | 2017-10-25 | 2017-11-03 |  | 8 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 | 2017-11-10 |  |  |  | 0 | 9 | 9
4CUR-63 | RFS.131 | M-A-H | BAU | Pre-AT | 0.1 | Completed | 26-Oct: Awaiting input from AP | 2017-10-25 | Arunika Joy | 2017-10-25 | 2017-10-27 |  | 3 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 |  |  |  |  | 0 | 4 | 4
2PET-66 | RFS.129 | M-M-H | BAU | Design | 2 | Rejected |  | 2017-10-25 | ChristieThomas | 2017-10-25 | 2017-10-27 |  | 3 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 | 2017-10-30 |  |  |  | 0 | 4 | 4
2PET-68 | RFS.131 | M-M-H | BAU | Design | 2 | Completed | 26-Oct : Awaiting AP input,2 locations outside SAM. 27-Oct : Area Planning provided input. | 2017-10-25 | ShabeenaShamsudin | 2017-10-25 | 2017-10-27 |  | 3 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 |  |  |  |  | 0 | 4 | 4
2PYM-64 | RFS.136 | M-M-H | BAU | Design | 0.1 | Completed - Handover done | 30-Oct:Awaiting AP input 31-Oct:Boundary not correctly updated by AP team 01-Nov:AP not properly responded.1 location outside the SAM 06-Nov : Area Planning has raised the Change request after that only this issue will be fixed. | 2017-10-25 | VishnuS | 2017-10-26 | 2017-10-27 |  | 3 | 2017-10-27 | 2017-11-14 | 2017-11-14 |  | 12 |  |  |  |  | 0 | 15 | 15
4FHL-61 | RFS.122 | M-A-Q | HAC | Pre-AT | 0.1 | Completed |  | 2017-10-25 | S Shilpa | 2017-10-25 | 2017-10-26 |  | 2 | 2017-10-26 | 2017-10-27 | 2017-10-27 |  | 2 |  |  |  |  | 0 | 4 | 4
4AAR-61 | RFS.103 | M-A-H [P] | BAU | Pre-AT | 3 | Completed | 25-Oct: Awaiting input from AP 30-Oct:AP response received | 2017-10-25 | Saiju Xavier | 2017-10-25 | 2017-10-25 |  | 1 | 2017-10-25 | 2017-10-31 | 2017-10-31 |  | 5 |  |  |  |  | 0 | 6 | 6
2STL-66 | RFS.104 | M-A-Q | HAC | Pre-AT | 4 | Completed |  | 2017-10-24 | Reenu Treesa Peter | 2017-10-24 | 2017-10-25 |  | 2 | 2017-10-25 | 2017-10-26 | 2017-10-26 |  | 2 |  |  |  |  | 0 | 4 | 4
5FLN-60 | RFS.107 | H-B-J | BAU | Pre-AT | 3.1 | Completed |  | 2017-10-25 | SanjanaKrishnan | 2017-10-25 | 2017-10-27 |  | 3 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 |  |  |  |  | 0 | 4 | 4
2CRM-62 | RFS.72 | H-A-Q | BAU | Post RFS | 1 | Completed |  | 2017-10-25 | George | 2017-10-25 | 2017-10-26 |  | 2 | 2017-10-26 | 2017-10-26 | 2017-10-26 |  | 1 |  |  |  |  | 0 | 3 | 3
2WET-60 | RFS.63 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-26 | Manjusha M | 2017-10-26 | 2017-10-26 |  | 1 | 2017-10-26 | 2017-10-26 | 2017-10-26 |  | 1 |  |  |  |  | 0 | 2 | 2
3TYH-61 | RFS.118 | M-M-H | BAU | Design | 2 | Completed |  | 2017-10-26 | Reenu Treesa Peter | 2017-10-30 | 2017-10-30 |  | 3 | 2017-10-30 | 2017-10-31 | 2017-10-31 |  | 2 |  |  |  |  | 0 | 5 | 5
3CLA-68 | RFS.102 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-26 | Saiju Xavier | 2017-10-26 | 2017-10-27 |  | 2 | 2017-10-30 | 2017-10-30 | 2017-10-30 |  | 1 |  |  |  |  | 0 | 3 | 3
2ING-65 | RFS.130 | M-M-H | BAU | Design | 2 | Rejected |  | 2017-10-26 | George | 2017-10-31 | 2017-10-31 |  | 4 | 2017-10-31 | 2017-11-01 | 2017-11-01 |  | 2 |  |  |  |  | 0 | 6 | 6
2SHA-21 | RFS.137 | M-M-H | BAU | Design | 0.1 | On Hold | 02-Nov: On hold , awaiting for documents. 22-Nov: Re-commenced using the same payload , added new entry below. | 2017-10-26 | JadeeraKT | 2017-10-26 | 2017-10-27 |  | 2 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 |  |  |  |  | 0 | 3 | 3
3WHL-60 | RFS.66 | H-M-H | BAU | Post RFS | 1 | Completed |  | 2017-10-26 | ShabeenaShamsudin | 2017-10-26 | 2017-10-27 |  | 2 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 |  |  |  |  | 0 | 3 | 3
4FHL-64 | RFS.80 | M-M-H | BAU | Post RFS | 0.3 | Completed - Handover done | 6-Nov-17 : Rejected due to critical Design issues. | 2017-10-26 | George | 2017-10-26 | 2017-10-27 |  | 2 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 |  |  |  |  | 0 | 3 | 3
2CYS-63 | RFS.105 | M-B-H | BAU | Design | 1 | Completed - Handover done | 31-Oct: Awaiting AP response 01-Nov:Awaiting AP input 02-Nov:Awaiting AP input | 2017-10-26 | SanjanaKrishnan | 2017-10-26 | 2017-11-03 |  | 7 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 8 | 8
4FHL-20 | RFS.108 | M-B-H | BAU | Pre-AT | 1 | Completed |  | 2017-10-26 | Manjusha M | 2017-10-26 | 2017-10-27 |  | 2 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | 1 |  |  |  |  | 0 | 3 | 3
3HGT-67 | RFS.116 | H-A-Q | HAC | Pre-AT | 1 | Completed |  | 2017-10-27 | JadeeraKT | 2017-10-30 | 2017-10-30 | 4 | 2 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 458 | 1 |  |  |  |  | 0 | 3 | 3
6SUB-66 | RFS.127 | M-M-H | BAU | Design | 3 | Completed - Handover done |  | 2017-10-27 | Jowharulla.M | 2017-11-01 | 2017-11-01 |  | 4 | 2017-11-01 | 2017-11-02 | 2017-11-02 |  | 2 |  |  |  |  | 0 | 6 | 6
3WIR-69 | RFS.106 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-10-27 | Arunika Joy | 2017-10-27 | 2017-10-31 |  | 3 | 2017-10-31 | 2017-10-31 | 2017-10-31 |  | 1 |  |  |  |  | 0 | 4 | 4
2ROS-67 | RFS.135 | H-A-Q | HAC | Pre-AT | 2 | Completed - Handover done |  | 2017-10-27 | ChristieThomas | 2017-10-30 | 2017-10-31 |  | 3 | 2017-10-31 | 2017-11-01 | 2017-11-01 |  | 2 |  |  |  |  | 0 | 5 | 5
5WES-66 | RFS.125 | H-M-Q | BAU | Design | 0.1 | Completed - Handover done |  | 2017-10-27 | Kavya Methil | 2017-11-02 | 2017-11-06 |  | 7 | 2017-11-06 | 2017-11-06 | 2017-11-06 |  | 1 |  |  |  |  | 0 | 8 | 8
4MGA-64 | RFS.79 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-27 | S Shilpa | 2017-10-27 | 2017-10-30 |  | 2 | 2017-10-30 | 2017-10-30 | 2017-10-30 |  | 1 |  |  |  |  | 0 | 3 | 3
4CPB-60 | RFS.65 | M-M-J | BAU | Post RFS | 0.6 | Completed - Handover done | 13-Nov: Rejected due to missing artifacts | 2017-10-27 | George | 2017-10-27 | 2017-10-30 |  | 2 | 2017-10-30 | 2017-10-30 | 2017-10-30 |  | 1 | 2017-11-13 |  |  |  | 0 | 3 | 3
4CPB-61 | RFS.63 | M-A-J | BAU | Post RFS | 0.8 | Rejected | 09-Nov: Rejected due to critical Design issues. | 2017-10-27 | Manjusha M | 2017-10-27 | 2017-10-27 |  | 1 | 2017-10-30 | 2017-11-01 | 2017-11-01 |  | 3 | 2017-11-09 |  |  |  | 0 | 4 | 4
5NRW-63 | RFS.118 | M-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-10-27 | VishnuS | 2017-10-30 | 2017-11-01 |  | 4 | 2017-11-01 | 2017-11-01 | 2017-11-01 |  | 1 |  |  |  |  | 0 | 5 | 5
2PEN-67 | RFS.105 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done | 30-Oct: Duplicate issues raised 31-Oct: Duplicate issues fixed. | 2017-10-30 | Goutham A S | 2017-10-30 | 2017-11-01 |  | 3 | 2017-11-01 | 2017-11-01 | 2017-11-01 |  | 1 |  |  |  |  | 0 | 4 | 4
4CHD-61 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | Completed |  | 2017-10-30 | ShabeenaShamsudin | 2017-10-30 | 2017-10-30 |  | 1 | 2017-10-30 | 2017-10-31 | 2017-10-31 |  | 2 |  |  |  |  | 0 | 3 | 3
4CHP-66 | RFS.108 | M-B-H | BAU | Pre-AT | 1 | Completed - Handover done | 01-Nov: Awaiting AP input | 2017-10-30 | Kavya Methil | 2017-10-30 | 2017-11-03 |  | 5 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 6 | 6
2HUR-62 | RFS.108 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-10-30 | JadeeraKT | 2017-10-31 | 2017-11-02 |  | 4 | 2017-11-02 | 2017-11-02 | 2017-11-02 |  | 1 |  |  |  |  | 0 | 5 | 5
6WMB-61 | RFS.106 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-10-30 | Saiju Xavier | 2017-10-31 | 2017-11-02 |  | 4 | 2017-11-02 | 2017-11-02 | 2017-11-02 |  | 1 |  |  |  |  | 0 | 5 | 5
5BRI-62 | RFS.107 | H-A-Q | HAC | Pre-AT | 2 | Completed - Handover done | 31-Oct: Awaiting AP response | 2017-10-30 | S Shilpa | 2017-10-31 | 2017-10-31 |  | 2 | 2017-10-31 | 2017-11-01 | 2017-11-01 |  | 2 |  |  |  |  | 0 | 4 | 4
3NES-62 | RFS.124 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done | 02-Nov:Awaiting AP response 06-Nov: AP team has fixed the issue. | 2017-10-30 | Arunika Joy | 2017-10-31 | 2017-11-06 |  | 6 | 2017-11-06 | 2017-11-06 | 2017-11-06 |  | 1 |  |  |  |  | 0 | 7 | 7
2PNN-69 | RFS.76 | M-A-H | BAU | Post RFS | 1 | Completed - Handover done | 01-Nov:4 SL outside SAM boundary, Awaiting AP input 06-Nov : Area Planning has raised the Change request after that only this issue will be fixed. ETA- Friday EOD. | 2017-10-30 | Revathy A | 2017-11-01 | 2017-11-01 |  | 3 | 2017-11-14 | 2017-11-14 | 2017-11-14 |  | 1 |  |  |  |  | 0 | 4 | 4
5BRI-64 | RFS.123 | H-M-H | BAU | Design | 2 | Completed |  | 2017-10-30 | Revathy A | 2017-11-01 | 2017-11-01 |  | 3 | 2017-11-01 | 2017-11-01 | 2017-11-01 |  | 1 |  |  |  |  | 0 | 4 | 4
5NRW-60 | RFS.120 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-10-30 | Jumana.M | 2017-10-31 | 2017-11-03 |  | 5 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 6 | 6
6SUB-62 | RFS.132 | M-M-H | BAU | Design | 3 | Rejected | 09-Nov: Rejected due to critical Design issues. | 2017-10-31 | Revathy A | 2017-11-02 | 2017-11-08 |  | 6 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | 1 | 2017-11-09 |  |  |  | 0 | 7 | 7
2HUR-65 |  | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-10-31 | S Shilpa | 2017-11-02 | 2017-11-02 |  | 3 | 2017-11-02 | 2017-11-03 | 2017-11-03 |  | 2 |  |  |  |  | 0 | 5 | 5
5GUG-66 | RFS.78 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done |  | 2017-10-31 | S Shilpa | 2017-11-01 | 2017-11-01 |  | 2 | 2017-11-01 | 2017-11-01 | 2017-11-01 |  | 1 |  |  |  |  | 0 | 3 | 3
5EDW-60 | RFS.78 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done |  | 2017-10-31 | Manjusha M | 2017-11-02 | 2017-11-03 |  | 4 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 5 | 5
2CRM-60 | RFS.80 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done |  | 2017-10-31 | Manjusha M | 2017-11-01 | 2017-11-02 |  | 3 | 2017-11-02 | 2017-11-02 | 2017-11-02 |  | 1 |  |  |  |  | 0 | 4 | 4
2PNN-65 | RFS.80 | H-A-H | BAU | Post RFS | 1 | Completed |  | 2017-10-31 | S Shilpa | 2017-11-01 | 2017-11-01 |  | 2 | 2017-11-01 | 2017-11-01 | 2017-11-01 |  | 1 |  |  |  |  | 0 | 3 | 3
4ASH-66 | RFS.70 | M-M-J | BAU | Post RFS | 0.4 | Rejected | 13-Nov : Rejected due to missing artifacts | 2017-10-31 | VishnuS | 2017-11-03 | 2017-11-06 |  | 5 | 2017-11-06 | 2017-11-06 | 2017-11-06 |  | 1 | 2017-11-13 |  |  |  | 0 | 6 | 6
5NRW-64 | RFS.120 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 31-Oct: Awaiting AP response 01-Nov:Awaiting AP input 02-Nov: Reminder sent 06-Nov : Area Planning has raised the Change request after that only this issue will be fixed. | 2017-10-25 | Anet Jose | 2017-10-25 | 2017-11-01 |  | 6 | 2017-11-14 | 2017-11-14 | 2017-11-14 |  | 1 |  |  |  |  | 0 | 7 | 7
4SOP-64 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | Completed | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-10-30 | Tajinder Kaur | 2017-10-30 | 2017-10-30 |  | 1 | 2017-10-30 | 2017-10-30 | 2017-10-30 |  | 1 |  |  |  |  | 0 | 2 | 2
2PYM-62 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | Completed | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-10-30 | Tajinder Kaur | 2017-10-30 | 2017-10-30 |  | 1 | 2017-10-30 | 2017-10-30 | 2017-10-30 |  | 1 |  |  |  |  | 0 | 2 | 2
2ING-64 | RFS.106 | M-A-H | BAU | Pre-AT | 1 | Completed | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-11-03 | Tajinder Kaur | 2017-11-03 | 2017-11-03 |  | 1 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 2 | 2
2PYM-63 | RFS.107 | M-A-H | BAU | Pre-AT | 1 | Completed | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-10-30 | Tajinder Kaur | 2017-10-30 | 2017-10-30 |  | 1 | 2017-10-30 | 2017-10-30 | 2017-10-30 |  | 1 |  |  |  |  | 0 | 2 | 2
6GIR-64 | RFS.106 | M-A-H | BAU | Pre-AT | 1 | Completed | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-11-03 | Tajinder Kaur | 2017-11-03 | 2017-11-03 |  | 1 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 2 | 2
4BUR-67 | RFS.106 | M-A-H | BAU | Pre-AT | 3 | Completed | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-11-03 | Tajinder Kaur | 2017-11-03 | 2017-11-03 |  | 1 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 2 | 2
4CPR-60 | RFS.108 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-11-01 | ChristieThomas | 2017-11-01 | 2017-11-03 |  | 3 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 4 | 4
2NSY-60 | RFS.84 | H-M-H | BAU | Post RFS | 0.2 | Completed - Handover done |  | 2017-11-01 | Jowharulla.M | 2017-11-02 | 2017-11-03 |  | 3 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 4 | 4
2PET-64 | RFS.108 | M-M-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-11-01 | George | 2017-11-01 | 2017-11-03 |  | 3 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 4 | 4
3MIT-60 | RFS.106 | M-M-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-01 | ShabeenaShamsudin | 2017-11-01 | 2017-11-02 |  | 2 | 2017-11-02 | 2017-11-02 | 2017-11-02 |  | 1 |  |  |  |  | 0 | 3 | 3
2PAR-62 | RFS.125 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-01 | SanjanaKrishnan | 2017-11-01 | 2017-11-03 |  | 3 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | 1 |  |  |  |  | 0 | 4 | 4
5MOD-63 | RFS.97 | M-A-J | BAU | Post RFS | 2 | Rejected | 07-Nov: Critical defect Identified by LDM nad design team. Task is not yet paused due to APPIAN issue. | 2017-11-02 | SanjanaKrishnan | 2017-11-02 |  |  | -30717 |  |  |  |  | 0 | 2017-11-07 |  |  |  | 0 | -30717 | -30717
2PEN-01 | RFS.134 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-11-02 | ShabeenaShamsudin | 2017-11-02 | 2017-11-03 |  | 2 | 2017-11-03 | 2017-11-07 | 2017-11-07 |  | 2 |  |  |  |  | 0 | 4 | 4
2PYM-63 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | Completed - Handover done |  | 2017-11-02 | Goutham A S | 2017-11-02 | 2017-11-02 |  | 1 | 2017-11-02 | 2017-11-03 | 2017-11-03 |  | 2 |  |  |  |  | 0 | 3 | 3
3TYH-69 | RFS.116 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-11-03 | JadeeraKT | 2017-11-03 | 2017-11-06 |  | 2 | 2017-11-06 | 2017-11-07 | 2017-11-07 |  | 1 |  |  |  |  | 0 | 3 | 3
4AGV-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-11-01 | Swathy Mohandas | 2017-11-01 | 2017-11-01 |  | 1 | 2017-11-01 | 2017-11-01 | 2017-11-01 |  | 1 |  |  |  |  | 0 | 2 | 2
2HLS-61 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | Completed - Handover done | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-10-30 | Tajinder Kaur | 2017-10-30 | 2017-10-30 |  | 1 | 2017-10-30 | 2017-10-30 | 2017-10-30 |  | 1 |  |  |  |  | 0 | 2 | 2
2LIV-66 | RFS.118 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-11-03 | George | 2017-11-03 | 2017-11-06 |  | 2 | 2017-11-06 | 2017-11-07 | 2017-11-07 |  | 1 |  |  |  |  | 0 | 3 | 3
4ASH-64 | RFS.113 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done | As Design payload was delivered in April long back.Hence the Pre AT Payload needs to be delivered for same version. | 2017-11-03 | Jumana.M | 2017-11-06 | 2017-11-06 |  | 2 | 2017-11-06 | 2017-11-06 | 2017-11-06 |  | 1 |  |  |  |  | 0 | 3 | 3
4MRA-60 | RFS.70 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done |  | 2017-11-06 | Saiju Xavier | 2017-11-06 | 2017-11-07 |  | 1 | 2017-11-07 | 2017-11-07 | 2017-11-07 |  | 0 |  |  |  |  | 0 | 1 | 1
4MGB-63 | RFS.95 | H-A-Q | BAU | Post RFS | 1 | Rejected | 07-Nov: Critical defect Identified by LDM team. | 2017-11-06 | Saranya Geetha | 2017-11-06 |  |  | -30719 |  |  |  |  | 0 | 2017-11-07 |  |  |  | 0 | -30719 | -30719
4MGB-62 | RFS.101 | M-M-H | BAU | Post RFS | 1 | Completed - Handover done |  | 2017-11-06 | ChristieThomas | 2017-11-06 | 2017-11-07 |  | 1 | 2017-11-07 | 2017-11-07 | 2017-11-07 |  | 0 |  |  |  |  | 0 | 1 | 1
4FHL-62 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-06 | Jowharulla.M | 2017-11-06 | 2017-11-08 |  | 2 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | 1 |  |  |  |  | 0 | 3 | 3
4MRA-64 | RFS.113 | M-M-Q | HAC | Pre-AT | 0.1 | Rejected | 09-Nov: Rejected due to critical LDM and DESG issues. | 2017-11-06 | Goutham A S | 2017-11-06 | 2017-11-07 |  | 1 |  |  |  |  | 0 | 2017-11-09 |  |  |  | 0 | 1 | 1
6GIR-65 | RFS.143 | M-M-H | BAU | Design | 1 | Completed - Handover done | 09-Nov:Awaiting AP input-51 LOCATIONS ARE OUTSIDE THE BOUNDARY due to boundary mismatch | 2017-11-06 | ShabeenaShamsudin | 2017-11-09 | 2017-11-10 |  | 4 | 2017-11-10 | 2017-11-13 | 2017-11-13 |  | 2 |  |  |  |  | 0 | 6 | 6
2PEN-65 | RFS.109 | M-M-H | BAU | Design | 1 | Rejected | 15-Nov : Rejected due to Design critical defects | 2017-11-06 | Manjusha M | 2017-11-06 | 2017-11-08 |  | 2 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | 1 |  |  |  |  | 0 | 3 | 3
4SOP-65 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 13-Nov: Changed from HAC to BAU for the split load( from M-A-Q to M-A-H) and will stay in group 110 | 2017-11-06 | VishnuS | 2017-11-07 | 2017-11-08 |  | 2 | 2017-11-08 | 2017-11-09 | 2017-11-09 |  | 2 |  |  |  |  | 0 | 4 | 4
3DAN-61 | RFS.49 | M-A-H | BAU | Post RFS | 2 | Rejected | 13-Nov : Rejected due to missing artifacts | 2017-11-06 | Kavya Methil | 2017-11-07 | 2017-11-08 |  | 2 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | 1 | 2017-11-13 |  |  |  | 0 | 3 | 3
5NRW-62 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 09-Nov: Changed from HAC to BAU for the split load( from M-A-Q to M-A-H) and will stay in group 110 | 2017-11-06 | Jumana.M | 2017-11-07 | 2017-11-08 |  | 2 | 2017-11-08 | 2017-11-10 | 2017-11-10 |  | 3 |  |  |  |  | 0 | 5 | 5
4BLH-61 | RFS.80 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done |  | 2017-11-06 | ShabeenaShamsudin | 2017-11-07 | 2017-11-08 |  | 2 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | 1 |  |  |  |  | 0 | 3 | 3
2NEW-63 | RFS.139 | M-M-H | BAU | Design | 1 | On Hold | 10-Nov:Duplicate address issue 15-Nov : On Hold in APPIAN , awaiting DDDM submission from Telstra | 2017-11-06 | Jowharulla.M | 2017-11-09 |  |  | -30719 |  |  |  |  | 0 |  |  |  |  | 0 | -30719 | -30719
3DNC-63 | RFS.132 | H-M-Q | BAU | Design | 1 | Completed - Handover done |  | 2017-11-06 | Saranya Geetha | 2017-11-07 | 2017-11-08 |  | 2 | 2017-11-08 | 2017-11-09 | 2017-11-09 |  | 2 |  |  |  |  | 0 | 4 | 4
2RYD-64 | RFS.110 | H-A-Q | HAC | Pre-AT | 1 | Rejected | 15-Nov: Rejected due to Area Planning defects | 2017-11-06 | Arunika Joy | 2017-11-06 | 2017-11-08 |  | 2 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | 1 |  |  |  |  | 0 | 3 | 3
4EMP-25 | RFS.108 | M-B-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-11-06 | Reenu Treesa Peter | 2017-11-06 | 2017-11-06 |  | 1 | 2017-11-06 | 2017-11-06 | 2017-11-07 |  | 1 |  |  |  |  | 0 | 2 | 2
2HUR-64 | RFS.108 | M-M-Q | BAU | Design | 0.1 | Rejected | 08-Nov :Awaiting AP input-15 LOCATIONS ARE OUTSIDE THE BOUNDARY. 13-Nov: AP response received | 2017-11-07 | Reenu Treesa Peter | 2017-11-07 | 2017-11-09 |  | 2 | 2017-11-09 | 2017-11-13 | 2017-11-13 |  | 3 | 2017-11-14 |  |  |  | 0 | 5 | 5
3CTA-63 | RFS.78 | H-A-H | BAU | Post RFS | 1 | Rejected | 13-Nov: Rejected due to missing artifacts | 2017-11-08 | ChristieThomas | 2017-11-08 | 2017-11-08 |  | 1 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | 1 | 2017-11-13 |  |  |  | 0 | 2 | 2
4CUR-60 | RFS.108 | M-A-Q | HAC | Pre-AT | 2 | Completed - Handover done |  | 2017-11-07 | George | 2017-11-07 | 2017-11-10 |  | 3 | 2017-11-10 | 2017-11-10 | 2017-11-10 |  | 1 |  |  |  |  | 0 | 4 | 4
4MRA-65 | RFS.84 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done | 08-Nov:Awaiting response from LMS. | 2017-11-07 | ChristieThomas | 2017-11-08 | 2017-11-08 |  | 1 | 2017-11-14 | 2017-11-14 | 2017-11-14 |  | 1 |  |  |  |  | 0 | 2 | 2
2SHA-60 | RFS.80 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done | 08-Nov:Awaiting response from LMS. | 2017-11-07 | SanjanaKrishnan | 2017-11-08 | 2017-11-08 |  | 1 | 2017-11-14 | 2017-11-14 | 2017-11-14 |  | 1 |  |  |  |  | 0 | 2 | 2
4NDG-62 | RFS.127 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done | 09-Nov:Awaiting AP input-1 LOCATION IS OUTSIDE THE BOUNDARY due to boundary mismatch 13-Nov:AP Response received | 2017-11-07 | JadeeraKT | 2017-11-07 | 2017-11-09 |  | 2 | 2017-11-09 | 2017-11-13 | 2017-11-13 |  | 3 |  |  |  |  | 0 | 5 | 5
2LIV-67 | RFS.125 | M-M-H | BAU | Design | 4 | Rejected | 15-Nov: Prior Feedback unresolved | 2017-11-08 | Revathy A | 2017-11-09 | 2017-11-09 |  | 2 | 2017-11-09 | 2017-11-10 | 2017-11-10 |  | 2 |  |  |  |  | 0 | 4 | 4
3FNT-61 | RFS.63 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done | 09-Nov:Awaiting Telstra Input and LMS | 2017-11-08 | Goutham A S | 2017-11-08 | 2017-11-08 |  | 1 | 2017-11-14 | 2017-11-14 | 2017-11-14 |  | 1 |  |  |  |  | 0 | 2 | 2
4WTF-65 | RFS.136 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-11-08 | Arunika Joy | 2017-11-09 | 2017-11-10 |  | 3 | 2017-11-10 | 2017-11-13 | 2017-11-13 |  | 2 |  |  |  |  | 0 | 5 | 5
5WES-62 | RFS.108 | H-A-Q | HAC | Pre-AT | 2 | Completed - Handover done | 10-Nov:Awaiting telstra input | 2017-11-09 | Manjusha M | 2017-11-09 | 2017-11-10 |  | 2 | 2017-11-10 | 2017-11-16 | 2017-11-16 |  | 5 |  |  |  |  | 0 | 7 | 7
4CHD-21 | RFS.109 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-11-09 | ChristieThomas | 2017-11-09 | 2017-11-09 |  | 1 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | 1 |  |  |  |  | 0 | 2 | 2
5WES-61 | RFS.108 | M-M-H | BAU | Pre-AT | 0.4 | Rejected |  | 2017-11-09 | Kavya Methil | 2017-11-09 | 2017-11-09 |  | 1 | 2017-11-10 | 2017-11-13 | 2017-11-10 |  | 1 |  |  |  |  | 0 | 2 | 2
4OXE-62 | RFS.107 | H-A-Q | HAC | Pre-AT | 2 | Completed - Handover done | 08-Nov : Currently NA team not able to resume it in Appian , will be tracked outside the APPIAN. 24-Nov : Task luanched in APPIAN and has been actulaized | 2017-11-08 | Anet Jose | 2017-11-08 | 2017-11-08 |  | 1 | 2017-11-08 | 2017-11-09 | 2017-11-09 |  | 2 |  |  |  |  | 0 | 3 | 3
4SLA-67 | RFS.81 | M-A-H | BAU | Post RFS | 2 | Rejected | 23-Nov: Critical design Issues | 2017-11-09 | Reenu Treesa Peter | 2017-11-09 | 2017-11-09 |  | 1 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | 1 | 2017-11-23 |  |  |  | 0 | 2 | 2
3CAU-67 | RFS.111 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-09 | Goutham A S | 2017-11-09 | 2017-11-10 |  | 2 | 2017-11-10 | 2017-11-13 | 2017-11-13 |  | 2 |  |  |  |  | 0 | 4 | 4
2FRE-63 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done | 13-Nov : Awaiting response from LMS team. | 2017-11-09 | Saiju Xavier | 2017-11-09 | 2017-11-10 |  | 2 | 2017-11-14 | 2017-11-14 | 2017-11-14 |  | 1 |  |  |  |  | 0 | 3 | 3
5EDW-65 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-11-09 | VishnuS | 2017-11-10 | 2017-11-10 |  | 2 | 2017-11-10 | 2017-11-10 | 2017-11-10 |  | 1 |  |  |  |  | 0 | 3 | 3
3CAN-64 | RFS.120 | H-A-Q | HAC | Pre-AT | 0.1 | Completed - Handover done | 13-Nov: Duplicate address issue , awaiting response from NA. 14-Nov: NA provided input. 16-Nov : Awaiting response from NA. 17-Nov : Input received | 2017-11-10 | Reenu Treesa Peter | 2017-11-10 | 2017-11-14 |  | 3 | 2017-11-14 | 2017-11-17 | 2017-11-17 |  | 4 |  |  |  |  | 0 | 7 | 7
4CHL-70 | RFS.130 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-11-10 | ChristieThomas | 2017-11-10 | 2017-11-10 |  | 1 | 2017-11-10 | 2017-11-13 | 2017-11-13 |  | 2 |  |  |  |  | 0 | 3 | 3
2CRR-66 | RFS.116 | M-M-H | BAU | Design | 4 | Completed - Handover done | 13-Nov:Awaiting telstra input | 2017-11-10 | Saranya Geetha | 2017-11-10 | 2017-11-13 |  | 2 | 2017-11-13 | 2017-11-14 | 2017-11-14 |  | 2 |  |  |  |  | 0 | 4 | 4
4OXE-60 | RFS.109 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-13 | Jumana.M | 2017-11-13 | 2017-11-14 |  | 2 | 2017-11-14 | 2017-11-15 |  |  | -30724 |  |  |  |  | 0 | -30722 | -30722
5NRW-66 | RFS.110 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done | 15-Nov: Boundary mismatch,awaiting response from AP team 17-Nov: CR has been raised by area planning team, ETA to complete is next week. | 2017-11-13 | Manjusha M | 2017-11-13 | 2017-11-15 |  | 3 | 2017-11-15 | 2017-11-21 | 2017-11-21 |  | 5 |  |  |  |  | 6 | 8 | 2
4OXE-61 | RFS.110 | M-A-H | BAU | Pre-AT | 2 | Completed - Handover done |  | 2017-11-13 | SanjanaKrishnan | 2017-11-13 | 2017-11-14 |  | 2 | 2017-11-14 | 2017-11-15 | 2017-11-15 |  | 2 |  |  |  |  | 0 | 4 | 4
4FHL-60 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done | 16-Nov:Boundary mismatch,awaiting response from AP team 20-Nov: CR has been raised by area planning team, awaiting response | 2017-11-14 | Arunika Joy | 2017-11-14 | 2017-11-16 |  | 3 | 2017-11-16 | 2017-11-21 | 2017-11-21 |  | 4 |  |  |  |  | 5 | 7 | 2
3SSN-61 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-14 | ShabeenaShamsudin | 2017-11-14 | 2017-11-15 |  | 2 | 2017-11-15 | 2017-11-15 | 2017-11-15 |  | 1 |  |  |  |  | 0 | 3 | 3
2PYM-65 | RFS.118 | M-A-Q | HAC | Pre-AT | 1 | Rejected |  | 2017-11-14 | George | 2017-11-14 | 2017-11-15 |  | 2 | 2017-11-16 | 2017-11-17 | 2017-11-17 |  | 2 |  |  |  |  | 0 | 4 | 4
2HUR-60 | RFS.135 | M-M-Q | BAU | Design | 1 | On Hold | 14-Nov : Waiting for FTTB - EXPECTED ON 8 DEC 15-Jan : Resumed in APPIAN. 16-Jan : Waiting for FTTB -- ETA 25 JAN | 2017-11-14 | Reenu Treesa Peter | 2018-01-15 |  |  | -30724 |  |  |  |  | 0 |  | 2018-01-16 |  |  | -30766 | -30724 | 42
4BNP-62 | RFS.83 | H-A-H | BAU | Post RFS | 1 | Completed - Handover done |  | 2017-11-14 | Jowharulla.M | 2017-11-15 | 2017-11-15 |  | 2 | 2017-11-15 | 2017-11-15 | 2017-11-15 |  | 1 |  |  |  |  | 0 |  | 0
3TYH-66 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 15-Nov: On hold trailling FTTB forecast 22-Nov : RECEIVED TRAILING FTTB: MPS-018/ RESUMED ON 22 NOV. | 2017-11-14 | Reenu Treesa Peter | 2017-11-22 | 2017-11-23 |  | 8 | 2017-11-23 | 2017-11-24 | 2017-11-24 |  | 2 |  | 2017-11-15 | 2017-11-22 |  | 6 |  | -6
2MOS-64 | RFS.75 | H-A-Q | BAU | Post RFS | 1 | Completed - Handover done | 16-Nov:Awaiting input from NA | 2017-11-14 | Kavya Methil | 2017-11-14 | 2017-11-14 |  | 1 | 2017-11-17 | 2017-11-17 | 2017-11-17 |  | 1 |  |  |  |  | 0 |  | 0
6CTO-20 | RFS.133 | M-M-H | BAU | Design | 3 | Rejected | 17-Nov:Awaiting input from NA 20-Nov : NA provided response, awaiting input from Telstra. 24-Nov: | 2017-11-15 | VishnuS | 2017-11-15 |  |  | -30725 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0
3GLI-60 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done | 16-Nov:Awaiting response from LMS | 2017-11-15 | Anet Jose | 2017-11-15 | 2017-11-15 |  | 1 | 2017-11-20 | 2017-11-20 | 2017-11-20 |  | 1 |  |  |  |  | 0 |  | 0
4MRA-64 | RFS.113 | M-M-Q | HAC | Pre-AT | 0.2 | Completed - Handover done |  | 2017-11-15 | ChristieThomas | 2017-11-15 | 2017-11-16 |  | 2 | 2017-11-16 | 2017-11-17 | 2017-11-17 |  | 2 |  |  |  |  | 0 |  | 0
6WMB-62 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-11-16 | Saiju Xavier | 2017-11-16 | 2017-11-17 |  | 2 | 2017-11-17 | 2017-11-20 | 2017-11-20 |  | 2 |  |  |  |  | 0 |  | 0
2RYD-65 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 17-Nov: Boundary issue raised. 21-Nov : Boundary Manager team is currently working on resolving the issues within 2RYD and 2RDL FSA. Boundary issue will be fixed post this clean up. | 2017-11-16 | Jowharulla.M | 2017-11-16 | 2017-11-20 |  | 3 | 2017-11-24 | 2017-11-24 | 2017-11-24 |  | 1 |  |  |  |  | 2 |  | -2
4BNP-61 | RFS.83 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-11-16 | JadeeraKT | 2017-11-16 | 2017-11-16 |  | 1 | 2017-11-16 | 2017-11-17 | 2017-11-17 |  | 2 |  |  |  |  | 0 |  | 0
3DNC-64 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-11-16 | Jumana.M | 2017-11-16 | 2017-11-16 |  | 1 | 2017-11-16 | 2017-11-17 | 2017-11-17 |  | 2 |  |  |  |  | 0 |  | 0
3OAK-69 | RFS.137 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-11-16 | Goutham A S | 2017-11-16 | 2017-11-17 |  | 2 | 2017-11-17 | 2017-11-20 | 2017-11-20 |  | 2 |  |  |  |  | 0 |  | 0
4MGB-63 | RFS.95 | H-A-Q | BAU | Post RFS | 1.1 | Completed - Handover done |  | 2017-11-16 | Saranya Geetha | 2017-11-16 | 2017-11-16 |  | 1 | 2017-11-16 | 2017-11-17 | 2017-11-17 |  | 2 |  |  |  |  | 0 |  | 0
4CHD-60 | RFS.126 | M-B-H | BAU | Design | 2 | Rejected | 17-Nov:Awaiting input from NA 21-Nov: NA provided input, but rejected due to critical design issues. | 2017-11-16 | Revathy A | 2017-11-16 |  |  | -30726 |  |  |  |  | 0 | 2017-11-21 |  |  |  | 0 |  | 0
2RYD-66 | RFS.110 | M-A-H | BAU | Pre-AT | 0.1 | Completed - Handover done | 20-Nov: Awaiting response from NA and Area Planning 21-Nov : Input provided by NA. Also 2RYD-66 has been relaunched as BAU(M-A-H) as it was decided to Split load 21-Nov : Boundary Manager team is currently working on resolving the issues within 2RYD and 2RDL FSA. Boundary issue will be fixed post this clean up. | 2017-11-16 | SanjanaKrishnan | 2017-11-16 | 2017-11-21 |  | 4 | 2017-11-21 | 2017-11-23 | 2017-11-23 |  | 3 |  |  |  |  | 1 |  | -1
2PEN-65 | RFS.109 | M-M-H | BAU | Design | 0.1 | Completed - Handover done |  | 2017-11-17 | Arunika Joy | 2017-11-17 | 2017-11-21 |  | 3 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | 1 |  |  |  |  | 0 |  | 0
2HUR-66 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-17 | ShabeenaShamsudin | 2017-11-17 | 2017-11-21 |  | 3 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | 1 |  |  |  |  | 0 |  | 0
2EAS-69 | RFS.130 | M-M-Q | BAU | Design | 1 | Completed - Handover done | 20-Nov:NAT boundary missing in PNI | 2017-11-17 | Reenu Treesa Peter | 2017-11-17 | 2017-11-21 |  | 3 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | 1 |  |  |  |  | 0 |  | 0
4EMP-25 | RFS.108 | M-B-H | BAU | Pre-AT | 2 | Completed - Handover done |  | 2017-11-17 | Anet Jose | 2017-11-17 | 2017-11-17 |  | 1 | 2017-11-17 | 2017-11-17 | 2017-11-17 |  | 1 |  |  |  |  | 0 |  | 0
4FHL-22 | RFS.141 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-11-17 | JadeeraKT | 2017-11-17 | 2017-11-21 |  | 3 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | 1 |  |  |  |  | 0 |  | 0
2WRO-60 | RFS.139 | M-A-Q | HAC | Pre-AT | 1 | Completed - Handover done | 20-Nov : It was incorrectly commenced by Network acceptance as BAU on 17th Nov, relaunched as HAC. Updated M-M-H to M-A-Q and BAU to HAC | 2017-11-17 | George | 2017-11-17 | 2017-11-20 |  | 2 | 2017-11-20 | 2017-11-20 | 2017-11-20 |  | 1 |  |  |  |  | 0 |  | 0
5HNL-20 | RFS.153 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-11-17 | ChristieThomas | 2017-11-17 | 2017-11-21 |  | 3 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | 1 |  |  |  |  | 0 |  | 0
3KGP-20 | RFS.135 | M-M-Q | BAU | Design | 1 | Completed - Handover done | 22-Nov: Handover on hold as this is a FTTC pilot SAM. | 2017-11-17 | Saranya Geetha | 2017-11-17 | 2017-11-23 |  | 5 | 2017-11-23 | 2017-11-23 | 2017-11-23 |  | 1 |  |  |  |  | 0 |  | 0
3HDB-68 | RFS.111 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-20 | Jumana.M | 2017-11-20 | 2017-11-21 |  | 2 | 2017-11-21 | 2017-11-22 | 2017-11-22 |  | 2 |  |  |  |  | 0 |  | 0
3TNI-62 | RFS.111 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-11-20 | Manjusha M | 2017-11-20 | 2017-11-21 |  | 2 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | 1 |  |  |  |  | 0 |  | 0
5WES-61 | RFS.111 | M-M-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-11-21 | Revathy A | 2017-11-21 | 2017-11-21 |  | 1 | 2017-11-21 | 2017-11-22 | 2017-11-22 |  | 2 |  |  |  |  | 0 |  | 0
3CAU-66 | RFS.125 | M-M-Q | BAU | Design | 3 | Completed - Handover done |  | 2017-11-22 | ChristieThomas | 2017-11-22 | 2017-11-22 |  | 1 | 2017-11-22 | 2017-11-23 | 2017-11-23 |  | 2 |  |  |  |  | 0 |  | 0
4FHL-63 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-11-22 | Jowharulla.M | 2017-11-22 | 2017-11-23 |  | 2 | 2017-11-23 | 2017-11-23 | 2017-11-23 |  | 1 |  |  |  |  | 0 |  | 0
5SAL-64 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done | 27-Nov: Rejected due to artefacts missing 29-Jan : NA updated that rejection was by mistake. 29-Jan : Relaunched SAM as H-A-H from M-A-H , actualized the task in APPIAN. | 2017-11-22 | SanjanaKrishnan | 2017-11-22 | 2017-11-23 |  | 2 | 2017-11-23 | 2017-11-23 | 2017-11-23 |  | 1 |  |  |  |  | 0 |  | 0
2SHA-21 | RFS.137 | M-M-H | BAU | Design | 0.1 | Completed - Handover done | 22-Nov :This SAM has been Re-commenced using the same payload. LDM has already delivered the SAM on 27th Oct, just actualizing the task in APPIAN. | 2017-11-22 | Tajinder Kaur | 2017-11-22 | 2017-11-22 |  | 1 | 2017-11-22 | 2017-11-22 | 2017-11-22 |  | 1 |  |  |  |  | 0 |  | 0
2KNS-61 | RFS.111 | M-A-H | BAU | Pre-AT | 0.1 | Completed - Handover done | 22-Nov:Duplicate address issue, Awaiting response from NA 23-Nov: Missing FTTB DDM, to be able to meet RFS Group 111 it was decided to SPLIT LOAD. It has now been launched as BAU, updated M-A-Q to M-A-H and HAC to BAU. | 2017-11-22 | ShabeenaShamsudin | 2017-11-22 | 2017-11-24 |  | 3 | 2017-11-24 | 2017-11-27 | 2017-11-27 |  | 2 |  |  |  |  | 0 |  | 0
2LIV-67 | RFS.125 | M-M-H | BAU | Design | 5 | Completed - Handover done |  | 2017-11-22 | George | 2017-11-22 | 2017-11-22 |  | 1 | 2017-11-22 | 2017-11-23 | 2017-11-23 |  | 2 |  |  |  |  | 0 |  | 0
6JDL-21 | RFS.80 | M-M-J | BAU | Post RFS | 0.5 | Completed - Handover done |  | 2017-11-22 | Saranya Geetha | 2017-11-22 | 2017-11-27 |  | 4 | 2017-11-27 | 2017-11-27 | 2017-11-27 |  | 1 |  |  |  |  | 0 |  | 0
2SEV-20 | RFS.146 | M-M-H | BAU | Design | 1 | Completed - Handover done | 28-Nov:Final validation in progress, some locations are outside SAM, Awaiting confirmation from NA. | 2017-11-23 | Arunika Joy | 2017-11-23 | 2017-11-27 |  | 3 | 2017-11-30 | 2017-11-30 | 2017-11-30 |  | 1 |  |  |  |  | 2 |  | -2
6SUB-62 | RFS.132 | M-M-H | BAU | Design | 4 | Completed - Handover done |  | 2017-11-23 | Manjusha M | 2017-11-23 | 2017-11-28 |  | 4 | 2017-11-28 | 2017-11-29 | 2017-11-29 |  | 2 |  |  |  |  | 0 |  | 0
6MLO-20 | RFS.150 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-11-23 | Jumana.M | 2017-11-23 | 2017-11-27 |  | 3 | 2017-11-27 | 2017-11-28 | 2017-11-28 |  | 2 |  |  |  |  | 0 |  | 0
4NDG-60 | RFS.127 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-23 | JadeeraKT | 2017-11-23 | 2017-11-24 |  | 2 | 2017-11-24 | 2017-11-24 | 2017-11-24 |  | 1 |  |  |  |  | 0 |  | 0
4PDP-63 | RFS.143 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-23 | ChristieThomas | 2017-11-24 | 2017-11-27 |  | 3 | 2017-11-27 | 2017-11-28 | 2017-11-28 |  | 2 |  |  |  |  | 0 |  | 0
5GLL-20 | RFS.137 | M-M-Q | BAU | Design | 1 | Completed - Handover done |  | 2017-11-23 | Goutham A S | 2017-11-23 | 2017-11-27 |  | 3 | 2017-11-27 | 2017-11-28 | 2017-11-28 |  | 2 |  |  |  |  | 0 |  | 0
2LIV-63 | RFS.118 | M-M-H | BAU | Design | 3 | Completed - Handover done | 28-Nov:Loc id needs to be created by LMS team as part of Repurposing in NAT boundary (PONSA). Awaiting LMS Response | 2017-11-24 | George | 2017-11-24 | 2017-11-29 |  | 4 | 2017-11-29 | 2017-11-29 | 2017-11-29 |  | 1 |  |  |  |  | 2 |  | -2
3MLN-61 | RFS.125 | M-M-Q | BAU | Design | 3 | Completed - Handover done |  | 2017-11-24 | SanjanaKrishnan | 2017-11-24 | 2017-11-29 |  | 4 | 2017-11-29 | 2017-11-29 | 2017-11-29 |  | 1 |  |  |  |  | 0 |  | 0
2ING-65 | RFS.129 | M-M-H | BAU | Design | 3 | Completed - Handover done |  | 2017-11-24 | Revathy A | 2017-11-24 | 2017-11-27 |  | 2 | 2017-11-27 | 2017-11-28 | 2017-11-28 |  | 2 |  |  |  |  | 0 |  | 0
6MLO-62 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-11-24 | Kavya Methil | 2017-11-24 | 2017-11-27 |  | 2 | 2017-11-27 | 2017-11-27 | 2017-11-27 |  | 1 |  |  |  |  | 0 |  | 0
6CTO-20 | RFS.133 | M-M-H | BAU | Design | 4 | Completed - Handover done | 28-Nov:2 locations outside SAM, Awaiting confirmation for Design from NA. | 2017-11-24 | JadeeraKT | 2017-11-27 | 2017-11-28 |  | 3 | 2017-11-28 | 2017-11-30 | 2017-11-30 |  | 3 |  |  |  |  | 0 |  | 0
4MRA-61 | RFS.58 | M-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-11-27 | Jowharulla.M | 2017-11-27 | 2017-11-28 |  | 2 | 2017-11-28 | 2017-11-28 | 2017-11-28 |  | 1 |  |  |  |  | 0 |  | 0
2GBE-64 | RFS.112 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 30-Nov-17 : Relaunched in APPIAN as BAU for Split Load . Updated from HAC to BAU , M-A-Q to M-A-H and will stay in group 112 30-Nov : Duplicate address issue raised with NA 01-Dec : NA provided input 01-Dec-5 locations outside and reside in in-service MPS , Awaiting LMS response. 05-Dec : LMS provided input | 2017-11-27 | Kavya Methil | 2017-11-28 | 2017-12-01 |  | 5 | 2017-12-01 | 2017-12-05 | 2017-12-05 |  | 3 |  |  |  |  | 0 |  | 0
2CHA-62 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | Rejected | 1-Dec : Critical AP team issues. | 2017-11-27 | VishnuS | 2017-11-27 | 2017-11-29 |  | 3 | 2017-11-29 | 2017-11-29 | 2017-11-29 |  | 1 | 2017-12-01 |  |  |  | 0 |  | 0
4FHL-66 | RFS.78 | M-M-H | BAU | Post RFS | 1.1 | Completed - Handover done |  | 2017-11-27 | Revathy A | 2017-11-28 | 2017-11-28 |  | 2 | 2017-11-28 | 2017-11-29 | 2017-11-29 |  | 2 |  |  |  |  | 0 |  | 0
2NEW-23 | RFS.133 | M-M-H | BAU | Design | 1 | Rejected | 29-Nov:1 Locations are outside the SAM, Awaiting NA team response 30-Nov : Input provided by NA. 1-Dec : Rejected due to Critical Design issues. 30-Nov : Relaunched to correct phase. Updated phase from Pre-AT to Design | 2017-11-27 | ChristieThomas | 2017-11-28 |  |  | -30733 |  |  |  |  | 0 | 2017-12-01 |  |  |  | 0 |  | 0
2GBE-65 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-27 | ShabeenaShamsudin | 2017-11-27 | 2017-11-29 |  | 3 | 2017-11-29 | 2017-11-29 | 2017-11-29 |  | 1 |  |  |  |  | 0 |  | 0
3KYG-65 | RFS.113 | H-A-H | BAU | Pre-AT | 3 | Completed - Handover done |  | 2017-11-27 | Reenu Treesa Peter | 2017-11-28 | 2017-11-29 |  | 3 | 2017-11-29 | 2017-11-30 | 2017-11-30 |  | 2 |  |  |  |  | 0 |  | 0
2CRR-20 | RFS.112 | M-B-H | BAU | Pre-AT | 4 | Completed - Handover done |  | 2017-11-28 | Saiju Xavier | 2017-11-28 | 2017-11-30 |  | 3 | 2017-11-30 | 2017-11-30 | 2017-11-30 |  | 1 |  |  |  |  | 0 |  | 0
2BON-61 | RFS.123 | M-M-H | BAU | Design | 3 | Completed - Handover done |  | 2017-11-29 | Goutham A S | 2017-11-29 | 2017-12-01 |  | 3 | 2017-12-01 | 2017-12-04 | 2017-12-04 |  | 2 |  |  |  |  | 0 |  | 0
5WES-65 | RFS.125 | H-M-H | BAU | Pre-AT | 4 | Completed - Handover done |  | 2017-11-29 | Jowharulla.M | 2017-11-29 | 2017-11-30 |  | 2 | 2017-11-30 | 2017-11-30 | 2017-11-30 |  | 1 |  |  |  |  | 0 |  | 0
3NBA-63 | RFS.97 | H-A-Q | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-11-30 | ShabeenaShamsudin | 2017-11-30 | 2017-12-01 |  | 2 | 2017-12-01 | 2017-12-01 | 2017-12-01 |  | 1 |  |  |  |  | 0 |  | 0
2RYD-64 | RFS.110 | H-A-Q | HAC | Pre-AT | 4 | Completed - Handover done |  | 2017-11-30 | Manjusha M | 2017-11-30 | 2017-12-04 |  | 3 | 2017-12-04 | 2017-12-04 | 2017-12-04 |  | 1 |  |  |  |  | 0 |  | 0
3KYG-69 | RFS.113 | M-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-11-30 | Revathy A | 2017-11-30 | 2017-12-05 |  | 4 | 2017-12-05 | 2017-12-05 | 2017-12-05 |  | 1 |  |  |  |  | 0 |  | 0
2RDL-62 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 01-Dec : CHANGED TO M-A-H (FROM M-A-Q) SPLIT LOAD TRAILING FTTB DDDM EXPECTED ON 15 DEC 05-Dec-17 : FTTB due 15 Dec, on hold and not split now with new RFS change | 2017-12-01 | Arunika Joy | 2017-12-01 | 2017-12-13 |  | 9 | 2017-12-13 | 2017-12-14 | 2017-12-14 |  | 2 |  | 2017-12-05 | 2017-12-13 |  | 7 |  | -7
3NAW-62 | RFS.114 | M-M-Q | HAC | Pre-AT | 0.5 | Completed - Handover done | 19-Dec : Critical Design defect | 2017-12-01 | Saiju Xavier | 2017-12-01 | 2017-12-05 |  | 3 | 2017-12-05 | 2017-12-05 | 2017-12-05 |  | 1 |  |  |  |  | 0 |  | 0
5GNG-60 | RFS.116 | M-A-H | BAU | Pre-AT | 3 | Completed - Handover done | 04-Dec:1 location is outside SAM, Awaiting NA input. | 2017-12-01 | Saranya Geetha | 2017-12-01 | 2017-12-05 |  | 3 | 2017-12-05 | 2017-12-05 | 2017-12-05 |  | 1 |  |  |  |  | 0 |  | 0
6GIR-20 | RFS.151 | M-B-H | BAU | Design | 2 | Completed - Handover done |  | 2017-12-01 | ChristieThomas | 2017-12-01 | 2017-12-04 |  | 2 | 2017-12-04 | 2017-12-04 | 2017-12-04 |  | 1 |  |  |  |  | 0 |  | 0
3MIT-62 | RFS.125 | H-M-H | BAU | Design | 1 | Completed - Handover done | 04-Dec:Location address issue , Awaiting NA input. 07-Dec : NA provided input, awaiting response from Area Planning for same location. 08-Dec : Issue fixed by Area Planning Team | 2017-12-01 | SanjanaKrishnan | 2017-12-01 | 2017-12-08 |  | 6 | 2017-12-08 | 2017-12-08 | 2017-12-08 |  | 1 |  | 2017-12-02 | 2017-12-07 |  | 4 |  | -4
2STL-64 | RFS.104 | M-M-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-01 | VishnuS | 2017-12-01 | 2017-12-04 |  | 2 | 2017-12-04 | 2017-12-04 | 2017-12-04 |  | 1 |  |  |  |  | 0 |  | 0
4EMP-02 | RFS.110 | M-B-H | BAU | Pre-AT | 0.3 | Completed - Handover done | Decided to be rejected due to Design issue, but after discussion with Telstra same payload has been recommenced no fix required. | 2017-12-01 | Kavya Methil | 2017-12-01 | 2017-12-05 |  | 3 | 2017-12-05 | 2017-12-05 | 2017-12-05 |  | 1 |  |  |  |  | 0 |  | 0
4CHD-63 | RFS.127 | M-M-H | BAU | Design | 2 | Completed - Handover done | 01-Dec : CHANGED TO M-M-H (FROM M-M-Q) AND RECOMMENCED | 2017-12-01 | ShabeenaShamsudin | 2017-12-04 | 2017-12-05 |  | 3 | 2017-12-05 | 2017-12-05 | 2017-12-06 |  | 2 |  |  |  |  | 0 |  | 0
2RDL-61 | RFS.139 | M-M-H | BAU | Design | 1 | Rejected | 11-Dec: Critical Design issues | 2017-12-04 | Reenu Treesa Peter | 2017-12-04 | 2017-12-06 |  | 3 | 2017-12-06 | 2017-12-06 | 2017-12-06 |  | 1 | 2017-12-11 |  |  |  | 0 |  | 0
4SRW-69 | RFS.149 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-12-04 | SanjanaKrishnan | 2017-12-06 | 2017-12-08 |  | 5 | 2017-12-08 | 2017-12-08 | 2017-12-08 |  | 1 |  |  |  |  | 0 |  | 0
4CHL-68 | RFS.130 | H-A-Q | HAC | Pre-AT | 3 | Completed - Handover done |  | 2017-12-04 | Goutham A S | 2017-12-04 | 2017-12-05 |  | 2 | 2017-12-05 | 2017-12-06 | 2017-12-06 |  | 2 |  |  |  |  | 0 |  | 0
2CAM-60 | RFS.139 | M-M-Q | BAU | Design | 1 | On Hold | 07-Dec:OUTSTANDING FTTB: [MPS-248] - EXPECTED ON 28 DEC | 2017-12-04 | Manjusha M | 2017-12-06 |  |  | -30738 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0
5NRW-65 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 07-Dec:4 locations outside SAM, Awaiting NA input 08-Dec: NA provided input. | 2017-12-05 | VishnuS | 2017-12-05 | 2017-12-07 |  | 3 | 2017-12-07 | 2017-12-08 | 2017-12-08 |  | 2 |  |  |  |  | 0 |  | 0
4RBN-61 | RFS.113 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-12-05 | ChristieThomas | 2017-12-05 | 2017-12-07 |  | 3 | 2017-12-07 | 2017-12-07 | 2017-12-07 |  | 1 |  |  |  |  | 0 |  | 0
4TGP-63 | RFS.135 | H-A-Q | HAC | Pre-AT | 1 | Completed - Handover done |  | 2017-12-05 | JadeeraKT | 2017-12-05 | 2017-12-06 |  | 2 | 2017-12-06 | 2017-12-06 | 2017-12-06 |  | 1 |  |  |  |  | 0 |  | 0
4CHD-60 | RFS.126 | M-B-H | BAU | Design | 3 | Completed - Handover done | 21-Dec: Critical Design Issues | 2017-12-05 | Devika Kala | 2017-12-05 | 2017-12-07 |  | 3 | 2017-12-07 | 2017-12-07 | 2017-12-07 |  | 1 | 2017-12-21 |  |  |  | 0 |  | 0
4SUR-61 | RFS.113 | M-A-Q | BAU | Post RFS | 0.1 | Rejected | 21-Dec : Design Issues | 2017-12-05 | George | 2017-12-05 | 2017-12-06 |  | 2 | 2017-12-06 | 2017-12-06 | 2017-12-06 |  | 1 | 2017-12-21 |  |  |  | 0 |  | 0
4CUR-63 | RFS.110 | M-A-H | BAU | Pre-AT | 5 | Completed - Handover done | 8-Dec:Awaiting response from NA team for 2 locations outside the SAM 13-Dec:Response received | 2017-12-06 | Jowharulla.M | 2017-12-06 | 2017-12-08 |  | 3 | 2017-12-08 | 2017-12-13 | 2017-12-13 |  | 4 |  | 2017-12-11 | 2017-12-13 |  | 3 |  | -3
4ABO-62 | RFS.135 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 14-Dec: SAM moved from HAC to BAU to allow Split Load. Updated M-A-Q to M-A-H | 2017-12-06 | S Shilpa | 2017-12-06 | 2017-12-08 |  | 3 | 2017-12-08 | 2017-12-08 | 2017-12-08 |  | 1 |  |  |  |  | 0 |  | 0
4TGP-67 | RFS.135 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-12-06 | Revathy A | 2017-12-06 | 2017-12-08 |  | 3 | 2017-12-08 | 2017-12-08 | 2017-12-08 |  | 1 |  |  |  |  | 0 |  | 0
4ASH-66 | RFS.70 | H-M-J | BAU | Post RFS | 1 | Completed - Handover done |  | 2017-12-06 | Saiju Xavier | 2017-12-06 | 2017-12-08 |  | 3 | 2017-12-08 | 2017-12-08 | 2017-12-08 |  | 1 |  |  |  |  | 0 |  | 0
3TNB-62 | RFS.135 | H-M-Q | BAU | Design | 1 | Completed - Handover done |  | 2017-12-06 | JadeeraKT | 2017-12-07 | 2017-12-11 |  | 4 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  | 1 |  |  |  |  | 0 |  | 0
3NCO-68 | RFS.126 | H-M-Q | BAU | Design | 1 | Rejected | 07-Dec: New T18 received with HFC Trailing MDUs integrated | 2017-12-06 | Arunika Joy | 2017-12-06 |  |  | -30740 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0
4LNH-62 | RFS.142 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 15-Dec : CHANGED FROM H-M-H TO H-A-H( AS IN PCC) and Design to Pre-AT | 2017-12-06 | Manjusha M | 2017-12-07 | 2017-12-11 |  | 4 | 2017-12-11 | 2017-12-12 | 2017-12-12 |  | 2 |  |  |  |  | 0 |  | 0
3SSN-62 | RFS.132 | M-M-H | BAU | Design | 4 | Completed - Handover done |  | 2017-12-06 | Manjusha M | 2017-12-06 | 2017-12-06 |  | 1 | 2017-12-06 | 2017-12-06 | 2017-12-06 |  | 1 |  |  |  |  | 0 |  | 0
3DNC-65 | RFS.70 | H-A-H | BAU | Post RFS | 0.2 | Completed - Handover done |  | 2017-12-06 | ShabeenaShamsudin | 2017-12-06 | 2017-12-07 |  | 2 | 2017-12-07 | 2017-12-07 | 2017-12-07 |  | 1 |  |  |  |  | 0 |  | 0
4ABC-61 | RFS.113 | M-M-H | BAU | Pre-AT | 0.1 | Completed - Handover done |  | 2017-12-06 | Goutham A S | 2017-12-07 | 2017-12-08 |  | 3 | 2017-12-08 | 2017-12-11 | 2017-12-11 |  | 2 |  |  |  |  | 0 |  | 0
4SLA-73 | RFS.73 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-06 | George | 2017-12-07 | 2017-12-07 |  | 2 | 2017-12-07 | 2017-12-07 | 2017-12-07 |  | 1 |  |  |  |  | 0 |  | 0
3CTA-65 | RFS.140 | M-M-H | BAU | Design | 1 | Completed - Handover done | 12-Dec : Awaiting response from NA | 2017-12-07 | Reenu Treesa Peter | 2017-12-11 | 2017-12-14 |  | 6 | 2017-12-14 | 2017-12-14 | 2017-12-14 |  | 1 |  | 2017-12-11 | 2017-12-13 |  | 3 |  | -3
2MEN-63 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-12-07 | Reenu Treesa Peter | 2017-12-07 | 2017-12-07 |  | 1 | 2017-12-07 | 2017-12-07 | 2017-12-07 |  | 1 |  |  |  |  | 0 |  | 0
4AAR-64 | RFS.63 | H-A-H | BAU | Post RFS | 0.2 | Completed - Handover done |  | 2017-12-07 | ShabeenaShamsudin | 2017-12-08 | 2017-12-11 |  | 3 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  | 1 |  |  |  |  | 0 |  | 0
2PYM-61 | RFS.116 | M-A-H | BAU | Pre-AT | 2 | Completed - Handover done |  | 2017-12-07 | George | 2017-12-08 | 2017-12-08 |  | 2 | 2017-12-08 | 2017-12-08 | 2017-12-08 |  | 1 |  |  |  |  | 0 |  | 0
4MGB-66 | RFS.95 | H-M-Q | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-07 | Devika Kala | 2017-12-08 | 2017-12-11 |  | 3 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  | 1 |  |  |  |  | 0 |  | 0
3FNT-63 | RFS.87 | M-M-H | BAU | Post RFS | 0.2 | Completed - Handover done |  | 2017-12-07 | ChristieThomas | 2017-12-08 | 2017-12-11 |  | 3 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  | 1 |  |  |  |  | 0 |  | 0
3KYG-61 | RFS.147 | M-M-H | BAU | Design | 0.1 | Completed - Handover done |  | 2017-12-07 | Jumana.M | 2017-12-11 | 2017-12-13 |  | 5 | 2017-12-13 | 2017-12-14 | 2017-12-14 |  | 2 |  |  |  |  | 0 |  | 0
2CHA-62 | RFS.112 | H-A-Q | HAC | Pre-AT | 2 | Completed - Handover done |  | 2017-12-08 | Arunika Joy | 2017-12-08 | 2017-12-12 |  | 3 | 2017-12-12 | 2017-12-12 | 2017-12-12 |  | 1 |  |  |  |  | 0 |  | 0
3DAN-61 | RFS.49 | M-A-H | BAU | Post RFS | 2.1 | Completed - Handover done |  | 2017-12-08 | Revathy A | 2017-12-08 | 2017-12-11 |  | 2 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  | 1 |  |  |  |  | 0 |  | 0
2CRR-67 | RFS.83 | H-M-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-08 | Devika Kala | 2017-12-08 | 2017-12-11 |  | 2 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  | 1 |  |  |  |  | 0 |  | 0
3RES-64 | RFS.126 | H-M-H | BAU | Design | 1 | Completed - Handover done | 12-Dec : Awaiting NA and CR has been raised by AP awaiting response. 13-Dec : NA provided input. CR has been raised by AP awaiting response. 14-Dec : NA provided input, awaiting confirmation from Telstra and AP 14-Dec:AP issue fixed, Awaiting Telstra input | 2017-12-08 | Kavya Methil | 2017-12-11 | 2017-12-19 |  | 8 | 2017-12-19 | 2017-12-19 | 2017-12-19 |  | 1 |  |  |  |  | 0 |  | 0
4FHL-68 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-11 | Goutham A S | 2017-12-11 | 2017-12-12 |  | 2 | 2017-12-12 | 2017-12-12 | 2017-12-12 |  | 1 |  |  |  |  | 0 |  | 0
3SPL-66 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-11 | Jowharulla.M | 2017-12-11 | 2017-12-12 |  | 2 | 2017-12-12 | 2017-12-12 | 2017-12-12 |  | 1 |  |  |  |  | 0 |  | 0
2SHA-60 | RFS.80 | H-A-H | BAU | Post RFS | 1.1 | On Hold | 13-Dec : DOWNSTREAM DESIGN SEEKING CLARIFICATION AND NOTIFICATION FROM TLS ON UPDATED T18 | 2017-12-11 | ChristieThomas | 2017-12-12 |  |  | -30743 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0
3CTA-60 | RFS.58 | H-A-H | BAU | Post RFS | 2 | Completed - Handover done |  | 2017-12-11 | VishnuS | 2017-12-11 | 2017-12-13 |  | 3 | 2017-12-13 | 2017-12-13 | 2017-12-13 |  | 1 |  |  |  |  | 0 |  | 0
4EMP-62 | RFS.80 | H-M-H | BAU | Post RFS | 0.1 | Completed - Handover done | 13-Dec : Awaiting response from LMS 18-Dec : LMS provided input, Design team raised query with Telstra awaiting their response. 09-Jan : Telstra provided input, awaiting response from Design team. 12-Jan: Design team provided input | 2017-12-11 | George | 2017-12-12 | 2018-01-15 |  | 23 | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | 1 |  | 2017-12-13 | 2018-01-15 |  | 21 |  | -21
4EMP-64 | RFS.58 | H-A-H | BAU | Post RFS | 0.1 | Rejected | 18-Dec : Critical Design Issues | 2017-12-11 | Revathy A | 2017-12-11 | 2017-12-12 |  | 2 | 2017-12-12 | 2017-12-12 | 2017-12-12 |  | 1 | 2017-12-18 |  |  |  | 0 |  | 0
2UND-61 | RFS.117 | H-M-Q | HAC | Pre-AT | 0.1 | Completed - Handover done |  | 2017-12-11 | SanjanaKrishnan | 2017-12-11 | 2017-12-13 |  | 3 | 2017-12-13 | 2017-12-13 | 2017-12-13 |  | 1 |  |  |  |  | 0 |  | 0
6SUB-66 | RFS.114 | M-A-H | BAU | Pre-AT | 3 | Completed - Handover done | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-12-11 | Tajinder Kaur | 2017-12-11 | 2017-12-11 |  | 1 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  | 1 |  |  |  |  | 0 |  | 0
2EPP-65 | RFS.114 | H-M-Q | HAC | Pre-AT | 0.1 | Completed - Handover done |  | 2017-12-11 | George | 2017-12-11 | 2017-12-12 |  | 2 | 2017-12-12 | 2017-12-12 | 2017-12-12 |  | 1 |  |  |  |  | 0 |  | 0
3CTA-63 | RFS.78 | H-A-H | BAU | Post RFS | 1.1 | Completed - Handover done |  | 2017-12-11 | JadeeraKT | 2017-12-12 | 2017-12-12 |  | 2 | 2017-12-12 | 2017-12-12 | 2017-12-12 |  | 1 |  |  |  |  | 0 |  | 0
4BNP-63 | RFS.83 | M-A-H | BAU | Post RFS | 0.1 | Completed - Handover done | 13-Dec: NAT Boundary mismatch issue ,Awaiting AP input 09-Jan : Area Planning team provided input. 10-Jan : Duplicate addresses found in PONSA, awaiting response from Design Team. | 2017-12-11 | Anet Jose | 2017-12-12 | 2018-01-12 |  | 22 | 2018-01-12 | 2018-01-12 | 2018-01-12 |  | 1 |  | 2017-12-13 | 2018-01-11 |  | 19 |  | -19
3BAY-67 | RFS.135 | M-M-H | BAU | Design | 1 | Rejected | 20-Dec : Critical Design defects | 2017-12-11 | Revathy A | 2017-12-13 | 2017-12-15 |  | 5 | 2017-12-15 | 2017-12-15 | 2017-12-15 |  | 1 |  |  |  |  | 0 |  | 0
3TYH-69 | RFS.114 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-12-11 | Tajinder Kaur | 2017-12-11 | 2017-12-11 |  | 1 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  | 1 |  |  |  |  | 0 |  | 0
5SAL-68 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-11 | ShabeenaShamsudin | 2017-12-11 | 2017-12-12 |  | 2 | 2017-12-12 | 2017-12-12 | 2017-12-12 |  | 1 |  |  |  |  | 0 |  | 0
4FHL-65 | RFS.122 | M-A-Q | HAC | Pre-AT | 1 | Rejected | 18-Dec : Critical Design Issues | 2017-12-11 | Saiju Xavier | 2017-12-11 | 2017-12-13 |  | 3 | 2017-12-14 | 2017-12-14 | 2017-12-14 |  | 1 | 2017-12-18 |  |  |  | 0 |  | 0
3NCO-68 | RFS.126 | H-M-Q | BAU | Design | 2 | Completed - Handover done |  | 2017-12-11 | ShabeenaShamsudin | 2017-12-12 | 2017-12-13 |  | 3 | 2017-12-13 | 2017-12-13 | 2017-12-13 |  | 1 |  |  |  |  | 0 |  | 0
2NEW-23 | RFS.133 | M-M-H | BAU | Design | 3 | Completed - Handover done | 13-Dec:Awaiting NA due to duplicate address issue 15-Dec : Design team provided input | 2017-12-11 | Goutham A S | 2017-12-13 | 2017-12-15 |  | 5 | 2017-12-15 | 2017-12-18 | 2017-12-18 |  | 2 |  |  |  |  | 0 |  | 0
2CAR-63 | RFS.116 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 12-Dec:Boundary Mismatch and 4 locations outside SAM 13-Dec : CR raised by AP to reflect the changes in PNI. ETA – 5 business days. 14-Dec : Recommenced in APPIAN as H-A-H type SAM , updated M-M-H to H-A-H and Design to Pre-AT 19-Dec: AP Team responded. | 2017-12-11 | Devika Kala | 2017-12-12 | 2017-12-13 |  | 3 | 2017-12-19 | 2017-12-19 | 2017-12-19 |  | 1 |  | 2017-12-12 | 2017-12-19 |  | 6 |  | -6
2BAN-60 | RFS.116 | M-B-H | BAU | Pre-AT | 1 | Rejected | 18-Dec : Critical Design Issues | 2017-12-11 | Revathy A | 2017-12-12 | 2017-12-12 |  | 2 | 2017-12-12 | 2017-12-12 | 2017-12-12 |  | 1 | 2017-12-18 |  |  |  | 0 |  | 0
2PEN-01 | RFS.134 | M-M-H | BAU | Design | 4.1 | Completed - Handover done |  | 2017-12-12 | JadeeraKT | 2017-12-13 | 2017-12-14 |  | 3 | 2017-12-14 | 2017-12-14 | 2017-12-14 |  | 1 |  |  |  |  | 0 |  | 0
2STL-66 | RFS.105 | M-A-Q | BAU | Post RFS | 0.1 | Completed - Handover done | 13-Dec : DOWNSTREAM DESIGN SEEKING CLARIFICATION FROM TLS FOR UPVERSIONED T18 | 2017-12-12 | SanjanaKrishnan | 2017-12-14 | 2017-12-14 |  | 3 | 2017-12-14 | 2017-12-14 | 2017-12-14 |  | 1 |  |  |  |  | 0 |  | 0
2QUA-63 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 15-Dec:Awaiting response from Design for 1 location outside the SAM 19-Dec : Awaiting confirmation from AP and Design team | 2017-12-12 | ChristieThomas | 2017-12-13 | 2017-12-15 |  | 4 | 2017-12-19 | 2017-12-19 | 2017-12-19 |  | 1 |  | 2017-12-15 | 2017-12-18 |  | 2 |  | -2
2CAR-60 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 14-Dec:Awaiting response from Design team for duplicate addresses 18-Dec: Design team raised the query with Telstra, awaiting response for the same. | 2017-12-13 | Jowharulla.M | 2017-12-13 | 2017-12-19 |  | 5 | 2017-12-19 | 2017-12-19 | 2017-12-19 |  | 1 |  | 2017-12-14 | 2017-12-18 |  | 3 |  | -3
4ALX-67 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 14-Dec: SAM moved from HAC to BAU to allow Split Load. Updated M-A-Q to M-A-H | 2017-12-13 | Manjusha M | 2017-12-13 | 2017-12-14 |  | 2 | 2017-12-14 | 2017-12-14 | 2017-12-14 |  | 1 |  |  |  |  | 0 |  | 0
3HDB-66 | RFS.115 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-12-13 | VishnuS | 2017-12-13 | 2017-12-15 |  | 3 | 2017-12-15 | 2017-12-15 | 2017-12-15 |  | 1 |  |  |  |  | 0 |  | 0
3WIR-65 | RFS.137 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-12-13 | Reenu Treesa Peter | 2017-12-14 | 2017-12-18 |  | 4 | 2017-12-18 | 2017-12-18 | 2017-12-18 |  | 1 |  |  |  |  | 0 |  | 0
5WES-63 | RFS.113 | H-M-H | BAU | Pre-AT | 1.1 | Rejected | 21-Dec : Critical AP issues | 2017-12-13 | George | 2017-12-13 | 2017-12-15 |  | 3 | 2017-12-15 | 2017-12-15 | 2017-12-15 |  | 1 | 2017-12-21 |  |  |  | 0 |  | 0
2CHA-60 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 14-Dec : SAM moved from HAC to BAU to allow load to be Split. Updated M-A-Q to M-A-H 15-Dec:Duplicate addresses. Awaiting response from Design team 19-Dec : Design team raised query with Telstra, awaiting confirmation from Telstra . Also HVMDU Issue, Awaiting Design Response 20-Dec : Response provided. | 2017-12-14 | ShabeenaShamsudin | 2017-12-14 | 2017-12-19 |  | 4 | 2017-12-19 | 2017-12-20 | 2017-12-20 |  | 2 |  | 2017-12-15 | 2017-12-20 |  | 4 |  | -4
6WMB-60 | RFS.113 | M-A-H | BAU | Pre-AT | 2 | Completed - Handover done |  | 2017-12-14 | Kavya Methil | 2017-12-14 | 2017-12-15 |  | 2 | 2017-12-15 | 2017-12-15 | 2017-12-15 |  | 1 |  |  |  |  | 0 |  | 0
5MOD-63 | RFS.97 | M-A-J | BAU | Post RFS | 2.1 | Rejected |  | 2017-12-14 | Anet Jose | 2017-12-14 | 2017-12-18 |  | 3 | 2017-12-18 | 2017-12-18 | 2017-12-18 |  | 1 | 2017-12-21 |  |  |  | 0 |  | 0
2CAS-65 | RFS.138 | M-M-H | BAU | Design | 2 | Rejected | 20-Dec : Critical Design defects | 2017-12-14 | Arunika Joy | 2017-12-14 | 2017-12-18 |  | 3 | 2017-12-18 | 2017-12-18 | 2017-12-18 |  | 1 | 2017-12-21 |  |  |  | 0 |  | 0
4TGP-68 | RFS.134 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-12-15 | Jumana.M | 2017-12-15 | 2017-12-19 |  | 3 | 2017-12-19 | 2017-12-20 | 2017-12-20 |  | 1 |  |  |  |  | 0 |  | 0
5EDW-61 | RFS.58 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done | 15-Dec:Duplicate Address, Awaiting Response from Design 19-Dec : Design team raised query with Telstra, awaiting confirmation from Telstra | 2017-12-15 | Saiju Xavier | 2017-12-15 | 2017-12-19 |  | 3 | 2017-12-19 | 2017-12-19 | 2017-12-19 |  | #REF! |  |  |  |  | 0 |  | 0
5SAL-67 | RFS.58 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-15 | Devika Kala | 2017-12-15 | 2017-12-18 |  | 2 | 2017-12-18 | 2017-12-18 | 2017-12-18 |  | 1 |  |  |  |  | 0 |  | 0
4SLA-64 | RFS.119 | M-M-H | BAU | Design | 3 | Completed - Handover done |  | 2017-12-18 | Manjusha M | 2017-12-18 | 2017-12-20 |  | 3 | 2017-12-20 | 2017-12-20 | 2017-12-20 |  | 1 |  |  |  |  | 0 |  | 0
5NRW-61 | RFS.146 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-12-19 | George | 2017-12-19 | 2017-12-22 |  | 4 | 2017-12-22 | 2017-12-22 | 2017-12-22 |  | 1 |  |  |  |  | 0 |  | 0
3RES-68 | RFS.135 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-12-19 | VishnuS | 2017-12-19 | 2017-12-21 |  | 3 | 2017-12-21 | 2017-12-21 | 2017-12-21 |  | 1 |  |  |  |  | 0 |  | 0
4ABO-65 | RFS.134 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-12-19 | Revathy A | 2017-12-19 | 2017-12-21 |  | 3 | 2017-12-21 | 2017-12-21 | 2017-12-21 |  | 1 |  |  |  |  | 0 |  | 0
4ALX-64 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-12-19 | Reenu Treesa Peter | 2017-12-19 | 2017-12-21 |  | 3 | 2017-12-21 | 2017-12-21 | 2017-12-21 |  | 1 |  |  |  |  | 0 |  | 0
3RES-67 | RFS.142 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-12-19 | Arunika Joy | 2017-12-19 | 2017-12-21 |  | 3 | 2017-12-21 | 2017-12-22 | 2017-12-22 |  | 2 |  |  |  |  | 0 |  | 0
3KYG-60 | RFS.117 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-12-19 | Goutham A S | 2017-12-19 | 2017-12-21 |  | 3 | 2017-12-21 | 2017-12-22 | 2017-12-22 |  | 2 |  |  |  |  | 0 |  | 0
3KYG-62 | RFS.117 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2017-12-19 | JadeeraKT | 2017-12-19 | 2017-12-21 |  | 3 | 2017-12-21 | 2017-12-22 | 2017-12-22 |  | 2 |  |  |  |  | 0 |  | 0
3BAY-71 | RFS.135 | M-M-H | BAU | Design | 1 | Rejected | 04-Jan: Rejected due to Design and Area Planning issues | 2017-12-19 | ShabeenaShamsudin | 2017-12-19 | 2017-12-21 |  | 3 | 2017-12-21 | 2017-12-21 | 2017-12-21 |  | 1 | 2018-01-04 |  |  |  | 0 |  | 0
2CAM-62 | RFS.142 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-12-19 | ChristieThomas | 2017-12-19 | 2017-12-21 |  | 3 | 2017-12-21 | 2017-12-21 | 2017-12-21 |  | 1 |  |  |  |  | 0 |  | 0
3DRP-61 | RFS.63 | M-A-H | BAU | Post RFS | 1.1 | Rejected | 08-Jan : Rejected due to Design issues | 2017-12-20 | Saiju Xavier | 2017-12-20 | 2017-12-22 |  | 3 | 2017-12-22 | 2017-12-22 | 2017-12-22 |  | 1 | 2018-01-08 |  |  |  | 0 |  | 0
4CHP-64 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2017-12-20 | Manjusha M | 2017-12-20 | 2017-12-21 |  | 2 | 2017-12-21 | 2017-12-22 | 2017-12-22 |  | 2 |  |  |  |  | 0 |  | 0
3BLB-65 | RFS.123 | H-M-H | BAU | Pre-AT | 0.1 | Completed - Handover done |  | 2017-12-20 | Jowharulla.M | 2017-12-20 | 2017-12-22 |  | 3 | 2017-12-22 | 2017-12-22 | 2017-12-22 |  | 1 |  |  |  |  | 0 |  | 0
2NSY-64 | RFS.83 | H-A-H | BAU | Post RFS | 0.1 | Rejected | 22-Dec: Repurposed cases in FAB, awaiting Telstra Input 08-Jan: Rejected due to TVT and LDM critical issues. | 2017-12-21 | VishnuS | 2017-12-21 |  |  | -30751 |  |  |  |  | 0 | 2018-01-08 |  |  |  | 0 |  | 0
5HNL-61 | RFS.118 | H-M-H | BAU | Pre-AT | 0.2 | Completed - Handover done |  | 2017-12-21 | Revathy A | 2017-12-21 | 2017-12-26 |  | 2 | 2017-12-26 | 2017-12-26 | 2017-12-26 |  | 0 |  |  |  |  | 0 |  | 0
5HNL-65 | RFS.139 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2017-12-21 | ShabeenaShamsudin | 2017-12-22 | 2017-12-26 |  | 2 | 2017-12-26 | 2017-12-26 | 2017-12-26 |  | 0 |  |  |  |  | 0 |  | 0
4BLH-62 | RFS.123 | M-B-H | BAU | Design | 1 | Completed - Handover done |  | 2017-12-23 | Manjusha M | 2017-12-26 | 2017-12-27 |  | 1 | 2017-12-27 | 2017-12-27 | 2017-12-27 |  | 1 |  |  |  |  | 0 |  | 0
2HUR-65 | RFS.115 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done | Sam processing was completed with Design payload.Actualized the Pre AT Payload | 2017-12-20 | Anet Jose | 2017-12-20 | 2017-12-20 |  | 1 | 2017-12-20 | 2017-12-20 | 2017-12-20 |  | 1 |  |  |  |  | 0 |  | 0
4TGP-65 | RFS.135 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2018-01-02 | Revathy A | 2018-01-02 | 2018-01-04 |  | 3 | 2018-01-04 | 2018-01-04 | 2018-01-04 |  | 1 |  |  |  |  | 0 |  | 0
2CAM-61 | RFS.118 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 03-Jan: Awaiting AP input for locations outside SAM 09-Jan: Area Planning awaiting stakeholder signoff ,once they have signed off - the boundary changes will be implemented in PNI. | 2018-01-03 | SanjanaKrishnan | 2018-01-03 | 2018-01-16 |  | 10 | 2018-01-16 | 2018-01-17 | 2018-01-17 |  | 2 |  | 2018-01-03 | 2018-01-16 |  | 10 |  | -10
2FRE-62 | RFS.119 | M-M-H | BAU | Pre-AT | 0.2 | Completed - Handover done |  | 2018-01-02 | ShabeenaShamsudin | 2018-01-02 | 2018-01-04 |  | 3 | 2018-01-04 | 2018-01-04 | 2018-01-04 |  | 1 |  |  |  |  | 0 |  | 0
4SRW-60 | RFS.120 | M-M-H | BAU | Pre-AT | 0.1 | Rejected | 11-Jan-18:Critical issues raised by AP team | 2018-01-02 | George | 2018-01-02 | 2018-01-04 |  | 3 | 2018-01-04 | 2018-01-04 | 2018-01-04 |  | 1 | 2018-01-11 |  |  |  | 0 |  | 0
2RDL-60 | RFS.142 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-02 | Arunika Joy | 2018-01-02 | 2018-01-04 |  | 3 | 2018-01-05 | 2018-01-05 | 2018-01-05 |  | 1 |  |  |  |  | 0 |  | 0
4MOG-22 | RFS.134 | M-B-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-02 | Jumana.M | 2018-01-02 | 2018-01-03 |  | 2 | 2018-01-03 | 2018-01-03 | 2018-01-03 |  | 1 |  |  |  |  | 0 |  | 0
3BLB-68 | RFS.144 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-02 | JadeeraKT | 2018-01-02 | 2018-01-05 |  | 4 | 2018-01-05 | 2018-01-05 | 2018-01-05 |  | 1 |  |  |  |  | 0 |  | 0
2NEW-61 | RFS.143 | M-M-H | BAU | Design | 1 | Completed - Handover done | 02-Jan: 2 Locations outside SAM due to boundary mismatch, Awaiting AP response. 09-Jan: AP raised multiple critical issues awaiting triage response to proceed with the SAM. 15-Jan : Resumed in APPIAN. Location issue not yet fixed, reminder sent to AP team again. 16-Jan : CR504318 raised by AP team , awaiting stakeholders approval. 1-Feb: Boundary issue Resolved | 2018-01-02 | ChristieThomas | 2018-01-02 | 2018-02-01 |  | 22 | 2018-02-01 | 2018-02-01 | 2018-02-01 |  | 1 |  | 2018-01-02 | 2018-02-01 |  | 22 |  | -22
2MEN-61 | RFS.137 | M-M-H | BAU | Design | 1 | Completed - Handover done | 12-Jan: Decided to be rejected due to critical design issues 02-Feb : TLS response validated , good to load. Resumed in APPIAN | 2018-01-03 | Jowharulla.M | 2018-01-03 | 2018-01-09 |  | 5 | 2018-01-09 | 2018-01-09 | 2018-01-09 |  | 1 |  |  |  |  | 0 |  | 0
5GLL-20 | RFS.137 | M-B-H | BAU | Design | 4 | Completed - Handover done | 12-Jan : 5GLL-20 has been changed from M-M-Q to M-B-H. All the checks conducted on version 4 of FDDD are correct and valid. Actualised the task in APPIAN. | 2018-01-03 | Goutham A S | 2018-01-03 | 2018-01-05 |  | 3 | 2018-01-05 | 2018-01-05 | 2018-01-05 |  | 1 |  |  |  |  | 0 |  | 0
4SLA-62 | RFS.99 | H-M-H | BAU | Pre-AT | 0.1 | Completed - Handover done |  | 2018-01-03 | Saiju Xavier | 2018-01-03 | 2018-01-05 |  | 3 | 2018-01-05 | 2018-01-08 | 2018-01-08 |  | 2 |  |  |  |  | 0 |  | 0
3DNC-66 | RFS.0 | M-M-H | BAU | Design | 1 | Completed - Handover done | 24-Jan : Recommenced as M-M-H from H-M-H. No new payload , NA suggested to actulaise the task. | 2018-01-03 | Jumana.M | 2018-01-04 | 2018-01-05 |  | 3 | 2018-01-05 | 2018-01-05 | 2018-01-05 |  | 1 |  |  |  |  | 0 |  | 0
2QUA-64 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 17-Jan: OUTSTANDING FTTB DDDM MPS-063 - ETA: 25/01 29-Jan : Review already completed for version 1 and delivered on 9th Jan. Acualized the task a suggested by NA team. | 2018-01-05 | ShabeenaShamsudin | 2018-01-05 | 2018-01-09 |  | 3 | 2018-01-09 | 2018-01-09 | 2018-01-09 |  | 1 |  | 2018-01-17 | 2018-01-29 |  | 8 |  | -8
4RBN-60 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2018-01-05 | Revathy A | 2018-01-05 | 2018-01-09 |  | 3 | 2018-01-09 | 2018-01-09 | 2018-01-09 |  | 1 |  |  |  |  | 0 |  | 0
2QUA-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | Rejected | 09-Jan:1 location outside SAM,Awaiting AP Response 11-Jan:Critical issues raised by Design team | 2018-01-05 | SanjanaKrishnan | 2018-01-05 | 2018-01-09 |  | 3 | 2018-01-09 |  |  |  | -30761 | 2018-01-11 |  |  |  | 0 |  | 0
2WRO-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2018-01-05 | George | 2018-01-05 | 2018-01-09 |  | 3 | 2018-01-09 | 2018-01-10 | 2018-01-10 |  | 2 |  |  |  |  | 0 |  | 0
5GLL-62 | RFS.141 | M-M-H | BAU | Design | 2 | Completed - Handover done | 10-Jan: One Location is outside the SAM, Awaiting action from AP team. 15-Jan : Boundary issue fixed by Area Planning. | 2018-01-05 | Goutham A S | 2018-01-09 | 2018-01-10 |  | 4 | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | 1 |  | 2018-01-10 | 2018-01-15 |  | 4 |  | -4
3DAD-64 | RFS.128 | M-M-H | BAU | Design | 4 | Completed - Handover done |  | 2018-01-05 | Reenu Treesa Peter | 2018-01-09 | 2018-01-12 |  | 6 | 2018-01-12 | 2018-01-12 | 2018-01-12 |  | 1 |  |  |  |  | 0 |  | 0
2GBE-62 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2018-01-05 | JadeeraKT | 2018-01-08 | 2018-01-10 |  | 4 | 2018-01-10 | 2018-01-10 | 2018-01-10 |  | 1 |  |  |  |  | 0 |  | 0
3RES-70 | RFS.118 | M-M-H | BAU | Design | 0.1 | Completed - Handover done |  | 2018-01-05 | Arunika Joy | 2018-01-08 | 2018-01-10 |  | 4 | 2018-01-10 | 2018-01-10 | 2018-01-10 |  | 1 |  |  |  |  | 0 |  | 0
2PET-66 | RFS.117 | M-M-H | BAU | Design | 2 | Rejected | 10-Jan : Outstanding FTTB DDDM. | 2018-01-05 | ChristieThomas | 2018-01-08 | 2018-01-08 |  | 2 | 2018-01-08 | 2018-01-08 | 2018-01-08 |  | 1 | 2018-01-10 |  |  |  | 0 |  | 0
2PEN-61 | RFS.120 | M-M-H | BAU | Design | 2 | Completed - Handover done |  | 2018-01-05 | Anet Jose | 2018-01-08 | 2018-01-09 |  | 3 | 2018-01-09 | 2018-01-10 | 2018-01-10 |  | 2
2PET-62 | RFS.115 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done | Sam processing was completed with Design payload.Actualized the Pre AT Payload for same version. | 2017-12-20 | Anet Jose | 2017-12-20 | 2017-12-20 |  | 1 | 2017-12-20 | 2017-12-20 | 2017-12-20 |  | 1
3BLB-60 | RFS.117 | M-M-H | BAU | Design | 1 | Rejected | 15-Jan : DESG issues | 2018-01-08 | Saranya Geetha | 2018-01-08 | 2018-01-10 |  | 3 | 2018-01-10 | 2018-01-10 | 2018-01-10 |  | 1 |  | 2018-01-15
3DAN-61 | RFS.49 | M-A-H | BAU | Post RFS | 2.1 | Completed - Handover done | 09-Jan: Loc ids for 2 locations needs to be created, Awaiting LMS response | 2018-01-08 | Devika Kala | 2018-01-08 | 2018-01-10 |  | 3 | 2018-01-10 | 2018-01-10 | 2018-01-10 |  | 1
5SAL-65 | RFS.78 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-08 | Goutham A S | 2018-01-08 | 2018-01-09 |  | 2 | 2018-01-09 | 2018-01-09 | 2018-01-09 |  | 1
2CRR-66 | RFS.118 | M-M-H | BAU | Pre-AT | 0.1 | Completed - Handover done | 8-Jan : This is getting tracked outside APPIAN. 10-Jan : One Dummy location is in Inservice area, Awaiting valid LOC ID from LMS 17-Jan:Address validation task launced in APPIAN | 2018-01-08 | Saiju Xavier | 2018-01-08 | 2018-01-12 |  | 5 | 2018-01-12 | 2018-01-12 | 2018-01-12 |  | 1
4DRR-62 | RFS.57 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-09 | Manjusha M | 2018-01-09 | 2018-01-09 |  | 1 | 2018-01-09 | 2018-01-09 | 2018-01-09 |  | 1
3DNC-62 | RFS.79 | H-A-H | BAU | Post RFS | 0.1 | Rejected | 09-Jan:IAB Repurpose cases encountered in FAB, Awaiting Response from Design Team. 11-Jan:Rejected due to Critical issues raised by Design and Location Team. | 2018-01-09 | Eldhose Joy | 2018-01-09 |  |  | -30761 |  |  |  |  | 0 | 2018-01-11
2HUR-64 | RFS.120 | M-M-H | BAU | Design | 2 | Completed - Handover done |  | 2018-01-09 | Revathy A | 2018-01-10 | 2018-01-11 |  | 3 | 2018-01-11 | 2018-01-11 | 2018-01-11 |  | 1
4NDG-61 | RFS.143 | M-M-H | BAU | Design | 1 | Completed - Handover done | 11-Jan : Partial_Onsa-1 LOC ID needs to be created in NAT boundary , awaiting LMS response. And duplicate addresses found, awaiting design team response. 12-Jan : LMS and design team provided response. 12-Jan : Raised issue with LMS FTTB team to create LocID for tempID and also with Design team for the location outside the SAM. 15-Jan : LMS FTTB team input. Design team requires further information on the same query again. Details provided by LDM team. 16-Jan : Design team replied for the query raised on location outside the SAM. | 2018-01-10 | Jowharulla.M | 2018-01-10 | 2018-01-16 |  | 5 | 2018-01-16 | 2018-01-16 | 2018-01-16 |  | 1
6MLO-63 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-10 | Manjusha M | 2018-01-10 | 2018-01-11 |  | 2 | 2018-01-11 | 2018-01-11 | 2018-01-11 |  | 1
5HNL-63 | RFS.119 | H-M-H | BAU | Pre-AT | 0.1 | Completed - Handover done |  | 2018-01-10 | ShabeenaShamsudin | 2018-01-10 | 2018-01-11 |  | 2 | 2018-01-11 | 2018-01-11 | 2018-01-11 |  | 1
3BAY-67 | RFS.135 | M-M-H | BAU | Design | 4 | Rejected | 17-Jan : Critical design issues | 2018-01-11 | ChristieThomas | 2018-01-11 | 2018-01-15 |  | 3 | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | 1 | 2018-01-17
3KGP-64 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done | 12-Jan : 1 location outside the SAM, raised query with Design Team. 16-Jan:Awaiting telstra response 19-Jan : Tesltra provided input to change the address, but it caused duplicate issue. Again raised with Design team. 30-Jan:Response recived | 2018-01-11 | Saiju Xavier | 2018-01-11 | 2018-01-31 |  | 14 | 2018-01-31 | 2018-01-31 | 2018-01-31 |  | 1 |  | 2018-01-12 | 2018-01-30
3TYH-61 | RFS.118 | M-M-H | BAU | Pre-AT | 0.2 | Completed - Handover done |  | 2018-01-11 | JadeeraKT | 2018-01-11 | 2018-01-15 |  | 3 | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | 1
4ARU-61 | RFS.123 | M-M-H | BAU | Design | 2 | Completed - Handover done | 15-Jan : In SAM 4ARU-61, One location found outside the SAM boundary. Awaiting Design response. 16-Jan : Design team provided input. | 2018-01-12 | Arunika Joy | 2018-01-12 | 2018-01-16 |  | 3 | 2018-01-17 | 2018-01-17 | 2018-01-17 |  | 1 |  | 2018-01-15 | 2018-01-17
3CTA-64 | RFS.150 | M-M-H | BAU | Design | 4 | Rejected | 1128 dummy locations are present in SL for address matching 18-Jan : 3 Active SLs outside SAM, Awaiting Design team response 22-Jan : Critical Area Planning issues | 2018-01-12 | SanjanaKrishnan | 2018-01-12 | 2018-01-17 |  | 4 |  |  |  |  | 0 | 2018-01-22 | 2018-01-18
4TGP-64 | RFS.145 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-13 | Goutham A S | 2018-01-13 | 2018-01-16 |  | 2 | 2018-01-16 | 2018-01-17 | 2018-01-17 |  | 2
3RES-66 | RFS.146 | M-M-H | BAU | Design | 1 | Completed - Handover done | 15-Jan : 1 location outside the SAM due to boundary mismatch, raised query with AP Team. 16-Jan : AP team provided input. | 2018-01-12 | Revathy A | 2018-01-12 | 2018-01-16 |  | 3 | 2018-01-16 | 2018-01-16 | 2018-01-16 |  | 1
3RES-72 | RFS.145 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-12 | Manjusha M | 2018-01-12 | 2018-01-15 |  | 2 | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | 1
5SAL-69 | RFS.87 | H-A-Q | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-12 | ShabeenaShamsudin | 2018-01-12 | 2018-01-15 |  | 2 | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | 1
2ENG-62 | RFS.123 | H-M-H | BAU | Pre-AT | 0.1 | Completed - Handover done |  | 2018-01-15 | Saiju Xavier | 2018-01-15 | 2018-01-16 |  | 2 | 2018-01-16 | 2018-01-16 | 2018-01-16 |  | 1
5NRW-63 | RFS.114 | M-A-H | BAU | Pre-AT | 2 | Completed - Handover done | 17-Jan : 7 Active SLs outside SAM, Awaiting response from Area planning team 1-Feb:Boundary mismatch resolved | 2018-01-15 | Revathy A | 2018-01-15 | 2018-01-17 |  | 3 | 2018-02-01 | 2018-02-01 | 2018-02-01 |  | 1 |  | 2018-01-17 | 2018-02-01
3DRP-60 | RFS.59 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-15 | JadeeraKT | 2018-01-16 | 2018-01-17 |  | 3 | 2018-01-17 | 2018-01-17 | 2018-01-17 |  | 1
2PET-66 | RFS.119 | M-A-H | BAU | Pre-AT | 3 | Completed - Handover done | 19-Jan : FTTx Design issues | 2018-01-15 | Eldhose Joy | 2018-01-15 | 2018-01-17 |  | 3 | 2018-01-17 | 2018-01-17 | 2018-01-17 |  | 1
3HDB-65 | RFS.123 | H-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2018-01-15 | George | 2018-01-15 | 2018-01-16 |  | 2 | 2018-01-16 | 2018-01-17 | 2018-01-17 |  | 2
3BAY-71 | RFS.135 | M-M-H | BAU | Design | 3 | Completed - Handover done |  | 2018-01-15 | ShabeenaShamsudin | 2018-01-16 | 2018-01-17 |  | 3 | 2018-01-17 | 2018-01-17 | 2018-01-17 |  | 1
2CAR-62 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done | 17-Jan : Resumed in APPIAN 18-Jan: Awaiting respoce from design team for one location,which is outside the SAM | 2018-01-17 | Manjusha M | 2018-01-17 | 2018-01-19 |  | 3 | 2018-01-19 | 2018-01-19 | 2018-01-19 |  | 1 |  | 2018-01-18 | 2018-01-19
3WIR-66 | RFS.150 | M-M-Q | BAU | Design | 1 | Completed - Handover done | 16-Jan : Resumed in APPIAN | 2018-01-16 | ChristieThomas | 2018-01-16 | 2018-01-17 |  | 2 | 2018-01-17 | 2018-01-17 | 2018-01-17 |  | 1 |  | 2018-01-15 | 2018-01-16
2BAN-60 | RFS.119 | M-B-H | BAU | Pre-AT | 1.1 | Completed - Handover done |  | 2018-01-17 | Saiju Xavier | 2018-01-17 | 2018-01-17 |  | 1 | 2018-01-17 | 2018-01-17 | 2018-01-17 |  | 1
4CHL-61 | RFS.130 | M-A-H | BAU | Pre-AT | 2 | On Hold | 22-Jan : Outstanding FTTB DDDM | 2018-01-18 | George | 2018-01-18 | 2018-01-22 |  | 3 |  |  |  |  | 0 |  | 2018-01-22
2HUR-61 | RFS.133 | M-M-H | BAU | Design | 3 | Completed - Handover done |  | 2018-01-18 | Jumana.M | 2018-01-18 | 2018-01-22 |  | 3 | 2018-01-22 | 2018-01-23 | 2018-01-23 |  | 2
4BEE-64 | RFS.122 | M-A-H | BAU | Pre-AT | 1 | On Hold | 19-Jan: Boundary issues reported to AP team | 2018-01-18 | ShabeenaShamsudin | 2018-01-18 | 2018-01-25 |  | 6 |  |  |  |  | 0 |  | 2018-01-19
2PYM-65 | RFS.118 | M-A-H | BAU | Pre-AT | 6 | Completed - Handover done |  | 2018-01-17 | Saiju Xavier | 2018-01-18 | 2018-01-19 |  | 3 | 2018-01-19 | 2018-01-19 | 2018-01-19 |  | 1
2PNN-63 | RFS.125 | H-M-H | BAU | Pre-AT | 0.1 | Completed - Handover done |  | 2018-01-19 | ChristieThomas | 2018-01-19 | 2018-01-23 |  | 3 | 2018-01-23 | 2018-01-23 | 2018-01-23 |  | 1
4BEE-63 | RFS.146 | M-M-H | BAU | Design | 1 | On Hold | 22-Jan: 3 valid locations are outside of SAM due to boundary mismatch | 2018-01-19 | Goutham A S | 2018-01-19 |  |  | -30769 |  |  |  |  | 0 |  | 2018-01-22
3TNB-64 | RFS.144 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-19 | Revathy A | 2018-01-19 | 2018-01-23 |  | 3 | 2018-01-23 | 2018-01-23 | 2018-01-23 |  | 1
3TNB-61 | RFS.144 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-19 | Eldhose Joy | 2018-01-19 | 2018-01-23 |  | 3 | 2018-01-23 | 2018-01-23 | 2018-01-23 |  | 1
2QUA-65 | RFS.121 | M-A-H | BAU | Pre-AT | 1 | On Hold | 22-Jan:20 valid Locations are outside the SAM due to boundary mismatch | 2018-01-22 | Manjusha M | 2018-01-22 | 2018-01-24 |  | 3 |  |  |  |  | 0 |  | 2018-01-24
3RES-60 | RFS.146 | M-M-H | BAU | Design | 1 | On Hold | 23-Jan:Appian task paused, DFN needs to be updated by Telstra | 2018-01-22 |  |  |  |  | -30770 |  |  |  |  | 0 |  | 2018-01-23
3SOA-62 | RFS.85 | H-A-Q | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-23 | JadeeraKT | 2018-01-22 | 2018-01-23 |  | 1 | 2018-01-23 | 2018-01-23 | 2018-01-23 |  | 1
3NBA-71 | RFS.70 | H-A-Q | BAU | Post RFS | 0.1 | On Hold | 23-Jan : Boundary mismatch , awaiting response from AP 24-Jan : Awaiting Telstra response for repursposed cases. 29-Jan: Boundary issue fixed. | 2018-01-23 | George | 2018-01-23 |  |  | -30771 |  |  |  |  | 0 |  | 2018-01-23
4CHL-66 | RFS.142 | M-M-H | BAU | Design | 1 | Rejected | 24-Jan:one Location is outise the SAM due to boundary mismatch | 2018-01-23 | Revathy A | 2018-01-23 | 2018-01-29 |  | 4 |  |  |  |  | 0 | 2018-01-31 | 2018-01-24
3SSN-65 | RFS.137 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-23 | Saiju Xavier | 2018-01-23 | 2018-01-25 |  | 3 | 2018-01-25 | 2018-01-25 | 2018-01-25 |  | 1
4ABO-66 | RFS.138 | H-A-H | BAU | Pre-AT | 2 | On Hold | 23-Jan: 10 valid locations are outside of SAM due to boundary mismatch | 2018-01-23 | ShabeenaShamsudin | 2018-01-23 |  |  | -30771 |  |  |  |  | 0 |  | 2018-01-23
3SCO-68 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-23 | Arunika Joy | 2018-01-23 | 2018-01-24 |  | 2 | 2018-01-24 | 2018-01-24 | 2018-01-24 |  | 1
4FHL-65 | RFS.122 | M-A-H | BAU | Pre-AT | 3 | Completed - Handover done | 23-Jan : Recommence as BAU SAM. Update M-A-Q to M-A-H | 2018-01-23 | Anet Jose | 2018-01-23 | 2018-01-24 |  | 2 | 2018-01-24 | 2018-01-24 | 2018-01-24 |  | 1
3RES-63 | RFS.150 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-23 | ChristieThomas | 2018-01-23 | 2018-01-25 |  | 3 | 2018-01-25 | 2018-01-25 | 2018-01-25 |  | 1
2EPP-61 | RFS.124 | H-M-H | BAU | Pre-AT | 0.1 | Completed - Handover done |  | 2018-01-23 | Jumana.M | 2018-01-23 | 2018-01-25 |  | 3 | 2018-01-25 | 2018-01-25 | 2018-01-25 |  | 1
4SLA-64 | RFS.125 | M-M-H | BAU | Pre-AT | 0.1 | On Hold | 30-Jan: Repurposing cases and Duplicate address update in FDDD stage not incorporated in IAB stage.Awaiting Telstra response. | 2018-01-25 | Goutham A S | 2018-01-25 | 2018-01-29 |  | 2 |  |  |  |  | 0 |  | 2018-01-30
3HGT-60 | RFS.63 | M-A-J | BAU | Post RFS | 2.1 | Completed - Handover done | 25-Jan : 4 locations that needs to be created is in inservice MPS | 2018-01-25 | Arunika Joy | 2018-01-25 | 2018-01-30 |  | 3 | 2018-01-30 | 2018-01-30 | 2018-01-30 |  | 1 |  | 2018-01-25 | 2018-01-30
3BNT-62 | RFS.123 | H-A-H | BAU | Pre-AT | 1 | On Hold | 25-Jan: 15 locations areoutside the SAM due to boundary mismatch.Awaiting AP response | 2018-01-25 | George | 2018-01-25 |  |  | -30773 |  |  |  |  | 0 |  | 2018-01-25
3BLB-60 | RFS.146 | M-A-H | BAU | Pre-AT | 3 | Completed - Handover done |  | 2018-01-25 | Manjusha M | 2018-01-25 | 2018-01-29 |  | 2 | 2018-01-29 | 2018-01-29 | 2018-01-29 |  | 1
3NBA-70 | RFS.144 | M-M-H | BAU | Design | 3 | On Hold | 31-Jan : Invalid Unit number and Location outside SAM, awaiting response from Design Team | 2018-01-25 | Revathy A | 2018-01-29 |  |  | -30773 |  |  |  |  | 0 |  | 2018-01-31
4ABC-62 | RFS.115 | M-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-25 | JadeeraKT | 2018-01-25 | 2018-01-30 |  | 3 | 2018-01-30 | 2018-01-30 | 2018-01-30 |  | 1
2QUA-62 | RFS.118 | M-A-H | BAU | Pre-AT | 3 | On Hold | 25-Jan: 1 location is outside the SAM due to boundary mismatch | 2018-01-25 | Revathy A | 2018-01-25 | 2018-01-25 |  | 1 |  |  |  |  | 0 |  | 2018-01-25
4LNH-60 | RFS.130 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2018-01-25 | Manjusha M | 2018-01-25 | 2018-01-30 |  | 3 | 2018-01-30 | 2018-01-31 | 2018-01-31 |  | 2
3CTA-64 | RFS.150 | M-M-H | BAU | Design | 5 | Completed - Handover done | 29-Jan:1 location is outside the SAM with design attached. Awating Design team response 31-Jan: Response received | 2018-01-25 | SanjanaKrishnan | 2018-01-25 | 2018-01-31 |  | 4 | 2018-01-31 | 2018-01-31 | 2018-01-31 |  | 1 |  | 2018-01-29 | 2018-01-31
2ENG-60 | RFS.78 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-01-25 | ShabeenaShamsudin | 2018-01-25 | 2018-01-29 |  | 2 | 2018-01-29 | 2018-01-29 | 2018-01-29 |  | 1
3KGP-66 | RFS.140 | H-A-H | BAU | Pre-AT | 1 | On Hold | 29-Jan:1 location is outside the SAM due to boundary mismatch | 2018-01-29 | Anet Jose | 2018-01-29 | 2018-01-30 |  | 2 |  |  |  |  | 0 |  | 2018-01-30
2CHA-61 | RFS.121 | M-A-H | BAU | Pre-AT | 1 | On Hold | 31-Jan:NAT boundary is not loaded in PNI boundary.Awaiting AP response | 2018-01-29 | Manjusha M | 2018-01-29 | 2018-02-01 |  | 4 |  |  |  |  | 0 |  | 2018-02-01
3BAY-67 | RFS.135 | M-M-H | BAU | Design | 5 | Completed - Handover done |  | 2018-01-29 | Jowharulla.M | 2018-01-30 | 2018-02-01 |  | 4 | 2018-02-01 | 2018-02-01 | 2018-02-01 |  | 1
4ABO-69 | RFS.143 | H-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-29 | Saiju Xavier | 2018-01-30 | 2018-02-01 |  | 4 | 2018-02-01 | 2018-02-01 | 2018-02-01 |  | 1
3TNB-60 | RFS.143 | M-M-H | BAU | Design | 1 | Completed - Handover done |  | 2018-01-30 | ShabeenaShamsudin | 2018-01-30 | 2018-02-01 |  | 3 | 2018-02-01 | 2018-02-01 | 2018-02-01 |  | 1
2ENG-61 | RFS.74 | H-A-H | BAU | Post RFS | 0.2 | Completed - Handover done |  | 2018-01-31 | George | 2018-01-31 | 2018-01-31 |  | 1 | 2018-01-31 | 2018-01-31 | 2018-01-31 |  | 1
3KYG-67 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | Completed - Handover done |  | 2018-02-01 | Eldhose Joy | 2018-02-01 | 2018-02-02 |  | 2 | 2018-02-02 | 2018-02-05 | 2018-02-05 |  | 2
3SCO-64 | RFS.77 | H-A-H | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-02-01 | George | 2018-02-01 | 2018-02-01 |  | 1 | 2018-02-01 | 2018-02-01 | 2018-02-01 |  | 1
2STL-60 | RFS.104 | H-M-Q | BAU | Post RFS | 0.1 | Completed - Handover done |  | 2018-02-01 | Saiju Xavier | 2018-02-01 | 2018-02-02 |  | 2 | 2018-02-02 | 2018-02-02 | 2018-02-02 |  | 1
4CHL-63 | RFS.137 | M-M-H | BAU | Design | 1 | On Hold | 02-Feb : Location outside SAM, awaiting Design and AP team response. | 2018-02-02 | Reenu Treesa Peter | 2018-02-02 |  |  | -30778 |  |  |  |  | 0 |  | 2018-02-02
5GUG-65 | RFS.58 | H-A-H | BAU | Post RFS | 0.1 | In Queue - FBR Completed |  | 2018-02-06 | George | 2018-02-06 |  |  | -30780 |  |  |  |  | 0
2EDG-63 | RFS.56 | H-A-H | BAU | Post RFS | 0.3 | In Queue - FBR Completed |  | 2018-02-06 | Arunika Joy | 2018-02-06 |  |  | -30780 |  |  |  |  | 0
4EMP-64 | RFS.58 | H-A-H | BAU | Post RFS | 0.2 | In Queue - FBR Completed |  | 2018-02-06 | ShabeenaShamsudin | 2018-02-06 |  |  | -30780 |  |  |  |  | 0
2WET-62 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 | In Queue - FBR Completed |  | 2018-02-06 | Goutham A S | 2018-02-06 |  |  | -30780 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0
Formulas:
Cycle Time (FBR & Temp ID) = NETWORKDAYS([T18 Input date],[End date],Holiday!$C2:C80)
Cycle Time (Address Alignment) = NETWORKDAYS([Address Alignment and Validations],[Actual LMS Handover Date],Holiday!$C2:C80)
Cycle Time (Address Alignment) = NETWORKDAYS([Address Alignment and Validations, row below],[Actual LMS Handover Date, row below],Holiday!$C2:C80)
LDM Waiting Time (External waiting time) = NETWORKDAYS([On Hold Start Date],[Recommencement Date],Holiday!$C2:C80)

## DESG T18 Allocation
Updated by : | Nisha | Updated on : | 2018-02-05 |  |  |  |  | Perform Checks [PC] or GDSS Load |  |  |  |  | PNI Load[GML] |  |  |  |  | Handover to NSO/ DSG? | [6 empty] | Internal Tracking
SAM Name | RFS Group | SAM Code | Program | Gate | Version | Overall Status | T18 Input Date | Assigned To [PC] | Start Date [PC] | End Date [PC] | Cycle Time [PC] | Comments | Assigned To [GML] | Input Date [GML] | PNI Load Start Date | PNI Load End Date | Cycle Time [GML] | Actual Handover Date | Comments | Rejection Date | On Hold Start Date [PC] | Recommencement Date[PC] | On Hold Start Date [GML] | Recommencement Date [GML] | Triage Waiting Time | PC Queue Time (Internal waiting time) | PC Waiting Time (External waiting time) | GML Queue Time (Internal waiting time) | GML Waiting Time (External waiting time) | DESG Overall Cycle Time | DESG Overall Processing Time | Entry type | Sr.No | Names | Droddowns Validations
2BON-62 |  | H-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-01 | Mahalakshmi | 2017-05-01 | 2017-05-03 | 2 |  | Mahalakshmi | 2017-05-03 | 2017-05-03 | 2017-05-03 | 1 | 2017-05-03 | [6 empty] | 1 | -1 | 0 | 0 | 0 | 2 | 2 |  | 1 | Sanjo Lopez | Sanjo Lopez
2CRM-66 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-01 | Linda | 2017-05-02 | 2017-05-03 | 2 |  | Rikku | 2017-05-04 | 2017-05-04 | 2017-05-05 | 2 | 2017-05-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2 |  | 2 | Arun Krishna | Arun Krishna
3CTA-66 |  | H-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-01 | Gaurav | 2017-05-02 | 2017-05-03 | 2 |  | Gaurav | 2017-05-03 | 2017-05-03 | 2017-05-04 | 2 | 2017-05-04 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 3 | 2 |  | 3 | Anusa Moottoolikandy | Anusa Moottoolikandy
4BLH-65 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-01 | Sanjana | 2017-05-02 | 2017-05-03 | 2 |  | Sanjana | 2017-05-04 | 2017-05-04 | 2017-05-05 | 2 | 2017-05-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2 |  | 4 | Arunika Joy | Arunika Joy
4CHP-63 |  | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-01 | Ashwin | 2017-05-02 | 2017-05-03 | 2 |  | Ashok H | 2017-05-05 | 2017-05-05 | 2017-05-08 | 2 | 2017-05-08 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 5 | 2 |  | 5 | S Shilpa | S Shilpa
6SUB-61 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-01 | Joju | 2017-05-02 | 2017-05-03 | 2 |  | Krishnan | 2017-05-04 | 2017-05-04 | 2017-05-05 | 2 | 2017-05-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2 |  | 6 | Deepa M04 | Deepa M04
4BLH-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-01 | NA | 2017-05-03 | 2017-05-04 | 2 |  | NA | 2017-05-04 | 2017-05-03 | 2017-05-04 | 2 | 2017-05-04 | [6 empty] | 1 | 1 | 0 | -3 | 0 | 3 | 4 |  | 7 | Dhanya A | Dhanya A
5GLL-66 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-02 | NA | 2017-05-05 | 2017-05-09 | 3 |  | NA | 2017-05-09 | 2017-05-08 | 2017-05-10 | 3 | 2017-05-10 | [6 empty] | 1 | 3 | 0 | -3 | 0 | 7 | 6 |  | 8 | SanjanaKrishnan | SanjanaKrishnan
2PNN-62 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-03 | Parth | 2017-05-03 | 2017-05-05 | 3 |  | Parth | 2017-05-08 | 2017-05-08 | 2017-05-09 | 2 | 2017-05-09 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 9 | Swathy Mohan | Swathy Mohan
4MRA-65 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-03 | Joshlee | 2017-05-03 | 2017-05-05 | 3 |  | Joshlee | 2017-05-05 | 2017-05-05 | 2017-05-05 | 1 | 2017-05-05 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 3 | 2 |  | 10 | Abhay Arora | Abhay Arora
5GLL-63 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-03 | NA | 2017-05-04 | 2017-05-10 | 5 |  | NA | 2017-05-10 | 2017-05-10 | 2017-05-16 | 5 | 2017-05-16 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 10 | 8 |  | 11 | Naveen Kumar Nagaraj | Naveen Kumar Nagaraj
5HNL-66 |  | M-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-03 | NA | 2017-05-08 | 2017-05-15 | 6 |  | NA | 2017-05-15 | 2017-05-15 | 2017-05-17 | 3 | 2017-05-17 | [6 empty] | 1 | 3 | 0 | 0 | 0 | 11 | 7 |  | 12 | Alan Babu | Alan Babu
4MGA-61 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-04 | Mahalakshmi | 2017-05-04 | 2017-05-08 | 3 |  | Mahalakshmi | 2017-05-09 | 2017-05-09 | 2017-05-10 | 2 | 2017-05-10 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 13 | Midhun RaJ | Midhun RaJ
4SLA-62 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-04 | Joju | 2017-05-04 | 2017-05-08 | 3 |  | Sangeetha | 2017-05-09 | 2017-05-09 | 2017-05-10 | 2 | 2017-05-10 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 14 | Bhagyalekshmi | Bhagyalekshmi
3BAY-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-04 | NA | 2017-05-09 | 2017-05-16 | 6 |  | NA | 2017-05-16 | 2017-05-15 | 2017-05-17 | 3 | 2017-05-17 | [6 empty] | 1 | 3 | 0 | -3 | 0 | 10 | 9 |  | 15 | Arya PS | Arya PS
2PET-64 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-05 | Gaurav | 2017-05-05 | 2017-05-09 | 3 |  | Ashok H | 2017-05-10 | 2017-05-10 | 2017-05-11 | 2 | 2017-05-11 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 16 | Ashok Hariharamoni | Ashok Hariharamoni
2CAS-61 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-05 | NA | 2017-05-08 | 2017-05-15 | 6 |  | NA | 2017-05-15 | 2017-05-15 | 2017-05-17 | 3 | 2017-05-17 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 9 | 7 |  | 17 | Rupesh | Rupesh
6CTO-61 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-05 | NA | 2017-05-05 | 2017-05-12 | 6 |  | NA | 2017-05-12 | 2017-05-12 | 2017-05-16 | 3 | 2017-05-16 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 8 | 7 |  | 18 | Sridhar | Sridhar
2BAN-60 |  | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-08 | Krishnan | 2017-05-08 | 2017-05-10 | 3 |  | Krishnan | 2017-05-11 | 2017-05-11 | 2017-05-12 | 2 | 2017-05-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 19 | Midhun | Midhun
2FRE-64 |  | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-08 | Ashwin | 2017-05-08 | 2017-05-10 | 3 |  | devi | 2017-05-12 | 2017-05-12 | 2017-05-15 | 2 | 2017-05-15 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3 |  | 20 | Joshlee | Joshlee
3NBA-66 |  | H-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-08 | Sanjana | 2017-05-08 | 2017-05-09 | 2 |  | Sanjana | 2017-05-09 | 2017-05-10 | 2017-05-10 | 1 | 2017-05-10 | [6 empty] | 1 | 0 | 0 | 1 | 0 | 3 | 1 |  | 21 | Linda | Linda
4BLH-63 |  | H-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-08 | Rikku | 2017-05-08 | 2017-05-10 | 3 |  | Rikku | 2017-05-11 | 2017-05-11 | 2017-05-12 | 2 | 2017-05-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 22 | Parth | Parth
4SLA-71 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-08 | devi | 2017-05-08 | 2017-05-10 | 3 |  | devi | 2017-05-11 | 2017-05-11 | 2017-05-12 | 2 | 2017-05-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 23 | Gaurav | Gaurav
5GNG-60 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-08 | Mohith | 2017-05-08 | 2017-05-10 | 3 |  | Rikku | 2017-05-17 | 2017-05-18 | 2017-05-19 | 2 | 2017-05-19 | [6 empty] | 6 | 0 | 0 | 1 | 0 | 10 | 3 |  | 24 | Rikku | Rikku
3NCO-63 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-08 | NA | 2017-05-08 | 2017-05-15 | 6 |  | NA | 2017-05-15 | 2017-05-15 | 2017-05-17 | 3 | 2017-05-17 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 8 | 7 |  | 25 | Sangeetha | Sangeetha
2SEV-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-08 | NA | 2017-05-11 | 2017-05-16 | 4 |  | NA | 2017-05-16 | 2017-05-17 | 2017-05-18 | 2 | 2017-05-18 | [6 empty] | 1 | 3 | 0 | 1 | 0 | 9 | 4 |  | 26 | Krishnan | Krishnan
2MIL-63 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-09 | Joju | 2017-05-09 | 2017-05-11 | 3 |  | Joju | 2017-05-12 | 2017-05-12 | 2017-05-15 | 2 | 2017-05-15 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 27 | Mohith | Mohith
4CHP-62 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-10 | Aravind | 2017-05-10 | 2017-05-10 | 1 |  | Aravind | 2017-05-11 | 2017-05-11 | 2017-05-12 | 2 | 2017-05-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 3 | 1 |  | 28 | Aravind | Aravind
6SUB-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-10 | NA | 2017-05-12 | 2017-05-16 | 3 |  | NA | 2017-05-16 | 2017-05-16 | 2017-05-19 | 4 | 2017-05-19 | [6 empty] | 1 | 2 | 0 | 0 | 0 | 8 | 5 |  | 29 | Mani | Mani
3DAD-61 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-10 | NA | 2017-05-10 | 2017-05-19 | 8 |  | NA | 2017-05-19 | 2017-05-17 | 2017-05-19 | 3 | 2017-05-19 | [6 empty] | 1 | 0 | 0 | -4 | 0 | 8 | 11 |  | 30 | Joju | Joju
2BON-61 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-11 | Ashwin | 2017-05-11 | 2017-05-15 | 3 |  | Ashwin | 2017-05-17 | 2017-05-17 | 2017-05-18 | 2 | 2017-05-18 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3 |  | 31 | Visakh | Visakh
2BON-64 |  | M-M-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-05-11 | Sanjana | 2017-05-11 | 2017-05-15 | 3 |  | Sanjana | 2017-05-15 | 2017-05-16 | 2017-06-01 | 13 | 2017-06-01 | [6 empty] | 1 | 0 | 0 | 1 | 0 | 16 | 14 |  | 32 | Devi Vidyadharan | Devi Vidyadharan
5BRI-71 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-11 | Parth | 2017-05-11 | 2017-05-15 | 3 |  | Manikandan | 2017-05-29 | 2017-05-29 | 2017-05-30 | 2 | 2017-05-30 | [6 empty] | 11 | 0 | 0 | 0 | 0 | 14 | 3 |  | 33 | Nisha | Nisha
3DAD-65 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-12 | NA | 2017-05-19 | 2017-05-23 | 3 |  | NA | 2017-05-23 | 2017-05-23 | 2017-05-25 | 3 | 2017-05-25 | [6 empty] | 1 | 5 | 0 | 0 | 0 | 10 | 4 |  | 34 | Mahalakshmi | Mahalakshmi
2EAS-60 |  | H-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-15 | Mahalakshmi | 2017-05-15 | 2017-05-17 | 3 |  | Sangeetha | 2017-05-18 | 2017-05-18 | 2017-05-19 | 2 | 2017-05-19 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 35 | Salil | Salil
2FRE-61 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-15 | Gaurav | 2017-05-15 | 2017-05-17 | 3 |  | Sangeetha | 2017-05-19 | 2017-05-19 | 2017-05-22 | 2 | 2017-05-22 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3 |  | 36 | Rijo Sunny | Rijo Sunny
3SPL-62 |  | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-05-15 | Manikandan | 2017-05-15 | 2017-05-17 | 3 | [5 empty] | 0 | [7 empty] | -30604 | 0 | 0 | -1 | 0 | -30602 | 3 |  | 37 | Reshma Menon | Reshma Menon
4MGA-63 |  | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-15 | Sangeetha | 2017-05-15 | 2017-05-17 | 3 |  | Sanjana | 2017-05-18 | 2017-05-18 | 2017-05-19 | 2 | 2017-05-19 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3 |  | 38 | Maria Joy | Maria Joy
3FNT-66 |  | H-M-Q | HAC | Pre-AT | 1 | Completed | 2017-05-15 | NA | 2017-05-19 | 2017-05-23 | 3 |  | NA | 2017-05-23 | 2017-05-23 | 2017-05-24 | 2 | 2017-05-24 | [6 empty] | 1 | 4 | 0 | 0 | 0 | 8 | 3 |  |  |  | NA
3DAD-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-15 | NA | 2017-05-19 | 2017-05-23 | 3 |  | NA | 2017-05-23 | 2017-05-23 | 2017-05-24 | 2 | 2017-05-24 | [6 empty] | 1 | 4 | 0 | 0 | 0 | 8 | 3
2CRM-65 |  | H-A-Q | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-05-16 | Ashok | 2017-05-16 | 2017-05-18 | 3 | [5 empty] | 0 | [7 empty] | -30605 | 0 | 0 | -1 | 0 | -30603 | 3
3TNI-62 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-16 | Joju | 2017-05-16 | 2017-05-18 | 3 |  | Rikku | 2017-05-22 | 2017-05-22 | 2017-05-23 | 2 | 2017-05-23 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
3WHL-65 |  | M-A-J | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-16 | Ashwin | 2017-05-16 | 2017-05-17 | 2 |  | Ashwin | 2017-05-18 | 2017-05-18 | 2017-05-19 | 2 | 2017-05-19 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
6SUB-68 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-16 | NA | 2017-05-17 | 2017-05-18 | 2 |  | NA | 2017-05-18 | 2017-05-18 | 2017-05-19 | 2 | 2017-05-19 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 4 | 2
2BAM-62 |  | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-17 | Ashok | 2017-05-17 | 2017-05-19 | 3 |  | Ashwin | 2017-05-19 | 2017-05-19 | 2017-05-22 | 2 | 2017-05-22 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
4BUR-67 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-17 | Devi | 2017-05-17 | 2017-05-18 | 2 |  | Parth | 2017-05-22 | 2017-05-22 | 2017-05-23 | 2 | 2017-05-23 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 5 | 2
3SOA-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-17 | NA | 2017-05-18 | 2017-05-22 | 3 |  | NA | 2017-05-22 | 2017-05-22 | 2017-05-23 | 2 | 2017-05-23 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 5 | 3
2EPP-63 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-18 | NA | 2017-05-25 | 2017-05-26 | 2 |  | NA | 2017-05-26 | 2017-05-26 | 2017-06-01 | 5 | 2017-06-01 | [6 empty] | 1 | 5 | 0 | 0 | 0 | 11 | 5
3MIT-61 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-18 | NA | 2017-05-19 | 2017-05-23 | 3 |  | NA | 2017-05-23 | 2017-05-23 | 2017-05-24 | 2 | 2017-05-24 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 5 | 3
6CTO-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-18 | NA | 2017-05-19 | 2017-05-26 | 6 |  | NA | 2017-05-26 | 2017-05-26 | 2017-05-26 | 1 | 2017-05-26 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 7 | 5
2MIL-60 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-19 | Ashok | 2017-05-19 | 2017-05-23 | 3 |  | Ashok | 2017-05-24 | 2017-05-24 | 2017-05-25 | 2 | 2017-05-25 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4BUR-20 |  | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-19 | Krishnan | 2017-05-19 | 2017-05-23 | 3 |  | Sangeetha | 2017-05-23 | 2017-05-23 | 2017-05-24 | 2 | 2017-05-24 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
4MRA-64 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-19 | Manikandan | 2017-05-19 | 2017-05-23 | 3 |  | Parth | 2017-05-24 | 2017-05-24 | 2017-05-25 | 2 | 2017-05-25 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4CPH-72 |  | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-22 | Sanjana | 2017-05-22 | 2017-05-24 | 3 |  | Gaurav | 2017-05-25 | 2017-05-25 | 2017-05-26 | 2 | 2017-05-26 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4OXE-61 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-22 | Mahalakshmi | 2017-05-22 | 2017-05-24 | 3 |  | Mahalakshmi | 2017-05-25 | 2017-05-25 | 2017-05-26 | 2 | 2017-05-26 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4WRN-60 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-22 | Gaurav | 2017-05-22 | 2017-05-24 | 3 |  | Gaurav | 2017-05-25 | 2017-05-25 | 2017-05-29 | 3 | 2017-05-29 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4WRN-61 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-22 | Aravind | 2017-05-22 | 2017-05-24 | 3 |  | Aravind | 2017-05-25 | 2017-05-25 | 2017-05-29 | 3 | 2017-05-29 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3SOA-62 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-22 | NA | 2017-05-22 | 2017-05-26 | 5 |  | NA | 2017-05-26 | 2017-05-24 | 2017-05-26 | 3 | 2017-05-26 | [6 empty] | 1 | 0 | 0 | -4 | 0 | 5 | 8
2BAN-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-22 | NA | 2017-06-02 | 2017-06-06 | 3 |  | NA | 2017-06-06 | 2017-06-07 | 2017-06-09 | 3 | 2017-06-09 | [6 empty] | 1 | 9 | 0 | 1 | 0 | 15 | 4
3SOA-63 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-22 | NA | 2017-06-19 | 2017-06-21 | 3 |  | NA | 2017-06-21 | 2017-06-21 | 2017-06-22 | 2 | 2017-06-22 | [6 empty] | 1 | 19 | 0 | 0 | 0 | 23 | 3
3NCO-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-22 | NA | 2017-06-16 | 2017-06-21 | 4 |  | NA | 2017-06-21 | 2017-06-21 | 2017-06-23 | 3 | 2017-06-23 | [6 empty] | 1 | 18 | 0 | 0 | 0 | 24 | 5
3TYH-68 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-23 | NA | 2017-06-08 | 2017-06-12 | 2 |  | NA | 2017-06-12 | 2017-06-12 | 2017-06-14 | 2 | 2017-06-14 | [6 empty] | 0 | 12 | 0 | -1 | 0 | 16 | 5
2NSY-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-23 | NA | 2017-05-23 | 2017-05-31 | 7 |  | NA | 2017-05-31 | 2017-05-31 | 2017-06-06 | 5 | 2017-06-06 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 11 | 10
4SLA-63 |  | H-A-H | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-05-24 | Ashwin | 2017-05-24 | 2017-05-29 | 4 | [5 empty] | 0 | [7 empty] | -30612 | 0 | 0 | -1 | 0 | -30609 | 4
5EDW-66 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-24 | Sangeetha | 2017-05-24 | 2017-05-26 | 3 |  | Sangeetha | 2017-05-29 | 2017-05-29 | 2017-05-31 | 3 | 2017-05-31 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
5HNL-63 |  | H-M-Q | BAU | Design |  | On Hold - [PC] Data Issues | 2017-05-24 | Rikku | 2017-05-24 | 2017-05-26 | 3 | [5 empty] | 0 | [7 empty] | -30611 | 0 | 0 | -1 | 0 | -30609 | 3
2ENG-65 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-24 | NA | 2017-05-25 | 2017-05-29 | 3 |  | NA | 2017-05-29 | 2017-05-29 | 2017-05-30 | 2 | 2017-05-30 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 5 | 3
3SPL-62 |  | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-05-25 |  | 2017-05-25 | 2017-05-29 | 3 | [5 empty] | 0 | [7 empty] | -30612 | 0 | 0 | -1 | 0 | -30610 | 3
3ELT-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-25 | NA | 2017-06-06 | 2017-06-09 | 4 |  | NA | 2017-06-09 | 2017-06-09 | 2017-06-13 | 2 | 2017-06-13 | [6 empty] | 1 | 8 | 0 | 0 | 0 | 13 | 4
2SEV-62 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-25 | NA | 2017-06-02 | 2017-06-06 | 3 |  | NA | 2017-06-06 | 2017-06-06 | 2017-06-09 | 4 | 2017-06-09 | [6 empty] | 1 | 6 | 0 | 0 | 0 | 12 | 5
2CRR-20 |  | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-29 | Mohith | 2017-05-29 | 2017-05-31 | 3 |  | Devi | 2017-06-01 | 2017-06-01 | 2017-06-02 | 2 | 2017-06-02 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
3NAW-66 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-29 | Mahalakshmi | 2017-05-29 | 2017-05-31 | 3 |  | Mahalakshmi | 2017-06-01 | 2017-06-01 | 2017-06-02 | 2 | 2017-06-02 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4BLH-66 |  | H-A-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-05-29 | Rikku | 2017-05-29 | 2017-05-31 | 3 | [5 empty] | 0 | [7 empty] | -30614 | 0 | 0 | -1 | 0 | -30612 | 3
5WES-65 |  | H-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-05-29 | Parth | 2017-05-29 | 2017-05-31 | 3 | [5 empty] | 0 | [7 empty] | -30614 | 0 | 0 | -1 | 0 | -30612 | 3
2PNN-63 |  | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-30 | Devi | 2017-05-30 | 2017-06-01 | 3 |  | Mohith | 2017-06-02 | 2017-06-02 | 2017-06-05 | 2 | 2017-06-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2PNN-70 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-05-30 | Gaurav | 2017-05-30 | 2017-06-01 | 3 |  | Mahalakshmi | 2017-06-02 | 2017-06-02 | 2017-06-05 | 2 | 2017-06-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
3FNT-63 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-30 | Krishnan | 2017-05-30 | 2017-06-01 | 3 |  | Krishnan | 2017-06-02 | 2017-06-02 | 2017-06-06 | 3 | 2017-06-06 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3KYG-65 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-30 | Sangeetha | 2017-05-30 | 2017-06-01 | 3 |  | Sangeetha | 2017-06-02 | 2017-06-02 | 2017-06-05 | 2 | 2017-06-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4BUR-66 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-30 | Mohith | 2017-05-30 | 2017-06-01 | 3 |  | Manikandan | 2017-06-02 | 2017-06-02 | 2017-06-05 | 2 | 2017-06-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4SOP-63 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-30 | Parth | 2017-05-30 | 2017-06-01 | 3 |  | Parth | 2017-06-02 | 2017-06-02 | 2017-06-05 | 2 | 2017-06-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5HNL-62 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-30 | Aravind | 2017-05-30 | 2017-06-01 | 3 |  | Aravind | 2017-06-02 | 2017-06-02 | 2017-06-06 | 3 | 2017-06-06 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
2EPP-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-30 | NA | 2017-06-06 | 2017-06-08 | 3 |  | NA | 2017-06-08 | 2017-06-08 | 2017-06-09 | 2 | 2017-06-09 | [6 empty] | 1 | 5 | 0 | 0 | 0 | 9 | 3
6SUB-63 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-05-30 | NA | 2017-06-05 | 2017-06-09 | 5 |  | NA | 2017-06-09 | 2017-06-09 | 2017-06-13 | 2 | 2017-06-13 | [6 empty] | 1 | 4 | 0 | 0 | 0 | 10 | 5
3WER-62 |  | H-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-05-31 | Rikku | 2017-05-31 | 2017-06-02 | 3 |  | Rikku | 2017-06-05 | 2017-06-05 | 2017-06-06 | 2 | 2017-06-06 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2ASH-63 |  | H-M-Q | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-06-01 | Mohith | 2017-06-01 | 2017-06-05 | 3 | [5 empty] | 0 | [7 empty] | -30617 | 0 | 0 | -1 | 0 | -30615 | 3
2STL-62 |  | H-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-01 | Sangeetha | 2017-06-01 | 2017-06-05 | 3 |  | Sangeetha | 2017-06-06 | 2017-06-06 | 2017-06-07 | 2 | 2017-06-07 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2UND-62 |  | H-M-Q | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-01 | Parth | 2017-06-02 | 2017-06-05 | 2 |  | Parth | 2017-06-07 | 2017-06-07 | 2017-06-08 | 2 | 2017-06-08 | [6 empty] | 3 | 1 | 0 | 0 | 0 | 6 | 2
4EMP-63 |  | M-M-H | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-01 | Rikku | 2017-06-01 | 2017-06-05 | 3 | [5 empty] | 0 | [7 empty] | -30617 | 0 | 0 | -1 | 0 | -30615 | 3
4SLA-63 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-01 | Ashwin | 2017-06-01 | 2017-06-02 | 2 |  | Ashwin | 2017-06-05 | 2017-06-05 | 2017-06-08 | 4 | 2017-06-08 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4SOP-60 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-01 | Devi | 2017-06-01 | 2017-06-05 | 3 |  | Devi | 2017-06-07 | 2017-06-23 | 2017-06-27 | 2 | 2017-06-27 | [6 empty] | 3 | 0 | 0 | 11 | 0 | 17 | 3
5MOD-63 |  | M-A-J | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-01 | Gaurav | 2017-06-01 | 2017-06-05 | 3 |  | Gaurav | 2017-06-06 | 2017-06-06 | 2017-06-07 | 2 | 2017-06-07 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2CRM-65 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-01 | NA | 2017-06-09 | 2017-06-12 | 1 |  | NA | 2017-06-12 | 2017-06-12 | 2017-06-14 | 2 | 2017-06-14 | [6 empty] | 0 | 6 | 0 | -1 | 0 | 9 | 4
3SPL-64 |  | M-B-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-05 | Mahalakshmi | 2017-06-05 | 2017-06-07 | 3 |  | Mahalakshmi | 2017-06-08 | 2017-06-08 | 2017-06-09 | 2 | 2017-06-09 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
3WER-61 |  | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-05 | Gaurav | 2017-06-05 | 2017-06-07 | 3 |  | Gaurav | 2017-06-08 | 2017-06-08 | 2017-06-09 | 2 | 2017-06-09 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4BUR-64 |  | M-M-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-05 | Mohith | 2017-06-05 | 2017-06-06 | 2 | [5 empty] | 0 | [7 empty] | -30618 | 0 | 0 | -1 | 0 | -30617 | 2
4SLA-70 |  | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-05 | Manikandan | 2017-06-05 | 2017-06-07 | 3 |  | Krishnan | 2017-06-08 | 2017-06-08 | 2017-06-09 | 2 | 2017-06-09 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
6GIR-61 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-05 | NA | 2017-06-06 | 2017-06-09 | 4 |  | NA | 2017-06-09 | 2017-06-09 | 2017-06-13 | 2 | 2017-06-13 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 6 | 4
2ASH-62 |  | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-06 | Krishnan | 2017-06-06 | 2017-06-08 | 3 |  | Ashwin | 2017-06-09 | 2017-06-09 | 2017-06-12 | 1 | 2017-06-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
2BAL-62 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-06 | Devi | 2017-06-06 | 2017-06-08 | 3 |  | Rikku | 2017-06-09 | 2017-06-09 | 2017-06-12 | 1 | 2017-06-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
6GIR-66 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-06 | NA | 2017-06-12 | 2017-06-15 | 3 |  | NA | 2017-06-15 | 2017-06-16 | 2017-06-19 | 2 | 2017-06-19 | [6 empty] | 1 | 3 | 0 | 1 | 0 | 9 | 4
4MGA-68 |  | M-M-H | BAU | Design |  | On Hold - [GML] Issues - NBN Internal | 2017-06-07 | Aravind | 2017-06-07 | 2017-06-08 | 2 |  | Aravind | 2017-06-09 | 2017-06-09 | 2017-06-13 | 2 | 2017-06-13 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
5HNL-63 |  | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-07 | Rikku | 2017-06-07 | 2017-06-09 | 3 |  | Krishnan | 2017-06-12 | 2017-06-12 | 2017-06-13 | 1 | 2017-06-13 | [6 empty] | 1 | 0 | 0 | -1 | 0 | 4 | 4
2BAL-64 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-07 | Mohith | 2017-06-07 | 2017-06-12 | 3 |  | Mohith | 2017-06-13 | 2017-06-13 | 2017-06-14 | 2 | 2017-06-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 5 | 4
4MGA-68 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-07 | Aravind | 2017-06-07 | 2017-06-08 | 2 |  | Aravind | 2017-06-09 | 2017-06-09 | 2017-06-20 | 7 | 2017-06-20 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 9 | 7
3GLI-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-07 | NA | 2017-06-16 | 2017-06-20 | 3 |  | NA | 2017-06-20 | 2017-06-20 | 2017-06-21 | 2 | 2017-06-21 | [6 empty] | 1 | 6 | 0 | 0 | 0 | 10 | 3
4BLH-67 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-07 | NA | 2017-06-07 | 2017-06-09 | 3 |  | NA | 2017-06-09 | 2017-06-09 | 2017-06-13 | 2 | 2017-06-13 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
2CAS-62 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-07 | NA | 2017-06-19 | 2017-06-22 | 4 |  | NA | 2017-06-22 | 2017-06-22 | 2017-06-26 | 2 | 2017-06-26 | [6 empty] | 1 | 7 | 0 | 0 | 0 | 12 | 4
2NEW-60 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-08 | Devi | 2017-06-08 | 2017-06-12 | 2 |  | Aravind | 2017-06-13 | 2017-06-13 | 2017-06-14 | 2 | 2017-06-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
3NCO-61 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-08 | Manikandan | 2017-06-08 | 2017-06-12 | 2 |  | Mohith | 2017-06-15 | 2017-06-15 | 2017-06-16 | 2 | 2017-06-16 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
4SOP-61 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-08 | Parth | 2017-06-08 | 2017-06-12 | 2 |  | Parth | 2017-06-15 | 2017-06-15 | 2017-06-16 | 2 | 2017-06-16 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
5EDW-66 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-08 | Ashwin | 2017-06-08 | 2017-06-12 | 2 |  | Rikku | 2017-06-13 | 2017-06-13 | 2017-06-14 | 2 | 2017-06-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
5FLN-61 |  | H-B-J | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-08 | Mahalakshmi | 2017-06-08 | 2017-06-12 | 2 |  | Mahalakshmi | 2017-06-13 | 2017-06-13 | 2017-06-14 | 2 | 2017-06-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
5HNL-61 |  | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-08 | Rikku | 2017-06-08 | 2017-06-12 | 2 |  | Rikku | 2017-06-14 | 2017-06-14 | 2017-06-15 | 2 | 2017-06-15 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
6SUB-67 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-08 | Sangeetha | 2017-06-08 | 2017-06-12 | 2 |  | Sangeetha | 2017-06-13 | 2017-06-13 | 2017-06-14 | 2 | 2017-06-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
2BON-64 |  | M-M-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-09 | Parth | 2017-06-09 | 2017-06-13 | 2 |  | parth | 2017-06-15 | 2017-06-15 | 2017-06-16 | 2 | 2017-06-16 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 5 | 2
2CRR-20 |  | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-09 | Devi | 2017-06-09 | 2017-06-13 | 2 |  | Devi | 2017-06-14 | 2017-06-14 | 2017-06-15 | 2 | 2017-06-15 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
4EMP-63 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-09 | Krishnan | 2017-06-09 | 2017-06-13 | 2 |  | Krishnan | 2017-06-13 | 2017-06-13 | 2017-06-14 | 2 | 2017-06-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 3 | 2
4SUR-61 |  | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-09 | Joju | 2017-06-09 | 2017-06-13 | 2 |  | Aravind | 2017-06-15 | 2017-06-15 | 2017-06-16 | 2 | 2017-06-16 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 5 | 2
5FLN-60 |  | H-B-J | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-09 | Linda | 2017-06-09 | 2017-06-13 | 2 |  | Linda | 2017-06-16 | 2017-06-16 | 2017-06-19 | 2 | 2017-06-19 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 6 | 2
3DNC-67 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-09 | NA | 2017-06-23 | 2017-06-20 | -4 |  | NA | 2017-06-20 | 2017-06-23 | 2017-06-29 | 4 | 2017-06-29 | [6 empty] | 1 | 9 | 0 | 3 | 0 | 13 | 0
2CRR-65 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-12 | Manikandan | 2017-06-12 | 2017-06-14 | 2 |  | Krishnan | 2017-06-19 | 2017-06-19 | 2017-06-20 | 2 | 2017-06-20 | [6 empty] | 4 | -1 | 0 | 0 | 0 | 6 | 3 |  | 39 | NA
3NAW-62 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-12 | Ashwin | 2017-06-12 | 2017-06-14 | 2 |  | Mahalakshmi | 2017-09-15 | 2017-09-15 | 2017-09-18 | 2 | 2017-09-18 | [6 empty] | 64 | -1 | 0 | 0 | 0 | 66 | 3
3SCO-65 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-13 | Devi | 2017-06-13 | 2017-06-15 | 3 |  | Devi | 2017-06-16 | 2017-06-16 | 2017-06-19 | 2 | 2017-06-19 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4SLA-68 |  | H-A-H | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-13 | Linda | 2017-06-13 | 2017-06-15 | 3 | [5 empty] | 0 | [7 empty] | -30624 | 0 | 0 | -1 | 0 | -30622 | 3
3CTA-62 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-13 | NA | 2017-06-13 | 2017-06-19 | 5 |  | NA | 2017-06-19 | 2017-06-14 | 2017-06-19 | 4 | 2017-06-19 | [6 empty] | 1 | 0 | 0 | -5 | 0 | 5 | 9
3HGT-74 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-13 | NA | 2017-06-19 | 2017-06-26 | 5 |  | NA | 2017-06-26 | 2017-06-26 | 2017-06-28 | 2 | 2017-06-28 | [6 empty] | 0 | 4 | 0 | -1 | 0 | 11 | 8
3RWO-65 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-13 | NA | 2017-06-14 | 2017-06-20 | 5 |  | NA | 2017-06-20 | 2017-06-16 | 2017-06-20 | 3 | 2017-06-20 | [6 empty] | 1 | 1 | 0 | -4 | 0 | 6 | 8
5SAL-69 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-13 | NA | 2017-06-14 | 2017-06-14 | 1 |  | NA | 2017-06-14 | 2017-06-15 | 2017-06-16 | 2 | 2017-06-16 | [6 empty] | 1 | 1 | 0 | 1 | 0 | 4 | 1
2CAS-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-13 | NA | 2017-06-23 | 2017-06-29 | 4 |  | NA | 2017-06-29 | 2017-06-29 | 2017-06-29 | 1 | 2017-06-29 | [6 empty] | 1 | 8 | 0 | 0 | 0 | 12 | 3
3SPL-62 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-14 | Joju | 2017-06-14 | 2017-06-16 | 3 |  | Mahalakshmi | 2017-06-19 | 2017-06-19 | 2017-06-21 | 3 | 2017-06-21 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
5FLN-62 |  | H-B-J | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-14 | Krishnan | 2017-06-14 | 2017-06-16 | 3 |  | Sanjana | 2017-06-21 | 2017-06-21 | 2017-06-22 | 2 | 2017-06-22 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 7 | 3
3KGP-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-14 | NA | 2017-06-19 | 2017-06-20 | 2 |  | NA | 2017-06-20 | 2017-06-20 | 2017-06-22 | 3 | 2017-06-22 | [6 empty] | 1 | 3 | 0 | 0 | 0 | 7 | 3
2ASH-63 |  | H-M-Q | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-15 | Ashwin | 2017-06-15 | 2017-06-19 | 3 |  | Gaurav | 2017-06-20 | 2017-06-20 | 2017-06-21 | 2 | 2017-06-21 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5WES-65 |  | H-M-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-15 | Mahalakshmi | 2017-06-15 | 2017-06-19 | 3 |  | Mahalakshmi | 2017-06-21 | 2017-06-21 | 2017-06-22 | 2 | 2017-06-22 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
4MGA-72 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-16 | Sangeetha | 2017-06-16 | 2017-06-20 | 3 |  | Sangeetha | 2017-06-21 | 2017-06-21 | 2017-06-22 | 2 | 2017-06-22 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5HNL-64 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-16 | Rikku | 2017-06-16 | 2017-06-20 | 3 |  | Rikku | 2017-06-21 | 2017-06-21 | 2017-06-22 | 2 | 2017-06-22 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2STL-65 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-16 | Manikandan | 2017-06-16 | 2017-06-20 | 3 |  | Manikandan | 2017-06-21 | 2017-06-21 | 2017-06-22 | 2 | 2017-06-22 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5BRI-62 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-16 | krishnan | 2017-06-16 | 2017-06-20 | 3 |  | Krishnan | 2017-06-21 | 2017-06-21 | 2017-06-22 | 2 | 2017-06-22 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
6SUB-65 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-16 | Aravind | 2017-06-16 | 2017-06-20 | 3 |  | Aravind | 2017-06-21 | 2017-06-21 | 2017-06-22 | 2 | 2017-06-22 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4AGV-63 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-19 | Sanjana | 2017-06-19 | 2017-06-21 | 3 |  | Ashwin | 2017-06-22 | 2017-06-22 | 2017-06-23 | 2 | 2017-06-23 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5BRI-66 |  | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2017-06-19 | Ashwin | 2017-06-19 | 2017-06-21 | 3 | [5 empty] | 0 | [7 empty] | -30628 | 0 | 0 | -1 | 0 | -30626 | 3
5WES-61 |  | M-M-H | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-19 | Devi | 2017-06-19 | 2017-06-21 | 3 |  | Devi | 2017-06-22 | 2017-06-22 | 2017-06-23 | 2 | 2017-06-23 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5BRI-66 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-19 | Ashwin | 2017-06-19 | 2017-06-21 | 3 |  | Gaurav | 2017-06-30 | 2017-06-30 | 2017-07-04 | 3 | 2017-07-04 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 11 | 4
3BOX-66 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-19 | NA | 2017-06-27 | 2017-06-27 | 1 |  | NA | 2017-06-27 | 2017-06-27 | 2017-07-04 | 6 | 2017-07-04 | [6 empty] | 1 | 5 | 0 | 0 | 0 | 11 | 5
3NBA-64 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-19 | NA | 2017-06-23 | 2017-06-28 | 3 |  | NA | 2017-06-28 | 2017-06-28 | 2017-06-29 | 3 | 2017-06-30 | [6 empty] | 1 | 4 | 0 | 0 | 0 | 9 | 4
2BAN-68 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-19 | NA | 2017-06-21 | 2017-06-23 | 3 |  | NA | 2017-06-23 | 2017-06-23 | 2017-06-27 | 2 | 2017-06-27 | [6 empty] | 1 | 2 | 0 | 0 | 0 | 6 | 3
2CAS-63 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-19 | NA | 2017-06-23 | 2017-06-28 | 3 |  | NA | 2017-06-28 | 2017-06-28 | 2017-06-29 | 2 | 2017-06-29 | [6 empty] | 1 | 4 | 0 | 0 | 0 | 8 | 3
2ASH-62 |  | H-M-Q | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-21 | Mahalakshmi | 2017-06-21 | 2017-06-27 | 4 | [5 empty] | 0 | [7 empty] | -30631 | 0 | 0 | -1 | 0 | -30628 | 4
4ASH-63 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-21 | Gaurav | 2017-06-21 | 2017-06-23 | 3 |  | Gaurav | 2017-06-27 | 2017-06-27 | 2017-06-27 | 1 | 2017-06-27 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
4SLA-68 |  | H-A-H | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-06-21 | Linda | 2017-06-21 | 2017-06-23 | 3 | [5 empty] | 0 | [7 empty] | -30630 | 0 | 0 | -1 | 0 | -30628 | 3
3NCO-65 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-21 | NA | 2017-06-21 | 2017-06-23 | 3 |  | NA | 2017-06-23 | 2017-06-23 | 2017-06-28 | 3 | 2017-06-28 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 5 | 4
4IAL-62 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-21 | NA | 2017-06-23 | 2017-06-28 | 3 |  | NA | 2017-06-28 | 2017-06-28 | 2017-06-29 | 3 | 2017-06-30 | [6 empty] | 1 | 2 | 0 | 0 | 0 | 7 | 4
2ROS-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-21 | NA | 2017-06-27 | 2017-07-04 | 6 |  | NA | 2017-07-04 | 2017-06-29 | 2017-07-04 | 4 | 2017-07-04 | [6 empty] | 1 | 3 | 0 | -5 | 0 | 9 | 10
2BAN-67 |  | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-22 | Aravind | 2017-06-22 | 2017-06-27 | 3 |  | Parth | 2017-06-28 | 2017-06-28 | 2017-06-29 | 2 | 2017-06-29 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4CPB-22 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-22 | Krishnan | 2017-06-22 | 2017-06-27 | 3 |  | Mahalakshmi | 2017-06-28 | 2017-06-28 | 2017-06-29 | 2 | 2017-06-29 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4AGV-61 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-22 | Rikku | 2017-06-22 | 2017-06-27 | 3 |  | Rikku | 2017-06-28 | 2017-06-28 | 2017-06-29 | 2 | 2017-06-29 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5GPC-60 |  | H-B-Q | HAC | Pre-AT | 1 | Completed | 2017-06-26 | NA | 2017-06-28 | 2017-07-05 | 6 |  | NA | 2017-07-05 | 2017-06-30 | 2017-07-06 | 5 | 2017-07-06 | [6 empty] | 1 | 1 | 0 | -5 | 0 | 8 | 11
3CAU-69 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-26 | NA | 2017-06-28 | 2017-07-04 | 5 |  | NA | 2017-07-04 | 2017-06-29 | 2017-07-05 | 5 | 2017-07-05 | [6 empty] | 1 | 1 | 0 | -5 | 0 | 7 | 10
4BLH-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-26 | NA | 2017-07-04 | 2017-07-11 | 6 |  | NA | 2017-07-11 | 2017-07-04 | 2017-07-11 | 6 | 2017-07-11 | [6 empty] | 1 | 5 | 0 | -7 | 0 | 11 | 12
2MOS-63 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-26 | NA | 2017-07-05 | 2017-07-12 | 6 |  | NA | 2017-07-12 | 2017-07-06 | 2017-07-12 | 5 | 2017-07-12 | [6 empty] | 1 | 6 | 0 | -6 | 0 | 12 | 11
4BUR-67 |  | M-M-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-27 | Manikandan | 2017-06-27 | 2017-06-29 | 3 | [5 empty] | 0 | [7 empty] | -30633 | 0 | 0 | -1 | 0 | -30631 | 3
5FLN-62 |  | H-B-J | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-06-27 | Sangeetha | 2017-06-27 | 2017-06-29 | 3 | [5 empty] | 0 | [7 empty] | -30633 | 0 | 0 | -1 | 0 | -30631 | 3
4IAL-61 |  | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (LDM) | 2017-06-28 | Gaurav | 2017-06-28 | 2017-06-30 | 3 | [5 empty] | 0 | [7 empty] | -30634 | 0 | 0 | -1 | 0 | -30632 | 3
3BGO-60 |  | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-06-28 | NA | 2017-07-03 | 2017-07-05 | 3 |  | NA | 2017-07-05 | 2017-07-04 | 2017-07-06 | 3 | 2017-07-06 | [6 empty] | 1 | 3 | 0 | -3 | 0 | 7 | 6
4CHD-63 |  | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-06-29 | Rikku | 2017-06-29 | 2017-06-30 | 2 | [5 empty] | 0 | [7 empty] | -30634 | 0 | 0 | -1 | 0 | -30633 | 2
2UND-61 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-06-29 | Devi | 2017-06-29 | 2017-07-03 | 3 |  | Devi Vidyadharan | 2017-07-04 | 2017-07-04 | 2017-07-05 | 2 | 2017-07-05 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5MOD-63 |  | M-A-J | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-29 | Sanjana | 2017-06-29 | 2017-07-03 | 3 | [5 empty] | 0 | [7 empty] | -30635 | 0 | 0 | -1 | 0 | -30633 | 3
2BON-64 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-30 | Manikandan | 2017-06-30 | 2017-07-04 | 3 |  | Gaurav | 2017-07-05 | 2017-07-05 | 2017-07-06 | 2 | 2017-07-06 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2CRR-69 |  | M-M-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (LDM) | 2017-06-30 | Mahalakshmi | 2017-06-30 | 2017-07-04 | 3 | [5 empty] | 0 | [7 empty] | -30636 | 0 | 0 | -1 | 0 | -30634 | 3
3NBA-69 |  | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-30 | Parth | 2017-06-30 | 2017-07-04 | 3 |  | krishnan | 2017-07-05 | 2017-07-05 | 2017-07-06 | 2 | 2017-07-06 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5GNG-61 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-06-30 | Sangeetha | 2017-06-30 | 2017-07-04 | 3 |  | Sangeetha | 2017-07-05 | 2017-07-05 | 2017-07-06 | 2 | 2017-07-06 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2CRR-69 |  | M-M-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (LDM) | 2017-06-30 | Mahalakshmi | 2017-06-30 | 2017-07-04 | 3 | [5 empty] | 0 | [7 empty] | -30636 | 0 | 0 | -1 | 0 | -30634 | 3
5MOD-63 |  | M-A-J | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-06-30 | Sanjana | 2017-06-29 | 2017-07-03 | 3 | [5 empty] | 0 | [7 empty] | -30635 | -3 | 0 | -1 | 0 | -30634 | 5
4OXE-61 | RFS.108 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-03 | Mahalakshmi | 2017-07-03 | 2017-07-05 | 3 |  | Mahalakshmi | 2017-07-13 | 2017-07-13 | 2017-07-14 | 2 | 2017-07-14 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 10 | 3
4SOP-61 | RFS.94 | H-A-H | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-07-04 | Manikandan | 2017-07-04 | 2017-07-06 | 3 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30636 | #VALUE!
2CRM-61 | RFS.89 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-05 | Krishnan | 2017-07-05 | 2017-07-07 | 3 |  | NA | 2017-07-13 | 2017-07-13 | 2017-07-14 | 2 | 2017-07-14 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 8 | 3
4CHD-21 | RFS.122 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-07-04 | Mahalakshmi | 2017-07-05 | 2017-07-06 | 2 |  | Manikandan | 2017-08-17 | 2017-08-17 | 2017-08-21 | 3 | 2017-08-21 | [6 empty] | 30 | 1 | 0 | 0 | 0 | 34 | 3
3SPL-67 |  | M-M-H | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-07-05 | Rikku | 2017-07-05 | 2017-07-10 | 4 | [5 empty] | 0 | [7 empty] | -30640 | 0 | 0 | -1 | 0 | -30637 | 4
2SEV-61 | RFS.115 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-05 | Mahalakshmi | 2017-07-05 | 2017-07-07 | 3 |  | Mahalakshmi | 2017-07-13 | 2017-07-13 | 2017-07-14 | 2 | 2017-07-14 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 8 | 3
2UND-62 | RFS.116 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-05 | Parth | 2017-07-05 | 2017-07-07 | 3 |  | Mahalakshmi | 2017-07-20 | 2017-07-20 | 2017-07-21 | 2 | 2017-07-21 | [6 empty] | 10 | 0 | 0 | 0 | 0 | 13 | 3
2CMO-63 | RFS.93 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-11 | Parth | 2017-07-11 | 2017-07-13 | 3 |  | NA | 2017-07-19 | 2017-07-19 | 2017-07-20 | 2 | 2017-07-20 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 8 | 3
3SPL-64 | RFS.100 | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-06 | Parth | 2017-07-06 | 2017-07-10 | 3 |  | Gaurav | 2017-07-17 | 2017-07-17 | 2017-07-18 | 2 | 2017-07-18 | [6 empty] | 6 | 0 | 0 | 0 | 0 | 9 | 3
4CHD-62 | RFS.97 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-06 | Gaurav | 2017-07-06 | 2017-07-10 | 3 |  | Gaurav | 2017-08-09 | 2017-08-09 | 2017-08-11 | 3 | 2017-08-11 | [6 empty] | 23 | 0 | 0 | 0 | 0 | 27 | 4
3BLB-67 |  | M-A-H | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-07-07 | Mahalakshmi | 2017-07-07 | 2017-07-11 | 3 | [5 empty] | 0 | [7 empty] | -30641 | 0 | 0 | -1 | 0 | -30639 | 3
5FLN-62 |  | H-B-J | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-07-05 | Deepa | 2017-07-05 | 2017-07-13 | 7 | [5 empty] | 0 | [7 empty] | -30643 | 0 | 0 | -1 | 0 | -30637 | 7
4MGA-70 | RFS.114 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-07-07 | Swathy Mohan | 2017-07-07 | 2017-07-11 | 3 |  | Abhay | 2017-07-19 | 2017-07-19 | 2017-07-20 | 2 | 2017-07-20 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 10 | 3
4OXE-62 |  | H-A-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-07-07 | Manikandan | 2017-07-07 | 2017-07-24 | 12 | [5 empty] | 0 | [7 empty] | -30650 | 0 | 0 | -1 | 0 | -30639 | 12
3MLN-63 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-08 | NA | 2017-07-08 | 2017-07-17 | 6 |  | NA | 2017-07-17 | 2017-07-10 | 2017-07-17 | 6 | 2017-07-17 | [6 empty] | 1 | -1 | 0 | -7 | 0 | 6 | 13
4SOP-64 |  | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-07-10 | Sangeetha | 2017-07-10 | 2017-07-19 | 8 | [5 empty] | 0 | [7 empty] | -30647 | 0 | 0 | -1 | 0 | -30640 | 8
2MOS-62 | RFS.95 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-03 | Parth | 2017-08-03 | 2017-08-04 | 2 |  | Parth | 2017-08-05 | 2017-08-05 | 2017-08-07 | 1 | 2017-08-07 | [6 empty] | 1 | 0 | 0 | -1 | 0 | 3 | 3
3BGO-62 |  | M-A-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-07-11 | Gaurav | 2017-07-11 | 2017-07-19 | 7 | [5 empty] | 0 | [7 empty] | -30647 | 0 | 0 | -1 | 0 | -30641 | 7
5BRI-60 | RFS.140 | H-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-07-11 | NA | 2017-07-11 | 2017-07-13 | 3 |  | NA | 2017-07-19 | 2017-07-19 | 2017-07-20 | 2 | 2017-07-20 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 8 | 3
2EAS-65 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-13 | Sangeetha | 2017-07-13 | 2017-07-20 | 6 |  | sangeetha | 2017-07-18 | 2017-07-21 | 2017-07-24 | 2 | 2017-07-24 | [6 empty] | -3 | 0 | 0 | 3 | 0 | 8 | 8
3SPL-62 | RFS.107 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-07-14 | Neethu | 2017-07-14 | 2017-07-18 | 3 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30644 | #VALUE!
2ASH-62 |  | H-M-Q | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-07-14 | Aravind | 2017-07-14 | 2017-07-19 | 4 | [5 empty] | 0 | [7 empty] | -30647 | 0 | 0 | -1 | 0 | -30644 | 4
4BLH-66 | RFS.94 | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-06 | Parth | 2017-07-06 | 2017-07-10 | 3 |  | Gaurav | 2017-08-01 | 2017-08-01 | 2017-08-02 | 2 | 2017-08-02 | [6 empty] | 17 | 0 | 0 | 0 | 0 | 20 | 3
2BAL-65 | RFS.93 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-13 | Abhay | 2017-07-13 | 2017-07-17 | 3 |  | NA | 2017-07-24 | 2017-07-25 | 2017-07-26 | 2 | 2017-07-26 | [6 empty] | 6 | 0 | 0 | 1 | 0 | 10 | 3
2STL-63 | RFS.104 | H-B-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-07-14 | NA | 2017-07-14 | 2017-07-21 | 6 |  | NA | 2017-07-21 | 2017-07-20 | 2017-07-24 | 3 | 2017-07-24 | [6 empty] | 1 | 0 | 0 | -3 | 0 | 7 | 9
2ENG-62 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-14 | NA | 2017-07-14 | 2017-07-20 | 5 |  | NA | 2017-07-20 | 2017-07-18 | 2017-07-24 | 5 | 2017-07-24 | [6 empty] | 1 | 0 | 0 | -4 | 0 | 7 | 10
2EPP-61 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-14 | NA | 2017-07-14 | 2017-07-20 | 5 |  | NA | 2017-07-20 | 2017-07-20 | 2017-07-26 | 5 | 2017-07-26 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 9 | 8
2ROS-65 | RFS.92 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-14 | NA | 2017-07-17 | 2017-07-21 | 5 |  | NA | 2017-07-21 | 2017-07-19 | 2017-07-24 | 4 | 2017-07-24 | [6 empty] | 1 | 1 | 0 | -4 | 0 | 7 | 9
4OXE-63 | RFS.0 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-17 | Swathy | 2017-07-17 | 2017-07-19 | 3 |  | NA | 2017-07-20 | 2017-07-20 | 2017-07-23 | 3 | 2017-07-24 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4APL-60 | RFS.122 | M-M-H | BAU | Design | 1 | In Progress - [PC] Perform Check Completion | 2017-07-17 | NA | 2017-07-18 | 2017-07-25 | 6 |  | NA | 2017-07-25 | 2017-07-24 | 2017-07-27 | 4 | 2017-07-27 | [6 empty] | 1 | 1 | 0 | -3 | 0 | 9 | 10
4MGB-01 |  | M-B-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-07-17 | Swathy | 2017-07-17 | 2017-07-25 | 7 | [5 empty] | 0 | [7 empty] | -30651 | 0 | 0 | -1 | 0 | -30645 | 7
4CPH-69 | RFS.93 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-18 | Aravind | 2017-07-18 | 2017-07-20 | 3 |  | NA | 2017-07-20 | 2017-07-20 | 2017-07-27 | 6 | 2017-07-27 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 8 | 7
2ING-64 | RFS.112 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-07-31 | NA | 2017-08-01 | 2017-08-04 | 4 |  | NA | 2017-08-04 | 2017-08-04 | 2017-08-05 | 1 | 2017-08-05 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 5 | 3
4IAL-61 | RFS.114 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-19 | Aravind | 2017-07-19 | 2017-07-21 | 3 |  | Rikku | 2017-07-26 | 2017-07-26 | 2017-07-28 | 3 | 2017-07-28 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 8 | 4
4CHD-60 | RFS.126 | M-M-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-07-18 | Devi | 2017-07-18 | 2017-07-20 | 3 |  | Deepa | 2017-07-25 | 2017-07-25 | 2017-07-26 | 2 | 2017-07-26 |  | 2017-07-30 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 7 | 3
3BLB-67 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-18 | Gaurav | 2017-07-18 | 2017-07-20 | 3 |  | Manikandan | 2017-08-04 | 2017-08-04 | 2017-08-07 | 2 | 2017-08-07 | [6 empty] | 12 | 0 | 0 | 0 | 0 | 15 | 3
2PET-60 | RFS.92 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-18 | Sangeetha | 2017-07-18 | 2017-07-19 | 2 |  | NA | 2017-08-21 | 2017-08-21 | 2017-08-23 | 3 | 2017-08-23 | [6 empty] | 23 | 0 | 0 | 0 | 0 | 26 | 3
4CHD-01 | RFS.117 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-07-19 | Haritha | 2017-07-19 | 2017-07-21 | 3 |  | NA |  |  |  | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30647 | #VALUE!
4MGA-66 | RFS.114 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-19 | Mahalakshmi | 2017-07-19 | 2017-09-01 | 32 |  | joju | 2017-09-25 | 2017-09-25 | 2017-09-28 | 4 | 2017-09-29 | [6 empty] | 15 | 0 | 0 | 0 | 0 | 49 | 34
3NCO-60 |  | M-M-H | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-07-19 | Swathy | 2017-07-19 | 2017-07-21 | 3 | [5 empty] | 0 | [7 empty] | -30649 | 0 | 0 | -1 | 0 | -30647 | 3
2BAM-64 | RFS.93 | M-M-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2017-07-19 | Krishnan | 2017-07-19 | 2017-07-31 | 9 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30647 | #VALUE!
4SLA-75 |  | M-B-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-07-19 | Deepa | 2017-07-19 | 2017-07-21 | 3 | [5 empty] | 0 | [7 empty] | -30649 | 0 | 0 | -1 | 0 | -30647 | 3
2LIV-68 | RFS.93 | M-M-H | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-07-20 | Parth | 2017-07-20 | 2017-07-24 | 3 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30648 | #VALUE!
4CHD-64 | RFS.97 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-07-20 | NA | 2017-07-20 | 2017-07-24 | 3 |  | Aravind | 2017-08-28 | 2017-08-28 | 2017-08-30 | 3 | 2017-08-30 | [6 empty] | 25 | 0 | 0 | 0 | 0 | 29 | 4
4BUR-68 | RFS.91 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-21 | Alan Babu | 2017-07-21 | 2017-07-22 | 1 |  | NA | 2017-07-23 | 2017-07-26 | 2017-07-26 | 1 | 2017-07-26 | [6 empty] | 0 | 0 | 0 | 2 | 0 | 4 | 2
3GLI-61 | RFS.91 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-20 | Anusa Moottoolikandy | 2017-07-20 | 2017-07-24 | 3 |  | NA | 2017-07-25 | 2017-07-25 | 2017-07-28 | 4 | 2017-07-28 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
3NCO-68 | RFS.97 | H-A-Q | HAC | Pre-AT |  | On Hold | 2017-07-21 | Aravind | 2017-07-21 | 2017-07-25 | 3 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30649 | #VALUE!
2BAN-63 | RFS.112 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-24 | Manikandan | 2017-07-24 | 2017-07-27 | 4 |  | Haritha | 2017-07-28 | 2017-07-28 | 2017-07-31 | 2 | 2017-07-31 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3CAU-62 | RFS.92 | H-A-Q | HAC | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-07-21 | Sangeetha | 2017-07-21 | 2017-07-24 | 2 | [5 empty] | 0 | [7 empty] | -30650 | 0 | 0 | -1 | 0 | -30649 | 2
4CHD-65 | RFS.97 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-25 | Swathy | 2017-07-25 | 2017-07-28 | 4 |  | NA | 2017-07-31 | 2017-07-31 | 2017-08-02 | 3 | 2017-08-02 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
3MIT-64 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-24 | NA | 2017-07-25 | 2017-07-31 | 5 |  | NA | 2017-07-31 | 2017-07-31 | 2017-08-01 | 2 | 2017-08-01 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 7 | 5
3KGP-65 | RFS.93 | M-A-H | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-07-24 | Swathy | 2017-07-24 | 2017-07-24 | 1 |  | swathy mohan | 2017-07-31 | 2017-07-31 | 2017-07-31 | 1 | 2017-07-31 | [6 empty] | 6 | 0 | 0 | 0 | 0 | 6 | 0
3BGO-62 |  | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-25 | Swathy | 2017-07-25 | 2017-07-28 | 4 |  | swathy mohan | 2017-07-31 | 2017-07-31 | 2017-08-02 | 3 | 2017-08-02 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
3SPL-67 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-25 | Parth | 2017-07-25 | 2017-07-27 | 3 |  | Arya | 2017-07-28 | 2017-07-28 | 2017-07-31 | 2 | 2017-07-31 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2ASH-68 | RFS.0 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-25 | NA | 2017-07-26 | 2017-07-31 | 4 |  | NA | 2017-07-31 | 2017-07-27 | 2017-08-01 | 4 | 2017-08-01 | [6 empty] | 1 | 1 | 0 | -4 | 0 | 6 | 8
2ROS-62 | RFS.94 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-25 | NA | 2017-07-26 | 2017-07-31 | 4 |  | NA | 2017-07-31 | 2017-07-31 | 2017-08-04 | 5 | 2017-08-04 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 9 | 7
2SHA-62 | RFS.94 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-26 | Mahalakshmi | 2017-07-26 | 2017-07-28 | 3 |  | NA | 2017-07-28 | 2017-07-31 | 2017-08-03 | 4 | 2017-08-03 | [6 empty] | 1 | 0 | 0 | 1 | 0 | 7 | 5
2ASH-62 |  | H-M-Q | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-07-27 | Nisha | 2017-07-27 | 2017-07-28 | 2 | [5 empty] | 0 | [7 empty] | -30654 | 0 | 0 | -1 | 0 | -30653 | 2
4MGA-68 | RFS.114 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-07-27 | Parth | 2017-07-28 | 2017-07-31 | 2 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 1 | 0 | #VALUE! | 0 | -30653 | #VALUE!
2EDG-65 | RFS.65 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-27 | Gaurav | 2017-07-27 | 2017-07-31 | 3 |  | Gaurav | 2017-08-01 | 2017-08-01 | 2017-08-03 | 3 | 2017-08-03 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4SLA-75 |  | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-07-31 | Mahalakshmi | 2017-07-31 | 2017-08-02 | 3 |  | mahalakshmi | 2017-08-08 | 2017-08-08 | 2017-08-09 | 2 | 2017-08-09 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 8 | 3
2MEN-63 | RFS.117 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-28 | Swathy | 2017-07-28 | 2017-08-02 | 4 |  | Swathy | 2017-08-05 | 2017-08-05 | 2017-08-09 | 3 | 2017-08-09 | [6 empty] | 3 | 0 | 0 | -1 | 0 | 9 | 7
4CHD-63 | RFS.107 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-28 | Manikandan | 2017-07-28 | 2017-07-31 | 2 |  | Manikandan | 2017-08-02 | 2017-08-02 | 2017-08-03 | 2 | 2017-08-03 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 5 | 2
4SOP-64 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-07-28 | Swathy | 2017-07-28 | 2017-08-02 | 4 |  | Swathy | 2017-08-05 | 2017-08-05 | 2017-08-09 | 3 | 2017-08-09 | [6 empty] | 3 | 0 | 0 | -1 | 0 | 9 | 7
3BLB-64 | RFS.93 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-28 | NA | 2017-07-28 | 2017-08-01 | 3 |  | NA | 2017-08-01 | 2017-08-01 | 2017-08-02 | 2 | 2017-08-02 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
6GIR-62 | RFS.97 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-28 | NA | 2017-07-28 | 2017-08-02 | 4 |  | NA | 2017-08-02 | 2017-08-02 | 2017-08-07 | 4 | 2017-08-07 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 7 | 6
5BRI-67 | RFS.100 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-07-31 | Rikku | 2017-07-31 | 2017-08-02 | 3 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30655 | #VALUE!
2STL-61 | RFS.104 | M-M-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-07-31 | Linda | 2017-07-31 | 2017-08-02 | 3 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30655 | #VALUE!
4SLA-68 | RFS.68 | H-A-H | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-07-31 | Mahalakshmi | 2017-07-31 | 2017-08-02 | 3 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30655 | #VALUE!
2PET-63 |  | H-A-Q | HAC | Pre-AT | 1 | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-07-31 | Alan Babu | 2017-07-31 | 2017-07-31 | 1 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | #VALUE! | #VALUE!
3DNC-61 | RFS.98 | H-A-Q | HAC | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-08-01 | Aravind | 2017-08-01 | 2017-08-03 | 3 |  | NA | 2017-08-04 | 2017-08-04 | 2017-08-04 | 1 | 2017-08-04 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
3RWO-60 | RFS.98 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-07-31 | Anusa Moottoolikandy | 2017-07-31 | 2017-08-01 | 2 |  | NA | 2017-08-01 | 2017-08-01 | 2017-08-05 | 4 | 2017-08-05 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 5 | 4
6KSL-60 | RFS.95 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-08-01 | Sangeetha | 2017-08-01 | 2017-08-03 | 3 |  | NA | 2017-08-03 | 2017-08-03 | 2017-08-05 | 2 | 2017-08-05 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
2SEF-67 | RFS.95 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-01 | Aravind | 2017-08-01 | 2017-08-04 | 4 |  | Aravind | 2017-08-04 | 2017-08-04 | 2017-08-04 | 1 | 2017-08-04 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
4MGB-61 |  | H-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-02 | Krishnan | 2017-08-03 | 2017-08-07 | 3 |  | Manikandan | 2017-08-10 | 2017-08-10 | 2017-08-11 | 2 | 2017-08-11 | [6 empty] | 4 | 1 | 0 | 0 | 0 | 8 | 3
2EPP-62 | RFS.117 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-08-02 | Joju | 2017-08-02 | 2017-08-04 | 3 |  | Linda | 2017-09-27 | 2017-09-28 | 2017-09-29 | 1 | 2017-09-29 | [6 empty] | 36 | 0 | 0 | 1 | 0 | 39 | 2
2PET-63 |  | H-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-08-02 | Nisha | 2017-08-02 | 2017-08-05 | 3 |  | Gaurav | 2017-08-06 | 2017-08-07 | 2017-08-10 | 4 | 2017-08-10 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 7 | 7
2EAS-62 |  | M-M-H | BAU | Design |  | On Hold - [PC] Awaiting Boundary Update | 2017-08-02 | Abhay | 2017-08-02 | 2017-08-03 | 2 | [5 empty] | 0 | [7 empty] | -30658 | 0 | 0 | -1 | 0 | -30657 | 2
6SUB-66 | RFS.0 | M-M-H | BAU | Design | 1 | Rejected - [PC] Sent Back to Telstra (AP) | 2017-08-02 | Linda | 2017-08-02 | 2017-08-16 | 10 |  | mani | 2017-08-04 | 2017-08-04 | 2017-08-09 | 4 | 2017-08-09 | [6 empty] | -8 | 0 | 0 | 0 | 0 | 6 | 14
3MIT-63 | RFS.98 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-02 | Alan Babu | 2017-08-02 | 2017-08-03 | 2 |  | NA | 2017-08-04 | 2017-08-05 | 2017-08-09 | 3 | 2017-08-09 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
5EDW-68 | RFS.120 | H-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-03 | Gaurav | 2017-08-03 | 2017-08-05 | 2 |  | Krishnan | 2017-08-15 | 2017-08-15 | 2017-08-16 | 1 | 2017-08-16 | [6 empty] | 6 | 0 | 0 | -1 | 0 | 9 | 4
4OXE-62 |  | H-A-H | BAU | Pre-AT |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-08-03 | Gaurav | 2017-08-03 | 2017-08-24 | 15 | [5 empty] | 0 | [7 empty] | -30672 | 0 | 0 | -1 | 0 | -30658 | 15
4BUR-64 | RFS.95 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-03 | Krishnan | 2017-08-03 | 2017-08-04 | 2 |  | Krishnan | 2017-08-17 | 2017-08-17 | 2017-08-18 | 2 | 2017-08-18 | [6 empty] | 9 | 0 | 0 | 0 | 0 | 11 | 2
5MOD-63 |  | M-A-J | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-08-03 | Anusa | 2017-08-03 | 2017-08-14 | 8 | [5 empty] | 0 | [7 empty] | -30665 | 0 | 0 | -1 | 0 | -30658 | 8
4MGA-67 | RFS.117 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-04 | Nisha | 2017-08-04 | 2017-08-07 | 2 |  | Sangeetha | 2017-09-06 | 2017-09-06 | 2017-09-06 | 3 | 2017-09-08 | [6 empty] | 20 | 0 | 0 | 0 | 0 | 23 | 3
4BUR-62 | RFS.94 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-04 | Mahalakshmi | 2017-08-04 | 2017-08-08 | 3 |  | Parth | 2017-08-09 | 2017-08-09 | 2017-08-16 | 5 | 2017-08-16 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 8 | 6
4MGB-66 |  | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-03 | Deepa M04 | 2017-08-03 | 2017-08-04 | 2 |  | NA | 2017-08-07 | 2017-08-07 | 2017-08-10 | 4 | 2017-08-10 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3WIR-62 | RFS.96 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-07 | Anusa Moottoolikandy | 2017-08-07 | 2017-08-09 | 3 |  | NA | 2017-08-10 | 2017-08-10 | 2017-08-14 | 3 | 2017-08-14 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
2CRR-69 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-07 | Aravind | 2017-08-07 | 2017-08-09 | 3 |  | Aravind | 2017-08-14 | 2017-08-14 | 2017-08-16 | 2 | 2017-08-16 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 7 | 3
3WER-64 | RFS.100 | M-B-H [P] | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-07 | Bhagyalekshmi | 2017-08-07 | 2017-08-09 | 3 |  | Bhagyalekshmi | 2017-09-19 | 2017-09-19 | 2017-09-21 | 4 | 2017-09-22 | [6 empty] | 27 | 0 | 0 | 0 | 0 | 32 | 5
3NCO-60 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-07 | Abhay | 2017-08-07 | 2017-08-09 | 3 |  | Krishnan | 2017-08-28 | 2017-08-28 | 2017-08-31 | 4 | 2017-08-31 | [6 empty] | 13 | 0 | 0 | 0 | 0 | 18 | 5
2BAL-66 | RFS.97 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-07 | Abhay | 2017-08-07 | 2017-08-09 | 3 |  | Krishnan | 2017-08-11 | 2017-08-11 | 2017-08-15 | 2 | 2017-08-15 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
4BNP-64 | RFS.115 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2017-08-08 | Naveen | 2017-08-08 | 2017-08-24 | 12 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30661 | #VALUE!
2CRR-72 | RFS.95 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-07 | Krishnan | 2017-08-07 | 2017-08-09 | 3 |  | Parth | 2017-08-16 | 2017-08-16 | 2017-08-18 | 3 | 2017-08-18 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 9 | 4
3NCO-66 | RFS.97 | M-M-H | BAU | Design | 1 | In Progress - [PC] Perform Check Completion | 2017-08-07 | Parth | 2017-08-07 | 2017-08-09 | 3 | [5 empty] | 30665 | 2017-08-14 | [6 empty] | -30662 | 0 | 0 | -1 | 0 | 6 | 30669
2ASH-62 |  | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-08 | Manikandan | 2017-08-08 | 2017-08-09 | 2 |  | Mahalakshmi | 2017-08-17 | 2017-08-17 | 2017-08-18 | 21 | 2017-09-18 | [6 empty] | 6 | 0 | 0 | 0 | 0 | 27 | 21
4MGB-01 |  | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-08 | Naveen | 2017-08-08 | 2017-08-10 | 3 |  | Rikku | 2017-08-15 | 2017-08-15 | 2017-08-16 | 1 | 2017-08-16 | [6 empty] | 3 | 0 | 0 | -1 | 0 | 6 | 4
5FLN-62 |  | H-B-J | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-08-08 | Mahalakshmi | 2017-08-08 | 2017-08-24 | 12 | [5 empty] | 0 | [7 empty] | -30672 | 0 | 0 | -1 | 0 | -30661 | 12
4SLA-64 | RFS.104 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-08-08 | Mahalakshmi | 2017-08-08 | 2017-08-17 | 7 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30661 | #VALUE!
2BAN-61 | RFS.113 | H-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-08-08 | Abhay | 2017-08-08 | 2017-08-29 | 15 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30661 | #VALUE!
3SOA-60 | RFS.96 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-08 | Nisha | 2017-08-08 | 2017-08-10 | 3 |  | Krishnan | 2017-08-21 | 2017-08-21 | 2017-08-22 | 2 | 2017-08-22 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 10 | 3
2PET-69 | RFS.96 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-08 | Gaurav | 2017-08-08 | 2017-08-10 | 3 |  | Parth | 2017-08-21 | 2017-08-21 | 2017-08-23 | 3 | 2017-08-23 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 11 | 4
4MGB-63 | RFS.95 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-09 | Anusa Moottoolikandy | 2017-08-09 | 2017-08-11 | 3 |  | NA | 2017-08-12 | 2017-08-12 | 2017-08-17 | 3 | 2017-08-17 | [6 empty] | 1 | 0 | 0 | -1 | 0 | 6 | 6
4ASH-62 | RFS.95 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-09 | Deepa M04 | 2017-08-09 | 2017-08-12 | 3 |  | NA | 2017-08-12 | 2017-08-12 | 2017-08-15 | 1 | 2017-08-15 | [6 empty] | 0 | 0 | 0 | -1 | 0 | 4 | 5
2EAS-67 | RFS.96 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-11 | Aravind | 2017-08-11 | 2017-08-15 | 2 |  | Mohith | 2017-08-18 | 2017-08-18 | 2017-08-22 | 4 | 2017-08-23 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 8 | 5
2EAS-68 | RFS.0 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-11 | Mahalakshmi | 2017-08-11 | 2017-08-15 | 2 |  | Mahalakshmi | 2017-08-21 | 2017-08-21 | 2017-08-25 | 5 | 2017-08-25 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 10 | 6
4CHP-60 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-14 | Gaurav | 2017-08-14 | 2017-08-16 | 2 |  | Gaurav | 2017-08-17 | 2017-08-17 | 2017-08-21 | 3 | 2017-08-21 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
5BRI-64 | RFS.123 | H-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-08-14 | Abhay Arora | 2017-08-14 | 2017-08-29 | 11 | [5 empty] | #VALUE! | [7 empty] | #VALUE! | 0 | 0 | #VALUE! | 0 | -30665 | #VALUE!
2EAS-65 | 96 | M-M-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-08-14 | Mahalakshmi | 2017-08-14 | 2017-08-15 | 1 |  | Mahalakshmi | 2017-08-16 | 2017-08-16 | 2017-08-16 | 1 | 2017-08-16 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 2 | 1
2BON-65 | RFS.99 | H-A-Q | HAC | Pre-AT | 1 | Completed | 2017-08-15 | Mahalakshmi | 2017-08-15 | 2017-08-16 | 1 |  | NA | 2017-08-17 | 2017-08-17 | 2017-08-21 | 3 | 2017-08-21 | [6 empty] | 2 | -1 | 0 | 0 | 0 | 4 | 3
3SOA-65 | RFS.98 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-15 | Deepa M04 | 2017-08-15 | 2017-08-18 | 3 |  | NA | 2017-08-21 | 2017-08-21 | 2017-08-22 | 2 | 2017-08-22 | [6 empty] | 2 | -1 | 0 | 0 | 0 | 5 | 4
2EDG-62 | RFS.96 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-16 | Nisha | 2017-08-16 | 2017-08-17 | 2 |  | Aravind | 2017-08-18 | 2017-08-18 | 2017-08-21 | 2 | 2017-08-21 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
2EAS-62 |  | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-16 | Naveen | 2017-08-16 | 2017-08-17 | 2 |  | Naveen Kumar | 2017-08-18 | 2017-08-18 | 2017-08-21 | 2 | 2017-08-21 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
4WTF-22 | RFS.22 | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-17 | Nisha | 2017-08-17 | 2017-08-21 | 3 |  | Rikku | 2017-12-04 | 2017-12-11 | 2017-12-13 | 3 | 2017-12-13 | 4/12: SAM Placed on hold. Awaiting confirmation from NA team to proceed. 6/12: Awaiting project details to proceed with full run | [5 empty] | 70 | 0 | 0 | 5 | 0 | 79 | 4
2PEN-63 |  | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-15 | Mohith | 2017-08-15 | 2017-08-18 | 3 |  | NA | 2017-08-21 | 2017-08-21 | 2017-08-31 | 9 | 2017-08-31 | [6 empty] | 2 | -1 | 0 | 0 | 0 | 12 | 11
2PET-63 |  | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-17 | Alan Babu | 2017-08-17 | 2017-08-18 | 2 |  | NA | 2017-08-18 | 2017-08-18 | 2017-08-18 | 3 | 2017-08-22 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
3CAU-62 | RFS.92 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-17 | Sangeetha | 2017-08-17 | 2017-08-18 | 2 |  | NA | 2017-08-18 | 2017-08-18 | 2017-08-25 | 6 | 2017-08-25 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 7 | 6
4EMP-63 | RFS.98 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-18 | Sangeetha | 2017-08-18 | 2017-08-21 | 2 |  | sangeetha | 2017-08-22 | 2017-08-22 | 2017-08-22 | 1 | 2017-08-22 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 3 | 1
2BON-67 | RFS.67 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-18 | Alan | 2017-08-18 | 2017-08-21 | 2 |  | NA | 2017-08-22 | 2017-08-22 | 2017-08-25 | 4 | 2017-08-25 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
2STL-64 | RFS.104 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-18 | Nisha | 2017-08-18 | 2017-08-22 | 3 |  | Manikandan | 2017-08-24 | 2017-08-23 | 2017-08-24 | 2 | 2017-08-24 | [6 empty] | 3 | 0 | 0 | -3 | 0 | 5 | 5
4CUR-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-18 | Mohith | 2017-08-18 | 2017-08-18 | 1 |  | mohith | 2017-08-21 | 2017-08-21 | 2017-08-21 | 6 | 2017-08-28 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
4SRW-62 | RFS.121 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-08-18 | Abhay Arora | 2017-08-18 | 2017-08-24 | 5 | [5 empty] | 0 | [7 empty] | -30672 | 0 | 0 | -1 | 0 | -30668 | 5
5MOD-63 | RFS.63 | M-A-J | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-21 | Joju | 2017-08-21 | 2017-08-23 | 3 |  | Krishnan | 2017-08-24 | 2017-08-24 | 2017-08-28 | 3 | 2017-08-28 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4AAR-63 | RFS.122 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-08-21 | Linda | 2017-08-22 | 2017-08-24 | 3 | [5 empty] | 0 | [7 empty] | -30672 | 1 | 0 | -1 | 0 | -30669 | 3
4AGV-64 | RFS.122 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-08-21 | Gaurav | 2017-08-22 | 2017-08-29 | 6 | [5 empty] | 0 | [7 empty] | -30675 | 1 | 0 | -1 | 0 | -30669 | 6
4MGA-63 | RFS.0 | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-22 | Swathy Mohan | 2017-08-22 | 2017-08-24 | 3 |  | Mohith | 2017-08-29 | 2017-08-29 | 2017-08-29 | 1 | 2017-08-29 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 6 | 2
3BOX-65 | RFS.98 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-22 | Abhay Arora | 2017-08-22 | 2017-08-23 | 2 |  | Parth | 2017-08-31 | 2017-08-31 | 2017-09-07 | 4 | 2017-09-07 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 11 | 4
6MLO-64 | RFS.99 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-22 | Anusa Moottoolikandy | 2017-08-22 | 2017-08-22 | 1 |  | Anusa Moottoolikandy | 2017-08-23 | 2017-08-24 | 2017-08-24 | 3 | 2017-08-28 | [6 empty] | 2 | 0 | 0 | 1 | 0 | 5 | 2
3BLB-65 | RFS.0 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-23 | Mahalakshmi | 2017-08-23 | 2017-08-25 | 3 |  | Manikandan | 2017-09-07 | 2017-09-07 | 2017-09-12 | 4 | 2017-09-12 | [6 empty] | 8 | 0 | 0 | 0 | 0 | 13 | 5
4BUR-67 | RFS.112 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-23 | Nisha | 2017-08-23 | 2017-08-25 | 3 |  | Manikandan | 2017-08-28 | 2017-08-28 | 2017-08-29 | 2 | 2017-08-29 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2WET-65 | RFS.100 | M-M-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-08-24 | Parth | 2017-08-24 | 2017-08-31 | 6 | [5 empty] | 0 | [7 empty] | -30677 | 0 | 0 | -1 | 0 | -30672 | 6
4CPB-20 | RFS.98 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-24 | Joju | 2017-08-24 | 2017-08-25 | 2 |  | Naveen Kumar | 2017-09-06 | 2017-09-06 | 2017-09-08 | 3 | 2017-09-08 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 10 | 3
3DNC-61 | RFS.95 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-24 | Alan Babu | 2017-08-24 | 2017-08-25 | 2 |  | alan babu | 2017-08-29 | 2017-08-29 | 2017-09-01 | 4 | 2017-09-01 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 7 | 4
4NDG-60 | RFS.143 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-25 | Mahalakshmi | 2017-08-25 | 2017-08-29 | 3 |  | Krishnan | 2017-11-13 | 2017-11-16 | 2017-11-17 | 2 | 2017-11-17 | 17/11: Cycle time increased due to high SAM volume | [5 empty] | 49 | 0 | 0 | 3 | 0 | 55 | 3
4BUR-21 | RFS.94 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-25 | Swathy Mohan | 2017-08-25 | 2017-08-29 | 3 |  | mahalakshmi | 2017-09-06 | 2017-09-06 | 2017-09-08 | 3 | 2017-09-08 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 9 | 4
2EPP-65 | RFS.118 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-25 | Nisha | 2017-08-25 | 2017-08-29 | 3 |  | Sangeetha | 2017-08-31 | 2017-08-31 | 2017-09-01 | 2 | 2017-09-01 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
2CRR-60 | RFS.100 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-25 | Linda | 2017-08-25 | 2017-08-29 | 3 |  | Gaurav | 2017-09-03 | 2017-09-06 | 2017-09-08 | 3 | 2017-09-08 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 9 | 5
3BNT-63 | RFS.96 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-28 | Anusa Moottoolikandy | 2017-08-28 | 2017-08-28 | 1 |  | Anusa Moottoolikandy | 2017-08-29 | 2017-08-29 | 2017-08-31 | 3 | 2017-08-31 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
4SRW-61 | RFS.103 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-28 | Bhagyalekshmi | 2017-08-28 | 2017-08-28 | 1 |  | Bhagyalekshmi | 2017-08-29 | 2017-08-29 | 2017-09-01 | 4 | 2017-09-01 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
3DAD-67 | RFS.97 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-28 | Naveen Kumar | 2017-08-28 | 2017-08-28 | 1 |  | Naveen Kumar | 2017-08-29 | 2017-08-29 | 2017-09-01 | 4 | 2017-09-01 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4AGV-62 | RFS.118 | M-M-H | BAU | Design |  | Completed [PC] - Trigger Triage | 2017-08-28 | Rikku | 2017-08-29 | 2017-08-31 | 3 | [5 empty] | 0 | [7 empty] | -30677 | 1 | 0 | -1 | 0 | -30674 | 3
2BAN-70 | RFS.124 | M-B-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-08-28 | Sangeetha | 2017-08-29 | 2017-08-31 | 3 | [5 empty] | 0 | [7 empty] | -30677 | 1 | 0 | -1 | 0 | -30674 | 3
2CRR-66 | RFS.105 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-08-28 | Nisha | 2017-08-29 | 2017-08-31 | 3 | [5 empty] | 0 | [7 empty] | -30677 | 1 | 0 | -1 | 0 | -30674 | 3
4BLH-62 | RFS.118 | M-B-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-08-28 | Mohith | 2017-08-29 | 2017-08-31 | 3 | [5 empty] | 0 | [7 empty] | -30677 | 1 | 0 | -1 | 0 | -30674 | 3
4WTF-60 | RFS.122 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-08-28 | Naveen Kumar | 2017-08-29 | 2017-08-31 | 3 | [5 empty] | 0 | [7 empty] | -30677 | 1 | 0 | -1 | 0 | -30674 | 3
2BAN-63 | RFS.112 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-28 | Parth | 2017-08-29 | 2017-08-31 | 3 |  | Mohith | 2017-11-30 | 2017-11-30 | 2017-12-04 | 3 | 2017-12-04 | [6 empty] | 60 | 1 | 0 | 0 | 0 | 65 | 4
4CPR-62 | RFS.121 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (LDM) | 2017-08-28 | Gaurav | 2017-08-29 | 2017-08-31 | 3 | [5 empty] | 0 | [7 empty] | -30677 | 1 | 0 | -1 | 0 | -30674 | 3
4EMP-02 | RFS.99 | M-B-H | BAU | Pre-AT |  | Rejected | 2017-08-28 | Gaurav | 2017-08-28 | 2017-08-30 | 3 | [5 empty] | 0 | [7 empty] | -30676 | 0 | 0 | -1 | 0 | -30674 | 3
2STL-63 | RFS.103 | H-B-Q | HAC | Pre-AT |  | Completed | 2017-08-28 | Mahalakshmi | 2017-08-29 | 2017-08-31 | 3 |  | Mani | 2017-09-01 | 2017-09-01 | 2017-09-06 | 2 | 2017-09-06 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 6 | 3
3RWO-61 | RFS.98 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-28 | Deepa M04 | 2017-08-30 | 2017-08-30 | 1 |  | deepa m04 | 2017-08-31 | 2017-08-31 | 2017-09-01 | 2 | 2017-09-01 | [6 empty] | 2 | 2 | 0 | 0 | 0 | 5 | 1
3DAD-66 | RFS.97 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-28 | Alan Babu | 2017-08-29 | 2017-08-29 | 1 |  | alan babu | 2017-08-30 | 2017-08-30 | 2017-09-08 | 6 | 2017-09-08 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 8 | 5
3DAD-63 | RFS.97 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-08-28 | Aravind | 2017-08-30 | 2017-08-31 | 2 |  | aravind | 2017-09-01 | 2017-09-01 | 2017-09-07 | 3 | 2017-09-07 | [6 empty] | 2 | 2 | 0 | 0 | 0 | 7 | 3
4CPH-66 | RFS.115 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-29 | Linda | 2017-08-29 | 2017-08-31 | 3 |  | Parth | 2017-09-04 | 2017-09-04 | 2017-09-11 | 4 | 2017-09-11 | [6 empty] | 2 | 0 | 0 | -1 | 0 | 8 | 7
4AAR-63 | RFS.122 | M-M-H | BAU | Design |  | [PC] On Hold - Data Issues | 2017-08-29 | Swathy Mohan | 2017-08-29 | 2017-08-30 | 2 | [5 empty] | 0 | [7 empty] | -30676 | 0 | 0 | -1 | 0 | -30675 | 2
4APL-60 | RFS.122 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-08-29 | Bhagyalekshmi | 2017-08-30 | 2017-08-31 | 2 | [5 empty] | 0 | [7 empty] | -30677 | 1 | 0 | -1 | 0 | -30675 | 2
6GIR-68 | RFS.118 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-08-30 | Mahalakshmi | 2017-08-30 | 2017-09-01 | 3 | [5 empty] | 0 | [7 empty] | -30678 | 0 | 0 | -1 | 0 | -30676 | 3
2STL-61 | RFS.104 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-08-30 | Gaurav | 2017-08-30 | 2017-09-06 | 4 |  | Gaurav | 2017-09-19 | 2017-09-20 | 2017-09-22 | 3 | 2017-09-22 | [6 empty] | 10 | 0 | 0 | 1 | 0 | 16 | 5
5WES-64 | RFS.108 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-30 | Deepa M04 | 2017-08-30 | 2017-08-31 | 2 |  | deepa m04 | 2017-09-01 | 2017-09-01 | 2017-09-11 | 5 | 2017-09-11 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
2MIL-60 | RFS.103 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-31 | Nisha | 2017-08-31 | 2017-09-06 | 3 |  | Krishnan | 2017-09-27 | 2017-09-27 | 2017-09-29 | 2 | 2017-09-29 | [6 empty] | 16 | 0 | 0 | 0 | 0 | 19 | 3
2PYM-60 | RFS.99 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-08-31 | mohith | 2017-08-31 | 2017-09-01 | 2 |  | Mohith | 2017-09-06 | 2017-09-06 | 2017-09-13 | 6 | 2017-09-13 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 8 | 6
3SSN-62 | RFS.121 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-01 | Bhagyalekshmi | 2017-09-07 | 2017-09-11 | 3 | [5 empty] | 0 | [7 empty] | -30682 | 2 | 0 | -1 | 0 | -30678 | 3
3WER-65 | RFS.99 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-01 | Krishnan | 2017-09-01 | 2017-09-01 | 1 |  | krishnan | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2 | 2017-09-07 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 3 | 2
4MGB-62 | RFS.99 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-01 | linda | 2017-09-01 | 2017-09-01 | 1 |  | Rikku | 2017-09-06 | 2017-09-06 | 2017-09-08 | 3 | 2017-09-08 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
3GLI-62 | RFS.100 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-01 | Sangeetha | 2017-09-01 | 2017-09-07 | 3 |  | Sangeetha | 2017-09-08 | 2017-09-08 | 2017-09-12 | 3 | 2017-09-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3KYG-64 | RFS.100 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-01 | Mani | 2017-09-04 | 2017-09-07 | 2 |  | Mani |  | 2017-09-13 | 2017-10-06 | 16 | 2017-10-06 | 13/9: Portless scenario reported to NA Team. Waiting for confirmation. 06/10: Handed over the SAM to DSG. 54 Partial trace is due to the telstra inservice hdl cables conncted to spigot port. We don't approval from nso to fix this issue. Only 1.7% of the total SL count is affected due to this. | [5 empty] | -30680 | 0 | 0 | 30683 | 0 | 22 | 19
6GIR-22 | RFS.0 | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-01 | Krishnan | 2017-09-08 | 2017-09-13 | 4 |  | Mohith | 2017-09-18 | 2017-09-18 | 2017-09-21 | 4 | 2017-09-21 | [6 empty] | 4 | 3 | 0 | 0 | 0 | 13 | 6
5WES-63 | RFS.108 | M-M-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (AP) | 2017-09-01 | Parth | 2017-09-08 | 2017-09-08 | 1 | [5 empty] | 0 | [7 empty] | -30681 | 3 | 0 | -1 | 0 | -30678 | 1
4CUR-60 | RFS.126 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-01 | Gaurav | 2017-09-12 | 2017-09-14 | 3 |  | Swathy Mohan | 2017-09-28 | 2017-09-28 | 2017-10-04 | 3 | 2017-10-04 | [6 empty] | 11 | 5 | 0 | 0 | 0 | 20 | 4
2FRE-62 | RFS.102 | M-M-H | BAU | Design |  | Completed [PC] - Trigger Triage | 2017-09-01 | Gaurav | 2017-09-07 | 2017-09-22 | 12 | SAM was placed on hold in Appian on 8/9/2017. PC activites resumed on 20/9/2017. |  |  |  |  | 0 | [7 empty] | -30691 | 2 | 0 | -1 | 0 | -30678 | 12
2PEN-66 | RFS.99 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-01 | Alan Babu | 2017-09-01 | 2017-09-01 | 1 |  | alan babu | 2017-09-06 | 2017-09-06 | 2017-09-08 | 3 | 2017-09-08 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
3BOX-61 | RFS.98 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-01 | Anusa Moottoolikandy | 2017-09-01 | 2017-09-01 | 1 |  | Anusa Moottoolikandy | 2017-09-06 | 2017-09-06 | 2017-09-11 | 4 | 2017-09-11 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
3SSN-66 | RFS.99 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-01 | Aravind | 2017-09-06 | 2017-09-11 | 4 |  | Gaurav | 2017-11-20 | 2017-11-20 | 2017-11-22 | 3 | 2017-11-22 | [6 empty] | 47 | 1 | 0 | 0 | 0 | 53 | 5
6GIR-21 | RFS.0 | M-B-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-04 | Mahalakshmi | 2017-09-11 | 2017-09-11 | 1 | [5 empty] | 0 | [7 empty] | -30682 | 3 | 0 | -1 | 0 | -30678 | 2
3WHL-65 | RFS.63 | M-A-J | BAU | Pre-AT |  | [PC] Sent Back to Telstra (Design, TVT and AP) | 2017-09-04 |  |  |  | 0 | SAM was not processed in DESG since it was POST RFS load. SAM was rejected on 15/9/2017. |  |  |  |  | 0 | [7 empty] | 0 | -30679 | 0 | -1 | 0 | -30678 | 2
3HGT-60 | RFS.63 | M-A-J | BAU | Pre-AT |  | [PC] Sent Back to Telstra (Design & AP) | 2017-09-04 |  |  |  | 0 | SAM was not processed in DESG since it was POST RFS load. SAM was rejected on 15/9/2017. |  |  |  |  | 0 | [7 empty] | 0 | -30679 | 0 | -1 | 0 | -30678 | 2
2CRR-20 | RFS.101 | M-B-H | BAU | Pre-AT |  | In Progress - [PC] Perform Check Completion | 2017-09-04 | Parth | 2017-09-06 | 2017-09-08 | 3 | [5 empty] | 0 | [7 empty] | -30681 | 0 | 0 | -1 | 0 | -30678 | 4
2PET-71 | RFS.118 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-04 | Bhagyalekshmi | 2017-09-12 | 2017-09-14 | 3 |  | Mani | 2017-09-26 | 2017-09-26 | 2017-09-29 | 3 | 2017-09-29 | [6 empty] | 9 | 4 | 0 | 0 | 0 | 17 | 4
6GIR-64 | RFS.115 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-04 | Deepa M04 | 2017-09-11 | 2017-09-14 | 4 |  | Naveen Kumar | 2017-10-04 | 2017-10-05 | 2017-10-09 | 3 | 2017-10-09 | [6 empty] | 13 | 3 | 0 | 1 | 0 | 22 | 5
6CTO-20 | RFS.121 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-04 | Anusa Moottoolikandy | 2017-09-05 | 2017-09-07 | 2 | [5 empty] | 0 | [7 empty] | -30680 | -1 | 0 | -1 | 0 | -30678 | 4
2PEN-62 | RFS.100 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-05 | Mahalakshmi | 2017-09-05 | 2017-09-06 | 1 |  | mahalakshmi | 2017-09-07 | 2017-09-07 | 2017-09-12 | 4 | 2017-09-12 | [6 empty] | 2 | -1 | 0 | 0 | 0 | 5 | 4
5GLL-61 | RFS.101 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-05 | Swathy Mohan | 2017-09-07 | 2017-09-08 | 2 |  | swathy mohan | 2017-09-12 | 2017-09-12 | 2017-09-15 | 4 | 2017-09-15 | [6 empty] | 3 | 1 | 0 | 0 | 0 | 8 | 4
2BAN-61 | RFS.113 | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-05 | Nisha | 2017-09-07 | 2017-09-11 | 3 |  | Mohith | 2017-10-03 | 2017-10-03 | 2017-10-05 | 3 | 2017-10-05 | [6 empty] | 15 | 1 | 0 | 0 | 0 | 20 | 4
4BUR-60 | RFS.103 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-05 | Krishnan | 2017-09-06 | 2017-09-08 | 3 |  | Krishnan | 2017-09-10 | 2017-09-11 | 2017-09-13 | 3 | 2017-09-13 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 6 | 5
2LIV-63 | RFS.118 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-05 | Mohith | 2017-09-11 | 2017-09-13 | 3 | [5 empty] | 0 | [7 empty] | -30684 | 3 | 0 | -1 | 0 | -30678 | 4
2CAS-66 | RFS.118 | M-M-H | BAU | Design |  | [PC] On Hold - Data Issues | 2017-09-05 | Aravind | 2017-09-11 | 2017-09-11 | 1 | SAM placed on hold due to variant issue. |  |  |  |  | 0 | [7 empty] | -30682 | 3 | 0 | -1 | 0 | -30678 | 2
4MGB-20 | RFS.100 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-06 | Naveen Kumar | 2017-09-06 | 2017-09-08 | 3 |  | Naveen Kumar | 2017-09-11 | 2017-09-11 | 2017-09-13 | 3 | 2017-09-13 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4AAR-61 | RFS.103 | M-A-Q | HAC | Pre-AT |  | [PC] Sent Back to Telstra (AP) | 2017-09-07 | Alan Babu | 2017-09-08 | 2017-09-13 | 4 | SAM Rejected by AP team on 15/9/2017 |  |  |  |  | 0 | [7 empty] | -30684 | 1 | 0 | -1 | 0 | -30680 | 4
4ASH-61 | RFS.100 | M-B-H | BAU | Pre-AT |  | [PC] Sent Back to Telstra (DESG and Design) | 2017-09-07 | Anusa Moottoolikandy | 2017-09-07 | 2017-09-11 | 3 | SAM Rejected due to issues reported by DESG and Design team on 11/9/2017 |  |  |  |  | 0 | [7 empty] | -30682 | 0 | 0 | -1 | 0 | -30680 | 3
2BAN-70 | RFS.124 | M-B-H | BAU | Design |  | Not Applicable | 2017-09-07 |  |  |  | 0 | 22/9: DESG received the SAM on 19/9. This is an invalid entry. |  |  |  |  | 0 | [7 empty] | 0 | -30681 | 0 | -1 | 0 | -30680 | 2
5WES-61 | RFS.108 | M-M-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-09-07 | Gaurav | 2017-09-07 | 2017-09-11 | 3 | [5 empty] | 0 |  |  | 2017-09-15 |  |  |  |  | -30682 | 0 | 0 | -1 | 0 | -30680 | 3
4ASH-63 | RFS.134 | H-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-07 | Mahalakshmi | 2017-09-12 | 2017-09-14 | 3 |  | Mahalakshmi | 2017-09-19 | 2017-09-19 | 2017-09-22 | 4 | 2017-09-22 | [6 empty] | 4 | 3 | 0 | 0 | 0 | 12 | 5
4CPR-62 | RFS.121 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-08 | Rikku | 2017-09-11 | 2017-09-13 | 3 | [5 empty] | 0 | [7 empty] | -30684 | 1 | 0 | -1 | 0 | -30681 | 3
2SEV-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-08 | Swathy Mohan | 2017-09-11 | 2017-09-13 | 3 |  | Krishnan | 2017-09-14 | 2017-09-14 | 2017-09-18 | 3 | 2017-09-18 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 7 | 4
3NCO-66 | RFS.98 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-05 | Bhagyalekshmi | 2017-09-06 | 2017-09-07 | 2 |  | Bhagyalekshmi | 2017-09-08 | 2017-09-08 | 2017-09-13 | 4 | 2017-09-13 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3CAU-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-08 | Rijo Sunny | 2017-09-11 | 2017-09-12 | 2 |  | Rijo Sunny | 2017-09-13 | 2017-09-13 | 2017-09-15 | 3 | 2017-09-15 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 6 | 3
4CPR-61 | RFS.101 | H-A-Q | HAC | Pre-AT |  | Completed | 2017-09-08 | Nisha | 2017-09-11 | 2017-09-12 | 2 |  | Nisha | 2017-09-13 | 2017-09-13 | 2017-09-18 | 4 | 2017-09-18 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 7 | 4
2PYM-63 | RFS.107 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-11 | Parth | 2017-09-14 | 2017-09-18 | 3 | [5 empty] | 0 | [7 empty] | -30687 | 3 | 0 | -1 | 0 | -30682 | 3
2LIV-67 | RFS.117 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-12 | Rikku | 2017-09-13 | 2017-09-18 | 4 | [5 empty] | 0 | [7 empty] | -30687 | 1 | 0 | -1 | 0 | -30683 | 4
4AGV-20 | RFS.126 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-12 | Gaurav | 2017-09-13 | 2017-09-15 | 3 |  | Naveen Kumar | 2017-09-18 | 2017-09-18 | 2017-10-06 | 13 | 2017-10-06 | 20/9: SAM placed on hold due to Remodelling issue | [5 empty] | 2 | 1 | 0 | 0 | 0 | 17 | 14
2FRE-60 | RFS.126 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-12 | S Shilpa | 2017-09-15 | 2017-09-18 | 2 |  | Krishnan | 2017-12-01 | 2017-12-01 | 2017-12-06 | 4 | 2017-12-06 | 4/12: GDSS issue INC000006723569 | [5 empty] | 51 | 3 | 0 | 0 | 0 | 58 | 4
4SUR-62 | RFS.113 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-12 | Mohith | 2017-09-14 | 2017-09-18 | 3 |  | Mohith | 2017-09-27 | 2017-09-27 | 2017-10-13 | 11 | 2017-10-13 | 3/10: SAM placed on hold due to design issue. Awaiting response from Telstra. | [5 empty] | 8 | 2 | 0 | 0 | 0 | 22 | 12
3TNI-64 | RFS.103 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-12 | Joju | 2017-09-12 | 2017-09-14 | 3 |  | Parth | 2017-09-15 | 2017-09-18 | 2017-09-20 | 3 | 2017-09-20 | [6 empty] | 2 | 0 | 0 | 1 | 0 | 7 | 4
3MLN-65 | RFS.100 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-12 | Aravind | 2017-09-13 | 2017-09-15 | 3 |  | Aravind | 2017-09-18 | 2017-09-18 | 2017-09-20 | 3 | 2017-09-20 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 7 | 4
2STL-63 | RFS.103 | H-M-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-12 | Mahalakshmi | 2017-08-28 | 2017-08-30 | 3 |  | mahalakshmi | 2017-09-01 | 2017-09-01 | 2017-09-07 | 3 | 2017-09-07 | [6 empty] | 3 | -11 | 0 | 0 | 0 | -4 | 4
4MGA-70 | RFS.101 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-13 | Deepa M04 | 2017-09-13 | 2017-09-15 | 3 |  | Deepa M04 | 2017-09-16 | 2017-09-16 | 2017-09-19 | 2 | 2017-09-19 | [6 empty] | 1 | 0 | 0 | -1 | 0 | 5 | 5
4MGA-72 | RFS.101 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-13 | Alan Babu | 2017-09-13 | 2017-09-14 | 2 |  | Alan Babu | 2017-09-15 | 2017-09-15 | 2017-09-18 | 2 | 2017-09-18 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
4SLA-64 | RFS.104 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-13 | Naveen Kumar | 2017-09-14 | 2017-09-15 | 2 | [5 empty] | 0 | [7 empty] | -30686 | 1 | 0 | -1 | 0 | -30684 | 2
5WES-65 | RFS.108 | H-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-13 | Gaurav | 2017-09-15 | 2017-09-19 | 3 | [5 empty] | 0 | [7 empty] | -30688 | 2 | 0 | -1 | 0 | -30684 | 3
2ASH-66 | RFS.118 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-13 | Joju | 2017-09-14 | 2017-09-18 | 3 |  | Mani | 2017-09-29 | 2017-09-29 | 2017-10-04 | 2 | 2017-10-04 | [6 empty] | 9 | 1 | 0 | -1 | 0 | 14 | 5
2PET-66 | RFS.123 | M-M-H | BAU | Design | 1 | In Progress - [PC] Perform Check Completion | 2017-09-13 | Anusa Moottoolikandy | 2017-09-13 | 2017-09-19 | 5 | [5 empty] | 0 | [7 empty] | -30688 | 0 | 0 | -1 | 0 | -30684 | 5
2CAS-66 | RFS.101 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-15 | Swathy Mohan | 2017-09-15 | 2017-09-19 | 3 |  | Swathy Mohan | 2017-09-20 | 2017-09-20 | 2017-09-25 | 4 | 2017-09-25 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
5GLL-62 | RFS.125 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-15 | mani | 2017-09-18 | 2017-09-20 | 3 | [5 empty] | 0 | [7 empty] | -30689 | 1 | 0 | -1 | 0 | -30686 | 3
2WET-65 | RFS.100 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-18 | Krishnan | 2017-09-18 | 2017-09-20 | 3 |  | Krishnan | 2017-09-22 | 2017-09-22 | 2017-09-26 | 4 | 2017-09-27 | 27/9: Manual fixes were involved and hence SLA missed by one day. | [5 empty] | 3 | 0 | 0 | 0 | 0 | 8 | 5
4CPR-65 | RFS.105 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-18 | Rijo Sunny | 2017-09-18 | 2017-09-20 | 3 |  | Mahalakshmi | 2017-09-25 | 2017-09-25 | 2017-09-27 | 4 | 2017-09-28 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 9 | 5
4AGV-64 | RFS.122 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-18 | Aravind | 2017-09-20 | 2017-09-22 | 3 |  | Aravind | 2017-09-25 | 2017-09-25 | 2017-09-25 | 1 | 2017-09-25 | [6 empty] | 2 | 2 | 0 | 0 | 0 | 6 | 2
4CPR-62 | RFS.121 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-18 | S Shilpa | 2017-09-18 | 2017-09-20 | 3 |  | S Shilpa | 2017-09-21 | 2017-09-21 | 2017-09-25 | 3 | 2017-09-25 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4CHL-68 | RFS.143 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-18 | Mohith | 2017-09-19 | 2017-09-21 | 3 |  | Mani | 2017-09-22 | 2017-09-22 | 2017-09-27 | 4 | 2017-09-27 | 26/9: SAM placed on hold due to job lock | [5 empty] | 2 | 1 | 0 | 0 | 0 | 8 | 5
2PYM-62 | RFS.124 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-18 | Rikku | 2017-09-18 | 2017-09-21 | 4 |  | Rikku | 2017-09-22 | 2017-09-22 | 2017-09-26 | 3 | 2017-09-26 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
4APL-60 | RFS.122 | M-M-H | BAU | Design |  | [PC] On Hold - Data Issues | 2017-09-18 |  |  |  | 0 | 18/9: SAM placed on hold. DESG didn't receive the perform check task in Appian. |  |  |  |  | 0 | [7 empty] | 0 | -30688 | 0 | -1 | 0 | -30687 | 2
2CAS-65 | RFS.124 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-19 | Gaurav | 2017-09-19 | 2017-09-21 | 3 | [5 empty] | 0 | [7 empty] | -30690 | 0 | 0 | -1 | 0 | -30688 | 3
4ABC-63 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-19 | Anusa Moottoolikandy | 2017-09-19 | 2017-09-20 | 2 | SAM rejected on 21/09 | Anusa Moottoolikandy | 2017-11-14 | 2017-12-13 | 2017-12-15 | 3 | 2017-12-15 | 13/12: Package was rejected on 21/09. Got confirmation from NA team on 6/12 to proceed with the same package. FTTN only load for Active NDD | 2017-09-21 |  |  |  |  | 36 | 0 | 0 | 21 | 0 | 60 | 3
4IAL-64 | RFS.141 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-19 | Joju | 2017-09-19 | 2017-09-21 | 3 |  | Anusa Moottoolikandy | 2017-09-27 | 2017-09-28 | 2017-10-04 | 3 | 2017-10-04 | [6 empty] | 5 | 0 | 0 | 1 | 0 | 10 | 4
4SUR-60 |  | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-19 | Gaurav | 2017-09-20 | 2017-09-22 | 3 |  | Gaurav | 2017-10-09 | 2017-10-09 | 2017-10-10 | 2 | 2017-10-10 | 9/10: Reported LOC ID issue on 6/10. Received clarification on 9/10. | [5 empty] | 10 | 1 | 0 | 0 | 0 | 14 | 3
2HLS-61 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-19 | Naveen Kumar | 2017-09-20 | 2017-09-21 | 2 |  | Naveen Kumar | 2017-09-26 | 2017-09-26 | 2017-09-28 | 3 | 2017-09-28 | [6 empty] | 4 | 1 | 0 | 0 | 0 | 8 | 3
2HLS-60 |  | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-19 | Rijo Sunny | 2017-09-21 | 2017-09-22 | 2 |  | Rijo Sunny | 2017-09-26 | 2017-09-26 | 2017-09-29 | 3 | 2017-09-29 | [6 empty] | 3 | 2 | 0 | 0 | 0 | 8 | 3
2BAN-70 | RFS.124 | M-B-H | BAU | Design |  | [GML] Completed - Handover to DSG | 2017-09-19 | Alan Babu | 2017-09-19 | 2017-09-20 | 2 |  | joju | 2017-09-27 | 2017-10-03 | 2017-10-05 | 3 | 2017-10-05 | [6 empty] | 6 | 0 | 0 | 2 | 0 | 11 | 3
3OAK-60 | RFS.99 | H-M-Q | BAU | Design |  | [GML] Completed - Handover to DSG | 2017-09-19 | Mahalakshmi | 2017-09-20 | 2017-09-22 | 3 |  | Rijo Sunny | 2017-09-27 | 2017-10-03 | 2017-10-05 | 3 | 2017-10-05 | [6 empty] | 4 | 1 | 0 | 2 | 0 | 11 | 4
3BOX-64 | RFS.100 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-20 | Deepa M04 | 2017-09-20 | 2017-09-22 | 3 |  | Deepa M04 | 2017-09-25 | 2017-09-25 | 2017-09-28 | 4 | 2017-09-29 | Error encountered during trace generation. PNI incident raised (REQ000002822059). | [5 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
5BRI-61 | RFS.104 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-21 | Nisha | 2017-09-21 | 2017-09-25 | 3 |  | Nisha | 2017-09-26 | 2017-09-26 | 2017-09-29 | 3 | 2017-09-29 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4BNP-64 | RFS.115 | M-M-H | BAU | Design |  | [GML] Completed - Handover to DSG | 2017-09-21 | S Shilpa | 2017-09-21 | 2017-09-25 | 3 |  | Mahalakshmi | 2017-09-27 | 2017-09-28 | 2017-10-03 | 3 | 2017-10-04 | [6 empty] | 3 | 0 | 0 | 1 | 0 | 8 | 4
4MGB-01 | RFS.102 | M-B-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-09-21 | Parth | 2017-09-21 | 2017-09-25 | 3 | [5 empty] | 0 |  |  | 2017-09-27 |  |  |  |  | -30692 | 0 | 0 | -1 | 0 | -30690 | 3
2FRE-64 | RFS.106 | M-B-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-22 | Mohith | 2017-09-22 | 2017-09-26 | 3 |  | Anusa Moottoolikandy | 2017-10-25 | 2017-10-25 | 2017-10-26 | 2 | 2017-10-26 | [6 empty] | 19 | 0 | 0 | 0 | 0 | 22 | 3
6SUB-66 | RFS.113 | M-M-H | BAU | Design | 2 | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-09-22 | Anusa Moottoolikandy | 2017-09-22 | 2017-09-26 | 3 | 9/10: SAM rejected. |  |  |  |  | 0 |  |  | 2017-10-09 |  |  |  |  | -30693 | 0 | 0 | -1 | 0 | -30691 | 3
4ABC-60 | RFS.113 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-20 | Bhagyalekshmi | 2017-09-22 | 2017-09-25 | 2 |  | bhagyalekshmi | 2017-09-26 | 2017-09-26 | 2017-09-27 | 2 | 2017-09-27 | [6 empty] | 2 | 2 | 0 | 0 | 0 | 6 | 2
4SRW-64 | RFS.105 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-22 | Anusa Moottoolikandy | 2017-09-26 | 2017-09-28 | 3 |  | Anusa Moottoolikandy | 2017-10-03 | 2017-10-03 | 2017-10-05 | 3 | 2017-10-05 | [6 empty] | 2 | 2 | 0 | 0 | 0 | 8 | 4
4CUR-61 | RFS.120 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-25 | Deepa M04 | 2017-09-25 | 2017-09-27 | 3 |  | Deepa M04 | 2017-10-03 | 2017-10-03 | 2017-10-12 | 8 | 2017-10-12 | 6/10: Awaiting input from Telstra regarding spec upgradation 11/10: Received new T18 package. Performing full run today. | [5 empty] | 3 | 0 | 0 | 0 | 0 | 12 | 9
3TYH-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-25 | Bhagyalekshmi | 2017-09-27 | 2017-09-29 | 2 |  | Bhagyalekshmi | 2017-09-29 | 2017-09-29 | 2017-10-04 | 2 | 2017-10-04 | [6 empty] | 0 | 2 | 0 | -1 | 0 | 6 | 5
2PEN-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-25 | Alan Babu | 2017-09-26 | 2017-09-28 | 3 |  | Alan Babu | 2017-09-29 | 2017-09-29 | 2017-10-04 | 2 | 2017-10-04 | [6 empty] | 1 | 1 | 0 | -1 | 0 | 6 | 5
3CLA-66 | RFS.101 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-25 | Aravind | 2017-09-26 | 2017-09-29 | 3 |  | Aravind | 2017-10-03 | 2017-10-03 | 2017-10-05 | 3 | 2017-10-05 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 7 | 5
5GLL-65 | RFS.102 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-25 | Mani | 2017-09-29 | 2017-10-03 | 1 |  | Krishnan | 2017-10-04 | 2017-10-04 | 2017-10-06 | 3 | 2017-10-06 | [6 empty] | 2 | 3 | 0 | 0 | 0 | 8 | 3
4WTF-63 | RFS.102 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-25 | Gaurav | 2017-09-26 | 2017-09-29 | 3 |  | Gaurav | 2017-09-29 | 2017-09-29 | 2017-10-03 | 1 | 2017-10-03 | [6 empty] | 0 | 1 | 0 | -1 | 0 | 5 | 5
4AAR-62 | RFS.103 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-25 | Naveen Kumar | 2017-09-27 | 2017-09-29 | 2 |  | Naveen Kumar | 2017-10-03 | 2017-10-03 | 2017-10-04 | 2 | 2017-10-04 | [6 empty] | 1 | 2 | 0 | 0 | 0 | 6 | 3
3BNT-66 | RFS.106 | H-A-Q | HAC | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-25 | Rikku | 2017-09-28 | 2017-10-03 | 2 |  | Rikku | 2017-10-04 | 2017-10-04 | 2017-10-06 | 3 | 2017-10-06 | [6 empty] | 2 | 3 | 0 | 0 | 0 | 8 | 3
2ROS-67 | RFS.135 | H-A-Q | HAC | Pre-AT | 1 | [GML] On Hold - Issues - NBN Internal | 2017-09-25 | Deepa M04 | 2017-09-28 | 2017-10-03 | 2 |  | Deepa M04 | 2017-10-04 | 2017-10-04 | 2017-10-06 | -30697 |  | 6/10: SAM Placed on hold in Appian due to issue reported by LDM. PNI load completed. Not yet handed over. | [5 empty] | 2 | 3 | 0 | 0 | 0 | -30692 | -30697
6GIR-21 | RFS.150 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-26 | Swathy Mohan | 2017-09-27 | 2017-09-29 | 2 |  | Mani | 2017-11-13 | 2017-11-13 | 2017-11-16 | 4 | 2017-11-16 | [6 empty] | 28 | 1 | 0 | 0 | 0 | 34 | 5
6GIR-20 | RFS.151 | M-M-H | BAU | Design |  | In Progress - [PC] Perform Check Completion | 2017-09-27 | Alan Babu | 2017-10-10 | 2017-10-12 | 3 | [5 empty] | 0 | [7 empty] | -30703 | 7 | 0 | -1 | 0 | -30694 | 3
2ING-65 | RFS.131 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-09-27 | Nisha | 2017-10-10 | 2017-10-10 | 1 |  | Deepa M04 | 2017-10-13 | 2017-10-13 | 2017-10-17 | 3 | 2017-10-17 | [6 empty] | 4 | 7 | 0 | 0 | 0 | 13 | 2
5BRI-63 | RFS.104 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-25 | Rijo Sunny | 2017-09-29 | 2017-10-03 | 1 |  | Rijo Sunny | 2017-10-09 | 2017-10-09 | 2017-10-10 | 2 | 2017-10-10 | 10/10: Changed from HAC to BAU queue on 6/10 | [5 empty] | 5 | 3 | 0 | 0 | 0 | 10 | 2
4WTF-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-28 | Mohith | 2017-09-28 | 2017-10-06 | 5 | 6/10: PC activities were placed on hold since SLs were outside the Sam boundary and was awaiting for the AP team to fix the issue. | Sangeetha | 2017-10-16 | 2017-10-16 | 2017-10-19 | 3 | 2017-10-19 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 13 | 6
4SRW-60 | RFS.105 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-09-28 | Krishnan | 2017-09-28 | 2017-10-03 | 2 | 23/11: Rejection. FTTx issue. |  |  |  |  | 0 |  |  | 2017-11-23 |  |  |  |  | -30696 | 0 | 0 | -1 | 0 | -30695 | 2
4ORM-60 | RFS.109 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-29 | Bhagyalekshmi | 2017-10-03 | 2017-10-06 | 4 |  | Mani | 2017-10-09 | 2017-10-09 | 2017-10-10 | 2 | 2017-10-10 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3CAU-63 | RFS.105 | M-A-H | BAU | Pre-AT |  | [GML] Completed - Handover to DSG | 2017-09-29 | Aravind | 2017-09-29 | 2017-10-04 | 2 |  | Aravind | 2017-10-05 | 2017-10-05 | 2017-10-06 | 2 | 2017-10-06 | [6 empty] | 2 | -1 | 0 | 0 | 0 | 4 | 3
3NBA-67 | RFS.104 | H-A-H | BAU | Pre-AT |  | On Hold - [PC] Issues - NBN Internal | 2017-09-29 | Gaurav | 2017-09-29 | 2017-10-03 | 1 | 4/10: SAM Placed on hold since FTTX documents are not present |  |  |  |  | 0 | [7 empty] | -30696 | -1 | 0 | -1 | 0 | -30695 | 3
2STL-60 | RFS.104 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-29 | Deepa M04 | 2017-10-04 | 2017-10-09 | 4 |  | Deepa M04 | 2017-10-09 | 2017-10-09 | 2017-10-11 | 3 | 2017-10-11 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 7 | 5
3TNI-63 | RFS.103 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-09-29 | Nisha | 2017-09-29 | 2017-10-04 | 2 |  | Mahalakshmi | 2017-10-05 | 2017-10-05 | 2017-10-09 | 4 | 2017-10-10 | [6 empty] | 2 | -1 | 0 | 0 | 0 | 6 | 5
4EMP-25 | RFS.103 | M-B-H | BAU | Pre-AT |  | Rejected | 2017-10-02 | Swathy Mohan | 2017-10-04 | 2017-10-06 | 3 | SAM Placed on hold in Appian |  |  |  |  | 0 |  |  | 2017-10-06 |  |  |  |  | -30699 | 1 | 0 | -1 | 0 | -30695 | 4
3TYH-61 | RFS.118 | M-M-H | BAU | Design |  | Rejected | 2017-10-03 | Nisha | 2017-10-04 | 2017-10-06 | 3 | 9/10: SAM rejected due sub serviceability threshold issue. |  |  |  |  | 0 |  |  | 2017-10-09 |  |  |  |  | -30699 | 1 | 0 | -1 | 0 | -30696 | 3
6WMB-63 | RFS.120 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-03 | Krishnan | 2017-10-03 | 2017-10-05 | 3 |  | Gaurav | 2017-10-12 | 2017-10-12 | 2017-10-16 | 3 | 2017-10-16 | [6 empty] | 6 | 0 | 0 | 0 | 0 | 10 | 4
2MIL-63 | RFS.103 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-03 | Gaurav | 2017-10-03 | 2017-10-05 | 3 |  | Aravind | 2017-10-09 | 2017-10-09 | 2017-10-10 | 2 | 2017-10-10 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
2LIV-60 | RFS.130 | M-M-H(P) | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-03 | Mani | 2017-10-09 | 2017-10-11 | 3 |  | Linda | 2017-11-08 | 2017-11-08 | 2017-11-10 | 3 | 2017-11-10 | [6 empty] | 19 | 4 | 0 | 0 | 0 | 27 | 4
3BOX-63 | RFS.105 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-03 | Rikku | 2017-10-03 | 2017-10-09 | 5 |  | Rikku | 2017-10-09 | 2017-10-09 | 2017-10-10 | 2 | 2017-10-10 | 9/10: Delayed address file. | [5 empty] | 1 | 0 | 0 | 0 | 0 | 6 | 5
3HDB-62 | RFS.102 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-03 | Mohith | 2017-10-03 | 2017-10-06 | 4 |  | Mohith | 2017-10-09 | 2017-10-09 | 2017-10-10 | 2 | 2017-10-10 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
2PNN-64 | RFS.80 | H-A-H | BAU | Pre-AT |  | [PC] On Hold - Issues - NBN Internal | 2017-09-29 | Mohith | 2017-10-09 |  | -30700 | 11/10: SAM placed on hold since perform check task is missing in Appian. |  |  |  |  | 0 | [7 empty] | 0 | 4 | 0 | -1 | 0 | -30695 | -30698
6CTO-20 | RFS.133 | M-M-H | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-03 | Gaurav | 2017-10-11 | 2017-10-11 | 1 | [5 empty] | 0 | [7 empty] | -30702 | 6 | 0 | -1 | 0 | -30696 | 1
2BAN-69 | RFS.104 | H-M-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-03 | linda | 2017-10-04 | 2017-10-06 | 3 | 10/10: SAM placed on hold at LDM. Didn't perform GDSS load since address file is not yet shared. | Rijo Sunny | 2017-10-12 | 2017-10-12 | 2017-10-13 | 2 | 2017-10-13 | [6 empty] | 5 | 1 | 0 | 0 | 0 | 9 | 3
4AAR-63 | RFS.122 | M-M-H | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-04 | Rikku | 2017-10-09 | 2017-10-11 | 3 | [5 empty] | 0 | [7 empty] | -30702 | 3 | 0 | -1 | 0 | -30697 | 3
2PEN-61 | RFS.105 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-10-04 | Bhagyalekshmi | 2017-10-04 | 2017-10-06 | 3 | [5 empty] | 0 |  |  | 2017-10-13 |  |  |  |  | -30699 | 0 | 0 | -1 | 0 | -30697 | 3
3BNT-60 | RFS.102 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-04 | Bhagyalekshmi | 2017-10-04 | 2017-10-09 | 4 |  | Bhagyalekshmi | 2017-10-09 | 2017-10-09 | 2017-10-11 | 3 | 2017-10-11 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 6 | 5
3BLB-69 | RFS.102 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-04 | Nisha | 2017-10-05 | 2017-10-06 | 2 | 9/10: Invalid pit specification. Critical issue reported in FBR. | Nisha | 2017-10-12 | 2017-10-12 | 2017-10-12 | 1 | 2017-10-12 | [6 empty] | 5 | 1 | 0 | 0 | 0 | 7 | 1
2PEN-64 | RFS.104 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-04 | linda | 2017-10-05 | 2017-10-09 | 3 | 9/10: Awaiting address file | swathy mohan | 2017-10-10 | 2017-10-10 | 2017-10-12 | 3 | 2017-10-12 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 7 | 4
4APL-60 | RFS.125 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-05 | Gaurav | 2017-10-05 | 2017-10-09 | 3 | 27/10: 96 locIds are missing in the locID mapping and those locations are in PONSA without PCD. Awaiting NA teams input. | Deepa M04 | 2017-10-23 | 2017-11-21 | 2017-11-28 | 6 | 2017-11-28 | 23/10: FTTN part was handed over to IAB on 19/10. Started with HFC load today. 26/10: 96 locIds are missing in the locID mapping and those locations are in PONSA without PCD. Awaiting confirmation from AP team 20/11; Received confirmation to disregard the issue and proceed. Copper demotion in progress. 22/11: For the SAM 4APL-60 26 locations having 2 associated PCDs. The additional PCDs are of FTTP and are promoted on 2014 all the FTTP PCDs are in PLANNED status. Attached the trace report for 26 locations. Awaiting onshore communication to proceed. 28/11: Got confirmation to delte PCDs and proceed. | [5 empty] | 10 | 0 | 0 | 20 | 0 | 37 | 7
2LIV-67 | RFS.125 | M-M-H(P) | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-05 | Mahalakshmi | 2017-10-09 | 2017-10-11 | 3 |  | Gaurav | 2017-10-20 | 2017-10-20 | 2017-10-24 | 3 | 2017-10-24 | [6 empty] | 7 | 2 | 0 | 0 | 0 | 13 | 4
4MGA-63 | RFS.103 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-05 | Joju | 2017-10-05 | 2017-10-09 | 3 |  | Joju | 2017-10-10 | 2017-10-10 | 2017-10-12 | 3 | 2017-10-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4SSB-61 | RFS.121 | M-M-H | BAU | Design |  | Rejected | 2017-10-05 | Anusa Moottoolikandy | 2017-10-09 | 2017-10-10 | 2 | [5 empty] | 0 |  |  | 2017-10-11 |  |  |  |  | -30701 | 2 | 0 | -1 | 0 | -30698 | 2
2PNN-68 | RFS.104 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-06 | Aravind | 2017-10-06 | 2017-10-10 | 3 |  | Aravind | 2017-10-11 | 2017-10-11 | 2017-10-12 | 2 | 2017-10-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4CPR-63 | RFS.106 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-06 | Krishnan | 2017-10-06 | 2017-10-09 | 2 |  | Anusa Moottoolikandy | 2017-10-10 | 2017-10-10 | 2017-10-12 | 3 | 2017-10-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4WTF-60 | RFS.130 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-09 | Rijo Sunny | 2017-10-09 | 2017-10-11 | 3 |  | swathy mohan | 2017-12-20 | 2017-12-21 | 2017-12-27 | 3 | 2017-12-27 | 21/12: Issues reported were fixed as per Appian note. GML load started for the same package. | 2017-10-23 |  |  |  |  | 49 | 0 | 0 | 1 | 0 | 54 | 4
4SRW-66 | RFS.106 | M-A-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-10-09 | Sangeetha | 2017-10-09 | 2017-10-11 | 3 |  | Sangeetha | 2017-10-12 | 2017-10-12 |  | -30703 |  | 12/10: Portleass scenario encountered. Awaiting onshore response. SAM Paused in Appian. | 2017-10-13 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | -30700 | -30702
2PET-68 | RFS.131 | M-M-H | BAU | Design |  | Rejected | 2017-10-09 | Anusa Moottoolikandy | 2017-10-09 | 2017-10-10 | 2 | [5 empty] | 0 |  |  | 2017-10-13 |  |  |  |  | -30701 | 0 | 0 | -1 | 0 | -30700 | 2
4SSB-60 | RFS.106 | M-A-Q | HAC | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-10-05 | Anusa Moottoolikandy | 2017-10-05 |  | -30698 | [5 empty] | 0 |  |  | 2017-10-09 |  |  |  |  | 0 | 0 | 0 | -1 | 0 | -30698 | -30697
2STL-61 | RFS.104 | M-M-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-10 | Mahalakshmi | 2017-10-11 | 2017-10-13 | 3 | 16/10: SAM paused in Appian by NA team | Deepa M04 | 2017-10-19 | 2017-10-19 | 2017-10-20 | 2 | 2017-10-20 | Only HFC part was loaded using the IAB payload | [5 empty] | 4 | 1 | 0 | 0 | 0 | 8 | 3
3OAK-61 | RFS.105 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-10 | Naveen Kumar | 2017-10-10 | 2017-10-11 | 2 |  | Krishnan | 2017-10-16 | 2017-10-16 | 2017-10-17 | 2 | 2017-10-17 | 16/10: Split Load. Only HFC to proceed since waiting for FTTx documents | [5 empty] | 4 | 0 | 0 | 0 | 0 | 6 | 2
2PYM-61 | RFS.125 | M-M-H | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-11 | Mani | 2017-10-12 | 2017-10-16 | 3 | 16/10: SAM paused in Appian due to missing FTTB artefacts |  |  |  |  | 0 | [7 empty] | -30705 | 1 | 0 | -1 | 0 | -30702 | 3
3CAU-64 | RFS.103 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-11 | Anusa Moottoolikandy | 2017-10-11 | 2017-10-13 | 3 |  | Anusa Moottoolikandy | 2017-10-13 | 2017-10-13 | 2017-10-17 | 3 | 2017-10-17 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 5 | 4
5BRI-65 | RFS.104 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-11 | Bhagyalekshmi | 2017-10-11 | 2017-10-12 | 2 |  | Bhagyalekshmi | 2017-10-13 | 2017-10-13 | 2017-10-16 | 2 | 2017-10-16 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
2ROS-66 | RFS.134 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-11 | Mohith | 2017-10-12 | 2017-10-16 | 3 | 12/10: PC task was pushed to Appian post 2:00 PM ACT. Hence DESG took it up on 12/10 | Alan Babu | 2017-10-16 | 2017-10-16 | 2017-10-19 | 3 | 2017-10-19 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 6 | 4
2PET-64 | RFS.108 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-13 | Rikku | 2017-10-13 | 2017-10-16 | 2 |  | Rikku | 2017-10-16 | 2017-10-16 | 2017-10-17 | 2 | 2017-10-17 | 16/10: FTTB load for Active NDD generation | [5 empty] | 1 | 0 | 0 | 0 | 0 | 3 | 2
3BAY-65 | RFS.126 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-12 | Nisha | 2017-10-12 | 2017-10-16 | 3 |  | Nisha | 2017-10-17 | 2017-10-17 | 2017-10-23 | 4 | 2017-10-23 | Manual fixes were involved. GDSS outage post noon on 20/10 | [5 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
4SSB-62 | RFS.126 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-13 | Rikku | 2017-10-13 | 2017-10-18 | 3 |  | Rikku | 2017-10-19 | 2017-10-19 | 2017-10-23 | 3 | 2017-10-23 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 6 | 5
5WES-63 | RFS.125 | M-M-H | BAU | Pre-AT |  | [PC] PC Completion & Triage Trigger | 2017-10-13 | Mani | 2017-10-13 | 2017-10-17 | 3 | [5 empty] | 0 | [7 empty] | -30706 | 0 | 0 | -1 | 0 | -30704 | 3
2PET-62 | RFS.124 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-16 | Anusa Moottoolikandy | 2017-10-16 | 2017-10-17 | 2 |  | Aravind | 2017-10-24 | 2017-10-24 | 2017-10-24 | 1 | 2017-10-24 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 6 | 1
4ABO-67 |  | H-A-Q | HAC | Pre-AT |  | On Hold - [GML] Issues - NBN Internal | 2017-10-16 | Mohith | 2017-10-16 | 2017-10-17 | 2 |  | Mohith | 2017-10-19 | 2017-10-19 |  | -30707 |  | 26/10: SAM placed on hold. NDD document will be shared only by Feb 2018. | [5 empty] | 2 | 0 | 0 | 0 | 0 | -30705 | -30707
4SSB-60 | RFS.126 | M-A-Q | HAC | Pre-AT |  | Not Applicable | 2017-10-16 |  |  |  | 0 | SAM moved to BAU queue with new package. To be tracked in new record below. |  |  |  |  | 0 | [7 empty] | 0 | -30706 | 0 | -1 | 0 | -30705 | 2
3OAK-64 | RFS.104 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-17 | Swathy Mohan | 2017-10-16 | 2017-10-18 | 2 |  | Swathy Mohan | 2017-10-19 | 2017-10-19 | 2017-10-25 | 5 | 2017-10-25 | [6 empty] | 1 | -3 | 0 | 0 | 0 | 6 | 8
4SLA-70 | RFS.108 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-17 | Mohith | 2017-10-19 | 2017-10-23 | 3 | 18/10/2017 was an offshore holiday | Mohith | 2017-10-24 | 2017-10-24 | 2017-10-25 | 2 | 2017-10-25 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 6 | 3
3NBA-67 | RFS.107 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-17 | Anusa Moottoolikandy | 2017-10-17 | 2017-10-19 | 2 |  | Mahalakshmi | 2017-10-23 | 2017-10-23 | 2017-10-25 | 3 | 2017-10-25 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
3SSN-63 | RFS.102 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-17 | Deepa M04 | 2017-10-17 | 2017-10-19 | 2 |  | Deepa M04 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 1 | 2017-10-31 | [6 empty] | 9 | 0 | 0 | 0 | 0 | 10 | 1
3MLN-61 | RFS.103 | M-M-Q | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-17 | Gaurav | 2017-10-17 | 2017-10-20 | 3 | [5 empty] | 0 | [7 empty] | -30708 | 0 | 0 | -1 | 0 | -30706 | 3
3CAU-66 | RFS.103 | H-M-Q | BAU | Design |  | On Hold - [PC] Issues - NBN Internal | 2017-10-17 | Rijo Sunny | 2017-10-17 |  | -30706 | SAM to be moved to HAC queue. Awaiting confirmation |  |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | -1 | 0 | -30706 | -30705
3MLN-62 | RFS.125 | M-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-17 | Sangeetha | 2017-10-17 | 2017-10-19 | 2 | 18/10/2017 was an offshore holiday | Rikku | 2017-11-01 | 2017-11-01 | 2017-11-03 | 3 | 2017-11-03 | [6 empty] | 10 | 0 | 0 | 0 | 0 | 13 | 3
2CRR-65 | RFS.105 | M-M-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-17 | Krishnan | 2017-10-19 | 2017-10-20 | 2 |  | Krishnan | 2017-10-20 | 2017-10-23 | 2017-10-25 | 3 | 2017-10-25 | [6 empty] | 1 | 1 | 0 | 1 | 0 | 6 | 3
5FLN-62 | RFS.105 | H-B-J | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-18 | Nisha | 2017-10-19 | 2017-10-20 | 2 |  | Mani | 2017-10-20 | 2017-10-23 | 2017-10-25 | 3 | 2017-10-25 | [6 empty] | 1 | 0 | 0 | 1 | 0 | 5 | 3
2BON-64 | RFS.104 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-18 | Aravind | 2017-10-19 | 2017-10-20 | 2 |  | Aravind | 2017-10-20 | 2017-10-20 | 2017-10-23 | 2 | 2017-10-23 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 3 | 2
2PNN-62 | RFS.108 | H-M-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-18 | linda | 2017-10-19 | 2017-10-23 | 3 |  | Linda | 2017-10-23 | 2017-10-23 | 2017-10-24 | 2 | 2017-10-24 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
2UND-62 | RFS.108 | H-M-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-18 | Alan Babu | 2017-10-19 | 2017-10-23 | 3 |  | Alan babu | 2017-10-24 | 2017-10-24 | 2017-10-27 | 4 | 2017-10-27 | portless issues were present. Trace issue resolved. | [5 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
4SSB-60 | RFS.106 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-18 | Bhagyalekshmi | 2017-10-19 | 2017-10-23 | 3 |  | Sangeetha | 2017-10-27 | 2017-10-27 | 2017-10-30 | 2 | 2017-10-30 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 8 | 3
2PAR-63 | RFS.125 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-19 | Bhagyalekshmi | 2017-10-23 | 2017-11-02 | 9 | 27/10: Perform check completed. Awaiting address file to complete GDSS load. 2/11: Received address file on 1/11. | Sangeetha | 2017-11-02 | 2017-11-02 | 2017-11-06 | 3 | 2017-11-06 | [6 empty] | 1 | 2 | 0 | 0 | 0 | 13 | 10
3RWO-66 | RFS.107 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-20 | Rikku | 2017-10-20 | 2017-10-24 | 3 |  | Rikku | 2017-10-26 | 2017-10-26 | 2017-10-30 | 3 | 2017-10-30 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 7 | 4
3DAD-64 | RFS.107 | M-M-H | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-20 | Gaurav | 2017-10-23 | 2017-10-25 | 3 | [5 empty] | 0 | [7 empty] | -30711 | 1 | 0 | -1 | 0 | -30708 | 3
6GIR-60 | RFS.104 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-20 | Sangeetha | 2017-10-20 | 2017-10-24 | 3 |  | Sangeetha | 2017-10-25 | 2017-10-25 | 2017-10-26 | 2 | 2017-10-26 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
6KSL-61 | RFS.104 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-20 | Naveen Kumar | 2017-10-20 | 2017-10-24 | 3 |  | Naveen Kumar | 2017-10-25 | 2017-10-25 | 2017-10-30 | 4 | 2017-10-30 | 27/10: Error pop up while editing the ADA boundary during node split. Waiating AP team's response. | [5 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
3KYG-66 | RFS.106 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-20 | Rijo Sunny | 2017-10-23 | 2017-10-25 | 3 |  | Rijo Sunny | 2017-10-26 | 2017-10-26 | 2017-10-30 | 3 | 2017-10-30 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 7 | 4
4SRW-66 | RFS.106 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-20 | Mohith | 2017-10-23 | 2017-10-24 | 2 |  | Mohith | 2017-10-26 | 2017-10-26 | 2017-10-30 | 3 | 2017-10-30 | [6 empty] | 3 | 1 | 0 | 0 | 0 | 7 | 3
4EMP-02 | RFS.106 | M-B-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-10-24 | Sangeetha | 2017-10-24 |  | -30710 | [5 empty] | 0 |  |  | 2017-10-27 |  |  |  |  | 0 | 0 | 0 | -1 | 0 | -30710 | -30709
3SPL-62 | RFS.120 | M-M-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-24 | Nisha | 2017-10-24 | 2017-10-26 | 3 |  | Nisha | 2017-10-27 | 2017-10-27 | 2017-10-31 | 3 | 2017-10-31 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4SRW-62 | RFS.108 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-24 | Swathy Mohan | 2017-10-24 | 2017-10-27 | 4 |  | Krishnan | 2017-10-27 | 2017-10-27 | 2017-11-08 | 8 | 2017-11-08 | 27/10: Loader issue. Raised incident with IT Central. REQ000003034871 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 11 | 10
4SSB-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-24 | Krishnan | 2017-10-24 | 2017-10-26 | 3 |  | Krishnan | 2017-10-26 | 2017-10-26 | 2017-10-30 | 3 | 2017-10-30 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 5 | 4
4MGB-01 | RFS.106 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-24 | Bhagyalekshmi | 2017-10-24 | 2017-10-26 | 3 |  | Krishnan | 2017-11-03 | 2017-11-03 | 2017-11-06 | 2 | 2017-11-06 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 10 | 3
2LIV-63 | RFS.118 | M-M-H | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-24 | Deepa M04 | 2017-10-24 | 2017-10-26 | 3 | [5 empty] | 0 | [7 empty] | -30712 | 0 | 0 | -1 | 0 | -30710 | 3
6GIR-68 | RFS.116 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-24 | linda | 2017-10-25 | 2017-10-27 | 3 | 01/11: Rejected due to FTTx feedback. | Joju | 2017-12-19 | 2017-12-19 | 2017-12-22 | 4 | 2017-12-22 | 19/12: TLS HAS RESOLVED DEFECT [FD77] - VALIDATED BY DDS AND RESUMED FOR LOAD | 2017-11-01 |  |  |  |  | 37 | 1 | 0 | 0 | 0 | 43 | 5
2FRE-61 | RFS.104 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-16 | Aravind | 2017-10-16 | 2017-10-16 | 1 |  | Aravind | 2017-10-16 | 2017-10-16 | 2017-10-17 | 2 | 2017-10-17 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 2 | 1
4CUR-63 | RFS.131 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-25 | Rikku | 2017-11-02 | 2017-11-06 | 3 | 25/10: TVT not available | Krishnan | 2017-11-22 | 2017-11-22 | 2017-11-24 | 3 | 2017-11-24 | [6 empty] | 12 | 6 | 0 | 0 | 0 | 22 | 4
2PET-66 | RFS.129 | M-M-H | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-25 | Aravind | 2017-10-25 | 2017-10-27 | 3 | [5 empty] | 0 | [7 empty] | -30713 | 0 | 0 | -1 | 0 | -30711 | 3
2PET-68 | RFS.131 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-25 | Krishnan | 2017-10-25 | 2017-10-27 | 3 |  | Rijo Sunny | 2017-11-02 | 2017-11-08 | 2017-11-13 | 4 | 2017-11-13 | [6 empty] | 5 | 0 | 0 | 3 | 0 | 13 | 5
2PYM-64 | RFS.136 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-25 | Swathy Mohan | 2017-11-15 | 2017-11-17 | 3 | 26/10: Error while searching SAM in Appian | Gaurav | 2017-11-21 | 2017-11-28 | 2017-12-01 | 4 | 2017-12-01 | [6 empty] | 3 | 14 | 0 | 5 | 0 | 27 | 5
4FHL-61 | RFS.122 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-25 | Alan Babu | 2017-10-25 | 2017-10-30 | 4 |  | Alan Babu | 2017-10-31 | 2017-10-31 | 2017-11-02 | 3 | 2017-11-02 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
4AAR-61 | RFS.103 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-25 | Mahalakshmi | 2017-10-19 | 2017-10-21 | 2 | 24/10: Design issue reported. Workaround done. Awaiting address file to proceed. | Mahalakshmi | 2017-10-25 | 2017-10-25 | 2017-10-27 | 3 | 2017-10-27 | [6 empty] | 3 | -6 | 0 | 0 | 0 | 3 | 6
2STL-66 | RFS.104 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-24 | Aravind | 2017-10-24 | 2017-10-25 | 2 |  | Aravind | 2017-10-26 | 2017-10-26 | 2017-10-26 | 1 | 2017-10-26 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 3 | 1
5FLN-60 | RFS.107 | H-B-J | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-25 | Mani | 2017-10-26 | 2017-10-30 | 3 | 25/10: SAM paused in Appian 26/10: Appian task unpaused | Mani | 2017-11-01 | 2017-11-01 | 2017-11-03 | 3 | 2017-11-03 | 01/11: Start equipment missing for 1 SDS cable. Issue reported. 02/11: There were issues with the GTD created which resulted in protless scenario. | [5 empty] | 3 | 1 | 0 | 0 | 0 | 8 | 4
3TYH-61 | RFS.118 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-26 | linda | 2017-10-27 | 2017-10-31 | 3 | 26/10: SAM task not taken up due to high SAM volume. | Sangeetha | 2017-11-06 | 2017-11-09 | 2017-11-13 | 3 | 2017-11-13 | 01/11: Start equipment missing for 1 SDS cable. Issue reported. | [5 empty] | 5 | 1 | 0 | 2 | 0 | 12 | 4
3CLA-68 | RFS.102 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-26 | Aravind | 2017-10-26 | 2017-10-30 | 3 |  | Aravind | 2017-10-30 | 2017-10-30 | 2017-10-31 | 2 | 2017-10-31 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 4 | 3
2ING-65 | RFS.130 | M-M-H | BAU | Design |  | Rejected - [GML] Sent Back to Telstra (DESG) | 2017-10-26 | Aravind | 2017-11-03 | 2017-11-08 | 3 | 26/10: SAM task not taken up due to high SAM volume. 7/11: Had to get confirmation on fiber and copper demotion. | Aravind | 2017-11-16 | 2017-11-16 |  | -30726 |  | 17/11: Duplicate fuse getting created in PNI. Incident REQ000003100450 raised. | 2017-11-24 |  |  |  |  | 7 | 6 | 0 | 0 | 0 | -30712 | -30725
2SHA-21 | RFS.137 | M-M-H | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-26 | Anusa Moottoolikandy | 2017-10-26 | 2017-10-30 | 3 | 02/11: Rejected. Waiting for documents. |  |  |  |  | 0 |  |  | 2017-11-02 |  |  |  |  | -30714 | 0 | 0 | -1 | 0 | -30712 | 3
2CYS-63 | RFS.105 | M-B-H | BAU | Design |  | [PC] PC Completion & Triage Trigger | 2017-10-26 | Swathy Mohan | 2017-10-26 | 2017-10-30 | 3 | 30/10: Couldn't actualize appian task due to an error thrown while searching SAM details. |  |  |  |  | 0 | [7 empty] | -30714 | 0 | 0 | -1 | 0 | -30712 | 3
4FHL-20 | RFS.108 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-26 | Gaurav | 2017-10-26 | 2017-10-30 | 3 |  | Deepa M04 | 2017-11-08 | 2017-11-08 | 2017-11-15 | 6 | 2017-11-15 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 14 | 7
3HGT-67 | RFS.116 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-27 | Rijo Sunny | 2017-10-31 | 2017-11-01 | 2 |  | Rijo Sunny | 2017-11-01 | 2017-11-01 | 2017-11-06 | 4 | 2017-11-06 | [6 empty] | 1 | 2 | 0 | 0 | 0 | 7 | 4
6SUB-66 | RFS.127 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-27 | Mani | 2017-10-31 | 2017-11-01 | 2 |  | Mohith | 2017-11-02 | 2017-11-14 | 2017-11-23 | 8 | 2017-11-23 | SAM taken up late due to high SAM volume 17/11: Duplicate fuse getting created in PNI. Incident REQ000003100450 raised. 23/11: Performed manual workaround and released the SAM. | [5 empty] | 2 | 2 | 0 | 7 | 0 | 19 | 8
3WIR-69 | RFS.106 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-27 | Anusa Moottoolikandy | 2017-10-27 | 2017-10-31 | 3 |  | Anusa Moottoolikandy | 2017-11-01 | 2017-11-01 | 2017-11-03 | 3 | 2017-11-03 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
2ROS-67 | RFS.135 | H-A-Q | HAC | Pre-AT | 2 | On Hold - [PC] NDD not available | 2017-10-27 |  |  |  | 0 | 03/11/2017: As per NA team, NDD design for 2ROS is scheduled to commence on 29/12/2017. Hence placing the SAM on hold. |  |  |  |  | 0 | [7 empty] | 0 | -30714 | 0 | -1 | 0 | -30713 | 2
5WES-66 | RFS.125 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-27 | linda | 2017-10-31 | 2017-11-01 | 2 |  | Krishnan | 2017-11-13 | 2017-11-13 | 2017-11-14 | 2 | 2017-11-14 | [6 empty] | 8 | 2 | 0 | 0 | 0 | 12 | 2
5NRW-63 | RFS.118 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-27 | Swathy Mohan | 2017-10-31 | 2017-11-02 | 3 |  | Swathy Mohan | 2017-11-02 | 2017-11-02 | 2017-11-07 | 3 | 2017-11-07 | [6 empty] | 1 | 2 | 0 | 0 | 0 | 7 | 4
2PEN-67 | RFS.105 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Krishnan | 2017-10-30 | 2017-11-01 | 3 |  | Krishnan | 2017-11-02 | 2017-11-02 | 2017-11-03 | 2 | 2017-11-03 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
4CHD-61 | RFS.107 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Nisha | 2017-10-31 | 2017-11-02 | 3 |  | Mohith | 2017-11-06 | 2017-11-06 | 2017-11-10 | 4 | 2017-11-10 | 9/11: SpatialNet Error encountered. Incident REQ000003082975 raised. | [5 empty] | 3 | 1 | 0 | 0 | 0 | 9 | 5
4CHP-66 | RFS.108 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Rikku | 2017-10-30 | 2017-11-01 | 3 |  | Deepa M04 | 2017-11-06 | 2017-11-06 | 2017-11-08 | 2 | 2017-11-08 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 7 | 3
2HUR-62 | RFS.108 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Nisha | 2017-10-30 | 2017-11-01 | 3 |  | Nisha | 2017-11-02 | 2017-11-02 | 2017-11-06 | 3 | 2017-11-06 | 2/11: Received address file today | [5 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
6WMB-61 | RFS.106 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Mahalakshmi | 2017-10-31 | 2017-11-02 | 3 | 02/11: Address file received on 2/11. | Mahalakshmi | 2017-11-10 | 2017-11-10 | 2017-11-13 | 2 | 2017-11-13 | 3/11: Partial trace encountered due to portless scenario. More than 7% of SLs are affected. Awaiting confirmation to proceed. 9/11: Workaround done. Few updates were done in design. Proceeding GML load. 13/11: Received new package on 10/11. Couldn't load due to GDSS outage. | [5 empty] | 6 | 1 | 0 | 0 | 0 | 10 | 3
5BRI-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Gaurav | 2017-10-30 | 2017-11-01 | 3 |  | Gaurav | 2017-11-02 | 2017-11-02 | 2017-11-03 | 2 | 2017-11-03 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
3NES-62 | RFS.124 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Reshma Menon | 2017-11-02 | 2017-11-06 | 3 |  | Reshma Menon | 2017-11-07 | 2017-11-07 | 2017-11-09 | 2 | 2017-11-09 | [6 empty] | 1 | 3 | 0 | -1 | 0 | 8 | 5
5BRI-64 | RFS.123 | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-30 | Deepa M04 | 2017-11-03 | 2017-11-07 | 2 |  | Naveen Kumar | 2017-11-15 | 2017-11-16 | 2017-11-16 | 1 | 2017-11-16 | [6 empty] | 6 | 4 | 0 | 1 | 0 | 13 | 2
5NRW-60 | RFS.120 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Mani | 2017-11-03 | 2017-11-07 | 2 |  | Mani | 2017-11-08 | 2017-11-08 | 2017-11-10 | 3 | 2017-11-10 | [6 empty] | 1 | 4 | 0 | 0 | 0 | 9 | 4
6SUB-62 | RFS.132 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-10-31 | Mani | 2017-11-08 |  | -30720 | [5 empty] | 0 |  |  | 2017-11-09 |  |  |  |  | 0 | 5 | 0 | -1 | 0 | -30715 | -30719
2HUR-65 |  | H-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-10-31 | Alan Babu | 2017-10-31 | 2017-11-02 | 3 |  | Krishnan | 2017-11-20 | 2017-11-20 | 2017-11-21 | 2 | 2017-11-21 | [6 empty] | 12 | 0 | 0 | 0 | 0 | 15 | 3
5NRW-64 | RFS.120 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-25 | Krishnan | 2017-11-01 | 2017-11-07 | 4 | 03/11: Critical boundary issue reported. Awaiting AP team to respond. 7/11: actualizing PC task. Rest of the PC task will be carried out once boundary issue is resolved. | Linda | 2017-11-16 | 2017-11-21 | 2017-11-27 | 5 | 2017-11-27 | 27/11: Demotion and MPS promotion was done during GML task. | [5 empty] | 7 | 5 | 0 | 3 | 0 | 23 | 8
4SOP-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Mohith | 2017-10-31 | 2017-10-31 | 1 |  | Mohith | 2017-10-31 | 2017-10-31 | 2017-11-01 | 2 | 2017-11-01 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 3 | 1
2PYM-62 | RFS.107 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Gaurav | 2017-10-31 | 2017-10-31 | 1 |  | Gaurav | 2017-10-31 | 2017-10-31 | 2017-11-01 | 2 | 2017-11-01 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 3 | 1
2ING-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Mahalakshmi | 2017-10-31 | 2017-10-31 | 1 | 31/10: RFS group changed and design only pckae is being delivered as Pre-AT after HFC load. | Mahalakshmi | 2017-10-31 | 2017-10-31 | 2017-11-01 | 2 | 2017-11-01 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 3 | 1
2PYM-63 | RFS.107 | M-A-H | BAU | Pre-AT |  | In Progress - [GML] PNI Load - Complete Run | 2017-10-30 | Anusa Moottoolikandy | 2017-10-31 | 2017-11-01 | 2 | package version 2.0 arrived. Starting PC activities again. Tracked in another record below. | Anusa Moottoolikandy | 2017-10-31 | 2017-11-03 | 2017-11-07 | 2 | 2017-11-07 | 01/11: Package version change confirmed. LDM should provide new address file to proceed. | [5 empty] | -2 | 1 | 0 | 3 | 0 | 6 | 4
6GIR-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Naveen Kumar | 2017-10-31 | 2017-10-31 | 1 | 31/10: RFS group changed and design only pckae is being delivered as Pre-AT after HFC load. | Naveen Kumar | 2017-10-31 | 2017-10-31 | 2017-11-01 | 2 | 2017-11-01 | [6 empty] | 1 | 1 | 0 | 0 | 0 | 3 | 1
4BUR-67 | RFS.107 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-10-30 | Sangeetha | 2017-10-31 | 2017-10-31 | 1 | 31/10: RFS group changed and design only pckae is being delivered as Pre-AT after HFC load. | Sangeetha | 2017-10-31 | 2017-10-31 | 2017-11-17 | 13 | 2017-11-17 | 01/11: 2 locations with 2 different PCD’s connected from 4BUR-67 and 4BUR-69. "selected port is already connected" error encountered.Awaiting onshore communication. 16/11: Received workaround on 16/11. | [5 empty] | 1 | 1 | 0 | 0 | 0 | 14 | 12
4CPR-60 | RFS.108 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-01 | Maria Joy | 2017-11-01 | 2017-11-03 | 3 |  | Mahalakshmi | 2017-11-07 | 2017-11-07 | 2017-11-10 | 3 | 2017-11-10 | [6 empty] | 2 | 0 | 0 | -1 | 0 | 7 | 6
2PET-64 | RFS.108 | M-M-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-01 | Linda | 2017-11-02 | 2017-11-03 | 2 |  | Sangeetha | 2017-11-07 | 2017-11-07 | 2017-11-09 | 2 | 2017-11-09 | [6 empty] | 2 | 1 | 0 | -1 | 0 | 6 | 4
3MIT-60 | RFS.106 | M-M-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-01 | Aravind | 2017-11-01 | 2017-11-02 | 2 |  | Aravind | 2017-11-03 | 2017-11-03 | 2017-11-06 | 2 | 2017-11-06 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
2PAR-62 | RFS.125 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-01 | Maria Joy | 2017-11-13 | 2017-11-15 | 3 |  | Maria Joy | 2017-11-15 | 2017-11-15 | 2017-11-17 | 3 | 2017-11-17 | [6 empty] | 1 | 7 | 0 | 0 | 0 | 12 | 4
2PEN-01 | RFS.134 | M-M-H | BAU | Design | 1 | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-11-02 | Linda | 2017-11-13 |  | -30723 | 14/11: T18 validation and fix failed. Awaiting onshore communication to proceed 16/11: Mismatch in package version. Awaiting NA team to respond 20/11: Will be relaunched in Appian and tracked in different record |  |  |  |  | 0 | [7 empty] | 0 | 6 | 0 | -1 | 0 | -30717 | -30722
2PYM-63 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | Completed - [GML] Handover to DSG | 2017-11-02 | Anusa Moottoolikandy | 2017-11-02 | 2017-11-02 | 1 |  | Anusa Moottoolikandy | 2017-11-02 | 2017-11-02 | 2017-11-07 | 3 | 2017-11-07 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 3 | 2
3TYH-69 | RFS.116 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-11-03 | Mohith | 2017-11-03 | 2017-11-07 | 2 |  | Krishnan | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2 | 2017-11-10 | [6 empty] | 1 | 0 | 0 | 1 | 0 | 5 | 3
4AGV-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-01 | Rikku | 2017-11-01 | 2017-11-01 | 1 | 3/11: Perform check activities were already completed. SAM phase change from Design to Pre AT. RFS Re prioritized. FTTX already loaded. Only HFC load. | Deepa M04 | 2017-11-01 | 2017-11-01 | 2017-11-03 | 3 | 2017-11-03 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 3 | 2
2HLS-61 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | Completed - [GML] Handover to DSG | 2017-10-30 | Naveen Kumar | 2017-10-30 | 2017-11-01 | 3 |  | Mohith | 2017-11-02 | 2017-11-02 | 2017-11-03 | 2 | 2017-11-03 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
2LIV-66 | RFS.118 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-11-03 | Maria Joy | 2017-11-07 | 2017-11-09 | 2 |  | Deepa M04 | 2017-11-13 | 2017-11-16 | 2017-11-20 | 3 | 2017-11-20 | 16/11: Taken up late due to high SAM volume | [5 empty] | 3 | 1 | 0 | 3 | 0 | 11 | 4
4ASH-64 | RFS.113 | H-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-03 | Maria Joy | 2017-11-03 | 2017-11-07 | 2 | 6/11: Copper entities from a different SAM is existing in 4ASH-64. Awaiting onshore communication to proceed with demotion | Anusa Moottoolikandy | 2017-11-15 | 2017-11-17 | 2017-11-21 | 3 | 2017-11-21 | [6 empty] | 6 | 0 | 0 | 2 | 0 | 12 | 4
4FHL-62 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-06 | Nisha | 2017-11-10 | 2017-11-14 | 3 |  | Nisha | 2017-11-15 | 2017-11-15 | 2017-11-17 | 3 | 2017-11-17 | [6 empty] | 2 | 3 | 0 | 0 | 0 | 9 | 4
4MRA-64 | RFS.113 | M-M-Q | HAC | Pre-AT | 1 | Rejected - [PC] Sent Back to Telstra (LDM) | 2017-11-06 | Alan Babu | 2017-11-06 |  | -30719 | 9/11: Location issue reported. SAM rejected |  |  |  |  | 0 |  |  | 2017-11-09 |  |  |  |  | 0 | 0 | 0 | -1 | 0 | -30719 | -30718
6GIR-65 | RFS.143 | M-M-H | BAU | Design |  | Completed [PC] - Trigger Triage | 2017-11-06 | Sangeetha | 2017-11-10 | 2017-11-13 | 2 | [5 empty] | 0 | [7 empty] | -30723 | 3 | 0 | -1 | 0 | -30719 | 2
2PEN-65 | RFS.109 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-11-06 | Nisha | 2017-11-07 | 2017-11-09 | 2 | 9/11: Exception thrown during demotion. Incident INC000006479535 raised. |  |  |  |  | 0 |  |  | 2017-11-15 |  |  |  |  | -30721 | 0 | 0 | -1 | 0 | -30719 | 3
4SOP-65 | RFS.110 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-06 | Rijo Sunny | 2017-11-07 | 2017-11-09 | 2 | 13/11: Missing FTTn docs. Will be re-launched. To be moved to M-A-H. | Rijo Sunny | 2017-11-14 | 2017-11-14 | 2017-11-15 | 2 | 2017-11-15 | 14/11: Only HFC part has been loaded | [5 empty] | 4 | 0 | 0 | 0 | 0 | 7 | 3
5NRW-62 | RFS.110 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-06 | Swathy Mohan | 2017-11-07 | 2017-11-09 | 2 |  | Sangeetha | 2017-11-14 | 2017-11-14 | 2017-11-16 | 3 | 2017-11-16 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 8 | 4
2NEW-63 | RFS.139 | M-M-H | BAU | Design |  | On Hold - [PC] Issues - NBN Internal | 2017-11-06 | Maria Joy | 2017-11-10 |  | -30722 | 13/11: SAM Placed on hold since FTTX documents are not available |  |  |  |  | 0 | [7 empty] | 0 | 3 | 0 | -1 | 0 | -30719 | -30721
3DNC-63 | RFS.132 | H-M-Q | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-11-06 | Aravind | 2017-11-30 | 2017-12-04 | 3 |  | Aravind | 2017-12-05 | 2017-12-07 | 2017-12-07 | 1 | 2017-12-07 | [6 empty] | 2 | 17 | 0 | 2 | 0 | 23 | 2
2RYD-64 | RFS.110 | H-A-Q | HAC | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-11-06 | Rikku | 2017-11-07 |  | -30719 | 7/11: Critical boundary issues reported. 8/11: SAM placed on hold. Awaiting onshore response to proceed. |  |  |  |  | 0 |  |  | 2017-11-15 |  |  |  |  | 0 | 0 | 0 | -1 | 0 | -30719 | -30718
4EMP-25 | RFS.108 | M-B-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-06 | Anusa Moottoolikandy | 2017-11-06 | 2017-11-08 | 2 | 8/11: Difference in packages. Awaiting onshore communication. | Anusa Moottoolikandy | 2017-11-09 | 2017-11-09 | 2017-11-14 | 4 | 2017-11-14 | 14/11: Existing data in PNI and the FAB payload had data discrepancies. Demoted copper entities and deleted fibre entites manually before proceeding with GML load task | [5 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
2HUR-64 | RFS.108 | M-M-Q | BAU | Design |  | On Hold - [PC] Issues - NBN Internal | 2017-11-07 | Deepa M04 | 2017-11-07 | 2017-11-09 | 2 | 7/11: TVT missing 13/11: Missing FTTn docs. On hold. To be changes to Design only due to sub serviceability. |  |  |  |  | 0 | [7 empty] | -30721 | -1 | 0 | -1 | 0 | -30719 | 4
4CUR-60 | RFS.108 | M-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-07 | Mohith | 2017-11-08 | 2017-11-09 | 2 |  | Deepa M04 | 2017-11-13 | 2017-11-13 | 2017-11-15 | 3 | 2017-11-15 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
4NDG-62 | RFS.127 | H-A-Q | HAC | Pre-AT |  | Completed [PC] - Trigger Triage | 2017-11-07 | Alan Babu | 2017-11-09 | 2017-10-13 | -18 | 13/10: PC completed. Partial trace encountered. |  |  |  |  | 0 | [7 empty] | -30704 | 1 | 0 | -1 | 0 | -30719 | -15
2LIV-67 | RFS.125 | M-M-H | BAU | Design |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-11-08 | Krishnan | 2017-11-10 | 2017-10-13 | -19 | [5 empty] | 0 |  |  | 2017-11-15 |  |  |  |  | -30704 | 2 | 0 | -1 | 0 | -30720 | -17
4WTF-65 | RFS.136 | M-M-H | BAU | Design |  | Completed [PC] - Trigger Triage | 2017-11-08 | Aravind | 2017-11-16 | 2017-12-15 | 22 | 17/11: SAM placed on hold due to critical issues reported. 15/12: PC task resumed in Appian. PC completed. |  |  |  |  | 0 | [7 empty] | -30747 | 6 | 0 | -1 | 0 | -30720 | 22
5WES-62 | RFS.108 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-09 | Anusa Moottoolikandy | 2017-11-09 | 2017-11-13 | 3 |  | Anusa Moottoolikandy | 2017-11-14 | 2017-11-14 | 2017-11-17 | 4 | 2017-11-17 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
4CHD-21 | RFS.109 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-09 | Rikku | 2017-11-09 | 2017-11-13 | 3 |  | Swathy Mohan | 2017-11-14 | 2017-11-14 | 2017-11-16 | 3 | 2017-11-16 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
5WES-61 | RFS.108 | M-M-H | BAU | Pre-AT |  | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-11-09 | Mani | 2017-11-09 | 2017-11-13 | 3 | [5 empty] | 0 |  | 21/11:IAB Resubmission | 2017-11-21 |  |  |  |  | -30723 | 0 | 0 | -1 | 0 | -30721 | 3
4OXE-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-08 | Aravind | 2017-11-08 | 2017-11-08 | 1 |  | Aravind | 2017-10-09 | 2017-11-09 | 2017-11-13 | 3 | 2017-11-13 | [6 empty] | -21 | 0 | 0 | 21 | 0 | 4 | 4
3CAU-67 | RFS.111 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-09 | Mani | 2017-11-14 | 2017-11-16 | 3 |  | Mani | 2017-11-20 | 2017-11-20 | 2017-11-21 | 2 | 2017-11-21 | [6 empty] | 3 | 3 | 0 | 0 | 0 | 9 | 3
3CAN-64 | RFS.120 | H-A-Q | HAC | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-10 | Reshma Menon | 2017-11-10 | 2017-11-14 | 3 |  | Reshma Menon | 2017-11-15 | 2017-11-15 | 2017-11-20 | 4 | 2017-11-20 | 17/11: SAM couldn't be released since the ADA issue reported is not yet resolved. Awaiting AP team to respond | [5 empty] | 2 | 0 | 0 | 0 | 0 | 7 | 5
4CHL-70 | RFS.130 | M-A-H | BAU | Pre-AT |  | Completed - [GML] Handover to DSG | 2017-11-10 | Nisha | 2017-11-15 | 2017-11-17 | 3 |  | Swathy Mohan | 2017-11-21 | 2017-11-21 | 2017-11-27 | 5 | 2017-11-27 | 27/11: Pretty high number of duct and trench failures occurred. Manual fixes were involved. | [5 empty] | 3 | 3 | 0 | 0 | 0 | 12 | 6
2CRR-66 | RFS.116 | M-M-H | BAU | Design |  | Completed - [GML] Handover to DSG | 2017-11-10 | Swathy Mohan | 2017-11-10 | 2017-11-14 | 3 |  | Rijo Sunny | 2017-11-15 | 2017-11-15 | 2017-11-17 | 3 | 2017-11-17 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4OXE-60 | RFS.109 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-13 | Mahalakshmi | 2017-11-13 | 2017-11-16 | 4 | 16/11: NAT overlap detected. Copper demoion took time. | Mahalakshmi | 2017-11-16 | 2017-11-16 | 2017-11-20 | 3 | 2017-11-20 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 6 | 5
5NRW-66 | RFS.110 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-13 | Alan Babu | 2017-11-14 | 2017-11-16 | 3 |  | Alan Babu | 2017-11-20 | 2017-11-20 | 2017-11-22 | 3 | 2017-11-22 | [6 empty] | 3 | 1 | 0 | 0 | 0 | 8 | 4
4OXE-61 | RFS.110 | M-A-H | BAU | Pre-AT | 2 | Completed - [GML] Handover to DSG | 2017-11-13 | Sangeetha | 2017-11-14 | 2017-11-16 | 3 |  | Sangeetha | 2017-11-16 | 2017-11-21 | 2017-11-23 | 3 | 2017-11-23 | 17/11: PNI error encountered during demotion. Had to validate whether service class was downgraded for the listed SLs. | [5 empty] | 1 | 1 | 0 | 3 | 0 | 9 | 4
4FHL-60 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | On Hold - [GML] Awaiting Boundary Update | 2017-11-14 | Swathy Mohan |  |  | 0 | [5 empty] | 0 | [7 empty] | 0 | -30725 | 0 | -1 | 0 | -30724 | 2
3SSN-61 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-14 | Mohith | 2017-11-22 | 2017-11-24 | 3 |  | Mohith | 2017-11-27 | 2017-11-27 | 2017-12-01 | 5 | 2017-12-01 | 29/11: Design issue reported. Awaiting onshore communication to proceed. | [5 empty] | 2 | 6 | 0 | 0 | 0 | 14 | 6
2PYM-65 | RFS.118 | M-A-Q | HAC | Pre-AT | 1 | Rejected - [PC] Sent Back to Telstra (LDM) | 2017-11-14 | Linda | 2017-11-14 |  | -30724 | [5 empty] | 0 |  |  | 2017-11-17 |  |  |  |  | 0 | 0 | 0 | -1 | 0 | -30724 | -30723
2HUR-60 | RFS.135 | M-M-Q | BAU | Design | 1 | On Hold - [PC] Issues - NBN Internal | 2017-11-14 | Nisha | 2017-11-20 |  | -30728 | 20/11: Waiting for FTTB. Expected to arrive on 08/12. 15/1: SAM task resumed. 16/1: SAM reluanched on 15/1 and placed On hold. Expecting a new package |  |  |  |  | 0 |  |  |  | 2017-11-20 |  |  |  | 0 | 4 | -30728 | -1 | 0 | -30724 | 1
3TYH-66 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-14 | Alan Babu | 2017-11-30 | 2017-12-04 | 3 |  | Anusa Moottoolikandy | 2017-12-05 | 2017-12-08 | 2017-12-12 | 3 | 2017-12-12 | [6 empty] | 2 | 12 | 0 | 3 | 0 | 21 | 4
6CTO-20 | RFS.133 | M-M-H | BAU | Design | 3 | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2017-11-15 |  |  |  | 0 | FTTB Not ready |  |  |  |  | 0 |  |  | 2017-11-17 |  |  |  |  | 0 | -30726 | 0 | -1 | 0 | -30725 | 2
4MRA-64 | RFS.113 | M-M-Q | HAC | Pre-AT | 0.2 | Completed - [GML] Handover to DSG | 2017-11-15 | Rikku | 2017-11-15 | 2017-11-17 | 3 |  | Rikku | 2017-11-20 | 2017-11-20 | 2017-11-22 | 3 | 2017-11-22 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
6WMB-62 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2017-11-16 | Rijo Sunny | 2017-11-16 | 2017-11-20 | 3 |  | Gaurav | 2017-11-23 | 2017-11-23 | 2017-11-27 | 3 | 2017-11-27 | 23/11: HFC only load | [5 empty] | 4 | 0 | 0 | 0 | 0 | 8 | 4
2RYD-65 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-16 | Alan Babu | 2017-11-16 | 2017-11-20 | 3 |  | Anusa Moottoolikandy | 2017-11-22 | 2017-11-22 | 2017-11-24 | 3 | 2017-11-24 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 7 | 4
3OAK-69 | RFS.137 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-11-16 | Mani | 2017-12-04 | 2017-12-06 | 3 |  | Mani | 2017-12-07 | 2017-12-11 | 2017-12-13 | 3 | 2017-12-13 | [6 empty] | 2 | 12 | 0 | 2 | 0 | 20 | 4
4CHD-60 | RFS.126 | M-B-H | BAU | Design | 2 | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-11-16 | Krishnan | 2017-11-16 | 2017-11-17 | 2 | 21/11: FTTx defects. |  |  |  |  | 0 |  |  | 2017-11-21 |  |  |  |  | -30727 | 0 | 0 | -1 | 0 | -30726 | 2
2RYD-66 | RFS.110 | M-A-H | BAU | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2017-11-16 | Maria Joy | 2017-11-20 | 2017-11-22 | 3 |  | Maria Joy | 2017-11-22 | 2017-11-22 | 2017-11-27 | 4 | 2017-11-27 | 24/11: PCD count mismatch in PNI trace. Awaiting onshore communication. | [5 empty] | 1 | 2 | 0 | 0 | 0 | 8 | 5
2PEN-65 | RFS.109 | M-M-H | BAU | Design | 0.1 | Completed - [GML] Handover to DSG | 2017-11-17 | Mohith | 2017-11-20 | 2017-11-22 | 3 | 22/11: PNI error encountered during demotion. Demotion will be done along with GML task. | Krishnan | 2017-11-27 | 2017-11-27 | 2017-11-29 | 3 | 2017-11-29 | [6 empty] | 4 | 1 | 0 | 0 | 0 | 9 | 4
2HUR-66 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-17 | Naveen Kumar Nagaraj | 2017-11-20 | 2017-11-22 | 3 |  | Naveen Kumar Nagaraj | 2017-11-23 | 2017-11-23 | 2017-11-28 | 4 | 2017-11-28 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 8 | 5
2EAS-69 | RFS.130 | M-M-Q | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-11-17 | Nisha | 2017-11-20 | 2017-11-21 | 2 |  | Rijo Sunny | 2017-11-24 | 2017-11-24 | 2017-11-28 | 3 | 2017-11-28 | [6 empty] | 4 | 1 | 0 | 0 | 0 | 8 | 3
4EMP-25 | RFS.108 | M-B-H | BAU | Pre-AT | 2 | Completed - [GML] Handover to DSG | 2017-11-17 | Aravind | 2017-11-17 | 2017-11-20 | 2 |  | Aravind | 2017-11-21 | 2017-11-21 | 2017-11-22 | 2 | 2017-11-22 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
4FHL-22 | RFS.141 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-11-17 | Rikku | 2017-12-01 | 2017-12-05 | 3 |  | Maria Joy | 2017-12-06 | 2017-12-11 | 2017-12-13 | 3 | 2017-12-13 | 08/12: Awaiting Project details | [5 empty] | 2 | 10 | 0 | 3 | 0 | 19 | 4
2WRO-60 | RFS.139 | M-M-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-17 | Deepa M04 | 2017-11-23 | 2017-11-27 | 3 |  | Deepa M04 | 2017-11-28 | 2017-11-28 | 2017-11-30 | 3 | 2017-11-30 | [6 empty] | 2 | 4 | 0 | 0 | 0 | 10 | 4
5HNL-20 | RFS.153 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-11-17 | Rikku | 2017-11-21 | 2017-11-23 | 3 |  | Anusa Moottoolikandy | 2017-11-24 | 2017-11-29 | 2017-12-01 | 3 | 2017-12-01 | [6 empty] | 2 | 2 | 0 | 3 | 0 | 11 | 4
3KGP-20 | RFS.135 | M-M-Q | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-11-17 | Sangeetha | 2017-11-21 | 2017-11-22 | 2 |  | Sangeetha | 2017-11-23 | 2017-11-23 | 2017-11-27 | 3 | 2017-11-27 | [6 empty] | 2 | 2 | 0 | 0 | 0 | 7 | 3
3HDB-68 | RFS.111 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-20 | Reshma Menon | 2017-11-20 | 2017-11-22 | 3 |  | Reshma Menon | 2017-11-23 | 2017-11-23 | 2017-11-27 | 3 | 2017-11-27 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3TNI-62 | RFS.111 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-20 | Rijo Sunny | 2017-11-21 | 2017-11-23 | 3 |  | Alan Babu | 2017-11-24 | 2017-11-27 | 2017-11-30 | 4 | 2017-11-30 | 30/11: VDI issues encountered post noon offshore time on 29/11. The system was very slow. SpatialNet as well had issues. INC000006691531 has been raised to track this. Delayed job post. | [5 empty] | 2 | 1 | 0 | 1 | 0 | 9 | 5
5WES-61 | RFS.111 | M-M-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-21 | Mani | 2017-11-22 | 2017-11-23 | 2 |  | Mani | 2017-11-27 | 2017-11-27 | 2017-11-29 | 3 | 2017-11-29 | [6 empty] | 3 | 1 | 0 | 0 | 0 | 7 | 3
3CAU-66 | RFS.125 | M-M-Q | BAU | Design | 3 | Completed - [GML] Handover to DSG | 2017-11-22 | Mohith | 2017-12-11 | 2017-12-14 | 4 |  | Rikku | 2017-12-15 | 2017-12-18 | 2017-12-20 | 3 | 2017-12-20 | [6 empty] | 2 | 13 | 0 | 1 | 0 | 21 | 5
2SHA-21 | RFS.137 | M-M-H | BAU | Design | 0.1 | Completed - [GML] Handover to DSG | 2017-11-22 | Naveen Kumar Nagaraj | 2017-11-22 | 2017-11-22 | 1 |  | Naveen Kumar Nagaraj | 2017-11-30 | 2017-12-01 | 2017-12-04 | 2 | 2017-12-04 | [6 empty] | 7 | 0 | 0 | 1 | 0 | 9 | 1
2KNS-61 | RFS.111 | M-A-H | BAU | Pre-AT | 0.1 | On Hold - [PC] Issues - NBN Internal | 2017-11-22 | Nisha | 2017-11-22 | 2017-11-26 | 3 |  | Aravind | 2017-11-29 | 2017-11-29 |  | -30735 |  | 01/12: SAM placed on hold due to design issues. | [5 empty] | 3 | 0 | 0 | 0 | 0 | -30730 | -30733
2LIV-67 | RFS.125 | M-M-H | BAU | Design | 5 | Completed - [GML] Handover to DSG | 2017-11-22 | Mani | 2017-11-29 | 2017-12-05 | 5 | 01/12: PNI error encountered during design export. REQ000003215999 raised. On hold: PNI incident raised INC000006693460. Error during demotion | Mani | 2017-12-06 | 2017-12-06 | 2017-12-08 | 3 | 2017-12-08 | [6 empty] | 2 | 5 | 0 | 0 | 0 | 13 | 6
2SEV-20 | RFS.146 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2017-11-23 | Anusa Moottoolikandy | 2017-12-21 | 2017-12-22 | 2 | [5 empty] | 0 | [7 empty] | -30752 | 20 | 0 | -1 | 0 | -30731 | 2
6SUB-62 | RFS.132 | M-M-H | BAU | Design | 4 | Completed - [GML] Handover to DSG | 2017-11-23 | Aravind | 2017-12-15 | 2017-12-19 | 3 |  | Aravind | 2018-01-09 | 2018-01-09 | 2018-01-11 | 3 | 2018-01-11 | [6 empty] | 13 | 16 | 0 | 0 | 0 | 33 | 4
6MLO-20 | RFS.150 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-11-23 | Gaurav | 2017-12-21 | 2017-12-26 | 2 |  | Swathy Mohan | 2018-01-05 | 2018-01-05 | 2018-01-09 | 3 | 2018-01-09 | [6 empty] | 7 | 20 | 0 | 0 | 0 | 31 | 4
4NDG-60 | RFS.127 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-23 | Anusa Moottoolikandy | 2017-11-24 | 2017-12-06 | 9 | 28/11: Awaiting confirmation from NA on SAM type 6/12: Got confirmation on the SAM type | Gaurav | 2017-12-07 | 2017-12-07 | 2017-12-08 | 2 | 2017-12-08 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 12 | 9
4PDP-63 | RFS.143 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-23 | Deepa M04 | 2017-12-01 | 2017-12-05 | 3 |  | Deepa M04 | 2017-12-06 | 2017-12-06 | 2017-12-08 | 3 | 2017-12-08 | [6 empty] | 2 | 6 | 0 | 0 | 0 | 12 | 4
5GLL-20 | RFS.137 | M-M-Q | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2017-11-23 | Sangeetha | 2017-11-27 | 2017-11-29 | 3 | [5 empty] | 0 | [7 empty] | -30735 | 2 | 0 | -1 | 0 | -30731 | 3
2LIV-63 | RFS.118 | M-M-H | BAU | Design | 3 | Completed [PC] - Trigger Triage | 2017-11-24 | Aravind | 2017-11-28 | 2017-11-30 | 3 | [5 empty] | 0 | [7 empty] | -30736 | 2 | 0 | -1 | 0 | -30732 | 3
3MLN-61 | RFS.125 | M-M-Q | BAU | Design | 3 | Completed - [GML] Handover to DSG | 2017-11-24 | Nisha | 2017-11-29 | 2017-12-01 | 3 | 01/12: Error encountered during demotion. INC000006706937 raised. | Mahalakshmi | 2017-12-05 | 2017-12-05 | 2017-12-08 | 4 | 2017-12-08 | 7/12: Error encountered during FTTB load | [5 empty] | 3 | 3 | 0 | 0 | 0 | 11 | 5
2ING-65 | RFS.129 | M-M-H | BAU | Design | 3 | Completed - [GML] Handover to DSG | 2017-11-24 | Aravind | 2017-11-24 | 2017-11-27 | 2 |  | Aravind | 2017-12-01 | 2017-12-01 | 2017-12-06 | 4 | 2017-12-06 | 4/12: GDSS issue. GML generation on hold. 5/12: Power cables and equipments were not getting created in PNI. Manual fixes were involved | [5 empty] | 5 | 0 | 0 | 0 | 0 | 9 | 4
6CTO-20 | RFS.133 | M-M-H | BAU | Design | 4 | Completed - [GML] Handover to DSG | 2017-11-24 | Maria Joy | 2018-01-18 | 2018-01-19 | 2 | 12/12: SAM rejected due to critical design issues. 18/1: SAM task resumed in Appian on 18/1 | Mohith | 2018-01-22 | 2018-01-22 | 2018-01-24 | 3 | 2018-01-24 |  | 2017-12-12 |  |  |  |  | 2 | 36 | 0 | 0 | 0 | 41 | 3
2GBE-64 | RFS.112 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-27 | Maria Joy | 2017-11-28 | 2017-11-30 | 3 |  | Sangeetha | 2017-12-13 | 2017-12-13 | 2017-12-15 | 3 | 2017-12-15 | [6 empty] | 10 | 1 | 0 | 0 | 0 | 15 | 4
2CHA-62 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | Rejected - [PC] Sent Back to Telstra (AP) | 2017-11-27 | Reshma Menon | 2017-11-28 |  | -30734 | 01/12: SAM rejected due to critical issues reported by boundary team. |  |  |  |  | 0 |  |  | 2017-12-01 |  |  |  |  | 0 | 1 | 0 | -1 | 0 | -30733 | -30733
2NEW-23 | RFS.133 | M-M-H | BAU | Pre-AT | 1 | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2017-11-27 | Krishnan | 2017-11-28 | 2017-12-01 | 4 | 01/12: SAM rejected due to critical boundary and design issues. |  |  |  |  | 0 |  |  | 2017-12-01 |  |  |  |  | -30737 | 1 | 0 | -1 | 0 | -30733 | 4
2GBE-65 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-27 | Mahalakshmi | 2017-11-28 | 2017-11-30 | 3 |  | Mahalakshmi | 2017-12-01 | 2017-12-01 | 2017-12-06 | 4 | 2017-12-06 | [6 empty] | 2 | 1 | 0 | 0 | 0 | 8 | 5
3KYG-65 | RFS.113 | H-A-H | BAU | Pre-AT | 3 | Completed - [GML] Handover to DSG | 2017-11-27 | Naveen Kumar Nagaraj | 2017-11-28 | 2017-12-01 | 4 |  | Sangeetha | 2017-12-04 | 2017-12-04 | 2017-12-06 | 3 | 2017-12-06 | 4/12: GDSS issue: INC000006723569 | [5 empty] | 2 | 1 | 0 | 0 | 0 | 8 | 5
2CRR-20 | RFS.112 | M-B-H | BAU | Pre-AT | 4 | Completed - [GML] Handover to DSG | 2017-11-28 | Rijo Sunny | 2017-11-29 | 2017-12-04 | 4 | 04/12: Issue encountered during demotion. OSP report before and after demotion had discrepancies. Had to perform demotion again. | Mohith | 2017-12-06 | 2017-12-06 | 2017-12-11 | 4 | 2017-12-11 | 8/12: FTTN design changes suggested. | [5 empty] | 3 | 1 | 0 | 0 | 0 | 10 | 6
2BON-61 | RFS.123 | M-M-H | BAU | Design | 3 | Completed - [GML] Handover to DSG | 2017-11-29 | Anusa Moottoolikandy | 2017-12-01 | 2017-12-05 | 3 | 7/12: SAM rejected due to issues with FTTB's | Sangeetha | 2018-01-18 | 2018-01-18 | 2018-01-23 | #VALUE! | 2018-01-23 | 18/1: FTTB availalble now. GMLload to be proceeded. 23/1: Sam was rejected before the PC activities were completed. Demotion and MPS promotion was performed along with GML load task. | 2017-12-07 |  |  |  |  | 30 | 2 | 0 | 0 | 0 | #VALUE! | #VALUE!
5WES-65 | RFS.125 | H-M-H | BAU | Pre-AT | 4 | Rejected - [PC] Sent Back to Telstra (AP) | 2017-11-29 | Reshma Menon | 2017-12-01 | 2017-12-05 | 3 | 7/12: SAM rejected due to critical boundary issues |  |  |  |  | 0 |  |  | 2017-12-07 |  |  |  |  | -30739 | 2 | 0 | -1 | 0 | -30735 | 3
2RYD-64 | RFS.110 | H-A-Q | HAC | Pre-AT | 4 | Completed - [GML] Handover to DSG | 2017-11-30 | Nisha | 2017-12-05 | 2017-12-07 | 3 |  | Deepa M04 | 2017-12-11 | 2017-12-11 | 2018-02-05 | 37 | 2018-02-05 | 13/12: SAM handover on hold. Awaiting confirmation on inverse PONSa |  |  |  | 2018-12-11 | 2018-02-05 | 3 | 3 | 0 | 0 | -205 | 44 | 243
3KYG-69 | RFS.113 | M-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-11-30 | Maria Joy | 2017-12-01 | 2017-12-05 | 3 |  | Maria Joy | 2017-12-06 | 2017-12-06 | 2017-12-11 | 4 | 2017-12-11 | 7/12: Cable failure due to seleced port already connected error. Awaiting onshore inputs to proceed. |  |  |  | 2017-12-07 | 2017-12-11 | 2 | 1 | 0 | 0 | 3 | 8 | 2
2RDL-62 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-01 | Aravind | 2017-12-14 | 2017-12-14 | 1 |  | Aravind | 2017-12-15 | 2017-12-15 | 2017-12-18 | 2 | 2017-12-18 | [6 empty] | 2 | 9 | 0 | 0 | 0 | 12 | 1
3NAW-62 | RFS.114 | M-M-Q | HAC | Pre-AT | 0.5 | Completed - [GML] Handover to DSG | 2017-12-01 | Rijo Sunny | 2017-12-01 | 2017-12-05 | 3 |  | Rijo Sunny | 2017-12-06 | 2017-12-08 | 2017-12-08 | 1 | 2017-12-08 | [6 empty] | 2 | 0 | 0 | 2 | 0 | 6 | 2
5GNG-60 | RFS.116 | M-A-H | BAU | Pre-AT | 3 | Completed - [GML] Handover to DSG | 2017-12-01 | Nisha | 2017-12-11 | 2017-12-13 | 3 |  | Gaurav | 2018-01-04 | 2018-01-04 | 2018-01-08 | 3 | 2018-01-08 | [6 empty] | 14 | 6 | 0 | 0 | 0 | 24 | 4
6GIR-20 | RFS.151 | M-B-H | BAU | Design | 2 | Completed - [GML] Handover to DSG | 2017-12-01 | Mohith | 2017-12-21 | 2017-12-26 | 2 |  | Krishnan | 2018-01-05 | 2018-01-05 | 2018-01-08 | 2 | 2018-01-08 | [6 empty] | 7 | 14 | 0 | 0 | 0 | 24 | 3
3MIT-62 | RFS.125 | H-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-01 | Reshma Menon | 2017-12-14 | 2017-12-18 | 3 |  | Reshma Menon | 2017-12-19 | 2017-12-19 | 2017-12-19 | 1 | 2017-12-19 | HFC only design only Sam. No handover required. | [5 empty] | 2 | 9 | 0 | 0 | 0 | 13 | 2
4EMP-02 | RFS.110 | M-B-H | BAU | Pre-AT | 0.3 | Completed - [GML] Handover to DSG | 2017-12-01 | Krishnan | 2017-12-01 | 2017-12-05 | 3 |  | Krishnan | 2017-12-06 | 2017-12-07 | 2017-12-11 | 3 | 2017-12-11 | [6 empty] | 2 | 0 | 0 | 1 | 0 | 7 | 4
4CHD-63 | RFS.127 | M-M-H | BAU | Design | 2 | Completed - [GML] Handover to DSG | 2017-12-01 | Rijo Sunny | 2017-12-14 | 2017-12-18 | 3 |  | Mohith | 2018-01-05 | 2018-01-05 | 2018-01-09 | 3 | 2018-01-09 | [6 empty] | 12 | 9 | 0 | 0 | 0 | 25 | 4
2RDL-61 | RFS.139 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2017-12-04 | Swathy Mohan | 2017-12-04 | 2017-12-06 | 3 | [5 empty] | 0 | [7 empty] | -30740 | 0 | 0 | -1 | 0 | -30738 | 3
4SRW-69 | RFS.149 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2017-12-04 | Gaurav | 2017-12-04 | 2017-11-06 | -20 | [5 empty] | 0 | [7 empty] | -30719 | 0 | 0 | -1 | 0 | -30738 | -18
4CHL-68 | RFS.130 | H-A-Q | HAC | Pre-AT | 3 | Completed - [GML] Handover to DSG | 2017-12-04 | Alan Babu | 2017-12-04 | 2017-12-06 | 3 |  | Alan Babu | 2017-12-07 | 2017-12-07 | 2017-12-11 | 3 | 2017-12-11 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
2CAM-60 | RFS.139 | M-M-Q | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2017-12-04 | Rikku | 2017-12-06 | 2017-12-06 | 1 | [5 empty] | 0 | [7 empty] | -30740 | 2 | 0 | -1 | 0 | -30738 | 1
5NRW-65 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-05 | Reshma Menon | 2017-12-05 | 2017-12-07 | 3 |  | Krishnan | 2017-12-11 | 2017-12-12 | 2017-12-14 | 3 | 2017-12-14 | [6 empty] | 3 | 0 | 0 | 1 | 0 | 8 | 4
4RBN-61 | RFS.113 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-05 | Mohith | 2017-12-05 | 2017-12-07 | 3 |  | Mohith | 2017-12-08 | 2017-12-08 | 2017-12-12 | 3 | 2017-12-12 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
4TGP-63 | RFS.135 | H-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-05 | Linda | 2017-12-15 | 2017-12-18 | 2 | 08/12: SAM placed on hold. NDD not available. 15/12: Proceeding without node split 19/12: GDSS partial trace encoountered. Notification send on 20/12 | Linda | 2017-12-20 | 2017-12-20 | 2017-12-22 | 3 | 2017-12-22 | [6 empty] | 3 | 8 | 0 | 0 | 0 | 14 | 3
4CHD-60 | RFS.126 | M-B-H | BAU | Design | 3 | Completed - [GML] Handover to DSG | 2017-12-05 | Sangeetha | 2017-12-20 | 2017-12-21 | 2 | Rejected : Critical Design Issues | Sangeetha | 2018-01-09 | 2018-01-09 | 2018-01-11 | 3 | 2018-01-11 | 02/01: Received feedback from Telstra. SLD updated. No new T18 package will be provided. Hence proceeding with the GML load. | 2017-12-21 |  |  |  |  | 11 | 11 | 0 | 0 | 0 | 25 | 3
4CUR-63 | RFS.110 | M-A-H | BAU | Pre-AT | 5 | Completed - [GML] Handover to DSG | 2017-12-06 | Anusa Moottoolikandy | 2017-12-06 | 2017-12-08 | 3 | 12/12: SAM rejected. Serviceability threshold not met. RFS being shifted | Swathy Mohan | 2018-01-30 | 2018-01-31 | 2018-02-06 | 5 | 2018-02-06 | 31/1: Issue resolved. Proceeding with T18 version 5.0. 1/1: PNI issue encountered (INC000007196503). 2/2: FTTN location is being served by PCD from another SAM. Awaiting business confirmation to proceed. 6/2: Got confirmation to include the location in 4CUR-63. Handing over to DSG. | 2017-12-12 |  |  | 2018-02-02 |  | 34 | 0 | 0 | 1 | -30778 | 41 | 30784
4ABO-62 | RFS.135 | M-A-Q | HAC | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-06 | Anusa Moottoolikandy | 2017-12-15 | 2017-12-18 | 2 | 11/12: SAM placed on hold. NDD missing in connect MTM 15/12: Proceeding without node split | Deepa M04 | 2017-12-19 | 2017-12-19 | 2017-12-21 | 3 | 2017-12-21 | [6 empty] | 2 | 7 | 0 | 0 | 0 | 12 | 3
4TGP-67 | RFS.135 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-06 | Sangeetha | 2017-12-15 | 2017-12-18 | 2 | 12/12: SAM placed on hold due to missing NDD. FBR placedVaidation performed without node split 15/12: Proceeding without node split | Sangeetha | 2017-12-18 | 2017-12-18 | 2017-12-20 | 3 | 2017-12-20 | [6 empty] | 1 | 7 | 0 | 0 | 0 | 11 | 3
3TNB-62 | RFS.135 | H-M-Q | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-06 | Maria Joy | 2017-12-18 | 2017-12-19 | 2 |  | Anusa Moottoolikandy | 2017-12-22 | 2017-12-28 | 2017-12-28 | -30754 |  | 28/12: H-M-Q design only SAM. HFC valiation run and fixes completed. No handover required. | [5 empty] | 4 | 8 | 0 | 2 | 0 | -30740 | -30754
3NCO-68 | RFS.126 | H-M-Q | BAU | Design | 1 | Not Applicable | 2017-12-06 |  |  |  | 0 | [5 empty] | 0 | [7 empty] | 0 | -30741 | 0 | -1 | 0 | -30740 | 2
4LNH-62 | RFS.142 | H-M-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-06 | Nisha | 2017-12-12 | 2017-12-14 | 3 |  | Nisha | 2017-12-18 | 2017-12-18 | 2017-12-20 | 3 | 2017-12-20 | [6 empty] | 3 | 4 | 0 | 0 | 0 | 11 | 4
3SSN-62 | RFS.132 | M-M-H | BAU | Design | 4 | Completed - [GML] Handover to DSG | 2017-12-06 | Mani | 2017-12-18 | 2017-12-19 | 2 |  | Rijo Sunny | 2017-12-20 | 2017-12-20 | 2017-12-22 | 3 | 2017-12-22 | [6 empty] | 2 | 8 | 0 | 0 | 0 | 13 | 3
4ABC-61 | RFS.113 | M-M-H | BAU | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2017-12-06 | Mani | 2017-12-11 | 2017-12-13 | 3 |  | Mani | 2017-12-14 | 2017-12-14 | 2017-12-18 | 3 | 2017-12-18 | [6 empty] | 2 | 3 | 0 | 0 | 0 | 9 | 4
3CTA-65 | RFS.140 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-07 | Reshma Menon | 2017-12-19 | 2017-12-21 | 3 |  | Mani | 2017-12-22 | 2017-12-28 | 2018-01-01 | 2 | 2018-01-01 | [6 empty] | 2 | 8 | 0 | 2 | 0 | 15 | 3
2MEN-63 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-07 | Nisha | 2017-12-07 | 2017-12-08 | 2 |  | Naveen Kumar Nagaraj | 2017-12-13 | 2018-01-09 | 2018-01-11 | 3 | 2018-01-11 | 14/12: Location issue.Waiting confirmation from Telstra. 9/1: Informed after triage that missing SL will be included in next package. Proceeding with GML load |  |  |  | 2017-12-14 | 2018-01-09 | 4 | 0 | 0 | 16 | 16 | 23 | -13
2PYM-61 | RFS.116 | M-A-H | BAU | Pre-AT | 2 | Completed - [GML] Handover to DSG | 2017-12-07 | Aravind | 2017-12-07 | 2017-12-11 | 3 |  | mahalakshmi | 2017-12-13 | 2017-12-13 | 2017-12-15 | 3 | 2017-12-15 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 7 | 4
3KYG-61 | RFS.147 | M-M-H | BAU | Design | 0.1 | Completed [PC] - Trigger Triage | 2017-12-07 | Krishnan | 2017-12-21 | 2017-12-26 | 2 | [5 empty] | 0 | [7 empty] | -30752 | 10 | 0 | -1 | 0 | -30741 | 2
2CHA-62 | RFS.112 | H-A-Q | HAC | Pre-AT | 2 | Completed - [GML] Handover to DSG | 2017-12-08 | Reshma Menon | 2017-12-08 | 2017-12-12 | 3 |  | Reshma Menon | 2017-12-14 | 2017-12-14 | 2017-12-15 | 2 | 2017-12-15 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
3RES-64 | RFS.126 | H-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-08 | Rikku | 2017-12-14 | 2017-12-18 | 3 |  | Reshma Menon | 2017-12-20 | 2017-12-20 | 2017-12-21 | 2 | 2017-12-21 | 21/12: Design only HFC Sam. No handover required. Validation run completed and SAM task actualized | [5 empty] | 3 | 4 | 0 | 0 | 0 | 10 | 3
2UND-61 | RFS.117 | H-M-Q | HAC | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2017-12-11 | Krishnan | 2017-12-11 | 2017-12-13 | 3 |  | Krishnan | 2017-12-14 | 2017-12-14 | 2017-12-19 | 5 | 2017-12-20 | 19/12: Manual fixes were involved. More than 36 duct were created manually. Delay in job posting. Raised incident INC000006894115 . | [5 empty] | 2 | 0 | 0 | 0 | 0 | 8 | 6
6SUB-66 | RFS.114 | M-A-H | BAU | Pre-AT | 3 | Completed - [GML] Handover to DSG | 2017-12-11 | Swathy Mohan | 2017-12-11 | 2017-11-13 | -21 |  | Mohith | 2017-12-18 | 2017-12-18 | 2017-12-22 | 5 | 2017-12-22 | 20/12: Manual fixes in PNI going on. Will be released on 21/12 | [5 empty] | 26 | 0 | 0 | 0 | 0 | 10 | -16
2EPP-65 | RFS.114 | H-M-Q | HAC | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2017-12-11 | Gaurav | 2017-12-11 | 2017-12-13 | 3 |  | Gaurav | 2017-12-14 | 2017-12-14 | 2017-12-18 | 3 | 2017-12-18 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 6 | 4
3BAY-67 | RFS.135 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2017-12-11 | Rijo Sunny | 2017-12-19 | 2017-12-21 | 3 | [5 empty] | 0 | [7 empty] | -30751 | 6 | 0 | -1 | 0 | -30743 | 3
3TYH-69 | RFS.114 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-11 | Mahalakshmi | 2017-12-11 | 2017-12-13 | 3 |  | Mahalakshmi | 2017-12-15 | 2017-12-15 | 2017-12-19 | 2 | 2017-12-19 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 7 | 4
4FHL-65 | RFS.122 | M-A-Q | HAC | Pre-AT | 1 | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2017-12-11 | Rijo Sunny | 2017-12-11 | 2017-12-13 | 3 |  | Rijo Sunny | 2017-12-14 | 2017-12-14 |  | -30746 |  | 18/12: SAM rejected due to critical design issues | 2017-12-18 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | -30743 | -30745
3NCO-68 | RFS.126 | H-M-Q | BAU | Design | 2 | Completed - [GML] Handover to DSG | 2017-12-11 | Krishnan | 2017-12-14 | 2017-12-15 | 2 |  | Linda | 2017-12-15 | 2017-12-15 | 2017-12-15 | 1 | 2017-12-15 | HFC only design only Sam. No handover required. | [5 empty] | 1 | 3 | 0 | 0 | 0 | 5 | 1
2NEW-23 | RFS.133 | M-M-H | BAU | Design | 3 | Completed - [GML] Handover to DSG | 2017-12-11 | Mahalakshmi | 2017-12-18 | 2017-12-20 | 3 |  | Sangeetha | 2017-12-22 | 2017-12-22 | 2017-12-27 | 2 | 2017-12-27 | [6 empty] | 3 | 5 | 0 | 0 | 0 | 11 | 3
2CAR-63 | RFS.116 | M-M-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-11 | Aravind | 2017-12-12 | 2017-12-13 | 2 |  | Anusa Moottoolikandy | 2017-12-18 | 2017-12-18 | 2017-12-20 | 3 | 2017-12-20 | [6 empty] | 4 | 1 | 0 | 0 | 0 | 8 | 3
2BAN-60 | RFS.116 | M-B-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2017-12-11 | sangeetha | 2017-12-12 | 2017-12-14 | 3 | [5 empty] | 0 | [7 empty] | -30746 | 1 | 0 | -1 | 0 | -30743 | 3
2PEN-01 | RFS.134 | M-M-H | BAU | Design | 4.1 | Completed - [GML] Handover to DSG | 2017-12-12 | Krishnan | 2017-12-19 | 2017-12-20 | 2 |  | Sangeetha | 2017-12-22 | 2017-12-27 | 2017-12-29 | 3 | 2017-12-29 | [6 empty] | 3 | 5 | 0 | 1 | 0 | 12 | 3
2QUA-63 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-12 | Gaurav | 2017-12-13 | 2017-12-15 | 3 |  | Alan Babu | 2017-12-18 | 2017-12-18 | 2017-12-21 | 4 | 2017-12-21 | 20/12: PNI manual fixes were involved. Planning to release on 21/12 | [5 empty] | 2 | 1 | 0 | 0 | 0 | 8 | 5
2CAR-60 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-13 | Nisha | 2017-12-13 | 2017-12-15 | 3 |  | Mani | 2017-12-20 | 2017-12-20 | 2017-12-22 | 3 | 2017-12-22 | 22/11: HFC only load | [5 empty] | 4 | 0 | 0 | 0 | 0 | 8 | 4
4ALX-67 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-13 | Sangeetha | 2017-12-15 | 2017-12-18 | 2 | 13/12: SAM placed on hold. Missing NDD 15/12: NDD available | Sangeetha | 2017-12-19 | 2017-12-19 | 2017-12-20 | 2 | 2017-12-20 | [6 empty] | 2 | 2 | 0 | 0 | 0 | 6 | 2
3HDB-66 | RFS.115 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-13 | Rikku | 2017-12-13 | 2017-12-15 | 3 |  | Gaurav | 2017-12-19 | 2017-12-19 | 2017-12-22 | 4 | 2017-12-22 | [6 empty] | 3 | 0 | 0 | 0 | 0 | 8 | 5
3WIR-65 | RFS.137 | H-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-13 | Aravind | 2017-12-20 | 2017-12-22 | 3 |  | Sangeetha | 2018-01-17 | 2018-01-17 | 2018-01-18 | 2 | 2018-01-18 | 18/1: HFC validation run completed. No handover required. | [5 empty] | 16 | 5 | 0 | 0 | 0 | 24 | 3
5WES-63 | RFS.113 | H-M-H | BAU | Pre-AT | 1.1 | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-12-13 | Deepa M04 | 2017-12-13 | 2017-12-15 | 3 | Rejected: Critical Area Planning issues |  |  |  |  | 0 |  |  | 2017-12-21 |  |  |  |  | -30747 | 0 | 0 | -1 | 0 | -30745 | 3
2CHA-60 | RFS.114 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-14 | Swathy Mohan | 2017-12-14 | 2017-12-15 | 2 |  | Krishnan | 2017-12-20 | 2017-12-20 | 2017-12-22 | 3 | 2017-12-22 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 7 | 3
6WMB-60 | RFS.113 | M-A-H | BAU | Pre-AT | 2 | Completed - [GML] Handover to DSG | 2017-12-14 | Maria Joy | 2017-12-14 | 2017-12-15 | 2 |  | Mahalakshmi | 2017-12-20 | 2017-12-20 | 2017-12-22 | 3 | 2017-12-22 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 7 | 3
2CAS-65 | RFS.138 | M-M-H | BAU | Design | 2 | Rejected - [PC] Sent Back to Telstra (DESG) | 2017-12-14 | Maria Joy | 2017-12-20 | 2017-12-21 | 2 | Rejected : Critical Design Issues |  |  |  |  | 0 |  |  | 2017-12-21 |  |  |  |  | -30751 | 4 | 0 | -1 | 0 | -30746 | 2
4TGP-68 | RFS.134 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-15 | Deepa M04 | 2017-12-15 | 2017-12-18 | 2 |  | Maria Joy | 2017-12-20 | 2017-12-20 | 2017-12-22 | 3 | 2017-12-22 | 22/12: NDD uploaded. One node which requires split is missing in NDD. Mail send to Thanh and team. | [5 empty] | 3 | 0 | 0 | 0 | 0 | 6 | 3
4SLA-64 | RFS.119 | M-M-H | BAU | Design | 3 | Completed [PC] - Trigger Triage | 2017-12-18 | Gaurav | 2017-12-18 | 2017-12-20 | 3 | [5 empty] | 0 | [7 empty] | -30750 | 0 | 0 | -1 | 0 | -30748 | 3
5NRW-61 | RFS.146 | H-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-19 | Reshma Menon | 2017-12-21 | 2017-12-22 | 2 |  | Aravind | 2018-01-03 | 2018-01-03 | 2018-01-04 | 2 | 2018-01-04 | [6 empty] | 6 | 2 | 0 | 0 | 0 | 10 | 2
3RES-68 | RFS.135 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-19 | Mohith | 2017-12-20 | 2017-12-22 | 3 |  | mani | 2018-01-09 | 2018-01-09 | 2018-01-11 | 3 | 2018-01-11 | [6 empty] | 10 | 1 | 0 | 0 | 0 | 15 | 4
4ABO-65 | RFS.134 | M-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-19 | Sangeetha | 2017-12-19 | 2017-12-21 | 3 |  | Aravind | 2017-12-22 | 2017-12-22 | 2017-12-26 | 1 | 2017-12-26 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 4 | 2
4ALX-64 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | On Hold - [PC] GDSS/PNI Issue | 2017-12-19 | Rikku | 2017-12-19 | 2017-12-21 | 3 | 21/12: PNI error encountered during demotion. REQ000003342321 raised. |  |  |  |  | 0 |  |  |  | 2017-12-21 |  |  |  | -30751 | 0 | -30751 | -1 | 0 | -30749 | 30754
3RES-67 | RFS.142 | H-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-19 | Nisha | 2017-12-20 | 2018-01-16 | 17 | 21/12: SAM placed on hold. HFC Power boundary status is PLANNED . But the cables and equipment inside are INSERVICE and OPTUS ownership. 15/1: Resolution shared for the OPTUS entities present in the SAM. | Mohith | 2018-01-17 | 2018-01-17 | 2018-01-19 | 3 | 2018-01-19 | Design only HFC only SAM. PNI validation run and fixes completed. No handover required |  | 2018-12-21 | 2018-01-15 |  |  | 2 | 1 | -227 | 0 | 0 | 21 | 245
3KYG-60 | RFS.117 | H-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-19 | Linda | 2017-12-19 | 2017-12-21 | 3 |  | Anusa Moottoolikandy | 2017-12-22 | 2017-12-22 | 2017-12-27 | 2 | 2017-12-27 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
3KYG-62 | RFS.117 | H-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-19 | Nisha | 2017-12-19 | 2017-12-21 | 3 |  | Deepa M04 | 2017-12-22 | 2017-12-22 | 2017-12-27 | 2 | 2017-12-27 | [6 empty] | 2 | 0 | 0 | 0 | 0 | 5 | 3
3BAY-71 | RFS.135 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2017-12-19 | Mani | 2017-12-20 | 2017-12-22 | 3 | [5 empty] | 0 | [7 empty] | -30752 | 1 | 0 | -1 | 0 | -30749 | 3
2CAM-62 | RFS.142 | H-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-19 | Deepa M04 | 2017-12-20 | 2017-12-22 | 3 |  | maria joy | 2018-01-17 | 2018-01-17 | 2018-01-18 | 2 | 2018-01-18 | 18/1: HFC validation run completed. No handover required. | [5 empty] | 16 | 1 | 0 | 0 | 0 | 20 | 3
3BLB-65 | RFS.123 | H-M-H | BAU | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2017-12-20 | Sangeetha | 2017-12-21 | 2017-12-27 | 3 |  | Swathy Mohan | 2018-01-17 | 2018-01-17 | 2018-01-19 | 3 | 2018-01-19 | [6 empty] | 15 | 1 | 0 | 0 | 0 | 20 | 4
5HNL-61 | RFS.118 | H-M-H | BAU | Pre-AT | 0.2 | Completed - [GML] Handover to DSG | 2017-12-21 | Gaurav | 2017-12-27 | 2017-12-29 | 3 |  | Maria Joy | 2018-01-11 | 2018-01-11 | 2018-01-15 | 3 | 2018-01-15 | [6 empty] | 9 | 2 | 0 | 0 | 0 | 15 | 4
5HNL-65 | RFS.139 | H-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2017-12-21 | Alan Babu | 2017-12-22 | 2017-12-26 | 1 | [5 empty] | 0 | [7 empty] | -30752 | 1 | 0 | -1 | 0 | -30751 | 1
4BLH-62 | RFS.123 | M-B-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2017-12-23 | Reshma Menon | 2017-12-23 | 2017-12-23 | 0 |  | Krishnan | 2018-01-19 | 2018-01-19 | 2018-01-22 | 2 | 2018-01-22 | [6 empty] | 17 | -1 | 0 | 0 | 0 | 18 | 2
2HUR-65 | RFS.115 | H-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-20 | Sangeetha | 2018-01-02 | 2018-01-04 | 3 |  | Sangeetha | 2018-01-04 | 2018-01-04 | 2018-01-05 | 2 | 2018-01-05 | [6 empty] | 1 | 6 | 0 | 0 | 0 | 10 | 3
4TGP-65 | RFS.135 | H-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2018-01-02 | Mani | 2018-01-02 | 2018-01-04 | 3 |  | Deepa M04 | 2018-01-17 | 2018-01-17 | 2018-01-19 | 3 | 2018-01-19 | [6 empty] | 10 | 0 | 0 | 0 | 0 | 14 | 4
2CAM-61 | RFS.118 | H-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2018-01-03 | Gaurav | 2018-01-03 | 2018-01-04 | 2 |  | Midhun RaJ | 2018-01-17 | 2018-01-17 | 2018-01-19 | 3 | 2018-01-19 | [6 empty] | 10 | 0 | 0 | 0 | 0 | 13 | 3
2FRE-62 | RFS.119 | M-M-H | BAU | Pre-AT | 0.2 | Completed - [GML] Handover to DSG | 2018-01-02 | Anusa Moottoolikandy | 2018-01-02 | 2018-01-04 | 3 |  | Mahalakshmi | 2018-01-10 | 2018-01-10 | 2018-01-12 | 3 | 2018-01-12 | [6 empty] | 5 | 0 | 0 | 0 | 0 | 9 | 4
4SRW-60 | RFS.120 | M-M-H | BAU | Pre-AT | 0.1 | Rejected - [PC] Sent Back to Telstra (AP) | 2018-01-02 | Maria Joy | 2018-01-02 | 2018-01-03 | 2 | 11/1: Rejected : Critical issues raised by AP team |  |  |  |  | 0 |  |  | 2018-01-11 |  |  |  |  | -30757 | 0 | 0 | -1 | 0 | -30756 | 2
2RDL-60 | RFS.142 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2018-01-02 | Deepa M04 | 2018-01-02 | 2018-01-04 | 3 |  | Krishnan | 2018-01-11 | 2018-01-11 | 2018-01-15 | 3 | 2018-01-15 | [6 empty] | 6 | 0 | 0 | 0 | 0 | 10 | 4
4MOG-22 | RFS.134 | M-B-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2018-01-02 | Krishnan | 2018-01-02 | 2018-01-04 | 3 |  | anusa moottoolikandy | 2018-01-09 | 2018-01-12 | 2018-01-16 | 3 | 2018-01-16 | 9/1: Project details missing in project list file. Awaiting Nathan's response |  |  |  | 2018-01-09 | 2018-01-12 | 4 | 0 | 0 | 3 | 4 | 11 | 0
3BLB-68 | RFS.144 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2018-01-02 | Swathy Mohan | 2018-01-02 | 2018-01-04 | 3 |  | Mohith | 2018-01-12 | 2018-01-12 | 2018-01-16 | 3 | 2018-01-16 | [6 empty] | 7 | 0 | 0 | 0 | 0 | 11 | 4
2NEW-61 | RFS.143 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-02 | Mohith | 2018-01-02 | 2018-02-02 | 23 | 3/1: Critical boundary issue reported. Cannot perform MPS promotion until it is resolved. 15/1: SAM task resumed. Boundary issue not yet resolved. Placed on hold again. 2/2: Boundary issue resolved. Commenced the pending PC activities |  |  |  |  | 0 |  |  |  | 2018-01-03 | 2018-02-02 |  |  | -30778 | 0 | 22 | -1 | 0 | -30756 | 1
2MEN-61 | RFS.137 | M-M-H | BAU | Design | 1 | In Progress - [GML] PNI Load - Complete Run | 2018-01-03 | Rijo Sunny | 2018-01-03 | 2018-01-05 | 3 | 12/1: Critical issues raised by Design team | Maria Joy | 2018-02-05 | 2018-02-05 |  | -30779 |  | 5/2: Design issues resolved. Got confirmation to proceed with the same package. | 2018-01-12 |  |  |  |  | 21 | 0 | 0 | 0 | 0 | -30757 | -30778
5GLL-20 | RFS.137 | M-M-Q | BAU | Design | 4 | Completed - [GML] Handover to DSG | 2018-01-03 | Aravind | 2018-01-03 | 2018-01-05 | 3 |  | Aravind | 2018-01-12 | 2018-01-12 | 2018-02-02 | 15 | 2018-02-02 | 16/1: 18 Locations have incorrect PCD to DPU mapping. 31/1: Received new T18 package. |  |  |  | 2018-01-16 | 2018-01-31 | 6 | 0 | 0 | 0 | 11 | 22 | 5
4SLA-62 | RFS.99 | H-M-H | BAU | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2018-01-03 | Mahalakshmi | 2018-01-03 | 2018-01-05 | 3 |  | Alan Babu | 2018-01-11 | 2018-01-11 | 2018-01-19 | -30763 |  | 11/1: Portless scenario encountered. Awaiting confirmation from onshore on the resolution shared. 19/1: Received workaround for portless scenario. |  |  |  | 2018-01-11 | 2018-01-19 | 5 | 0 | 0 | 0 | 7 | -30757 | -30769
3DNC-66 | RFS.0 | H-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2018-01-03 | Alan Babu | 2018-01-03 | 2018-01-04 | 2 |  | Rijo Sunny | 2018-01-17 | 2018-01-17 | 2018-01-18 | 2 | 2018-01-18 | [6 empty] | 10 | 0 | 0 | 0 | 0 | 12 | 2
2QUA-64 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-05 | Deepa M04 | 2018-01-05 | 2018-01-09 | 3 | 17-Jan: OUTSTANDING FTTB DDDM MPS-063 - ETA: 25/01 29-Jan : Review already completed for version 1 and delivered on 9th Jan. Acualized the task a suggested by NA team. |  |  |  |  | 0 | [7 empty] | -30761 | 0 | 0 | -1 | 0 | -30759 | 3
4RBN-60 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2018-01-05 | Aravind | 2018-01-05 | 2018-01-08 | 2 | 6/2: Rejected due to FTTx design issues |  |  |  |  | 0 |  |  | 2018-02-06 |  |  |  |  | -30760 | 0 | 0 | -1 | 0 | -30759 | 2
2QUA-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2018-01-05 | mani | 2018-01-05 | 2018-01-09 | 3 | 11/1: Rejected : Critical issues raised by Design team |  |  |  |  | 0 |  |  | 2018-01-11 |  |  |  |  | -30761 | 0 | 0 | -1 | 0 | -30759 | 3
2WRO-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-05 | Anusa Moottoolikandy | 2018-01-05 | 2018-01-08 | 2 | [5 empty] | 0 | [7 empty] | -30760 | 0 | 0 | -1 | 0 | -30759 | 2
5GLL-62 | RFS.141 | M-M-H | BAU | Design | 2 | Completed - [GML] Handover to DSG | 2018-01-05 | rikku | 2018-01-05 | 2018-01-09 | 3 |  | Aravind | 2018-01-18 | 2018-01-18 | 2018-01-19 | 2 | 2018-01-19 | [6 empty] | 8 | 0 | 0 | 0 | 0 | 11 | 3
3DAD-64 | RFS.128 | M-M-H | BAU | Design | 4 | Completed - [GML] Handover to DSG | 2018-01-05 | Bhagyalekshmi | 2018-01-05 | 2018-01-09 | 3 |  | Gaurav | 2018-01-15 | 2018-01-15 | 2018-01-17 |  | 2018-01-17
2GBE-62 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-05 | Maria Joy | 2018-01-05 | 2018-01-10 | 4 | 8/1: MPS overlap reported. MPS promotion placed on hold. 10/1: Got confirmation to remove the FTTB MPS. PC completed
3RES-70 | RFS.118 | M-M-H | BAU | Design | 0.1 | Completed [PC] - Trigger Triage | 2018-01-05 | Alan Babu | 2018-01-05 | 2018-01-09 | 3
2PET-66 | RFS.117 | M-M-H | BAU | Design | 2 | Completed [PC] - Trigger Triage | 2018-01-05 | Gaurav | 2018-01-05 | 2018-01-09 | 3
2PEN-61 | RFS.120 | M-M-H | BAU | Design | 2 | In Progress - [GML] PNI Load - Complete Run | 2018-01-05 | Naveen Kumar Nagaraj | 2018-01-05 | 2018-01-08 | 2 |  | mohith | 2018-02-05 | 2018-02-05
2PET-62 | RFS.115 | H-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2017-12-20 | sangeetha | 2017-12-21 | 2017-12-21 |  | Expecting to relaunch this SAM in Perform Check (instead of GML generation) as many PC activities were not performed earlier as FDDD | Sangeetha | 2017-12-28 | 2018-01-08 | 2018-01-08 | 1 | 2018-01-08
3BLB-60 | RFS.117 | M-M-H | BAU | Design | 1 | Rejected - [GML] Sent Back to Telstra (DESG) | 2018-01-08 | Mahalakshmi | 2018-01-08 | 2018-01-09 | 2 |  | Gaurav | 2018-01-12 | 2018-01-12 |  |  |  | 12/1:GDSS Partial trace encountered for more than 900 SLs. Awaiting confirmation. 15/1: SAM rejected | 2018-01-15
2CRR-66 | RFS.118 | M-M-H | BAU | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2018-01-08 | Rijo Sunny | 2018-01-08 | 2018-01-22 | 11 | 10/1: Error encountered during demotion. PNI incident REQ000003382121 has been raised, 22/1: PNI incident resolved. Demotion completed. | Krishnan | 2018-01-23 | 2018-01-23 | 2018-01-25 |  | 2018-01-25 |  |  |  |  | 2018-01-10 | 2018-01-22
2HUR-64 | RFS.120 | M-M-H | BAU | Design | 2 | Completed - [GML] Handover to DSG | 2018-01-09 | Nisha | 2018-01-09 | 2018-01-10 | 2 |  | Gaurav | 2018-01-18 | 2018-01-18 | 2018-01-22 |  | 2018-01-22
4NDG-61 | RFS.143 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-10 | Deepa M04 | 2018-01-10 | 2018-01-12 | 3
5HNL-63 | RFS.119 | H-M-H | BAU | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2018-01-10 | Mohith | 2018-01-10 | 2018-01-12 | 3 |  | Alan Babu | 2018-01-15 | 2018-01-23 | 2018-01-24 |  | 2018-01-24 | 15/1: Python error encountered during MPS promotion. PNI incident raised. REQ000003399108. 23/1: MPS boundaries were created manually. |  |  |  | 2018-01-15 | 2018-01-23
3BAY-67 | RFS.135 | M-M-H | BAU | Design | 4 | Completed [PC] - Trigger Triage | 2018-01-11 | Rijo Sunny | 2018-01-12 | 2018-01-15 | 2
3TYH-61 | RFS.118 | M-M-H | BAU | Pre-AT | 0.2 | Completed - [GML] Handover to DSG | 2018-01-11 | Rikku | 2018-01-12 | 2018-01-16 | 3 |  | Alan Babu | 2018-01-17 | 2018-01-17 | 2018-01-19 | 3 | 2018-01-19
4ARU-61 | RFS.123 | M-M-H | BAU | Design | 2 | Completed - [GML] Handover to DSG | 2018-01-12 | Mani | 2018-01-12 | 2018-01-16 | 3 |  | Anusa Moottoolikandy | 2018-01-18 | 2018-01-18 | 2018-01-22 |  | 2018-01-22
3CTA-64 | RFS.150 | M-M-H | BAU | Design | 4 | Rejected - [PC] Sent Back to Telstra (AP) | 2018-01-12 | Alan Babu | 2018-01-12 | 2018-01-15 | 2 | 22/1: Critical issues raised by AP team. SAM rejected.
4TGP-64 | RFS.145 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2018-01-13 | Sangeetha | 2018-01-13 | 2018-01-16 | 2 |  | SanjanaKrishnan | 2018-01-18 | 2018-01-18 | 2018-01-23 |  | 2018-01-23 | 23/1: 57 duct failures were fixed. Delayed due to the manual fixes involved.
3RES-66 | RFS.146 | M-M-H | BAU | Design | 1 | Completed - [GML] Handover to DSG | 2018-01-12 | Krishnan | 2018-01-12 | 2018-01-16 | 3 |  | Sangeetha | 2018-01-18 | 2018-01-18 | 2018-01-22 |  | 2018-01-22
3RES-72 |  | H-M-H | BAU | Design | 1 | In Progress - [GML] PNI Load - Complete Run | 2018-01-12 | Swathy Mohan | 2018-01-12 | 2018-01-16 | 3 |  | Anusa Moottoolikandy | 2018-01-29 | 2018-01-29 | 2018-01-29 |  | 2018-01-29 | 29/1: HFC design only SAM. No handover required.
2ENG-62 | RFS.123 | H-M-H | BAU | Pre-AT | 0.1 | Completed - [GML] Handover to DSG | 2018-01-15 | Sangeetha | 2018-01-15 | 2018-01-17 | 3 |  | Maria Joy | 2018-01-19 | 2018-01-19 | 2018-01-23 |  | 2018-01-23 | 19/1: Issue with GDSS load. REQ000003419442 |  |  |  | 2018-01-19 | 2018-01-22
5NRW-63 | RFS.114 | M-A-H | BAU | Pre-AT | 2 | On Hold - [PC] GDSS/PNI Issue | 2018-01-15 | Swathy Mohan | 2018-01-15 |  | -30765 | PNI error encountered during demotion. REQ000003408183 | [8 empty] | 2018-01-17
2PET-66 | RFS.119 | M-A-H | BAU | Pre-AT | 3 | Completed - [GML] Handover to DSG | 2018-01-15 | Midhun RaJ | 2018-01-15 | 2018-01-17 | 3 | 19/1: SAM rejected due to FTTx design issues. | Midhun RaJ | 2018-01-30 | 2018-01-31 | 2018-02-02 |  | 2018-02-02 | 31/1: Issue resolved. Proceeding with the same package. S: Drive issue reported on 30/1. Hence couldn't take up the SAM. INC000007203935 | 2018-01-19
3HDB-65 | RFS.123 | H-A-H | BAU | Pre-AT | 1 | Completed - [GML] Handover to DSG | 2018-01-15 | Gaurav | 2018-01-15 | 2018-01-17 | 3 |  | Mahalakshmi | 2018-01-25 | 2018-01-31 | 2018-02-02 |  | 2018-02-02 | GML load task was placed on hold since the node split artefact was missing in NDD. 31/1: Got confirmation from onshore to proceed. |  |  |  | 2018-01-25 | 2018-01-31
3BAY-71 | RFS.135 | M-M-H | BAU | Design | 3 | Completed - [GML] Handover to DSG | 2018-01-15 | Deepa M04 | 2018-01-15 | 2018-01-17 | 3 |  | Mani | 2018-01-22 | 2018-01-22 | 2018-01-24 |  | 2018-01-24
2CAR-62 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-17 | Alan Babu | 2018-01-17 | 2018-01-19 | 3 | 17/1: SAM task was paused in Appian on 15/1. Resumed today.
3WIR-66 | RFS.150 | M-M-Q | BAU | Design | 1 | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2018-01-18 | Mohith | 2018-01-18 | 2018-01-19 | 2 | 17/1: SAM task was paused in Appian. Reluanched on 17/1. 6/2: Rejected due to FTTx design issues. | [7 empty] | 2018-02-06
2BAN-60 | RFS.119 | M-B-H | BAU | Pre-AT | 1.1 | Completed - [GML] Handover to DSG | 2018-01-17 | Aravind | 2018-01-17 | 2018-01-19 | 3 |  | Anusa Moottoolikandy | 2018-01-23 | 2018-01-23 | 2018-01-25 |  | 2018-01-25
4CHL-61 | RFS.130 | M-A-H | BAU | Pre-AT | 2 | Completed [PC] - Trigger Triage | 2018-01-18 | Deepa M04 | 2018-01-18 | 2018-01-22 | 3 | 22/1: SAM paused in Appian
2HUR-61 | RFS.133 | M-M-H | BAU | Design | 3 | Completed [PC] - Trigger Triage | 2018-01-18 | Nisha | 2018-01-18 | 2018-01-19 | 2
4BEE-64 | RFS.122 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-18 | Rijo Sunny | 2018-01-18 | 2018-01-22 | 3
2PYM-65 | RFS.118 | M-A-H | BAU | Pre-AT | 6 | Completed - [GML] Handover to DSG | 2018-01-17 | Krishnan | 2018-01-17 | 2018-01-17 | 1 |  | Joju | 2018-01-18 | 2018-01-18 | 2018-01-23 | 4 | 2018-01-23 | 23/1: The delay in release is due to delayed address matching files from LDM.
2PNN-63 | RFS.125 | H-M-H | BAU | Pre-AT | 0.1 | Completed [PC] - Trigger Triage | 2018-01-19 | Aravind | 2018-01-19 | 2018-01-22 | 2
4BEE-63 | RFS.146 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-19 | Mohith | 2018-01-19 | 2018-01-23 | 3
3TNB-64 | RFS.144 | H-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-19 | Krishnan | 2018-01-19 | 2018-01-22 | 2
3TNB-61 | RFS.144 | H-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-19 | Mahalakshmi | 2018-01-19 | 2018-01-23 | 3
2QUA-65 | RFS.121 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-22 | Rikku | 2018-01-22 | 2018-01-24 | 3 | 22/1: SAM paused in Appian
3RES-60 | RFS.146 | M-M-H | BAU | Design | 1 | On Hold - [PC] Issues - NBN Internal | 2018-01-22 |  |  |  | 0 | 23-Jan:Appian task paused, DFN needs to be updated by Telstra | [8 empty] | 2018-01-23
4CHL-66 | RFS.142 | M-M-H | BAU | Design | 1 | Rejected - [PC] Sent Back to Telstra (Design/NA) | 2018-01-22 | Deepa M04 | 2018-01-22 | 2018-01-24 | 3 | FTTx Design defects, sent back to Telstra | [7 empty] | 2018-02-01
3SSN-65 | RFS.137 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-22 | Aravind | 2018-01-22 | 2018-01-23 | 2
4ABO-66 | RFS.138 | H-A-H | BAU | Pre-AT | 2 | Completed [PC] - Trigger Triage | 2018-01-22 | Rijo Sunny | 2018-01-22 | 2018-01-24 | 3
4FHL-65 | RFS.142 | M-A-Q | HAC | Pre-AT | 3 | Completed [PC] - Trigger Triage | 2018-01-22 | Gaurav | 2018-01-22 | 2018-01-24 | 3
3RES-63 | RFS.150 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-23 | Swathy Mohan | 2018-01-23 | 2018-01-24 | 2
2EPP-61 | RFS.124 | H-M-H | BAU | Pre-AT | 0.1 | Completed [PC] - Trigger Triage | 2018-01-23 | Mahalakshmi | 2018-01-23 | 2018-01-25 | 3
3DNC-66 | RFS.0 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-24 | Nisha | 2018-01-24 | 2018-01-24 | 1 | 24/1: SAM relaunched as M-M-H in appian. No new package was added. Hence actualized the appian task
4SLA-64 | RFS.125 | M-M-H | BAU | Pre-AT | 0.1 | Completed [PC] - Trigger Triage | 2018-01-25 | Mani | 2018-01-25 | 2018-01-29 | 2
3BNT-62 | RFS.123 | H-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-25 | Deepa M04 | 2018-01-25 | 2018-01-29
3BLB-60 | RFS.146 | M-A-H | BAU | Pre-AT | 3 | Completed [PC] - Trigger Triage | 2018-01-25 | Aravind | 2018-01-25 | 2018-01-25
3NBA-70 | RFS.144 | M-M-H | BAU | Design | 3 | Completed [PC] - Trigger Triage | 2018-01-25 | Rijo Sunny | 2018-01-25 | 2018-01-29
2QUA-62 | RFS.118 | M-A-H | BAU | Pre-AT | 3 | In Progress - [GML] PNI Load - Complete Run | 2018-01-25 | Swathy Mohan | 2018-01-25 | 2018-01-29 |  |  | Rikku | 2018-02-06 | 2018-02-06
4LNH-60 | RFS.130 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-25 | Alan Babu | 2018-01-25 | 2018-01-30
3CTA-64 | RFS.150 | M-M-H | BAU | Design | 5 | Completed [PC] - Trigger Triage | 2018-01-25 | Gaurav | 2018-01-25 | 2018-01-29
3KGP-66 | RFS.140 | H-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-29 | Mohith | 2018-01-29 | 2018-01-31
2CHA-61 | RFS.121 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-01-29 | Rijo Sunny | 2018-01-29 | 2018-01-31
3BAY-67 | RFS.135 | M-M-H | BAU | Design | 5 | Completed [PC] - Trigger Triage | 2018-01-29 | Nisha | 2018-01-29 | 2018-01-31
4ABO-69 | RFS.143 | H-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-29 | Anusa Moottoolikandy | 2018-01-29 | 2018-01-31
3TNB-60 | RFS.143 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-01-30 | Gaurav | 2018-01-30 | 2018-01-31
3KYG-67 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | Completed [PC] - Trigger Triage | 2018-02-01 | Gaurav | 2018-02-01 | 2018-02-02
4CHL-63 | RFS.137 | M-M-H | BAU | Design | 1 | Completed [PC] - Trigger Triage | 2018-02-02 | Deepa M04 | 2018-02-02 | 2018-02-06
Formulas:
Cycle Time [PC] = NETWORKDAYS([Start Date [PC]],[End Date [PC]],Holiday!$C2:C80)
Cycle Time [GML] = NETWORKDAYS([PNI Load Start Date],[Handover to NSO/ DSG?],Holiday!$C2:C80)
Cycle Time [GML] = NETWORKDAYS([PNI Load Start Date],[Comments],Holiday!$C2:C80)
Internal Tracking = NETWORKDAYS([End Date [PC]],[Input Date [GML]],Holiday!$C2:C80)
PC Queue Time (Internal waiting time) = NETWORKDAYS([T18 Input Date],[Start Date [PC]],Holiday!$C2:C80)-1
PC Waiting Time (External waiting time) = NETWORKDAYS([On Hold Start Date [PC]],[Recommencement Date[PC]],Holiday!$C2:C80)
GML Queue Time (Internal waiting time) = NETWORKDAYS([Input Date [GML]],[PNI Load Start Date],Holiday!$C2:C80)-1
GML Waiting Time (External waiting time) = NETWORKDAYS([On Hold Start Date [GML]],[Recommencement Date [GML]],Holiday!$C2:C80)
DESG Overall Cycle Time = NETWORKDAYS([T18 Input Date],[Handover to NSO/ DSG?],Holiday!$C2:C80)
DESG Overall Cycle Time = NETWORKDAYS([T18 Input Date],[Comments],Holiday!$C2:C80)

## DSG - IAB Allocation
Updated by : | [5 empty] | Expected |  |  |  |  | HFC Data Load | [6 empty] | MTM Data Load
SAM Name | RFS Group | SAM Code | Program | Gate | Version | Start Date | MTM Data Load Required? | MTM Payload Type | Overall Status | DSG Input Date | Assigned To | HFC Status | Start Date | End Date | No of Pre-RFS Defects [HFC] | NSO/NDQ Handover Date [HFC] | Cycle Time | Assigned To (FTTN) | Assigned To (FTTB) | MTM Tech | MTM Status | Start Date | End Date | NSO/NDQ/Active Handover Date [FTTx] | Cycle Time | Comments/ Issues/ Blockers | On Hold Start Date [HFC] | Recommencement Date [HFC] | On Hold Start Date [FTTx] | Recommencement Date [FTTx] | DSG In Queue Time (Internal Waiting Time) [HFC] | DSG External Waiting Time [HFC] | DSG In Queue Time (Internal Waiting Time) [FTTx] | DSG External Waiting Time [FTTx] | EUP Count | Traceability Percentage | Service Class Match | Overall Cycle Time DESG Hover to NSO Handover | Overall Processing Time | S.No | Names | Dropdown Validation
2CRM-63 | Pilot Wave 1 | H-A-Q | HAC | Pre-AT |  | 2017-02-23 | No |  | Completed | 2017-02-24 | Arul Dayalan | Completed | 2017-02-24 | 2017-02-28 | 0 | 2017-03-02 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30552 | 0 | 4024 | 100 | 100 | 5 | 30557 | 1 | Sanjo Lopez | Sanjo Lopez
2MIL-61 | Pilot Wave 2 | H-A-Q | HAC | Pre-AT |  | 2017-03-09 | No |  | Completed | 2017-03-09 | Alan Babu/ Arun Krishna | Completed | 2017-03-09 | 2017-03-14 | 0 | 2017-03-16 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30561 | 0 | 3976 | 100 | 100 | 5 | 30566 | 2 | Arul Dayalan | Arul Dayalan
2CRM-62 | Pilot Wave 3 | H-A-Q | HAC | Pre-AT |  | 2017-03-10 | No |  | Completed | 2017-03-10 | Saravanan | Completed | 2017-03-10 | 2017-03-10 | 0 | 2017-03-15 | 3 |  |  |  | NA |  |  |  | 0 | 14-Mar-17: SC downgrade required for 25 LOC IDs due to GTD status updates. Sent an email to LMS to update the reason code and downgrade the SC. 15-Mar-17: SAM handed over with SC mismatch for 25 LOC IDs mentioned in the Handover document. LMS had performed the changes, but will take 24 hours to reflect. This will checked in NDQ checks. 20-Mar-17: LMS had performed some repurposing for LOC000167573922 which is creating a mismatch. Sent a query to LMS for resolving DF079695. 22-Mar-17: LMS provided updated address matching file and reassosiaction of PCDs are done for LOC000167573922 upon confirmation. 23-Mar-17: NSO had provided some comments on the Handover document. Accomodating the changes. 24-Mar-17: Submitted Final Handover document including comments. |  |  |  |  | 0 | 0 | -30562 | 0 | 1009 | 100 | 100 | 3 | 30565 | 3 | Pooja Jacob | Pooja Jacob
4SLA-73 | Pilot Wave 3 | H-A-Q | HAC | Pre-AT |  | 2017-03-10 | No |  | Completed | 2017-03-09 | Ajay Mohan | Completed | 2017-03-09 | 2017-03-10 | 0 | 2017-03-14 | 3 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30561 | 0 | 594 | 100 | 100 | 3 | 30564 | 4 | Devika Kala | Devika Kala
2ENG-63 | Pilot Wave 3 | H-A-Q | HAC | Pre-AT |  | 2017-03-27 | No |  | Completed | 2017-03-24 | Pooja | Completed | 2017-03-24 | 2017-03-25 | 0 | 2017-03-28 | 3 |  |  |  | NA |  |  |  | 0 | 28-Mar-17: No issues. SAM handed over to NSO |  |  |  |  | 0 | 0 | -30571 | 0 | 986 | 100 | 100 | 3 | 30574 | 5 | Reenu Treesa Peter | Reenu Treesa Peter
3OAK-62 | Pilot Wave 3 | H-A-Q | HAC | Pre-AT |  | 2017-03-27 | No |  | Completed | 2017-03-24 | Geethu (Arul) | Completed | 2017-03-24 | 2017-03-25 | 0 | 2017-03-29 | 4 |  |  |  | NA |  |  |  | 0 | 29-Mar-17: 9 LOC IDs required Service Class downgrade due to GTD status updates. Raised it to LMS. |  |  |  |  | 0 | 0 | -30571 | 0 | 1973 | 100 | 100 | 4 | 30575 | 6 | Aswathy Baby | Aswathy Baby
2MOS-64 | RFS.75 | H-A-Q | HAC | Pre-AT |  | 2017-04-04 | No |  | Completed | 2017-04-03 | NA | Completed | 2017-04-03 | 2017-04-06 | 0 | 2017-04-10 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30577 | 0 | 885 | 100 | 100 | 6 | 30583 | 7 | Geethu Mol AG | Geethu Mol AG
2ASH-64 | RFS.75 | H-A-Q | HAC | Pre-AT |  | 2017-04-07 | No |  | Completed | 2017-04-06 | NA | Completed | 2017-04-06 | 2017-04-12 | 0 | 2017-04-13 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30580 | 0 | 3994 | 100 | 100 | 6 | 30586 | 8 | Swathy Mohan | Swathy Mohan
2EAS-66 | RFS.76 | H-A-Q | HAC | Pre-AT |  | 2017-04-18 | No |  | Completed | 2017-04-13 | Varghis/ Shambavi/ Renjini | Completed | 2017-04-13 | 2017-04-20 | 0 | 2017-04-21 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30585 | 0 | 2942 | 100 | 100 | 5 | 30590 | 9 | Abhay Arora | Abhay Arora
2SHA-63 | RFS.76 | H-A-Q | HAC | Pre-AT |  | 2017-04-12 | No |  | Completed | 2017-04-12 | Devika | Completed | 2017-04-12 | 2017-04-20 | 0 | 2017-04-21 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30584 | 0 | 3438 | 100 | 100 | 6 | 30590 | 10 | Shambhavi Chandra | Shambhavi Chandra
4IAL-63 | RFS.76 | H-A-Q | HAC | Pre-AT |  | 2017-04-18 | No |  | Completed | 2017-04-13 | Kavya | Completed | 2017-04-13 | 2017-04-20 | 0 | 2017-04-26 | 7 |  |  |  | NA |  |  |  | 0 | Extra Copper network was found in PNI during last day of execution. Required a demotion of that area again. Hence some delay. 1 extra location which is part of OLT FAN and served by FTTP technology is captured in the trace report. Hence the percentage is showing as 99.96% |  |  |  |  | 0 | 0 | -30585 | 0 | 2581 | 99.96 | 100 | 7 | 30592 | 11 | Latheefa Ul | Latheefa Ul
3SCO-69 | RFS.77 | H-A-Q | HAC | Pre-AT |  | 2017-04-07 | No |  | Completed | 2017-04-06 | NA | Completed | 2017-04-06 | 2017-04-12 | 0 | 2017-04-18 | 7 |  |  |  | NA |  |  |  | 0 | 13-Apr-17: Team has completed the execution on 12/04. Automation tool was tried on on 13/04. But it had some runtime errors. Sent the details to dev team. Waiting for the tool execution to be completed. 18-Apr-17: Completed the tool execution and handed over to NSO. (after Easter holidays of 2 days) |  |  |  |  | 0 | 0 | -30580 | 0 | 1326 | 100 | 100 | 7 | 30587 | 12 | Naveen Kumar Nagaraj | Naveen Kumar Nagaraj
2BAN-66 | RFS.77 | H-A-Q | HAC | Pre-AT |  | 2017-04-11 | No |  | Completed | 2017-04-10 | Abhay Arora (Arul) | Completed | 2017-04-10 | 2017-04-17 | 0 | 2017-04-20 | 7 |  |  |  | NA |  |  |  | 0 | Delay due to tool execution setup. |  |  |  |  | 0 | 0 | -30582 | 0 | 1029 | 100 | 100 | 7 | 30589 | 13 | Renjini R | Renjini R
3BAY-69 | RFS.77 | H-A-Q | HAC | Pre-AT |  | 2017-04-20 | No |  | Completed | 2017-04-19 | NA | Completed | 2017-04-19 | 2017-04-27 | 0 | 2017-04-28 | 7 |  |  |  | NA |  |  |  | 0 | Delay due to tool execution setup. |  |  |  |  | 0 | 0 | -30587 | 0 | 1752 | 100 | 100 | 7 | 30594 | 14 | Saranya Geetha | Saranya Geetha
3OAK-70 | RFS.77 | H-A-Q | HAC | Pre-AT |  | 2017-04-20 | No |  | Completed | 2017-04-19 | NA | Completed | 2017-04-19 | 2017-05-02 | 0 | 2017-05-02 | 8 |  |  |  | NA |  |  |  | 0 | 27-Apr-17: There was a mismatch between SAM boundary in PNI and T18. 2 cables and equipment lie outside the SAM boundary and getting excluded in the AT list. 2-May-17: AP & NSO disagreeing over trimming the boundary. The discussion is on which is blocking the delivery of the SAM to NSO. SAM put-on-hold & then delivered. |  |  |  |  | 0 | 0 | -30587 | 0 | 2220 | 100 | 100 | 8 | 30595 | 15 | Selva Shobana | Selva Shobana
5EDW-64 | RFS.77 | H-A-Q | HAC | Pre-AT |  | 2017-04-19 | No |  | Completed | 2017-04-18 | Reenu | Completed | 2017-04-18 | 2017-04-26 | 0 | 2017-04-27 | 7 |  |  |  | NA |  |  |  | 0 | 25-Apr-17: LMS reason code update job was not posted. IT incident was raised and fixed after 2 days. SAM released after rechecking. |  |  |  |  | 0 | 0 | -30586 | 0 | 2628 | 100 | 100 | 7 | 30593 | 16 | Sruthi James | Sruthi James
5EZB-60 | RFS.78 | H-A-Q | HAC | Pre-AT |  | 2017-04-26 | No |  | Completed | 2017-04-25 | NA | Completed | 2017-04-25 | 2017-05-11 | 0 | 2017-05-11 | 11 |  |  |  | NA |  |  |  | 0 | BAU team deleted ouside boundary Assets. SAM kept on hold and resumed, hence higher cycle time. |  |  |  |  | -1 | 0 | -30590 | 0 | 3471 | 100 | 100 | 11 | 30602 | 17 | Alan Babu | Alan Babu
2CMO-61 | RFS.79 | H-A-Q | HAC | Pre-AT |  | 2017-04-26 | No |  | Completed | 2017-04-24 | NA | Completed | 2017-04-24 | 2017-05-01 | 0 | 2017-05-02 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30590 | 0 | 850 | 100 | 100 | 5 | 30595 | 18 | Sree V | Sree V
2MEN-60 | RFS.79 | H-A-Q | HAC | Pre-AT |  | 2017-05-01 | No |  | Completed | 2017-05-04 | NA | Completed | 2017-05-04 | 2017-05-10 | 0 | 2017-05-11 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30596 | 0 | 2847 | 100 | 100 | 6 | 30602 | 19 | Aravind V | Aravind V
2ROC-60 | RFS.79 | H-A-Q [P] | HAC | Pre-AT |  | 2017-05-03 | No |  | Completed | 2017-05-02 | NA | Completed | 2017-05-02 | 2017-05-08 | 0 | 2017-05-17 | 12 |  |  |  | NA |  |  |  | 0 | 17-May-17: Partial ONSA case. 15 SLs fall outside the SAM boundary and is part of the NAT. Waited for confirmation from NSO, AP & E2e Design team at various stages. Hence higher cycle time. |  |  |  |  | 0 | 0 | -30594 | 0 | 2853 | 100 | 100 | 12 | 30606 | 20 | Bastin Joseph | Bastin Joseph
3DNC-62 | RFS.79 | H-A-Q | HAC | Pre-AT |  | 2017-04-26 | No |  | Completed | 2017-04-24 | NA | Completed | 2017-04-24 | 2017-05-03 | 0 | 2017-05-08 | 9 |  |  |  | NA |  |  |  | 0 | 08-May-17: This SAM had T18 resubmission. There was missing Port_Frequency data in the T18 V1. V2 was received on 28-Apr-17. The PNI load and remediation is already completed. Manual workaround performed to regenerate and load the GML with updated Frequency values. Hence higher cycle time. |  |  |  |  | 0 | 0 | -30590 | 0 | 1498 | 100 | 100 | 9 | 30599 | 21 | Brinson Bovas | Brinson Bovas
3KGP-62 | RFS.79 | H-A-Q | HAC | Pre-AT |  | 2017-04-26 | No |  | Completed | 2017-04-24 | NA | Completed | 2017-04-24 | 2017-04-28 | 0 | 2017-05-02 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30590 | 0 | 1894 | 100 | 100 | 5 | 30595 | 22 | Divyamol James | Divyamol James
3NBA-68 | RFS.79 | H-A-Q | HAC | Pre-AT |  | 2017-05-09 | No |  | Completed | 2017-05-10 | NA | Completed | 2017-05-10 | 2017-05-16 | 0 | 2017-05-17 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30600 | 0 | 3315 | 100 | 100 | 6 | 30606 | 23 | Gouri Gopal | Gouri Gopal
3TYH-65 | RFS.79 | H-A-Q | HAC | Pre-AT |  | 2017-05-09 | No |  | Completed | 2017-05-09 | NA | Completed | 2017-05-09 | 2017-05-15 | 0 | 2017-05-16 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30599 | 0 | 3159 | 100 | 100 | 6 | 30605 | 24 | Jijin Isaac | Jijin Isaac
4CPH-73 | RFS.79 | H-A-Q | HAC | Pre-AT |  | 2017-05-01 | No |  | Completed | 2017-05-05 | NA | Completed | 2017-05-05 | 2017-05-11 | 0 | 2017-05-12 | 6 |  |  |  | NA |  |  |  | 0 | Traceability 99.96%. This is because of a location being an OLT-FAN and the PCD NTD000024820486 is served with FTTP Tech. |  |  |  |  | 0 | 0 | -30597 | 0 | 2564 | 99.96 | 100 | 6 | 30603 | 25 | Krutika Neelak | Krutika Neelak
4BLH-64 | RFS.80 | H-A-Q | HAC | Pre-AT |  | 2017-05-05 | No |  | Completed | 2017-05-09 | NA | Completed | 2017-05-09 | 2017-05-15 | 0 | 2017-05-16 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30599 | 0 | 914 | 100 | 100 | 6 | 30605 | 26 | Shankar Venkatesan | Shankar Venkatesan
3NCO-63 | RFS.80 | H-A-Q | HAC | Pre-AT |  | 2017-05-18 | No |  | Completed | 2017-05-17 | NA | Completed | 2017-05-17 | 2017-05-25 | 0 | 2017-05-26 | 8 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30605 | 0 | 2397 | 100 | 100 | 8 | 30613 | 27 | Ratish Radhakrishnan | Ratish Radhakrishnan
2ASH-61 | RFS.80 | H-A-Q | HAC | Pre-AT |  | 2017-05-01 | No |  | Completed | 2017-05-05 | NA | Completed | 2017-05-05 | 2017-05-11 | 0 | 2017-05-12 | 6 |  |  |  | NA |  |  |  | 0 | Traceability 99.94%. Actual HFC Trace percentage is 100%. The 1 PCD which is failure is belonging to a FAN site and FTTP technology. |  |  |  |  | 0 | 0 | -30597 | 0 | 1715 | 99.94 | 100 | 6 | 30603 | 28 | Nayana Anilkumar | Nayana Anilkumar
2PET-67 | RFS.80 | H-A-Q | HAC | Pre-AT |  | 2017-05-10 | No |  | Completed | 2017-05-09 | NA | Completed | 2017-05-09 | 2017-05-09 | 0 | 2017-05-19 | 9 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30599 | 0 | 3271 | 100 | 100 | 9 | 30608 | 29 | Reshma T V | Reshma T V
4CPH-62 | RFS.80 | H-A-Q | HAC | Pre-AT |  | 2017-05-16 | No |  | Completed | 2017-05-15 | NA | Completed | 2017-05-15 | 2017-05-17 | 0 | 2017-05-24 | 8 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30603 | 0 | 3320 | 100 | 100 | 8 | 30611 | 30 | Alphy Manuel | Alphy Manuel
5BRI-68 | RFS.80 | H-A-Q | HAC | Pre-AT |  | 2017-04-11 | No |  | Completed | 2017-04-11 | Aswathy Baby | Completed | 2017-04-11 | 2017-04-19 | 0 | 2017-04-21 | 7 |  |  |  | NA |  |  |  | 0 | 20-Apr-17: Pre-RFS defect was identified. Confirmed with NSO. NSO agreed to provide additional document in the handover report. Hence delay. |  |  |  |  | 0 | 0 | -30583 | 0 | 2102 | 100 | 100 | 7 | 30590 | 31 | Swathi JS | Swathi JS
5GLL-63 | RFS.80 | H-A-Q | HAC | Pre-AT |  | 2017-05-17 | No |  | Completed | 2017-05-17 | NA | Completed | 2017-05-17 | 2017-05-25 | 0 | 2017-05-26 | 8 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30605 | 0 | 3402 | 100 | 100 | 8 | 30613 | 32 | Midhun RaJ | Midhun RaJ
6MLO-65 | RFS.80 | H-A-Q | HAC | Pre-AT |  | 2017-05-05 | No |  | Completed | 2017-05-11 | NA | Completed | 2017-05-11 | 2017-05-16 | 0 | 2017-05-18 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30601 | 0 | 3533 | 100 | 100 | 6 | 30607 | 33 | Reshma Rajan | Reshma Rajan
2CAS-61 | RFS.81 | H-A-Q [P] | HAC | Pre-AT |  | 2017-05-18 | No |  | Completed | 2017-05-18 | Geethu | Completed | 2017-05-18 | 2017-05-30 | 0 | 2017-05-31 | 10 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30606 | 0 | 2336 | 100 | 100 | 10 | 30616 | 34 | Bhagyalekshmi | Bhagyalekshmi
6SUB-60 | RFS.81 | H-A-Q | HAC | Pre-AT |  | 2017-05-22 | No |  | Completed | 2017-05-22 | Abhay | Completed | 2017-05-22 | 2017-05-30 | 0 | 2017-05-31 | 8 |  |  |  | NA |  |  |  | 0 | TAP port remediation issues in this SAM. Workaround applied to upgrade the TAP ports |  |  |  |  | 0 | 0 | -30608 | 0 | 3040 | 100 | 100 | 8 | 30616 | 35 | Haritha | Haritha
5HNL-66 | RFS.81 | H-A-Q | HAC | Pre-AT |  | 2017-05-18 | No |  | Completed | 2017-05-26 | Hold - 60% | Completed | 2017-05-26 | 2017-06-06 | 0 | 2017-06-07 | 9 |  |  |  | NA |  |  |  | 0 | FTTB SAM. Mixed Technology (MAQ SAM) |  |  |  |  | 0 | 0 | -30612 | 0 | 4168 | 100 | 100 | 9 | 30621 | 36 | Arya PS | Arya PS
3CLA-67 | RFS.82 | H-A-Q | HAC | Pre-AT |  | 2017-05-09 | No |  | Completed | 2017-05-11 | NA | Completed | 2017-05-11 | 2017-05-12 | 0 | 2017-05-18 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30601 | 0 | 2413 | 100 | 100 | 6 | 30607 | 37 | Karishma | Karishma
2CMO-60 | RFS.82 | H-A-Q | HAC | Pre-AT |  | 2017-05-09 | No |  | Completed | 2017-05-11 | NA | Completed | 2017-05-11 | 2017-05-17 | 0 | 2017-05-18 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30601 | 0 | 3069 | 100 | 100 | 6 | 30607 | 38 | Karthika V J | Karthika V J
6CTO-61 | RFS.82 | H-A-Q | HAC | Pre-AT |  | 2017-05-17 | No |  | Completed | 2017-05-16 | NA | Completed | 2017-05-16 | 2017-05-22 | 0 | 2017-05-23 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30604 | 0 | 1369 | 100 | 100 | 6 | 30610 | 39 | Roshni Johns | Roshni Johns
6SUB-68 | RFS.82 | H-A-Q | HAC | Pre-AT |  | 2017-05-22 | No |  | Completed | 2017-05-23 | Abhay | Completed | 2017-05-23 | 2017-05-29 | 0 | 2017-05-30 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30609 | 0 | 1253 | 100 | 100 | 6 | 30615 | 40 | Siva Kumar | Siva Kumar
2ROS-64 | RFS.83 | H-A-Q | HAC | Pre-AT |  | 2017-03-27 | No |  | Completed | 2017-03-27 | NA | Completed | 2017-03-27 | 2017-03-30 | 0 | 2017-03-31 | 5 |  |  |  | NA |  |  |  | 0 | 31-Mar-17: This is Advance T18 SAM. Not notified NSO on completion. Handed over internally to NDQ. |  |  |  |  | 0 | 0 | -30572 | 0 | 1885 | 100 | 100 | 5 | 30577 | 41 | Dona Babu | Dona Babu
3RWO-69 | RFS.83 | H-A-Q | HAC | Pre-AT |  | 2017-04-04 | No |  | Completed | 2017-04-03 | NA | Completed | 2017-04-03 | 2017-04-06 | 0 | 2017-04-10 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30577 | 0 | 4026 | 100 | 100 | 6 | 30583 | 42 | Pankaj Velavan | Pankaj Velavan
3SOA-61 | RFS.83 | H-A-Q | HAC | Pre-AT |  | 2017-04-07 | No |  | Completed | 2017-04-06 | NA | Completed | 2017-04-06 | 2017-04-12 | 0 | 2017-04-18 | 7 |  |  |  | NA |  |  |  | 0 | 13-Apr-17: Team has completed the execution on 12/04. Automation tool was tried on on 13/04. But it had some runtime errors. Sent the details to dev team. Waiting for the tool execution to be completed. 18-Apr-17: Completed the tool execution and handed over to NSO. (after Easter holidays of 2 days) |  |  |  |  | 0 | 0 | -30580 | 0 | 1916 | 100 | 100 | 7 | 30587 | 43 | Shyama P | Shyama P
2SEV-60 | RFS.83 | H-A-Q | HAC | Pre-AT |  | 2017-05-19 | No |  | Completed | 2017-05-23 | Sanjo | Completed | 2017-05-23 | 2017-05-29 | 0 | 2017-05-30 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30609 | 0 | 3585 | 100 | 100 | 6 | 30615 | 44 | Sreelekha K | Sreelekha K
3MIT-61 | RFS.83 | H-A-Q | HAC | Pre-AT |  | 2017-05-25 | No |  | Completed | 2017-05-25 | Naveen | Completed | 2017-05-25 | 2017-05-30 | 0 | 2017-05-31 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30611 | 0 | 709 | 100 | 100 | 5 | 30616 | 45 | Aswathy T | Aswathy T
3SOA-64 | RFS.83 | H-A-Q | HAC | Pre-AT |  | 2017-05-24 | No |  | Completed | 2017-05-29 | Ranjini | Completed | 2017-05-29 | 2017-06-02 | 0 | 2017-06-05 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30613 | 0 | 2775 | 100 | 100 | 6 | 30619 | 46 | Nimi Mol | Nimi Mol
5GNG-63 | RFS.83 | H-A-Q | HAC | Pre-AT |  | 2017-03-27 | No |  | Completed | 2017-03-27 | NA | Completed | 2017-03-27 | 2017-03-30 | 0 | 2017-03-31 | 5 |  |  |  | NA |  |  |  | 0 | 31-Mar-17: This is Advance T18 SAM. Not notified NSO on completion. Handed over internally to NDQ |  |  |  |  | 0 | 0 | -30572 | 0 | 3754 | 100 | 100 | 5 | 30577 | 47 | Mary Ann | Mary Ann
6CTO-64 | RFS.83 | H-A-Q | HAC | Pre-AT |  | 2017-05-29 | No |  | Completed | 2017-05-30 | NA | Completed | 2017-05-30 | 2017-06-05 | 0 | 2017-06-06 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30614 | 0 | 2510 | 100 | 100 | 6 | 30620 | 48 | Amalu Manuel | Amalu Manuel
2NSY-64 | RFS.83 | H-A-Q [P] | HAC | Pre-AT |  | 2017-06-07 | No |  | Completed | 2017-06-07 | NA | Completed | 2017-06-07 | 2017-06-13 | 0 | 2017-06-14 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30620 | 0 | 3004 | 100 | 100 | 5 | 30625 | 49 | Sriram Rajendra Kumar | Sriram Rajendra Kumar
3BAY-64 | RFS.84 | H-A-Q | HAC | Pre-AT |  | 2017-05-18 | No |  | Completed | 2017-05-31 | Aswathy B | Completed | 2017-05-31 | 2017-06-06 | 0 | 2017-06-07 | 6 |  |  |  | NA |  |  |  | 0 | Kept on hold due to other FY17 priority SAMs in queue to be completed |  |  |  |  | 0 | 0 | -30615 | 0 | 2363 | 100 | 100 | 6 | 30621 | 50 | Reethu Sebastian | Reethu Sebastian
2PET-61 | RFS.84 | H-A-Q | HAC | Pre-AT |  | 2017-05-08 | No |  | Completed | 2017-05-25 | NA | Completed | 2017-05-25 | 2017-06-01 | 0 | 2017-06-01 | 6 |  |  |  | NA |  |  |  | 0 | Kept on hold due to other FY17 priority SAMs in queue to be completed |  |  |  |  | 0 | 0 | -30611 | 0 | 952 | 100 | 100 | 6 | 30617 | 51 | Girish Chandran | Girish Chandran
5GLL-66 | RFS.84 | H-A-Q | HAC | Pre-AT |  | 2017-05-11 | No |  | Completed | 2017-06-05 | NA | Completed | 2017-06-05 | 2017-06-13 | 0 | 2017-06-13 | 6 |  |  |  | NA |  |  |  | 0 | Due to prioritisation of other SAMs |  |  |  |  | 0 | 0 | -30618 | 0 | 1631 | 100 | 100 | 6 | 30624 | 52 | Selbee Mathew | Selbee Mathew
2BAM-62 | RFS.84 | M-M-H | BAU | Pre-AT |  |  | Yes | Pre-AT | Completed | 2017-05-23 | Haritha | Completed | 2017-05-23 | 2017-05-29 | 1 | 2017-05-29 | 5 | Haritha |  | FTTB | NA | 2017-05-23 |  |  | -30608 | [5 empty] | 0 | 0 | 0 | 0 | 531 |  |  | 5 | 5 | 53 | Bijeta Biswal | Bijeta Biswal
2CRM-66 | RFS.84 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-08 | Ratish | Completed | 2017-05-08 | 2017-05-11 |  | 2017-05-11 | 4 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30598 | 0 | 1621 |  |  | 4 | 30602 | 54 | Anpu Susan | Anpu Susan
2EAS-60 | RFS.84 | H-M-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-22 | Pankaj | Completed | 2017-05-22 | 2017-05-26 |  | 2017-05-26 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30608 | 0 | 2553 |  |  | 5 | 30613 | 55 | Nahas Shajahan | Nahas Shajahan
2BON-62 | RFS.85 | H-M-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-03-19 | Shanker-BAU | Completed | 2017-03-19 | 2017-03-24 |  | 2017-03-24 | 5 |  |  |  | NA |  |  |  | 0 | Moved out of Current RFS group |  |  |  |  | -1 | 0 | -30566 | 0 | 430 | 100 |  | 5 | 30572 | 56 | Sahishna Krishna | Sahishna Krishna
3KGP-67 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-05-12 | No |  | Completed | 2017-05-24 | NA | Completed | 2017-05-24 | 2017-05-30 | 0 | 2017-05-31 | 6 |  |  |  | NA |  |  |  | 0 | Handover document completed(Review pending) |  |  |  |  | 0 | 0 | -30610 | 0 | 4132 | 100 | 100 | 6 | 30616 | 57 | Nevin Tom | Nevin Tom
3DAD-61 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-05-22 | No |  | Completed | 2017-06-01 | NA | Completed | 2017-06-01 | 2017-06-07 | 0 | 2017-06-08 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30616 | 0 | 2555 | 100 | 100 | 6 | 30622 | 58 | Meera Sudhakumar | Meera Sudhakumar
3FNT-66 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-05-25 | No |  | Completed | 2017-06-05 | Swathy | Completed | 2017-06-05 | 2017-06-13 | 0 | 2017-06-13 | 6 |  |  |  | NA |  |  |  | 0 | IAB SAM (HMQ). |  |  |  |  | 0 | 0 | -30618 | 0 | 2139 | 100 | 100 | 6 | 30624 | 59 | Naika Arjun | Naika Arjun
3DAD-65 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-05-26 | No |  | Completed | 2017-06-07 | NA | Completed | 2017-06-07 | 2017-06-14 | 0 | 2017-06-15 | 6 |  |  |  | NA |  |  |  | 0 | Due to prioritisation of other SAMs |  |  |  |  | 0 | 0 | -30620 | 0 | 2567 | 100 | 100 | 6 | 30626 | 60 | Aleena Johny | Aleena Johny
3ELT-60 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-06-14 | No |  | Completed | 2017-06-19 | NA | Completed | 2017-06-19 | 2017-06-23 | 0 | 2017-06-26 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30627 | 0 | 3415 | 100 | 100 | 5 | 30632 | 61 | Athul V | Athul V
3TYH-68 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-06-15 | No |  | Completed | 2017-06-15 | NA | Completed | 2017-06-15 | 2017-06-20 | 0 | 2017-06-21 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30625 | 0 | 4009 | 100 | 100 | 5 | 30630 | 62 | Jiya | Jiya
3SOA-62 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-05-29 | No |  | Completed | 2017-05-30 | NA | Completed | 2017-05-30 | 2017-06-05 | 0 | 2017-06-06 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30614 | 0 | 1017 | 100 | 100 | 6 | 30620 | 63 | Varun | Varun
2BAL-61 | RFS.85 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-03-19 | Shanker-BAU | Completed | 2017-03-19 | 2017-03-24 |  | 2017-03-24 | 5 |  |  |  | NA |  |  |  | 0 | Not yet Processed/Executed |  |  |  |  | -1 | 0 | -30566 | 0 | 3422 | 100 |  | 5 | 30572 | 64 | Rahul Menon | Rahul Menon
6SUB-61 | RFS.85 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-08 | Arya | Completed | 2017-05-08 | 2017-05-11 |  | 2017-05-11 | 4 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30598 | 0 | 936 |  |  | 4 | 30602 | 65 | Aparna Nampoothiri | Aparna Nampoothiri
6SUB-63 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-14 | No |  | Completed | 2017-06-19 | NA | Completed | 2017-06-19 | 2017-06-23 | 0 | 2017-06-26 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30627 | 0 | 3474 | 100 | 100 | 5 | 30632 | 66 | Anju Philip | Anju Philip
3CTA-62 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-20 | No |  | Completed | 2017-06-26 | NA | Completed | 2017-06-26 | 2017-06-30 | 0 | 2017-07-03 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | -1 | 0 | -30631 | 0 | 3180 | 100 | 100 | 5 | 30637 |  |  | NA
3GLI-64 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-22 | No |  | Completed | 2017-06-26 | NA | Completed | 2017-06-26 | 2017-07-12 | 0 | 2017-07-13 | 13 |  |  |  | NA |  |  |  | 0 | 3GLI-64 :: SL Migrated from ELMS to PNI- Duplicated. 4 days waiting period. 10-Jul-17: OTN out leg is connected to PWR port. Data issue in T18. Sent details back to Ahmad and TLS for confirming the correct details. 3 days waiting period. Total 7 days waiting period due to unexpected issues. |  |  |  |  | -1 | 0 | -30631 | 0 |  |  |  | 13 | 30645
3HGT-74 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-29 | No |  | Completed | 2017-06-30 | NA | Completed | 2017-06-30 | 2017-07-04 | 0 | 2017-07-05 | 4 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30635 | 0 | 859 | 100 | 100 | 4 | 30639
3NCO-65 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-29 | No |  | Completed | 2017-06-30 | NA | Completed | 2017-06-30 | 2017-07-06 | 0 | 2017-07-07 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30635 | 0 | 3935 | 100 | 100 | 6 | 30641
3SOA-63 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-23 | No |  | Completed | 2017-06-28 | NA | Completed | 2017-06-28 | 2017-07-05 | 0 | 2017-07-06 | 7 |  |  |  | NA |  |  |  | 0 | ELMS to PNI sync issue 130 LOC IDs got inserted. |  |  |  |  | 0 | 0 | -30633 | 0 | 3224 | 100 | 100 | 7 | 30640
6GIR-66 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-20 | No |  | Completed | 2017-06-20 | NA | Completed | 2017-06-20 | 2017-06-23 | 0 | 2017-06-26 | 4 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30628 | 0 | 3136 | 100 | 100 | 4 | 30632
2CRM-65 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-15 | No |  | Completed | 2017-06-19 | NA | Completed | 2017-06-19 | 2017-06-28 | 0 | 2017-06-29 | 8 |  |  |  | NA |  |  |  | 0 | 26/6 - Declared holiday @ offshore Overlapping design with HVMDU found. 3 days turnaround time for confirmation, and deleting the HVMDU design from T18 & PNI 2PCDs wrongly deleted while removing the HVMDU design. 1 Pre-RFS defect raised and recreated the PCDs in SNet. |  |  |  |  | 0 | 0 | -30627 | 0 | 3409 | 100 | 100 | 8 | 30635
4SLA-63 | RFS.86 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-08 | Roshny | Completed | 2017-06-08 | 2017-06-12 |  | 2017-06-12 | 2 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30621 | 0 | 2750 |  |  | 2 | 30623
2ENG-65 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-05-31 | No |  | Completed | 2017-06-01 | NA | Completed | 2017-06-01 | 2017-06-07 | 0 | 2017-06-08 | 6 |  |  |  | NA |  |  |  | 0 | Due to prioritisation of other SAMs |  |  |  |  | 0 | 0 | -30616 | 0 | 175 | 100 | 100 | 6 | 30622
3KGP-60 | RFS.87 | H-A-Q [P] | HAC | Pre-AT |  | 2017-06-23 | No |  | Completed | 2017-06-23 | NA | Completed | 2017-06-23 | 2017-07-10 | 0 | 2017-07-10 | 11 |  |  |  | NA |  |  |  | 0 | 5th July- LMS reinstated 42 LOC IDs. Delay due to that. 7-Jul-17: ELMS to PNI sync 142 additional LOCIDs got created |  |  |  |  | 0 | 0 | -30631 | 0 | 3138 | 100 | 100 | 11 | 30642
3NBA-64 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-07-03 | No |  | Completed | 2017-07-03 | NA | Completed | 2017-07-03 | 2017-07-05 | 0 | 2017-07-06 | 4 |  |  |  | NA |  |  |  | 0 | ELMS to PNI Sync issue 157 SLs |  |  |  |  | 0 | 0 | -30636 | 0 | 2617 | 100 | 100 | 4 | 30640
3NCO-64 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-06-26 | No |  | Completed | 2017-06-28 | NA | Completed | 2017-06-28 | 2017-07-10 | 0 | 2017-07-11 | 10 |  |  |  | NA |  |  |  | 0 | 3NCO-64 :: SLs Migrated from ELMS to PNI Issue. |  |  |  |  | 0 | 0 | -30633 | 0 | 1605 | 100 | 100 | 10 | 30643
3RWO-65 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-06-21 | No |  | Completed | 2017-06-21 | NA | Completed | 2017-06-21 | 2017-06-28 | 0 | 2017-06-29 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30629 | 0 | 976 | 100 | 100 | 6 | 30635
4BLH-67 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-06-14 | No |  | Completed | 2017-06-14 | NA | Completed | 2017-06-14 | 2017-06-19 | 0 | 2017-06-20 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30624 | 0 | 1461 | 100 | 100 | 5 | 30629
4IAL-62 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-07-03 | No |  | Completed | 2017-07-03 | NA | Completed | 2017-07-03 | 2017-07-07 | 0 | 2017-07-10 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30636 | 0 | 3695 | 100 | 100 | 6 | 30642
5SAL-69 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-06-19 | No |  | Completed | 2017-06-23 | NA | Completed | 2017-06-23 | 2017-06-26 | 0 | 2017-06-27 | 2 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30631 | 0 | 339 | 100 | 100 | 2 | 30633
6GIR-61 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-06-14 | No |  | Completed | 2017-06-14 | NA | Completed | 2017-06-14 | 2017-06-21 | 0 | 2017-06-22 | 7 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30624 | 0 | 2321 | 100 | 100 | 7 | 30631
4BUR-66 | RFS.87 | M-M-H | BAU | Pre-AT |  |  | Yes | Pre-AT | Completed | 2017-06-06 | Aswathy | Completed | 2017-06-06 | 2017-06-22 |  | 2017-06-22 | 12 | Karishma |  | FTTN | NA | 2017-08-21 |  |  | -30669 | Copper |  |  |  |  | 0 | 0 | 51 | 0 |  |  |  | 12 | -39
3FNT-63 | RFS.87 | M-M-H | BAU | Pre-AT |  |  | Yes | Pre-AT | Completed | 2017-06-06 | Alphy | Completed | 2017-06-06 | 2017-06-12 |  | 2017-06-12 | 4 | Alphy |  | FTTN | Completed | 2017-06-06 | 2017-06-12 | 2017-06-12 | 4 | Pilot SAM |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 4 | 4
4MGA-61 | RFS.87 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-11 | Karthika | Completed | 2017-05-11 | 2017-05-18 |  | 2017-05-18 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30601 | 0 |  |  |  | 6 | 30607
4SLA-71 | RFS.87 | H-A-H | BAU | Pre-AT |  |  | No |  | On Hold | 2017-05-15 | Bhagyalakshmi | On Hold | 2017-05-15 |  |  |  | -30602 |  |  |  | NA |  |  |  | 0 | MPS Package missing |  |  |  |  | 0 | 0 | -30603 | 0 |  |  |  | -30602 | 1
3DAD-60 | RFS.88 | H-A-Q | HAC | Pre-AT |  | 2017-05-25 | No |  | Completed | 2017-05-31 | NA | Completed | 2017-05-31 | 2017-06-06 | 0 | 2017-06-07 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30615 | 0 | 1888 | 100 | 100 | 6 | 30621
2EPP-63 | RFS.88 | H-A-Q | HAC | Pre-AT |  | 2017-06-02 | No |  | Completed | 2017-06-06 | NA | Completed | 2017-06-06 | 2017-06-13 | 0 | 2017-06-14 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30619 | 0 | 1929 | 100 | 100 | 6 | 30625
2BAN-62 | RFS.88 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-05 | NA | Completed | 2017-05-05 | 2017-05-11 |  | 2017-05-11 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30597 | 0 |  |  |  | 5 | 30602
2EPP-60 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-06-13 | No |  | Completed | 2017-06-15 | NA | Completed | 2017-06-15 | 2017-06-22 | 0 | 2017-06-23 | 7 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30625 | 0 | 3935 | 100 | 100 | 7 | 30632
2BAN-64 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-06-13 | No |  | Completed | 2017-06-15 | NA | Completed | 2017-06-15 | 2017-06-21 | 0 | 2017-06-22 | 6 |  |  |  | NA |  |  |  | 0 | The sum of confirmed and unconfirmed location is 3131. Number of Full traced PCD is 3003.This mismatch is because all 87 confirmed addresses with no PCD in PNI which will be served under FTTB and 41 SLs with NTD will be served with FTTP. |  |  |  |  | 0 | 0 | -30625 | 0 | 3003 | 98.65 | 100 | 6 | 30631
2BAN-68 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-06-28 | No |  | Completed | 2017-06-28 | NA | Completed | 2017-06-28 | 2017-07-05 | 0 | 2017-07-06 | 7 |  |  |  | NA |  |  |  | 0 | ELMS to PNI sync issue 10 LOC IDs got inserted. |  |  |  |  | 0 | 0 | -30633 | 0 | 3933 | 100 | 100 | 7 | 30640
2CAS-62 | RFS.89 | H-A-Q [P] | HAC | Pre-AT |  | 2017-06-27 | No |  | Completed | 2017-06-27 | NA | Completed | 2017-06-27 | 2017-07-10 | 0 | 2017-07-11 | 11 |  |  |  | NA |  |  |  | 0 | Overlapping HVMDU design found. Wait time of 3 days for confirmation from the HVMDU team. |  |  |  |  | 0 | 0 | -30632 | 0 | 3978 | 100 | 100 | 11 | 30643
2ROS-60 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-07-05 | No |  | Completed | 2017-07-05 | NA | Completed | 2017-07-05 | 2017-07-11 | 0 | 2017-07-12 | 6 |  |  |  | NA |  |  |  | 0 | Overlapping HVMDU design found. |  |  |  |  | 0 | 0 | -30638 | 0 | 3796 | 100 | 100 | 6 | 30644
5HNL-62 | RFS.89 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-06 | Midhun | Completed | 2017-06-06 | 2017-06-13 |  | 2017-06-13 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30619 | 0 | 4290 | 100 |  | 5 | 30624
4SOP-62 | RFS.89 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-04 | Nimi | Completed | 2017-05-04 | 2017-05-12 |  | 2017-05-12 | 7 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30596 | 0 |  |  |  | 7 | 30603
3BOX-66 | RFS.90 | H-A-Q | HAC | Pre-AT |  | 2017-07-05 | No |  | Completed | 2017-07-05 | NA | Completed | 2017-07-05 | 2017-07-11 | 0 | 2017-07-12 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30638 | 0 | 4136 | 100 | 100 | 6 | 30644
2SEV-62 | RFS.90 | H-A-Q | HAC | Pre-AT |  | 2017-06-13 | No |  | Completed | 2017-06-14 | NA | Completed | 2017-06-14 | 2017-06-20 | 0 | 2017-06-21 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30624 | 0 | 2762 | 100 | 100 | 6 | 30630
2CAS-63 | RFS.90 | H-A-Q [P] | HAC | Pre-AT |  | 2017-06-30 | No |  | Completed | 2017-06-30 | NA | Completed | 2017-06-30 | 2017-07-06 | 0 | 2017-07-07 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30635 | 0 | 3778 | 100 | 100 | 6 | 30641
5BRI-71 | RFS.90 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-31 | siva | Completed | 2017-05-31 | 2017-06-06 |  | 2017-06-06 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30615 | 0 |  |  |  | 5 | 30620
5GPC-60 | RFS.90 | H-B-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-07-06 | Karishma | Completed | 2017-07-06 | 2017-07-12 | 0 | 2017-07-12 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30639 | 0 |  |  |  | 5 | 30644
4SOP-60 | RFS.90 | M-A-H | BAU | Pre-AT |  |  | Yes | Design | Completed | 2017-06-27 | Dona | Completed | 2017-06-27 | 2017-07-04 |  | 2017-07-04 | 6 | Dona |  | FTTB | Completed | 2017-06-27 | 2017-07-04 |  | -30631 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 6 | 6
4SOP-63 | RFS.90 | M-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-06 | Sreelekha | Completed | 2017-06-06 | 2017-06-12 |  | 2017-06-12 | 4 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30619 | 0 |  |  |  | 4 | 30623
4WRN-61 | RFS.90 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-29 | NA | Completed | 2017-05-30 | 2017-06-06 |  | 2017-06-06 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 1 | 0 | -30613 | 0 |  |  |  | 7 | 30619
4WRN-60 | RFS.90 | M-A-H | BAU | Pre-AT |  |  | yes | Design | Completed | 2017-05-30 | Dona | Completed | 2017-05-30 | 2017-06-05 |  | 2017-06-05 | 5 |  | Rahul Menon | FTTB | Completed | 2017-11-02 | 2017-11-07 | 2017-11-21 | 13 | This SAM was pending for review and not handed over due to non-actualization of SAM in Appian. 21-Nov-2017: Got mail from Salah for rework. Revised handover sent by Alphy |  |  |  |  | 0 | 0 | 104 | 0 |  |  |  | 5 | -99
6SUB-65 | RFS.90 | M-A-H | BAU | Pre-AT |  | 2017-07-07 | Yes | Design | Completed | 2017-06-26 | Swathi | Completed | 2017-06-26 | 2017-06-30 |  | 2017-06-30 | 4 | Swathi |  | FTTN | Completed | 2017-06-26 | 2017-06-30 | 2017-06-30 | 4 | [5 empty] | -1 | 0 | -1 | 0 | 554 | 100 |  | 4 | 6
6SUB-67 | RFS.90 | M-A-H | BAU | Pre-AT |  | 2017-07-06 | Yes | Pre-AT | Completed | 2017-06-15 | Swathi | Completed | 2017-06-15 | 2017-06-21 |  | 2017-06-21 | 5 | Midhun |  | FTTB | Completed | 2017-07-17 | 2017-07-20 |  | -30645 | [5 empty] | 0 | 0 | 21 | 0 |  |  |  | 5 | -16
3BGO-60 | RFS.91 | H-A-Q | HAC | Pre-AT |  | 2017-06-30 | No |  | Completed | 2017-07-07 | NA | Completed | 2017-07-07 | 2017-07-14 | 0 | 2017-07-17 | 7 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30640 | 0 | 3783 | 100 | 100 | 7 | 30647
3CAU-69 | RFS.91 | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-07-06 | NA | Completed | 2017-07-06 | 2017-07-12 | 0 | 2017-07-13 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30639 | 0 | 3457 | 100 | 100 | 6 | 30645
2CAS-60 | RFS.91 | H-A-Q [P] | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-30 | NA | Completed | 2017-06-30 | 2017-07-07 | 0 | 2017-07-10 | 7 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30635 | 0 | 1470 | 100 | 100 | 7 | 30642
2BAL-62 | RFS.91 | M-A-H | BAU | Pre-AT |  |  | Yes | Pre-AT | Completed | 2017-06-13 | Shyama | Completed | 2017-06-13 | 2017-06-20 |  | 2017-06-20 | 6 | Reshma |  | FTTB | Completed | 2017-06-19 | 2017-06-21 |  | -30626 | [5 empty] | 0 | 0 | 4 | 0 |  |  |  | 6 | 2
3NBA-69 | RFS.91 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-07-07 | Dona | Completed | 2017-07-07 | 2017-07-19 |  | 2017-07-19 | 9 |  |  |  | NA |  |  |  | 0 | SAM was delayed due to missing Tap Frequency table & OSP issues |  |  |  |  | 0 | 0 | -30640 | 0 |  |  |  | 9 | 30649
4BUR-20 | RFS.91 | M-M-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-05-25 | Shankar | Completed | 2017-05-25 | 2017-06-16 |  | 2017-06-16 | 16 |  |  |  | NA |  |  |  | 0 | Received updated SLD on 14th June |  |  |  |  | 0 | 0 | -30611 | 0 |  |  |  | 16 | 30627
2CRR-20 | RFS.93 | M-B-H | BAU | Pre-AT |  |  | No |  | On Hold | 2017-06-15 | Nyana/Divya | On Hold | 2017-06-15 |  |  |  | -30624 |  |  |  | NA |  |  |  | 0 | On Hold. FBR Raised for updated SLD |  |  |  |  | 0 | 0 | -30625 | 0 |  |  |  | -30624 | 1
3NCO-61 | RFS.91 | M-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-19 | NA | Completed | 2017-06-19 | 2017-06-28 |  | 2017-06-28 | 7 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30627 | 0 |  |  |  | 7 | 30634 | 67 | NA
2NEW-60 | RFS.92 | H-A-H | BAU | Pre-AT |  | 2017-07-12 | No |  | Completed | 2017-06-14 | Dona | Completed | 2017-06-15 | 2017-06-22 |  | 2017-06-22 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 1 | 0 | -30624 | 0 |  |  |  | 7 | 30630
3DNC-67 | RFS.93 | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-30 | NA | Completed | 2017-06-30 | 2017-07-06 | 0 | 2017-07-07 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30635 | 0 | 2363 | 100 | 100 | 6 | 30641
4BLH-60 | RFS.94 | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-07-12 | Geethu Mol AG | Completed | 2017-07-10 | 2017-07-14 | 0 | 2017-07-17 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | -4 | 0 | -30643 | 0 | 3564 | 100 | 100 | 4 | 30651
5GNG-61 | RFS.95 | M-A-H | BAU | Pre-AT |  |  | Yes | Pre-AT | Completed | 2017-08-24 | Alphy | Completed | 2017-08-25 | 2017-09-01 |  | 2017-09-01 | 6 | Alphy |  | FTTN | On Hold | 2017-07-07 |  |  | -30639 | On Hold as per Program Team |  |  |  |  | 1 | 0 | -35 | 0 |  |  |  | 7 | 41
2MOS-63 | RFS.97 | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-07-14 | Brinson | Completed | 2017-07-14 | 2017-07-21 | 0 | 2017-07-21 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30645 | 0 | 2743 | 99.96 |  | 6 | 30651
5FLN-61 | RFS.99 | H-M-J | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-15 | Sreelekha K | Completed | 2017-06-15 | 2017-06-22 |  | 2017-06-22 | 6 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30625 | 0 |  |  |  | 6 | 30631
3WER-62 | RFS.99 | H-M-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-07 | Karthika VJ | Completed | 2017-06-07 | 2017-06-22 |  | 2017-06-22 | 11 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30620 | 0 |  |  |  | 11 | 30631
3WER-61 | RFS.100 | M-M-H | BAU | Pre-AT |  |  | Yes | Pre-AT | Completed | 2017-06-13 | Siva Kumar Ponniah Pillai | Completed | 2017-06-13 | 2017-06-19 |  | 2017-06-19 | 5 | Gouri |  | FTTN | Completed | 2017-06-13 | 2017-06-19 |  | -30622 | The SAM was put on hold due to unavailability of Ref OSP. Sam was relased from on-hold on 30tth October |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 5 | 5
3NAW-66 | RFS.103 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-05 | Reshma Rajan | Completed | 2017-06-05 | 2017-06-14 |  | 2017-06-14 | 7 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30618 | 0 |  |  |  | 7 | 30625
2STL-62 | RFS.104 | H-B-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-08 | Bhagyalekshmi | Completed | 2017-06-08 | 2017-06-14 |  | 2017-06-14 | 4 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30621 | 0 |  |  |  | 4 | 30625
5FLN-60 | RFS.104 | H-B-J | BAU | Pre-AT |  | 2017-11-09 | No |  | On Hold | 2017-06-20 | Reshma Rajan | On Hold | 2017-06-20 |  |  |  | -30627 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30628 | 0 |  |  |  | -30627 | 1
2STL-65 | RFS.104 | M-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-23 | Watan Zaidi | Completed | 2017-06-23 | 2017-06-30 |  | 2017-06-30 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30631 | 0 |  |  |  | 5 | 30636
4AGV-61 | RFS.108 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-30 | Roshny John | Completed | 2017-06-30 | 2017-07-06 |  | 2017-07-06 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30635 | 0 |  |  |  | 5 | 30640
4AGV-63 | RFS.108 | H-A-H | BAU | Pre-AT |  |  | No |  | Completed | 2017-06-23 | Karthika VJ | Completed | 2017-06-26 | 2017-07-03 |  | 2017-07-03 | 5 |  |  |  | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30631 | 0 |  |  |  | 6 | 30637
4CHP-62 | RFS.97 | M-A-X | BAU | Design |  |  | Yes | Design | Completed | 2017-04-20 | NA | NA |  |  |  |  | 0 | Gouri Gopal Nair |  | FTTB | Completed | 2017-04-20 | 2017-04-28 |  | -30587 | [5 empty] | -30588 | 0 | 0 | 0 |  |  |  | -30587 | 1
2CRR-72 | RFS.95 | M-B-X | BAU | Design |  |  | Yes | Design | Completed | 2017-04-28 | NA | NA |  |  |  |  | 0 | Gouri Gopal Nair |  | FTTN/FTTB | Completed | 2017-04-28 | 2017-05-04 |  | -30592 | [5 empty] | -30593 | 0 | 0 | 0 |  |  |  | -30592 | 1
2CRR-60 | RFS.85 | M-M-X | BAU | Design |  |  | Yes | Design | Completed | 2017-05-02 | NA | NA |  |  |  |  | 0 | Divyamol James |  | FTTN | Completed | 2017-05-02 | 2017-05-05 |  | -30593 | [5 empty] | -30594 | 0 | 0 | 0 |  |  |  | -30593 | 1
2PNN-68 | RFS.104 | M-M-X | BAU | Design |  |  | Yes | Design | Completed |  | NA | NA |  |  |  |  | 0 | Shankar Venkatesan |  | FTTN | Completed | 2017-05-03 | 2017-05-09 |  | -30594 | [5 empty] | -1 | 0 | 30593 | 0 |  |  |  | 0 | -30592
4FHL-20 | RFS.104 | M-B-X | BAU | Design |  |  | Yes | Design | Completed | 2017-05-11 | NA | NA |  |  |  |  | 0 | Reshma T V |  | FTTN | Completed | 2017-05-11 | 2017-05-22 |  | -30600 | [5 empty] | -30601 | 0 | 0 | 0 |  |  |  | -30600 | 1
4SLA-70 | RFS.106 | M-B-X | BAU | Design |  |  | Yes | Design | On Hold | 2017-05-11 | NA | NA |  |  |  |  | 0 | Nayana Peruvelil Anilkumar |  | FTTN | On Hold | 2017-05-11 |  |  | -30600 | Started working on 4SLA-70 FDDD SAM on 11/05/2017.Need Updated SLD For further processing |  |  |  |  | -30601 | 0 | 0 | 0 |  |  |  | -30600 | 1
2FRE-64 | RFS.106 | M-B-X | BAU | Design |  |  | Yes | Design | Completed | 2017-05-16 | NA | NA |  |  |  |  | 0 | Divyamol James |  | FTTN | Completed | 2017-05-16 | 2017-05-22 |  | -30603 | [5 empty] | -30604 | 0 | 0 | 0 |  |  |  | -30603 | 1
2BAN-60 | RFS.106 | M-B-X | BAU | Design |  |  | Yes | Design | Completed | 2017-05-16 | NA | NA |  |  |  |  | 0 | Alphy Manuel |  | FTTN | Completed | 2017-05-16 | 2017-05-25 |  | -30603 | [5 empty] | -30604 | 0 | 0 | 0 |  |  |  | -30603 | 1
2FRE-61 | RFS.101 | M-M-X | BAU | Design |  |  | Yes | Design | Completed | 2017-05-29 | Nayana | Completed | 2017-10-18 | 2017-10-23 |  | 2017-10-23 | 3 | Nayana Peruvelil Anilkumar |  | FTTN/FTTB | Completed | 2018-08-02 | 2017-08-08 |  | -30899 | Rejected by DESG team since no structure ids for Fibre cables in T18 |  |  |  |  | 94 | 0 | 287 | 0 |  |  |  | 98 | -283
5GNG-60 | RFS.113 | M-M-X | BAU | Design |  |  | Yes | Design | On Hold - HFC Completed | 2017-05-22 | NA | NA |  |  |  |  | 0 | Bhagyalekshmi |  | FTTN | Completed | 2017-05-22 |  |  | -30607 |  |  |  | 2017-06-01 |  | -30608 | 0 | 0 | -30615 |  |  |  | -30607 | 30616
2BON-61 | RFS.101 | M-M-X | BAU | Design |  |  | Yes | Design | On Hold - Data Issues | 2017-05-18 |  | NA |  |  |  |  | 0 | Arya PS | Nayana Anilkumar | FTTN/FTTB | On Hold - Data Issues | 2017-08-29 |  |  | -30675 | SAM is on hold since FTTB is already created as part of HVMDU activity. Came to DSG queue on 20-Sep, but again went on-hold due to documentation issues. |  |  |  |  | -30606 | 0 | 70 | 0 |  |  |  | -30605 | -69
4MGA-63 | RFS.0 | M-B-X | BAU | Design |  |  | Yes | Design | On Hold | 2017-05-30 | NA | NA |  |  |  |  | 0 | Bastin Joseph |  | FTTB | On Hold | 2017-05-30 |  |  | -30613 | MPS Package files not available. Issue raised in 9AM triage meeting |  |  |  |  | -30614 | 0 | 0 | 0 |  |  |  | -30613 | 1
3TNI-62 | RFS.116 | M-M-H | BAU | Design |  |  | Yes | Design | Completed | 2017-05-30 | NA | NA |  |  |  |  | 0 | Reshma T V |  | FTTN | Completed | 2017-05-30 | 2017-06-01 |  | -30613 | [5 empty] | -30614 | 0 | 0 | 0 |  |  |  | -30613 | 1
2MIL-60 | RFS.103 | M-M-X | BAU | Design |  |  | Yes | Design | Completed | 2017-09-29 | Karishma | Completed | 2017-10-04 | 2017-10-10 |  | 2017-10-10 | 5 | Reshma Rajan |  | FTTN | Completed | 2017-05-26 | 2017-06-01 | 2017-06-01 | 5 | [5 empty] | 1 | 0 | -86 | 0 |  |  |  | 6 | 91
4MRA-64 | RFS.95 | M-M-X | BAU | Design |  |  | Yes | Design | Completed | 2017-05-26 | NA | NA |  |  |  |  | 0 | Arya PS |  | FTTB | Completed | 2017-05-26 | 2017-05-31 |  | -30611 | [5 empty] | -30612 | 0 | 0 | 0 |  |  |  | -30611 | 1
4BUR-67 | RFS.112 | M-M-X | BAU | Design |  |  | Yes | Design | Completed | 2017-08-28 | NA | NA |  |  |  |  | 0 | Haritha |  | FTTN/FTTB | Completed | 2017-08-29 | 2017-09-01 |  | -30675 | Mismatch in BOMBOQ |  |  |  |  | -30675 | 0 | 1 | 0 |  |  |  | -30674 | 0
4SUR-61 | RFS.134 | M-B-X | BAU | Design |  |  | Yes | Design | Completed | 2017-06-16 | NA | NA |  |  |  |  | 0 | Nimi Mol P. F |  | FTTB | Completed | 2017-06-16 | 2017-06-23 |  | -30625 | [5 empty] | -30626 | 0 | 0 | 0 |  |  |  | -30625 | 1
2CRR-65 | RFS.102 | M-M-X | BAU | Design |  |  | Yes | Design | Completed | 2017-06-21 | NA | NA |  |  |  |  | 0 | Bhagyalekshmi |  | FTTN | Completed | 2017-06-21 | 2017-06-27 |  | -30628 | Active NDD |  |  |  |  | -30629 | 0 | 0 | 0 |  |  |  | -30628 | 1
5EDW-66 | RFS.113 | M-M-X | BAU | Design |  |  | Yes | Design | Completed | 2017-06-22 | NA | NA |  |  |  |  | 0 | Haritha |  | FTTB | Completed | 2017-06-22 | 2017-06-29 |  | -30629 | Active NDD |  |  |  |  | -30630 | 0 | 0 | 0 |  |  |  | -30629 | 1
5EDW-67 | RFS.81 | M-A-X | BAU | Design |  |  | Yes | Design | Completed | 2017-06-23 | NA | NA |  |  |  |  | 0 | Nayana Peruvelil Anilkumar |  | FTTN | Completed | 2017-06-23 | 2017-06-28 |  | -30630 | [5 empty] | -30631 | 0 | 0 | 0 |  |  |  | -30630 | 1
5EDW-62 | RFS.78 | M-A-X | BAU | Design |  |  | Yes | Design | Completed | 2017-06-24 | NA | NA |  |  |  |  | 0 | Siva Kumar Ponniah Pillai |  | FTTN | Completed | 2017-06-24 | 2017-06-29 |  | -30630 | [5 empty] | -30631 | 0 | -1 | 0 |  |  |  | -30630 | 2
4MGA-68 | RFS.114 | M-M-X | BAU | Design |  | 2017-06-20 | Yes | Design | Completed | 2017-06-27 | NA | NA |  |  |  |  | 0 | Alphy Manuel |  | FTTN | Completed | 2017-06-27 | 2017-07-03 |  | -30631 | Active NDD |  |  |  |  | -30632 | 0 | 0 | 0 |  |  |  | -30631 | 1
3KGP-61 | RFS.80 | M-A-X | BAU | Design |  |  | Yes | Design | Completed | 2017-06-30 | NA | NA |  |  |  |  | 0 | Reshma T V |  | FTTB | Completed | 2017-06-30 | 2017-07-05 |  | -30634 | HFC part is already completed .Task not assigned in Appian. |  |  |  |  | -30635 | 0 | 0 | 0 |  |  |  | -30634 | 1
2MIL-63 | RFS.100 | M-M-X | BAU | Design |  |  | Yes | Design | Completed | 2017-06-29 | NA | NA |  |  |  |  | 0 | Bhagyalekshmi |  | FTTN | Completed | 2017-06-29 | 2017-07-07 |  | -30633 | Active NDD |  |  |  |  | -30634 | 0 | 0 | 0 |  |  |  | -30633 | 1
4OXE-61 | RFS.108 | M-M-H | BAU | Design |  | 2017-07-10 | Yes | Design | Completed | 2017-07-14 | NA | NA |  |  |  |  | 0 | Alphy Manuel |  | FTTN | Completed | 2017-07-17 | 2017-07-24 |  | -30645 | [5 empty] | -30645 | 0 | 1 | 0 | 0 | 0 |  | -30644 | 0
4SOP-61 | RFS.94 | H-A-H | BAU | Pre-AT |  | 2017-07-11 | Yes | Design | Completed | 2017-07-25 | Siva | Completed | 2017-07-27 | 2017-08-02 |  | 2017-08-02 | 5 | Karishma |  | FTTB | Completed | 2018-07-21 | 2017-07-28 |  | -30890 | [5 empty] | 2 | 0 | 239 | 0 | 2685 | 100 |  | 7 | -234
2CRM-61 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-07-12 | No |  | Completed | 2017-07-11 | Reshma | Completed | 2017-07-11 | 2017-07-17 |  | 2017-07-17 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30642 | 0 |  | 0 |  | 5 | 30647
4CHD-21 | RFS.122 | M-M-H | BAU | Design |  | 2017-07-11 | Yes | Design | Completed | 2017-08-24 | NA | NA |  |  |  |  | 0 |  |  | FTTN / FTTB | Completed | 2017-08-25 | 2017-08-31 |  | -30673 | [5 empty] | -30673 | 0 | 1 | 0 | 0 | 0 |  | -30672 | 0
2SEV-61 | RFS.115 | M-M-H | BAU | Design |  | 2017-07-11 | Yes | Design | On Hold | 2017-07-14 | N/A | Not Applicable | N/A | N/A |  |  | #VALUE! |  |  | FTTB | On Hold |  |  |  | 0 | [5 empty] | #VALUE! | 0 | -30645 | 0 | 0 | 0 |  | -30644 | #VALUE!
2CMO-63 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-07-14 | No |  | Completed | 2017-07-18 | Arya | Completed | 2017-07-18 | 2017-07-28 |  | 2017-07-28 | 9 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30647 | 0 |  | 0 |  | 9 | 30656
4CHD-62 | RFS.97 | M-A-H | BAU | Pre-AT |  | 2017-07-14 | Yes | Design | Completed | 2017-08-11 | Brinson | Completed | 2017-08-11 | 2017-08-18 |  | 2017-08-18 | 5 |  | Karishma | FTTB | Completed | 2017-10-27 | 2017-10-30 | 2017-10-30 | 2 | Design only FTTB component was paused until 26-Oct-17 |  |  |  |  | 0 | 0 | 49 | 0 | 0 | 0 |  | 5 | -44
4MGA-70 | RFS.114 | M-M-H | BAU | Design |  | 2017-07-13 | Yes | Design | On Hold | 2017-07-20 | NA | NA |  |  |  |  | 0 | Bijeta |  | FTTB | On Hold |  |  |  | 0 | [5 empty] | -30649 | 0 | -30649 | 0 | 0 | 0 |  | -30648 | 30650
3MLN-63 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-07-17 | No |  | Completed | 2017-07-19 | Sruthi | Completed | 2017-07-19 | 2017-07-26 |  | 2017-07-26 | 6 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30648 | 0 | 0 | 0 |  | 6 | 30654
2MOS-62 | RFS.95 | M-A-H | BAU | Pre-AT |  | 2017-07-18 | Yes | Design | Completed | 2017-08-07 | Haritha | Completed | 2017-08-08 | 2017-08-11 |  | 2017-08-11 | 4 |  | Roshni Johns | FTTB | Completed | 2018-01-08 | 2018-01-16 | 2018-01-16 | 7 | 11-Jan:Awaiting for updated site design document with correct address. 16-Jan:Got confirmation that updated site design document will be avaliable later only can procced with release. |  |  | 2018-01-11 | 2018-01-16 | 1 | 0 | 100 | 4 | 0 | 0 |  | 5 | -100
2EAS-65 | RFS.89 | M-M-H | BAU | Pre-AT |  | 2017-07-20 | Yes | Pre-AT | Completed | 2017-07-24 | Divyamol James | Completed | 2017-07-25 | 2017-07-31 |  | 2017-07-31 | 5 | Haritha |  | FTTN/FTTB | Completed | 2017-07-25 | 2017-07-31 |  | -30651 | [5 empty] | 1 | 0 | 1 | 0 | 766 | 100 |  | 6 | 4
3SPL-62 | RFS.107 | M-M-H | BAU | Design |  | 2017-07-20 | Yes | Design | Completed | 2017-07-26 | NA | NA |  |  |  |  | 0 | Midhun |  | FTTB | Completed | 2017-07-27 | 2017-08-02 | 2017-08-02 | 5 | [5 empty] | -30653 | 0 | 1 | 0 | 0 | 0 |  | -30652 | 0
2BAL-65 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-07-21 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2ENG-62 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2018-01-26 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2EPP-61 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-07-24 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2ROS-65 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-07-24 | No |  | Completed | 2017-07-25 | Geethu | Completed | 2017-07-27 | 2017-08-02 |  | 2017-08-02 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 2 | 0 | -30652 | 0 | 0 | 0 |  | 7 | 30657
4OXE-63 | RFS.0 | H-A-Q | HAC | Pre-AT |  | 2017-07-24 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4CPH-69 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-07-26 | No |  | Completed | 2017-07-27 | Latheefa | Completed | 2017-07-31 | 2017-08-04 |  | 2017-08-04 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 2 | 0 | -30654 | 0 | 0 | 0 |  | 7 | 30659
2ING-64 | RFS.112 | M-M-H | BAU | Design |  | 2017-07-25 | Yes | Design | Completed | 2017-08-04 | NA | NA |  |  |  |  | 0 | Karishma |  | FTTN | Completed | 2017-08-05 | 2017-08-08 |  | -30659 | [5 empty] | -30660 | 0 | 0 | 0 | 0 | 0 |  | -30659 | 1
3BLB-67 | RFS.98 | M-A-H | BAU | Pre-AT |  | 2017-07-26 | Yes | Design | Completed | 2017-08-08 | Swathi | Completed | 2017-08-08 | 2017-08-11 |  | 2017-08-11 | 4 | Brinson |  | FTTB | Completed | 2017-08-08 | 2017-08-14 |  | -30661 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 4
2PET-60 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-07-27 | No |  | Completed | 2017-08-23 | Arya | Completed | 2017-08-24 | 2017-08-31 |  | 2017-08-31 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30672 | 0 |  |  |  | 7 | 30678
4CHD-01 | RFS.117 | M-M-H | BAU | Design |  | 2017-07-26 | Yes | Design | Not Started |  | NA | NA |  |  |  |  | 0 |  |  | FTTN / FTTB | Not Started |  |  |  | 0 | [5 empty] | -1 | 0 | -1 | 0 | 0 | 0 |  | 0 | 2
2BAM-64 | RFS.93 | M-M-H | BAU | Pre-AT |  | 2017-07-27 | Yes | Pre-AT | Completed | 2017-07-27 | Latheefa | Completed | 2017-07-28 | 2017-08-03 |  | 2017-08-03 | 5 | Kruthika |  | FTTN | Completed | 2017-07-28 | 2017-08-03 |  | -30654 | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0 |  | 6 | 4
4MGA-66 | RFS.114 | M-A-Q | HAC | Pre-AT |  | 2017-07-28 | Yes | Design | Completed | 2017-10-02 | Sanjo | Completed | 2017-10-03 | 2017-10-09 |  | 2017-10-09 | 5 | Arya PS |  | FTTB | Completed | 2017-09-29 | 2017-10-05 | 2017-10-05 | 3 | [5 empty] | 0 | 0 | -1 | 0 |  |  |  | 5 | 6
2LIV-68 | RFS.93 | M-M-H | BAU | Pre-AT |  | 2017-07-28 | Yes | Pre-AT | Completed | 2017-07-27 | Bijeta | Completed | 2017-07-28 | 2017-08-03 |  | 2017-08-03 | 5 | Bijeta |  | FTTN | Completed | 2017-07-28 | 2017-08-03 |  | -30654 | [5 empty] | 1 | 0 | 1 | 0 | 913 | 100 |  | 6 | 4
4CHD-64 | RFS.97 | M-A-H | BAU | Pre-AT |  | 2017-07-28 | Yes | Design | Completed | 2017-08-30 | Gouri | Completed | 2017-08-31 | 2017-09-06 |  | 2017-09-06 | 3 | Brinson Bovas |  | FTTB | Completed | 2017-09-15 | 2017-09-21 |  | -30686 | [5 empty] | 1 | 0 | 10 | 0 | 0 | 0 |  | 4 | -7
4BUR-68 | RFS.91 | H-A-Q | HAC | Pre-AT |  | 2017-07-28 | No |  | Completed | 2017-07-26 | Roshny | Completed | 2017-07-27 | 2017-08-02 |  | 2017-08-02 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 1 | 0 | -30653 | 0 | 0 | 0 |  | 6 | 30658
3GLI-61 | RFS.91 | H-A-Q | HAC | Pre-AT |  | 2017-07-28 | No |  | Completed | 2017-07-31 | Sruthi | Completed | 2017-07-31 | 2017-08-04 |  | 2017-08-04 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30656 | 0 | 0 | 0 |  | 5 | 30661
3CAU-62 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-07-31 | No |  | Completed | 2017-08-25 | Brinson Bovas | Completed | 2017-08-28 | 2017-09-01 |  | 2017-09-01 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30674 | 0 |  |  |  | 6 | 30679
4CHD-65 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-08-01 | No |  | Completed | 2017-07-31 | Aswathy | Completed | 2017-07-31 | 2017-08-04 |  | 2017-08-04 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30656 | 0 | 0 | 0 |  | 5 | 30661
3MIT-64 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-08-01 | No |  | Completed | 2017-08-01 | Brinson | Completed | 2017-08-01 | 2017-08-07 |  | 2017-08-07 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30657 | 0 | 0 | 0 |  | 5 | 30662
3KGP-65 | RFS.93 | M-A-H | BAU | Pre-AT |  | 2017-08-01 | No |  | Completed | 2017-07-31 | Alphy | Completed | 2017-08-01 | 2017-08-07 |  | 2017-08-07 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 1 | 0 | -30656 | 0 | 0 | 0 |  | 6 | 30661
3BGO-62 | RFS.93 | M-A-H | BAU | Pre-AT |  | 2017-08-02 | Yes | Design | Completed | 2017-08-02 | Siva | Completed | 2017-08-03 | 2017-08-10 |  | 2017-08-10 | 6 |  |  | FTTB | On Hold |  |  |  | 0 | [5 empty] | 1 | 0 | -30658 | 0 | 0 | 0 |  | 7 | 30664
3SPL-67 | RFS.93 | M-M-H | BAU | Pre-AT |  | 2017-08-02 | Yes | Design | Completed | 2017-07-21 | Dona | Completed | 2017-08-03 | 2017-08-08 |  | 2017-08-08 | 4 | Midhun |  | FTTB | Completed | 2017-07-21 | 2017-07-28 |  | -30649 | [5 empty] | 9 | 0 | 0 | 0 | 2475 | 100 |  | 13 | 4
2ASH-68 | RFS.0 | H-A-Q | HAC | Pre-AT |  | 2017-08-02 | No |  | Completed | 2017-08-08 | Dona | Completed | 2017-08-08 | 2017-08-16 |  | 2017-08-16 | 6 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30662 | 0 | 0 | 0 |  | 6 | 30668
2ROS-62 | RFS.94 | H-A-Q | HAC | Pre-AT |  | 2017-08-02 | No |  | Completed | 2017-08-01 | Brinson | Completed | 2017-08-01 | 2017-08-07 |  | 2017-08-07 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30657 | 0 | 0 | 0 |  | 5 | 30662
2SHA-62 | RFS.94 | H-A-Q | HAC | Pre-AT |  | 2017-08-02 | No |  | Completed | 2017-08-04 | Sruthi | Completed | 2017-08-05 | 2017-08-10 |  | 2017-08-10 | 4 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30660 | 0 | 0 | 0 |  | 5 | 30665
2EDG-65 | RFS.65 | M-M-H | BAU | Pre-AT |  | 2017-08-04 | Yes | Design | Completed | 2017-08-14 | Midhun | Completed | 2017-08-14 | 2017-08-21 |  | 2017-08-21 | 5 | Swathi JS |  | FTTB | Completed | 2017-09-15 | 2017-09-19 |  | -30686 | [5 empty] | 0 | 0 | 21 | 0 | 0 | 0 |  | 5 | -16
4SLA-75 | RFS.96 | M-B-H | BAU | Pre-AT |  | 2017-08-04 | Yes | Pre-AT | Completed | 2017-08-09 | NA | NA |  |  |  | 2017-08-11 | 30664 | Gouri |  | FTTN | Completed | 2017-08-09 | 2017-08-11 |  | -30662 | [5 empty] | -30663 | 0 | 0 | 0 | 0 | 0 |  | 3 | 30666
2MEN-63 | RFS.117 | M-M-H | BAU | Design |  | 2017-08-04 | Yes | Design | Completed | 2017-08-03 | NA | NA |  |  |  |  | 0 | Roshny John |  | FTTN | Completed | 2018-01-12 | 2018-01-16 | 2018-01-16 | 3 | [5 empty] | -30659 | 0 | 106 | 0 | 0 | 0 |  | -30658 | -105
4SOP-64 | RFS.0 | M-M-H | BAU | Design |  | 2017-08-04 | Yes | Design | Completed | 2017-08-10 | NA | NA |  |  |  |  | 0 |  |  | FTTN | Completed | 2017-08-10 | 2017-08-16 |  | -30663 | [5 empty] | -30664 | 0 | 0 | 0 | 0 | 0 |  | -30663 | 1
3BLB-64 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-08-07 | No |  | Completed | 2017-08-07 | Midhun | Completed | 2017-08-07 | 2017-08-18 |  | 2017-08-18 | 9 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30661 | 0 | 0 | 0 |  | 9 | 30670
6GIR-62 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-08-07 | No |  | Completed | 2017-08-02 | Karishma | Completed | 2017-08-02 | 2017-08-08 |  | 2017-08-08 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30658 | 0 | 0 | 0 |  | 5 | 30663
5BRI-67 | RFS.100 | H-A-Q | HAC | Pre-AT |  | 2017-08-07 | No |  | Completed | 2017-08-07 | Alphy | Completed | 2017-08-07 | 2017-08-14 |  | 2017-08-14 | 6 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30661 | 0 | 0 | 0 |  | 6 | 30667
4SLA-68 | RFS.68 | H-A-H | BAU | Pre-AT |  | 2017-08-08 | No |  | Completed | 2017-08-11 | Latheefa | Completed | 2017-08-11 | 2017-08-18 |  | 2017-08-18 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30665 | 0 | 0 | 0 |  | 5 | 30670
2PET-63 | RFS.96 | H-M-Q | HAC | Pre-AT |  | 2017-08-08 | No |  | Completed | 2017-08-22 | Dona | Completed | 2017-08-23 | 2017-08-30 |  | 2017-08-30 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30671 | 0 |  |  |  | 7 | 30677
3RWO-60 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-08-08 | No |  | Completed | 2017-08-05 | Latheefa | Completed | 2017-08-07 | 2017-08-11 |  | 2017-08-11 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30660 | 0 | 0 | 0 |  | 5 | 30665
6KSL-60 | RFS.95 | H-A-Q | HAC | Pre-AT |  | 2017-08-08 | No |  | Completed | 2017-08-05 | Geethu | Completed | 2017-08-07 | 2017-08-14 |  | 2017-08-14 | 6 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30660 | 0 | 0 | 0 |  | 6 | 30666
2SEF-67 | RFS.95 | M-M-H | BAU | Pre-AT |  | 2017-08-09 | No |  | Completed | 2017-08-04 | Aswathy | Completed | 2017-08-05 | 2017-08-10 |  | 2017-08-10 | 4 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30660 | 0 | 0 | 0 |  | 5 | 30665
3MIT-63 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-08-10 | No |  | Completed | 2017-08-09 | Nayana | Completed | 2017-08-09 | 2017-08-16 |  | 2017-08-16 | 5 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30663 | 0 | 0 | 0 |  | 5 | 30668
2EPP-62 | RFS.117 | M-M-H | BAU | Design |  | 2017-08-11 | Yes | Design | Completed |  |  | NA |  |  |  |  | 0 | Geethu Mol AG |  | FTTN | Completed | 2017-10-04 | 2017-10-06 | 2017-10-06 | 3 | [5 empty] | -1 | 0 | 30696 | 0 |  |  |  | 0 | -30695
5EDW-68 | RFS.120 | H-A-H | BAU | Pre-AT |  | 2017-08-11 | No |  | Completed | 2017-08-16 | Dona | Completed | 2017-08-17 | 2017-08-22 |  | 2017-08-22 | 4 |  |  | 0 |  |  |  |  | 0 | [5 empty] | 1 | 0 | -30667 | 0 | 0 | 0 |  | 5 | 30671
4MGA-67 | RFS.117 | M-M-H | BAU | Design |  | 2017-08-11 | Yes | Design | Completed | 2017-09-08 | NA | NA |  |  |  |  | 0 | Swathi JS |  | FTTN | Completed | 2017-09-11 | 2017-09-27 |  | -30682 | Line card deletion data not available in jumpering record |  |  |  |  | -30682 | 0 | 1 | 0 | 0 | 0 |  | -30681 | 0
4MGB-61 | RFS.95 | H-A-H | BAU | Pre-AT |  | 2017-08-11 | No |  | Completed | 2017-08-11 | Kruthika | Completed | 2017-08-12 | 2017-08-18 |  | 2017-08-18 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30665 | 0 |  |  |  | 5 | 30670
4BUR-62 | RFS.94 | M-M-H | BAU | Pre-AT |  | 2017-08-14 | Yes | Pre-AT | Completed | 2017-08-16 | Arya | Completed | 2017-08-17 | 2017-08-23 |  | 2017-08-23 | 5 | Roshny John |  | FTTN | Completed | 2017-08-17 | 2017-08-23 |  | -30667 | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0 |  | 6 | 4
3WIR-62 | RFS.96 | H-A-Q | HAC | Pre-AT |  | 2017-08-15 | No |  | Completed | 2017-08-15 | Geethu | Completed | 2017-08-16 | 2017-08-22 |  | 2017-08-22 | 5 |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | -30666 | 0 | 0 | 0 |  | 5 | 30671
2CRR-69 | RFS.93 | M-M-H | BAU | Pre-AT |  | 2017-08-15 | Yes | Pre-AT | Completed | 2017-08-16 | Haritha | Completed | 2017-08-17 | 2017-08-23 |  | 2017-08-23 | 5 | Nayana |  | FTTN | Completed | 2017-08-17 | 2017-08-23 |  | -30667 | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0 |  | 6 | 4
3WER-64 | RFS.100 | M-B-H [P] | BAU | Pre-AT |  | 2017-08-15 | Yes | Pre-AT | Completed | 2017-09-22 | Arya PS | Completed | 2017-09-25 | 2017-10-03 |  | 2017-10-03 | 5 | Geethu Mol AG |  | FTTN | Completed | 2017-09-25 | 2017-10-03 | 2017-10-03 | 5 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 6 | 4
3NCO-60 | RFS.97 | M-M-H | BAU | Pre-AT |  | 2017-08-14 | Yes | Design | Completed | 2017-08-31 | Nayana | Completed | 2017-09-06 | 2017-09-13 |  | 2017-09-13 | 6 | Divyamol James |  | FTTN | Completed | 2017-09-06 | 2017-09-08 |  | -30679 | [5 empty] | 2 | 0 | 2 | 0 | 0 | 0 |  | 8 | 4
2BAL-66 | RFS.97 | M-A-H | BAU | Pre-AT |  | 2017-08-15 | Yes | Design | Completed | 2017-08-15 | Karishma | Completed | 2017-08-16 | 2017-08-22 |  | 2017-08-22 | 5 |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | -30666 | 0 | 0 | 0 |  | 5 | 30671
2CRR-72 | RFS.95 | M-M-H | BAU | Pre-AT |  | 2017-08-15 | Yes | Pre-AT | Completed | 2017-04-28 | Brinson | Completed | 2017-08-19 | 2017-08-26 |  | 2017-08-26 | 5 | Reshma |  | FTTN/FTTB | Completed | 2018-08-19 | 2017-08-26 |  | -30909 | [5 empty] | 76 | 0 | 317 | 0 | 0 | 0 |  | 82 | -311
3NCO-66 | RFS.97 | M-M-H | BAU | Design |  | 2017-08-14 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4MGB-66 | RFS.95 | H-M-Q | BAU | Pre-AT |  | 2017-08-15 | No |  | Completed | 2017-08-10 | Sruthi | Completed | 2017-08-10 | 2017-08-21 |  | 2017-08-21 | 7 |  |  | 0 | NA |  |  |  | 0 | [5 empty] | 0 | 0 | -30664 | 0 | 0 | 0 |  | 7 | 30671
4MGB-01 | RFS.100 | M-B-H | BAU | Design |  | 2017-08-15 | Yes | Design | Completed | 2017-08-16 | NA | NA |  |  |  |  | 0 | Siva |  | FTTN | Completed | 2017-08-16 | 2017-08-22 |  | -30666 | [5 empty] | -30667 | 0 | 0 | 0 | 0 | 0 |  | -30666 | 1
3SOA-60 | RFS.96 | M-A-H | BAU | Pre-AT |  | 2017-08-17 | Yes | Design | Completed | 2017-08-22 | Sanjo | Completed | 2017-08-23 | 2017-08-30 |  | 2017-08-30 | 6 |  | Geethu Mol AG |  | Completed | 2017-11-28 | 2017-12-01 | 2017-12-01 | 4 | [5 empty] | 1 | 0 | 64 | 0 |  |  |  | 7 | -58
2PET-69 | RFS.96 | M-A-H | BAU | Pre-AT |  | 2017-08-17 | Yes | Design | Completed | 2017-08-24 | Nayana | Completed | 2017-08-25 | 2017-08-30 |  | 2017-08-30 | 4 | Midhun RaJ |  | FTTB | Completed | 2017-11-24 | 2017-12-06 | 2017-12-06 | 9 | 24-Nov: restarted 28-Nov : FTTx part is on hold as T18 data is not matching with SLD. New revised payload is available in connect MTM and DESG needs to start PNI load before this can be worked upon by DSG. 30-Nov: GML generated and made available by DESG. Activities to be started from Promotion onwards. 5 Dec: start the SAM execution of FTTx part |  |  |  |  | 1 | 0 | 60 | 0 |  |  |  | 5 | -56
4MGB-63 | RFS.95 | H-A-Q | HAC | Pre-AT |  | 2017-08-18 | No |  | Completed | 2017-08-18 | Divyamol James | Completed | 2017-08-18 | 2017-08-25 |  | 2017-08-25 | 6 |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | -30669 | 0 | 0 | 0 |  | 6 | 30675
4ASH-62 | RFS.95 | H-A-Q | HAC | Pre-AT |  | 2017-08-18 | No |  | Completed | 2017-08-15 | Aswathy | Completed | 2017-08-16 | 2017-08-22 |  | 2017-08-22 | 5 |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | -30666 | 0 | 0 | 0 |  | 5 | 30671
4EMP-63 | RFS.98 | M-B-H | BAU | Pre-AT |  | 2017-08-22 | Yes | Pre-AT | Completed | 2017-08-22 | Shankar | Completed | 2017-08-23 | 2017-08-29 |  | 2017-08-29 | 5 | Alphy Manuel |  |  | Completed | 2017-08-23 | 2017-08-29 |  | -30671 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 6 | 4
2EAS-67 | RFS.96 | M-M-H | BAU | Pre-AT |  | 2017-08-22 | Yes |  | Completed | 2017-08-22 | Latheefa | Completed | 2017-08-23 | 2017-08-26 |  | 2017-08-26 | 3 | Ratish Radhakrishnan |  | FTTB | Completed | 2017-08-23 | 2017-08-29 |  | -30671 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 4 | 2
2EAS-68 | RFS.0 | M-A-H | BAU | Pre-AT |  | 2017-08-22 | Yes | Design | Completed | 2017-08-24 | Latheefa | Completed | 2017-08-25 | 2017-08-31 |  | 2017-08-31 | 5 | Latheefa Ul | Sruthi James | FTTB | Completed | 2017-09-11 | 2017-12-08 | 2017-12-08 | 61 | Site Design Document is missing for MPS 2EAS-68-00-MPS-178 in Connect MTM 29 Dec: Resumed work on execution of FTTx part |  |  |  |  | 1 | 0 | 10 | 0 |  |  |  | 6 | -5
4CHP-60 | RFS.95 | M-M-H | BAU | Pre-AT |  | 2017-08-23 | Yes | Design | Completed | 2017-08-22 | Sruthi | Completed | 2017-08-23 | 2017-08-29 |  | 2017-08-29 | 5 | Midhun |  | FTTB | Completed | 2017-08-23 | 2017-08-24 |  | -30671 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 6 | 4
2EAS-65 | RFS.93 | M-M-H | BAU | Pre-AT |  | 2017-08-23 | Yes | Pre-AT | Completed | 2017-08-18 |  | NA |  |  |  | 2017-08-24 | 30672 | Gouri |  | FTTN/FTTB | Completed | 2017-08-21 | 2017-08-24 |  | -30669 | [5 empty] | -30669 | 0 | 1 | 0 | 766 | 100 |  | 5 | 30673
2BON-65 | RFS.99 | H-A-Q | HAC | Pre-AT |  | 2017-08-23 | No |  | Completed | 2017-08-21 | Swathi | Completed | 2017-08-22 | 2017-08-28 |  | 2017-08-28 | 5 |  |  | 0 |  |  |  |  | 0 | [5 empty] | 1 | 0 | -30670 | 0 | 0 | 0 |  | 6 | 30675
3SOA-65 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-08-23 | No |  | Completed | 2017-08-22 | Karishma | Completed | 2017-08-23 | 2017-08-30 |  | 2017-08-30 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30671 | 0 |  |  |  | 7 | 30677
2EDG-62 | RFS.96 | M-M-H | BAU | Pre-AT |  | 2017-08-24 | Yes | Design | Completed | 2017-08-21 | Aswathy | Completed | 2017-08-22 | 2017-08-28 |  | 2017-08-28 | 5 | Siva |  | FTTN | Completed | 2017-08-22 | 2017-08-28 |  | -30670 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 6 | 4
2EAS-62 | RFS.96 | M-M-H | BAU | Pre-AT |  | 2017-08-24 | Yes | Pre-AT | Completed | 2017-08-22 | Krutika | Completed | 2017-08-23 | 2017-08-29 |  | 2017-08-29 | 5 | Krutika Neelak |  | FTTB | Completed | 2017-08-23 | 2017-08-29 |  | -30671 | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0 |  | 6 | 4
4WTF-22 | RFS.22 | M-B-H | BAU | Design |  | 2017-08-30 | Yes | Design | Completed | 2017-12-13 | NA | Not Applicable |  |  |  |  | 0 | Arya PS |  | FTTN | Completed | 2017-12-14 | 2017-12-18 | 2017-12-18 | 3 | [5 empty] | -30746 | 0 | 1 | 0 | 0 | 0 |  | -30745 | 0
2PEN-63 |  | H-A-Q | HAC | Pre-AT |  | 2017-08-24 | No |  | Completed | 2017-08-31 | Alphy | Completed | 2017-09-06 | 2017-09-13 |  | 2017-09-13 | 6 | [7 empty] | 0 | [5 empty] | 2 | 0 | -30678 | 0 |  |  |  | 8 | 30684
4CPB-20 | RFS.96 | M-B-H | BAU | Design |  | 2017-08-24 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4EMP-63 | RFS.98 | M-B-H | BAU | Pre-AT |  | 2017-08-28 | Yes | Pre-AT | Completed | 2017-06-21 | Mary | Completed | 2017-06-21 | 2017-06-26 |  | 2017-06-26 | 3 | Gouri |  | FTTN | Completed | 2017-06-21 | 2017-07-07 |  | -30628 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 3 | 3
2BON-67 | RFS.67 | H-A-Q | HAC | Pre-AT |  | 2017-08-28 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2STL-64 | RFS.104 | M-M-H | BAU | Pre-AT |  | 2017-08-28 | Yes | Pre-AT | Completed | 2017-08-25 | Reshma Rajan | Completed | 2017-08-28 | 2017-10-18 |  | 2017-10-18 | 33 | Nayana |  | FTTN | Completed | 2017-08-28 | 2017-10-16 | 2017-10-16 | 32 | 31-Aug-2017 : went on hold because integration workbook was missing. 13-Oct-2017: got Integration Workbook and resumed execution. Handed over FTTN part on 16th Oct. Handed over HFc part on 18th Oct. Exported important reports again since SAM was on-hold for a month. |  |  |  |  | 1 | 0 | 1 | 0 | 1533 |  |  | 34 | 32
4CUR-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | 2017-08-28 | No |  | Completed | 2017-08-29 | Dona Babu | Completed | 2017-08-30 | 2017-09-08 |  | 2017-09-08 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30676 | 0 |  |  |  | 7 | 30682
5MOD-63 | RFS.63 | M-A-J | BAU | Pre-AT |  | 2017-08-28 | Yes | Design | Completed | 2017-08-28 | Haritha | Completed | 2017-08-29 | 2017-09-01 |  | 2017-09-01 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30675 | 0 |  |  |  | 5 | 30679
4MGA-63 | RFS.0 | M-B-H | BAU | Design |  | 2017-08-28 | Yes | Design | Completed | 2017-08-28 |  | NA |  |  |  |  | 0 | Karishma |  | FTTB | Completed | 2017-08-29 | 2017-09-08 |  | -30675 | [5 empty] | -30675 | 0 | 1 | 0 |  |  |  | -30674 | 0
3BOX-65 | RFS.98 | M-A-H | BAU | Pre-AT |  | 2017-08-29 | Yes | Design | Completed | 2017-09-07 | Dona Babu | Completed | 2017-09-08 | 2017-09-14 |  | 2017-09-14 | 5 |  |  |  | On Hold |  |  |  | 0 | [5 empty] | 1 | 0 | -30681 | 0 |  |  |  | 6 | 30686
6MLO-64 | RFS.99 | H-A-Q | HAC | Pre-AT |  | 2017-08-30 | No |  | Completed | 2017-08-28 | Roshni Johns | Completed | 2017-08-29 | 2017-09-01 |  | 2017-09-01 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30675 | 0 |  |  |  | 5 | 30679
4CPB-20 | RFS.98 | M-B-H | BAU | Pre-AT |  | 2017-09-01 | Yes | Pre-AT | Completed | 2017-09-08 | 2c | NA |  |  |  | 2017-09-19 | 30688 | Reshma T V |  | FTTN | Completed | 2017-09-11 | 2017-09-19 |  | -30682 | FNO count was high(10+) |  |  |  |  | -30682 | 0 | 1 | 0 |  |  |  | 8 | 30689
3DNC-61 | RFS.95 | H-A-Q | HAC | Pre-AT |  | 2017-09-01 | No |  | Completed | 2017-09-01 | Krutika Neelak | Completed | 2017-09-04 | 2017-09-08 |  | 2017-09-08 | 3 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30679 | 0 |  |  |  | 4 | 30683
4BUR-21 | RFS.94 | M-B-H | BAU | Pre-AT |  | 2017-09-01 | yes | Pre-AT | Completed | 2017-09-08 | [5 empty] | 2017-09-19 | 30688 | Nayana |  | FTTN | Completed | 2017-09-09 | 2017-09-19 |  | -30681 | [5 empty] | -30682 | 0 | 0 | 0 |  |  |  | 8 | 30690
2CRR-60 | RFS.100 | M-M-H | BAU | Pre-AT |  | 2017-09-04 | Yes | Design | Completed | 2017-09-08 | Arya PS | Completed | 2017-09-11 | 2017-09-15 |  | 2017-09-15 | 5 |  |  |  | On Hold |  |  |  | 0 | [5 empty] | 1 | 0 | -30682 | 0 |  |  |  | 6 | 30687
3BNT-63 | RFS.96 | H-A-Q | HAC | Pre-AT |  | 2017-09-07 | No |  | Completed | 2017-08-31 | Sanjo Lopez | Completed | 2017-09-01 | 2017-09-07 |  | 2017-09-07 | 3 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30678 | 0 |  |  |  | 4 | 30681
4SRW-61 | RFS.103 | H-A-Q | HAC | Pre-AT |  | 2017-09-07 | No |  | Completed | 2017-09-05 | Brinson Bovas | Completed | 2017-09-06 | 2017-09-14 |  | 2017-09-14 | 7 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30679 | 0 |  |  |  | 7 | 30686
3DAD-67 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-09-07 | No |  | Completed | 2017-09-01 | Sruthi James | Completed | 2017-09-05 | 2017-09-13 |  | 2017-09-13 | 6 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30679 | 0 |  |  |  | 7 | 30686
4AGV-62 | RFS.118 | M-M-H | BAU | Design |  | 2017-09-04 | [10 empty] | 0 | [7 empty] | 0 | FTTN yet to be assigned. FTTB handover was on 13-Nov-17 |  |  |  |  | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2BAN-70 | RFS.124 | M-B-H | BAU | Design |  | 2017-09-04 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4BLH-62 | RFS.118 | M-B-H | BAU | Design |  | 2017-09-04 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2BAN-63 | RFS.112 | M-M-H | BAU | Design |  | 2017-09-04 | Yes | Design | On Hold - Awaiting Upstream team Updates | 2017-12-05 | NA | Not Applicable |  |  |  |  | 0 | NA | Dona Babu | FTTB | On Hold - Awaiting Upstream team Updates | 2017-12-05 |  |  | -30739 | 5-Dec: Mismatch in site design document MPS boundary and T18. |  |  |  |  | -30740 | 0 | 0 | 0 |  |  |  | -30739 | 1
4CPR-62 | RFS.121 | M-M-H | BAU | Design |  | 2017-09-04 | Yes | Design | On Hold - HFC Completed | 2017-09-25 | Roshni Johns | Completed | 2017-09-26 | 2017-10-03 |  | 2017-10-03 | 4 | Swathi JS |  | FTTB | On Hold - Document Unavailability | 2017-09-26 |  |  | -30693 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 5 | 3
2STL-63 | RFS.103 | H-B-Q | BAU | Pre-AT |  | 2017-09-07 | No |  | Completed | 2017-09-06 | Sanjo Lopez | Completed | 2017-09-07 | 2017-09-13 |  | 2017-09-13 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30680 | 0 |  |  |  | 6 | 30685
3RWO-61 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-09-07 | No |  | Completed | 2017-09-01 | Midhun RaJ | Completed | 2017-09-06 | 2017-09-13 |  | 2017-09-13 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30679 | 0 |  |  |  | 7 | 30685
3DAD-66 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-09-07 | No |  | Completed | 2017-09-08 | Roshni Johns | Completed | 2017-09-11 | 2017-09-19 |  | 2017-09-19 | 7 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30682 | 0 | 3364 |  |  | 8 | 30689
3DAD-63 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-09-07 | No |  | Completed | 2017-09-07 | Geethu Mol AG | Completed | 2017-09-08 | 2017-09-15 |  | 2017-09-15 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30681 | 0 |  |  |  | 7 | 30687
4CPH-66 | RFS.115 | M-M-H | BAU | Design |  | 2017-09-07 | Yes | Design | On Hold | [7 empty] | 0 | Siva Kumar |  | FTTN | On Hold | 2017-09-12 |  |  | -30683 | Design is rejected back to Telstra for coming up with updated SLD and other artefacts. |  |  |  |  | -1 | 0 | 30682 | 0 |  |  |  | 0 | -30681
4APL-60 | RFS.122 | M-M-H | BAU | Design |  | 2017-10-04 |  |  | Not started | [7 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
5WES-64 | RFS.108 | H-A-Q | HAC | Pre-AT |  | 2017-09-11 | No |  | Completed | 2017-09-12 | Siva Kumar | Completed | 2017-09-13 | 2017-09-20 |  | 2017-09-20 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30684 | 0 |  |  |  | 7 | 30690
2MIL-60 | RFS.103 | M-M-H | BAU | Pre-AT |  | 2017-09-12 | No |  | Completed | 2017-09-29 | Karishma | Completed | 2017-10-04 | 2017-10-10 |  | 2017-10-10 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30696 | 0 |  |  |  | 6 | 30701
2PYM-60 | RFS.99 | H-A-Q | HAC | Pre-AT |  | 2017-09-12 | No |  | Completed | 2017-09-13 | Dona Babu | Completed | 2017-09-14 | 2017-09-22 |  | 2017-09-22 | 7 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30685 | 0 |  |  |  | 8 | 30692
3SSN-62 | RFS.121 | M-M-H | BAU | Design |  | 2017-09-12 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3WER-65 | RFS.99 | M-A-H | BAU | Pre-AT |  | 2017-09-12 | Yes | Design | Completed | 2017-09-07 | Aswathy Baby | Completed | 2017-09-08 | 2017-09-14 |  | 2017-09-14 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30681 | 0 |  |  |  | 6 | 30686
4MGB-62 | RFS.99 | M-M-H | BAU | Pre-AT |  | 2017-09-13 | Yes | Design | Completed | 2017-09-08 | Karishma | Completed | 2017-09-11 | 2017-09-15 |  | 2017-09-15 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30682 | 0 |  |  |  | 6 | 30687
3GLI-62 | RFS.100 | M-A-H | BAU | Pre-AT |  | 2017-09-12 | Yes | Design | Completed | 2017-09-12 | Sruthi James | Completed | 2017-09-13 | 2017-09-21 |  | 2017-09-21 | 7 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30684 | 0 | 2813 |  |  | 8 | 30691
3KYG-64 | RFS.100 | M-A-H | BAU | Pre-AT |  | 2017-09-15 | Yes | Design | On Hold - HFC Completed | 2017-09-18 | Geethu Mol AG | Completed | 2017-10-09 | 2017-10-12 |  | 2017-10-12 | 4 | Gouri Gopal |  | FTTB | On Hold - Awaiting Upstream team Updates | 2017-10-09 |  |  | -30700 | DFN Termination issue |  |  |  |  | 13 | 0 | 13 | 0 |  |  |  | 17 | -9
6GIR-22 | RFS.0 | M-B-H | BAU | Design |  | 2017-09-12 | Yes | Design | Completed | 2017-09-21 |  | NA |  |  |  |  | 0 | Reshma T V |  | FTTN | Completed | 2017-09-22 | 2017-10-03 | 2017-10-03 | 6 | [5 empty] | -30691 | 0 | 1 | 0 |  |  |  | -30690 | 0
4CUR-60 | RFS.126 | M-M-H | BAU | Design |  | 2017-09-19 | Yes | Design | On Hold - Document Unavailability | 2017-10-05 | [6 empty] | 0 | Siva Kumar |  | FTTB |  | 2017-10-06 |  |  | -30699 | [5 empty] | -30699 | 0 | 1 | 0 |  |  |  | -30698 | 0
2FRE-62 | RFS.102 | M-M-H | BAU | Design |  | 2017-09-19 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2PEN-66 | RFS.99 | H-A-Q | HAC | Pre-AT |  | 2017-09-13 | No |  | Completed | 2017-09-08 | Haritha | Completed | 2017-09-11 | 2017-09-18 |  | 2017-09-18 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30682 | 0 |  |  |  | 7 | 30688
3BOX-61 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-09-13 | No |  | Completed | 2017-09-11 | Krutika Neelak | Completed | 2017-09-12 | 2017-09-19 |  | 2017-09-19 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30683 | 0 |  |  |  | 7 | 30689
6GIR-21 | RFS.0 | M-B-H | BAU | Design |  | 2017-09-13 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2CRR-20 | RFS.101 | M-B-H | BAU | Pre-AT |  | 2017-09-14 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2PET-71 | RFS.118 | M-M-H | BAU | Design |  | 2017-09-13 | Yes | Design | Completed | 2017-09-29 |  | NA |  |  |  |  | 0 | Roshni Johns |  | FTTN | Completed | 2017-10-06 | 2017-10-10 | 2017-10-10 | 3 | [5 empty] | -30696 | 0 | 3 | 0 |  |  |  | -30695 | -2
6GIR-64 | RFS.115 | M-M-H | BAU | Design |  | 2017-09-13 | Yes | Design | Completed | 2017-10-09 |  | NA |  |  |  |  | 0 | Roshni Johns |  | FTTB | Completed | 2017-10-12 | 2017-10-17 | 2017-10-17 | 4 | [5 empty] | -30701 | 0 | 3 | 0 |  |  |  | -30700 | -2
2PEN-62 | RFS.100 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-12 | Latheefa Ul | Completed | 2017-09-13 | 2017-09-20 |  | 2017-09-20 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30684 | 0 |  |  |  | 7 | 30690
5GLL-61 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-17 | Geethu | Completed | 2017-09-18 | 2017-09-25 |  | 2017-09-25 | 6 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30687 | 0 |  |  |  | 6 | 30693
4BUR-60 | RFS.103 | M-A-Q | HAC | Pre-AT |  | 2017-09-13 | No |  | Completed | 2017-09-13 | Divyamol James | Completed | 2017-09-14 | 2017-09-21 |  | 2017-09-21 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30685 | 0 |  |  |  | 7 | 30691
2LIV-63 | RFS.118 | M-M-H | BAU | Design |  | 2017-09-13 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2CAS-66 | RFS.118 | M-M-H | BAU | Design |  | 2017-09-21 | No | Design | Completed | 2017-09-25 | Sruthi James | Completed | 2017-09-26 | 2017-10-03 |  | 2017-10-03 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30693 | 0 |  |  |  | 5 | 30697
4MGB-20 | RFS.100 | M-B-H | BAU | Pre-AT |  | 2017-09-14 | Yes | Pre-AT | Completed | 2017-09-13 |  | NA |  |  |  | 2017-09-21 | 30690 | Midhun |  |  | Completed | 2017-09-14 | 2017-09-21 |  | -30685 | [5 empty] | -30685 | 0 | 1 | 0 |  |  |  | 7 | 30691
2BAN-70 | RFS.124 | M-B-H | BAU | Design |  | 2017-09-14 | Yes | Design | Completed | 2017-10-06 | NA | Not Applicable |  |  |  |  | 0 | Latheefa Ul |  | FTTN/FTTB | Completed | 2017-10-06 | 2017-10-13 | 2017-10-13 | 6 | FTTN: Latheefa, FTTb:Dona |  |  |  |  | -30700 | 0 | 0 | 0 |  |  |  | -30699 | 1
4ASH-63 | RFS.134 | H-M-H | BAU | Pre-AT |  | 2017-09-15 | Yes | Design | Completed | 2017-09-22 | Karishma | Completed | 43003 | 2017-09-29 |  | 2017-09-29 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30692 | 0 |  |  |  | 5 | 30696
4CPR-62 | RFS.121 | M-M-H | BAU | Design |  | 2017-09-15 | Yes | Design | Completed | 2017-09-25 | Roshni Johns | Completed | 2017-09-26 | 2017-10-03 |  | 2017-10-03 | 4 | Swathi JS |  | FTTB | On Hold - Awaiting Upstream team Updates | 2017-09-26 |  |  | -30693 | DFN Termination details missing |  |  |  |  | 1 | 0 | 1 | 0 |  |  |  | 5 | 3
2SEV-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-09-18 | Yes | Design | Completed | 2017-09-18 | Brinson Bovas | Completed | 2017-09-20 | 2017-09-28 |  | 2017-09-28 | 7 | Arya PS |  | FTTB | Completed | 2017-09-20 | 2017-09-22 |  | -30689 | [5 empty] | 2 | 0 | 2 | 0 | 2059 |  |  | 9 | 5
3NCO-66 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-13 | Alphy Manuel | Completed | 2017-09-14 | 2017-09-22 |  | 2017-09-22 | 7 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30685 | 0 |  |  |  | 8 | 30692
3CAU-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-18 | No |  | Completed | 2017-09-17 | Swathi JS | Completed | 2017-09-18 | 2017-09-26 |  | 2017-09-26 | 7 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30687 | 0 |  |  |  | 7 | 30694
4CPR-61 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-18 | No |  | Completed | 2017-09-18 | Roshni Johns | Completed | 2017-09-19 | 2017-09-26 |  | 2017-09-26 | 6 | [7 empty] | 0 | 21-Sep-17 : 1 loc and associated tap in different ADA. |  |  |  |  | 1 | 0 | -30688 | 0 |  |  |  | 7 | 30694
2PYM-63 | RFS.125 | M-M-H | BAU | Design |  | 2017-09-18 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4AGV-20 | RFS.126 | M-A-H | BAU | Pre-AT |  | 2017-09-25 | Yes | Design | Completed | 2017-10-06 | Siva Kumar | Completed | 2017-10-06 | 2017-10-13 |  | 2017-10-13 | 6 | Haritha |  | FTTB | Completed | 2017-10-16 | 2017-10-17 | 2017-10-17 | 2 | [5 empty] | 0 | 0 | 6 | 0 |  |  |  | 6 | 0
2FRE-60 | RFS.126 | M-M-H | BAU | Design |  | 2017-09-19 | Yes | Design | Completed | 2017-12-07 | NA | Not Applicable |  |  |  |  | 0 | Dona Babu |  | FTTN | Completed | 2017-12-07 | 2017-12-08 | 2017-12-08 | 2 | [5 empty] | -30742 | 0 | 0 | 0 |  |  |  | -30741 | 1
4SUR-62 | RFS.113 | M-A-H | BAU | Pre-AT |  | 2017-09-20 | Yes | Design | Completed | 2017-10-13 | Divyamol James | Completed | 2017-10-16 | 2017-10-23 |  | 2017-10-23 | 5 | Swathi JS |  | FTTB | Completed | 2017-10-17 | 2017-10-20 |  | -30706 | [5 empty] | 1 | 0 | 2 | 0 |  |  |  | 6 | 3
3TNI-64 | RFS.103 | M-A-H | BAU | Pre-AT |  | 2017-09-20 | Yes | Design | Completed | 2017-09-21 | Haritha | Completed | 2017-09-21 | 2017-09-27 |  | 2017-09-27 | 5 | Karishma |  | FTTN | Completed | 2017-09-21 | 2017-09-26 |  | -30690 | [5 empty] | 0 | 0 | 0 | 0 | 4268 |  |  | 5 | 5
3MLN-65 | RFS.100 | H-A-Q | HAC | Pre-AT |  | 2017-09-20 | No |  | Completed | 2017-09-20 | Siva Kumar | Completed | 2017-09-21 | 2017-09-27 |  | 2017-09-27 | 5 | [7 empty] | 0 | 21-Sep-17 : Not able to update ADA-01. Issue raised to AP. One OTN serving more than one ADA's causing SC mismatches. |  |  |  |  | 1 | 0 | -30690 | 0 |  |  |  | 6 | 30695
4MGA-70 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-21 | No |  | Completed | 2017-09-19 | Dona Babu | Completed | 2017-09-20 | 2017-09-27 |  | 2017-09-27 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30689 | 0 |  |  |  | 7 | 30695
4MGA-72 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-21 | No |  | Completed | 2017-09-18 | Aswathy Baby | Completed | 2017-09-19 | 2017-09-26 |  | 2017-09-26 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30688 | 0 |  |  |  | 7 | 30694
4SLA-64 | RFS.104 | M-M-H | BAU | Design |  | 2017-09-20 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2ASH-66 | RFS.118 | M-M-H | BAU | Design |  | 2017-09-20 | Yes | Design | Completed |  | NA | Not Applicable |  |  |  |  | 0 | Swathi JS |  | FTTN | Completed | 2017-10-06 | 2017-10-13 | 2017-10-13 | 6 | [5 empty] | -1 | 0 | 30698 | 0 |  |  |  | 0 | -30697
2CAS-66 | RFS.101 | M-A-H | BAU | Pre-AT |  | 2017-09-25 | Yes | Design | Completed | 2017-09-25 | Sruthi James | Completed | 2017-09-26 | 2017-10-03 |  | 2017-10-03 | 4 | Alphy Manuel |  | FTTN | Completed | 2017-09-26 | 2017-09-29 | 2017-09-29 | 3 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 5 | 3
5GLL-62 | RFS.125 | M-M-H | BAU | Design |  | 2017-09-22 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2WET-65 | RFS.100 | M-M-H | BAU | Pre-AT |  | 2017-09-26 | Yes | Pre-AT | Completed | 2017-09-27 | Reshma Rajan | Completed | 2017-09-27 | 2017-10-05 |  | 2017-10-05 | 5 | Siva Kumar |  | FTTN | Completed | 2017-09-27 | 2017-10-05 | 2017-10-05 | 5 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 5 | 5
4CPR-65 | RFS.105 | M-A-H | BAU | Pre-AT |  | 2017-09-26 | Yes | Design | Completed | 2017-09-27 | Latheefa Ul | Completed | 2017-09-28 | 2017-10-06 |  | 2017-10-06 | 5 | Brinson Bovas |  | FTTN | Completed | 2017-09-28 | 2017-10-04 | 2017-10-04 | 3 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 6 | 4
4AGV-64 | RFS.122 | M-M-H | BAU | Design |  | 2017-09-25 | Yes | Design | Completed | 2017-09-25 |  | NA |  |  |  |  | 0 | Aswathy Baby |  | FTTN | Completed | 2017-09-26 | 2017-09-29 | 2017-09-29 | 3 | [5 empty] | -30693 | 0 | 1 | 0 |  |  |  | -30692 | 0
4CPR-62 | RFS.121 | M-A-H | BAU | Pre-AT |  | 2017-09-26 | Yes | Design | On Hold - HFC Completed | 2017-09-25 | Roshni Johns | Completed | 2017-09-26 | 2017-10-03 |  | 2017-10-03 | 4 | Swathi JS |  | FTTB | On Hold - Awaiting Upstream team Updates | 2017-09-26 |  |  | -30693 | DFN Termination missing |  |  |  |  | 1 | 0 | 1 | 0 |  |  |  | 5 | 3
4CHL-68 | RFS.143 | M-M-H | BAU | Design |  | 2017-09-25 | Yes | Design | On Hold - Document Unavailability | 2017-09-27 | [6 empty] | 0 | Haritha |  | FTTB |  |  |  |  | 0 | [5 empty] | -30695 | 0 | -30695 | 0 |  |  |  | -30694 | 30696
2PYM-62 | RFS.124 | M-M-H | BAU | Design |  | 2017-09-25 | Yes | Design | Completed | 2017-09-26 | NA | Not Applicable |  |  |  |  | 0 | Dona Babu |  | FTTN | Completed | 2017-09-27 | 2017-09-29 | 2017-09-29 | 2 | [5 empty] | -30694 | 0 | 1 | 0 |  |  |  | -30693 | 0
4APL-60 | RFS.122 | M-M-H | BAU | Design |  | 2017-10-04 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4ABC-63 | RFS,.121 | M-M-H | BAU | Design |  | 2017-09-26 | Yes | Design | Completed | 2017-12-18 |  | Not Applicable |  |  |  |  | 0 | Anju Philip |  | FTTN | Completed | 2017-12-18 | 2017-12-27 | 2017-12-27 | 6 | [5 empty] | -30749 | 0 | 0 | 0 |  |  |  | -30748 | 1
4IAL-64 | RFS.122 | M-M-H | BAU | Design |  | 2017-09-26 | Yes | Design | Completed | 2017-10-05 | NA | Not Applicable |  |  |  |  | 0 | Roshni Johns |  | FTTN | Completed | 2017-10-06 | 2017-10-12 | 2017-10-12 | 5 | [5 empty] | -30699 | 0 | 1 | 0 |  |  |  | -30698 | 0
4SUR-60 | RFS.128 | M-B-H | BAU | Design |  | 2017-09-26 | Yes | Design | Completed | 2017-10-10 | NA | Not Applicable |  |  |  |  | 0 | Geethu Mol AG |  | FTTB | Completed | 2017-10-11 | 2017-10-19 | 2017-10-19 | 6 | [5 empty] | -30702 | 0 | 1 | 0 |  |  |  | -30701 | 0
2HLS-61 | RFS.118 | M-M-H | BAU | Design |  | 2017-09-26 | Yes | Design | Completed | 2017-09-28 |  | NA |  |  |  |  | 0 | Alphy Manuel |  | FTTN\FTTB | Completed | 2017-09-29 | 2017-10-05 | 2017-10-05 | 3 | Alphy-FTTB, Dona-FTTN |  |  |  |  | -30696 | 0 | 0 | 0 |  |  |  | -30695 | 1
2HLS-60 | RFS.124 | M-M-H | BAU | Design |  | 2017-09-26 | Yes | Design | Completed | 2017-09-28 |  | NA |  |  |  |  | 0 | Aswathy Baby |  | FTTN | Completed | 2017-09-29 | 2017-10-04 | 2017-10-04 | 2 | [5 empty] | -30696 | 0 | 0 | 0 |  |  |  | -30695 | 1
3BOX-64 | RFS.100 | H-A-Q | HAC | Pre-AT |  | 2017-09-28 |  |  | Completed | 2017-09-28 | Divyamol James | Completed | 2017-09-29 | 2017-10-09 |  | 2017-10-09 | 5 |  |  |  | On Hold - Awaiting Upstream team Updates |  |  |  | 0 | 21-Dec : FTTB location not loaded in PNI and T18 contains temp id LOC in SL table. Nothing can be processed further. Mail sent to LDM for confirmation on whether temp ID mapping was done. 22-dec: Split Load. New T18 available and loaded by DESG. Putting on-hold as per Kiran’s comment. |  |  |  |  | 0 | 0 | -30696 | 0 |  |  |  | 6 | 30702
5BRI-61 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-09-29 |  |  | Completed | 2017-09-28 | Haritha | Completed | 2017-09-29 | 2017-10-09 |  | 2017-10-09 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30696 | 0 |  |  |  | 6 | 30702
4BNP-64 | RFS.115 | M-M-H | BAU | Design |  | 2017-09-28 | Yes | Design | Completed | 2017-10-05 |  | NA |  |  |  |  | 0 | Alphy Manuel |  | FTTN | Completed | 2017-10-06 | 2017-10-12 | 2017-10-12 | 5 | [5 empty] | -30699 | 0 | 1 | 0 |  |  |  | -30698 | 0
2FRE-64 | RFS.106 | M-B-H | BAU | Design |  | 2017-09-29 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
6SUB-66 | RFS.113 | M-M-H | BAU | Design |  | 2017-11-09 | [10 empty] | 0 | [7 empty] | 0 | Missing document in NDD Document |  |  |  |  | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4ABC-60 | RFS.113 | H-A-Q | HAC | Pre-AT |  | 2017-09-28 | No |  | Completed | 2017-09-27 | Midhun RaJ | Completed | 2017-09-28 | 2017-10-06 |  | 2017-10-06 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30695 | 0 |  |  |  | 6 | 30700
4SRW-64 | RFS.105 | H-A-Q | HAC | Pre-AT |  | 2017-10-02 |  |  | Completed | 2017-10-05 | Nayana Anilkumar | Completed | 2017-10-06 | 2017-10-13 |  | 2017-10-13 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30699 | 0 |  |  |  | 7 | 30705
4CUR-61 | RFS.120 | M-A-H | BAU | Pre-AT |  | 2017-10-04 | Yes | Design | Completed | 2017-10-13 | Karishma | Completed | 2017-10-13 | 2017-10-20 |  | 2017-10-20 | 5 | Arya PS |  | FTTN | Completed | 2017-10-16 | 2017-10-18 | 2017-10-18 | 2 | [5 empty] | 0 | 0 | 1 | 0 |  |  |  | 5 | 4
3TYH-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-10-04 |  |  | Completed | 2017-10-04 | Reshma Rajan | Completed | 2017-10-05 | 2017-10-11 |  | 2017-10-11 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30698 | 0 |  |  |  | 6 | 30703
2PEN-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-10-04 |  |  | Completed | 2017-10-04 | Aswathy Baby | Completed | 2017-10-05 | 2017-10-11 |  | 2017-10-11 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30698 | 0 |  |  |  | 6 | 30703
3CLA-66 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-10-04 |  |  | Completed | 2017-10-05 | Brinson Bovas | Completed | 2017-10-23 | 2017-10-27 |  | 2017-10-27 | 5 | [7 empty] | 0 | went on hold on 13-Oct-2017 due to GML issues and was up only on 23-Oct-17 after ASM team fixed demotion issue |  |  |  |  | 11 | 0 | -30699 | 0 |  |  |  | 16 | 30704
5GLL-65 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-04 |  |  | Completed | 2017-10-06 | Haritha | Completed | 2017-10-09 | 2017-10-13 |  | 2017-10-13 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30700 | 0 |  |  |  | 6 | 30705
4WTF-63 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-04 |  |  | Completed | 2017-10-03 | Brinson Bovas | Completed | 2017-10-04 | 2017-10-11 |  | 2017-10-11 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30697 | 0 |  |  |  | 7 | 30703
4AAR-62 | RFS.103 | H-A-Q | HAC | Pre-AT |  | 2017-10-04 |  |  | Completed | 2017-10-04 | Reshma T V | Completed | 2017-10-05 | 2017-10-12 |  | 2017-10-12 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30698 | 0 |  |  |  | 7 | 30704
3BNT-66 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-10-04 |  |  | Completed | 2017-10-06 | Divyamol James | Completed | 2017-10-06 | 2017-10-13 |  | 2017-10-13 | 6 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30700 | 0 |  |  |  | 6 | 30706
6GIR-21 | RFS.150 | M-M-H | BAU | Design |  | 2017-10-04 | Yes | Design | Completed | 2017-11-16 | NA | Not Applicable |  |  |  |  | 0 | Dona Babu |  | FTTN | Completed | 2017-11-17 | 2017-11-23 | 2017-11-23 | 5 | [5 empty] | -30727 | 0 | 1 | 0 |  |  |  | -30726 | 0
6GIR-20 | RFS.151 | M-M-H | BAU | Design |  | 2017-10-05 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2ING-65 | RFS.131 | M-M-H | BAU | Design |  | 2017-10-05 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
5BRI-63 | RFS.104 | M-A-H | BAU | Pre-AT |  | 2017-10-04 | Yes | Design | Completed | 2017-10-10 | Alphy Manuel | Completed | 2017-10-11 | 2017-10-17 |  | 2017-10-17 | 5 |  | Siva Kumar | FTTB | Completed | 2017-11-27 | 2017-11-29 | 2017-11-29 | 3 | [5 empty] | 1 | 0 | 32 | 0 |  |  |  | 6 | -27
4WTF-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-10-16 | Yes | Design | Completed | 2017-10-19 | Sruthi James | Completed | 2017-10-20 | 2017-10-26 |  | 2017-10-26 | 5 | Ratish Radhakrishnan | Jijin Isaac | FTTN/FTTB | Completed | 2017-11-29 |  |  | -30735 | Went on hold on 20-Oct-17 due to missing DFN termination details |  |  |  |  | 1 | 0 | 28 | 0 |  |  |  | 6 | -23
4ORM-60 | RFS.109 | H-A-Q | HAC | Pre-AT |  | 2017-10-10 | No |  | Completed | 2017-10-10 | Haritha | Completed | 2017-10-11 | 2017-10-19 |  | 2017-10-19 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30702 | 0 |  | 100 |  | 7 | 30708
3CAU-63 | RFS.105 | M-A-H | BAU | Pre-AT |  | 2017-10-10 | Yes | Design | On Hold - HFC Completed | 2017-10-06 | Midhun RaJ | Completed | 2017-10-06 | 2017-10-13 |  | 2017-10-13 | 6 | Siva Kumar |  | FTTB | On Hold - Document Unavailability | 2017-10-06 |  |  | -30699 | Went on hold on 06-Oct-17 due to missing MPS package |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 6 | 6
2STL-60 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-10 |  |  | Completed | 2017-10-11 | Latheefa Ul | Completed | 2017-10-12 | 2017-10-16 |  | 2017-10-16 | 3 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30703 | 0 |  |  |  | 4 | 30706
3TNI-63 | RFS.103 | M-A-Q | HAC | Pre-AT |  | 2017-10-10 | Yes | Design | Completed | 2017-10-10 | Arya PS | Completed | 2017-10-11 | 2017-10-16 |  | 2017-10-16 | 4 |  | Karishma | FTTB | Completed | 2018-01-08 | 2018-01-10 | 2018-01-10 | 3 | 8-Jan:Updated DFN received on 8th Jan, work resumed |  |  |  |  | 1 | 0 | 59 | 0 |  |  |  | 5 | -55
6WMB-63 | RFS.120 | M-A-H | BAU | Pre-AT |  | 2017-10-11 |  |  | Completed | 2017-10-17 | Ratish Radhakrishnan | Completed | 2017-10-17 | 2017-10-23 |  | 2017-10-23 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30707 | 0 |  |  |  | 4 | 30711
2MIL-63 | RFS.103 | M-M-H | BAU | Pre-AT |  | 2017-10-11 |  |  | Completed | 2017-10-10 | Swathi JS | Completed | 2017-10-10 | 2017-10-17 |  | 2017-10-17 | 6 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30702 | 0 |  |  |  | 6 | 30708
2LIV-60 | RFS.130 | M-M-H(P) | BAU | Design |  | 2017-10-10 | Yes | Design | Completed | 2017-11-10 | NA | Not Applicable |  |  |  |  | 0 | Latheefa Ul |  | FTTN | Completed | 2017-11-23 | 2017-11-24 | 2017-11-24 | 2 | [5 empty] | -30723 | 0 | 9 | 0 |  |  |  | -30722 | -8
3BOX-63 | RFS.105 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-11 | Sanjo Lopez | Completed | 2017-10-11 | 2017-10-18 |  | 2017-10-18 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30703 | 0 |  |  |  | 5 | 30708
3HDB-62 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-11 | Karishma | Completed | 2017-10-11 | 2017-10-26 |  |  | -30702 | [7 empty] | 0 | Went on hold on 16-Oct for latest NDD from upstream team. Node missing in current NDD. |  |  |  |  | 0 | 0 | -30703 | 0 |  |  |  | -30702 | 1
2PNN-64 | RFS.80 | H-A-H | BAU | Pre-AT |  | 2017-10-17 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2BAN-69 | RFS.104 | H-M-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-13 | Reshma T V | Completed | 2017-10-16 | 2017-10-23 |  |  | -30705 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30705 | 0 |  |  |  | -30704 | 0
4AAR-63 | RFS.122 | M-M-H | BAU | Design |  | 2017-09-15 | Yes | Design | Completed | 2017-12-11 | NA | Not Applicable |  |  |  |  | 0 | Aparna Nampoothiri |  | FTTN | Completed | 2017-12-11 | 2017-12-14 | 2017-12-14 | 4 | [5 empty] | -30744 | 0 | 0 | 0 |  |  |  | -30743 | 1
3BNT-60 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-12 |  |  | Completed | 2017-10-11 | Reshma Rajan | Completed | 2017-10-12 | 2017-10-17 |  | 2017-10-17 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30703 | 0 |  |  |  | 5 | 30707
3BLB-69 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-12 |  |  | Completed | 2017-10-12 | Sruthi James | Completed | 2017-10-13 | 2017-10-20 |  | 2017-10-20 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30704 | 0 |  |  |  | 6 | 30709
2PEN-64 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-12 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4WTF-60 | RFS.130 | M-M-H | BAU | Design |  | 2017-10-17 | Yes | Design | Completed | 2017-12-28 | [7 empty] | Divyamol James | Haritha | FTTN/FTTB | Completed | 2017-12-28 | 2018-01-05 | 2018-01-05 |  | 2 Jan:FTTN active N51 request has raised 2 Jan:FTTB Active N52 request work started
4APL-60 | RFS.125 | M-A-H | BAU | Pre-AT |  | 2017-10-18 | Yes | Design | On Hold - Awaiting Upstream team Updates | 2017-11-28 | Brinson Bovas | On Hold - Awaiting Upstream team Updates | 2017-11-29 |  |  |  | -30735 | Geethu Mol AG |  | FTTN | Completed | 2017-10-23 | 2017-10-24 | 2017-10-24 | 2 | HFC load is not handed over by DESG as of 24-Oct-17 and hence not able to complete handover. 01-Dec : 7 Extra MPS found in PNI which is affecting trace. Issue raised. Awaiting response. 4-Dec: Received response to delete the 7 MPS boundaries and proceed. 5-Dec: SAM on Hold because of the P-ONSA design gaps (P-ONSA failing to meet 98% trace) |  |  |  |  | 1 | 0 | -27 | 0 |  |  |  | -30734 | -30708
2LIV-67 | RFS.125 | M-M-H(P) | BAU | Design |  | 2017-12-07 | Yes | Design | On Hold - Awaiting Upstream team Updates | 2017-10-24 | [6 empty] | 0 | Haritha |  | FTTN | On Hold - Awaiting Upstream team Updates | 2017-10-25 |  |  | -30711 | This is marked as on-hold on 25-Oct as we are awaiting DFN termination details. |  |  | 2017-10-25 |  | -30711 | 0 | 1 | -30711 |  |  |  | -30710 | 30711
2BAN-69 | RFS.103 | M-A-Q | HAC | Pre-AT |  | 2017-10-13 | Yes | Pre-AT | Completed | 2017-10-13 | Dona Babu | Completed | 2017-10-13 | 2017-10-23 |  | 2017-10-23 | 6 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30705 | 0 |  |  |  | 6 | 30711
2PNN-68 | RFS.104 | M-A-H | BAU | Pre-AT |  | 2017-10-16 |  |  | Completed | 2017-10-12 | Reshma Rajan | Completed | 2017-10-17 | 2017-10-20 |  | 2017-10-20 | 3 | [7 empty] | 0 | [5 empty] | 3 | 0 | -30704 | 0 |  |  |  | 6 | 30707
4CPR-63 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-10-16 | No |  | Completed | 2017-10-12 | Aswathy Baby | Completed | 2017-10-16 | 2017-10-24 |  | 2017-10-24 | 6 | [7 empty] | 0 | [5 empty] | 2 | 0 | -30704 | 0 |  |  |  | 8 | 30710
2STL-61 | RFS.104 | M-M-Q | HAC | Pre-AT |  | 2017-10-24 | Yes | Pre-AT | Completed | 2017-10-20 | Siva Kumar | Completed | 2017-10-23 | 2017-10-30 |  | 2017-10-30 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30709 | 0 |  |  |  | 7 | 30715
3OAK-61 | RFS.105 | M-A-H | BAU | Pre-AT |  | 2017-10-18 |  |  | Completed | 2017-10-17 | Swathi JS | Completed | 2017-10-19 | 2017-10-25 |  | 2017-10-25 | 5 |  | Alphy Manuel | FTTB | Completed | 2017-12-13 | 2017-12-15 | 2017-12-15 | 3 | [5 empty] | 1 | 0 | 39 | 0 |  |  |  | 6 | -34
2PYM-61 | RFS.125 | M-M-H | BAU | Design |  | 2017-10-18 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3CAU-64 | RFS.103 | H-A-Q | HAC | Pre-AT |  | 2017-10-20 | No |  | Completed | 2017-10-17 | Haritha | Completed | 2017-10-19 | 2017-10-25 |  | 2017-10-25 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30707 | 0 |  |  |  | 6 | 30712
5BRI-65 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-20 | No |  | Completed | 2017-10-16 | Brinson Bovas | Completed | 2017-10-17 | 2017-10-24 |  | 2017-10-24 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30706 | 0 |  |  |  | 6 | 30711
2ROS-66 | RFS.134 | H-A-Q | HAC | Pre-AT |  | 2017-10-20 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2PET-64 | RFS.108 | M-M-H | BAU | Design |  | 2017-10-23 | Yes | Design | Completed | 2017-11-09 | Arya PS | Completed | 2017-11-10 | 2017-11-21 |  | 2017-11-21 | 8 | Latheefa Ul |  | FTTB | Completed | 2017-10-19 | 2017-10-20 | 2017-10-20 | 2 | HFC part - waiting for NEO acceptance on tap upliftment.Went on hold on 14-Nov-17. |  |  |  |  | 1 | 0 | -16 | 0 |  |  |  | 9 | 24
3BAY-65 | RFS.126 | H-A-Q | HAC | Pre-AT |  | 2017-10-23 | No |  | Completed | 2017-10-23 | Dona Babu | Completed | 2017-10-24 | 2017-10-31 |  | 2017-10-31 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30710 | 0 |  |  |  | 7 | 30716
4SSB-62 | RFS.126 | H-A-Q | HAC | Pre-AT |  | 2017-10-24 | No |  | Completed | 2017-10-23 | Divyamol James | Completed | 2017-10-24 | 2017-10-27 |  | 2017-10-27 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30710 | 0 |  |  |  | 5 | 30714
4ABO-67 |  | H-A-Q | HAC | Pre-AT |  | 2017-10-30 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4SSB-60 | RFS.126 | M-A-Q | HAC | Pre-AT |  | 2017-10-25 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3OAK-64 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-26 | No |  | Completed | 2017-10-26 | Latheefa Ul | Completed | 2017-10-27 | 2017-11-15 |  | 2017-11-15 | 13 | [7 empty] | 0 | Expecting a updated NDD with missing Node OA19 only on Mon(20th Nov). So this needs to be paused for now.Latest Document avaliable on 13-NOV-17. Went on hold on 1-Nov.Resumed working on 14th Nov |  |  |  |  | 1 | 0 | -30713 | 0 |  |  |  | 14 | 30726
4SLA-70 | RFS.108 | M-B-H | BAU | Pre-AT |  | 2017-10-26 | Yes | Pre-AT | Completed | 2017-10-25 |  | NA | NA | NA |  | NA | #VALUE! | Haritha |  | FTTN | Completed | 2017-10-26 | 2017-11-01 | 2017-11-01 | 5 | [5 empty] | #VALUE! | 0 | 1 | 0 |  |  |  | #VALUE! | #VALUE!
3NBA-67 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-10-17 | Yes | Design | On Hold - HFC Completed | 2017-10-25 | Midhun RaJ | Completed | 2017-10-26 | 2017-10-31 |  | 2017-10-31 | 4 | Sanjo Lopez | Alphy Manuel | FTTN/FTTB | On Hold - Awaiting Upstream team Updates | 2017-10-26 |  |  | -30712 | DFN Termination missing. |  |  |  |  | 1 | 0 | 1 | 0 |  |  |  | 5 | 3
3MLN-61 | RFS.103 | M-M-Q | BAU | Design |  | 2017-10-25 | Yes | Design | Completed | 2017-12-08 | NA | Not Applicable |  |  |  |  | 0 |  | Nayana Anilkumar | FTTB | Completed | 2017-12-08 | 2017-12-11 |  | -30742 | [5 empty] | -30743 | 0 | 0 | 0 |  |  |  | -30742 | 1
3MLN-62 | RFS.125 | M-M-Q | BAU | Design |  | 2017-10-25 | Yes | Design | Completed | 2017-11-03 | NA | Not Applicable |  |  |  |  | 0 |  | Aparna Nampoothiri | FTTB | Completed | 2017-11-08 | 2017-11-14 | 2017-11-14 | 5 | [5 empty] | -30719 | 0 | 2 | 0 |  |  |  | -30718 | -1
2CRR-65 | RFS.105 | M-M-H | BAU | Pre-AT |  | 2017-10-26 | Yes | Pre-AT | Completed | 2017-10-25 | Geethu Mol AG | Completed | 2017-10-26 | 2017-11-01 |  | 2017-11-01 | 5 | Swathi JS |  | FTTN | Completed | 2017-10-26 | 2017-11-01 | 2017-11-01 | 5 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 6 | 4
5FLN-62 | RFS.105 | H-B-J | BAU | Pre-AT |  | 2017-10-27 |  |  | Completed | 2017-10-26 | Reshma Rajan | Completed | 2017-10-26 | 2017-11-02 |  | 2017-11-02 | 6 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30713 | 0 |  |  |  | 6 | 30719
2BON-64 | RFS.104 | M-A-H | BAU | Pre-AT |  | 2017-10-27 |  |  | Completed | 2017-10-24 | Aswathy Baby | Completed | 2017-10-24 | 2017-10-30 |  | 2017-10-30 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30711 | 0 |  |  |  | 5 | 30716
2PNN-62 | RFS.108 | H-M-Q | HAC | Pre-AT |  | 2017-10-27 | No |  | Completed | 2017-10-25 | Latheefa Ul | Completed | 2017-10-25 | 2017-10-27 |  | 2017-10-27 | 3 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30712 | 0 |  |  |  | 3 | 30715
2UND-62 | RFS.108 | H-M-Q | HAC | Pre-AT |  | 2017-10-27 |  |  | Completed | 2017-10-30 | Sruthi James | Completed | 2017-10-30 | 2017-11-03 |  | 2017-11-03 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30715 | 0 |  |  |  | 5 | 30720
4SSB-60 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-10-27 | Yes |  | On Hold - HFC Completed | 2017-10-31 | Siva kumar | Completed | 2017-10-31 | 2017-11-07 |  | 2017-11-07 | 5 |  | Gouri Gopal | FTTB | On Hold - Document Unavailability | 2017-11-02 |  |  | -30717 | Placed on hold on 6-Nov-17 due to missing MPS package MPS-165. |  |  |  |  | 0 | 0 | 2 | 0 |  |  |  | 5 | 3
2PAR-63 | RFS.125 | H-A-Q | HAC | Pre-AT |  | 2017-10-27 | No |  | Completed | 2017-11-06 | Haritha | Completed | 2017-11-08 | 2017-11-15 |  | 2017-11-15 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30720 | 0 |  |  |  | 7 | 30726
3RWO-66 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-10-30 | Yes | Design | Completed | 2017-10-30 | Midhun RaJ | Completed | 2017-11-01 | 2017-11-07 |  | 2017-11-07 | 4 |  | Jijin Isaac | FTTB | Completed | 2017-10-31 | 2017-11-09 | 2017-11-09 | 7 | DFN splice was missing in PNI |  |  |  |  | 2 | 0 | 1 | 0 |  |  |  | 6 | 3
3DAD-64 | RFS.107 | M-M-H | BAU | Design |  | 2017-10-27 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
6GIR-60 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-30 | No |  | Completed | 2017-10-26 | Roshni Johns | Completed | 2017-10-27 | 2017-11-02 |  | 2017-11-02 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30713 | 0 |  |  |  | 6 | 30718
6KSL-61 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-30 | No |  | Completed | 2017-10-31 | Karishma | Completed | 2017-10-31 | 2017-11-03 |  | 2017-11-03 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30716 | 0 |  |  |  | 4 | 30720
3KYG-66 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-10-30 | No |  | Completed | 2017-10-31 | Aswathy Baby | Completed | 2017-10-31 | 2017-11-07 |  | 2017-11-07 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30716 | 0 |  |  |  | 5 | 30721
4SRW-66 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-10-30 | Yes | Design | On Hold - HFC Completed | 2017-10-31 | Nayana Anilkumar | Completed | 2017-10-31 | 2017-11-07 |  | 2017-11-07 | 5 |  | Sanjo Lopez | FTTB | On Hold - Awaiting Upstream team Updates |  |  |  | 0 | [5 empty] | 0 | 0 | -30716 | 0 |  |  |  | 5 | 30721
3SPL-62 | RFS.120 | M-M-Q | HAC | Pre-AT |  | 2017-11-01 | No | Pre-AT | Completed | 2017-11-01 | Haritha | Completed | 2017-11-02 | 2017-12-08 |  | 2017-12-08 | 26 | [7 empty] | 0 | 7th Nov: Went on hold on. Tap Upliftment confirmation was pending from NA and NEO. 14th Nov: Got response from NA. Not resumed since no resources were available. 15th: NEO responded not agreeing to NAs response 30 Nov: Resumed work on SAM execution | 2017-11-01 | 2017-11-30 |  |  | 1 | 21 | -30717 | 0 |  |  |  | 27 | 30722
4SRW-62 | RFS.108 | M-A-Q | HAC | Pre-AT |  | 2017-11-08 | Yes | Design | On Hold - HFC Completed | 2017-11-09 | Latheefa Ul | Completed | 2017-11-09 | 2017-11-27 |  | 2017-11-27 | 13 |  | Sanjo Lopez | FTTB | On Hold - Document Unavailability | 2017-11-10 |  |  | -30722 | Waiting for the updated NDD Document since Node is missing in the document , went on Hold on 13-Nov-17 1 FTTB Planned. DFN Termination details missing. Communication sent. |  |  |  |  | 0 | 0 | 1 | 0 |  |  |  | 13 | 12
4SSB-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-11-01 | Yes | Design | Completed | 2017-10-31 | Dona Babu | Completed | 2017-10-31 | 2017-11-07 |  | 2017-11-07 | 5 | Nayana Anilkumar |  | FTTN | Completed | 2017-11-02 | 2017-11-09 | 2017-11-09 | 5 | [5 empty] | 0 | 0 | 2 | 0 |  |  |  | 5 | 3
4MGB-01 | RFS.106 | M-B-H | BAU | Pre-AT |  | 2017-11-01 | Yes | Pre-AT | Completed | 2017-11-06 |  | Not Applicable |  |  |  |  | 0 | Dona Babu |  | FTTN | Completed | 2017-11-08 | 2017-11-21 | 2017-11-21 | 10 | 13-Nov-17 : Outstanding T18 data issues. Raised issues to Nathan.Placed on hold. 20-Nov-17: Response received from Indika and re-started working |  |  | 2017-11-10 | 2017-11-17 | -30720 | 0 | 1 | 6 |  |  |  | -30719 | -6
2LIV-63 | RFS.118 | M-M-H | BAU | Design |  | 2017-10-31 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
6GIR-68 | RFS.116 | M-A-H | BAU | Pre-AT |  | 2017-11-01 | Yes | Design | Completed | 2017-12-25 | Aparna Nampoothiri | Completed | 2017-12-27 | 2018-01-02 |  | 2018-01-02 | 4 | Midhun RaJ | Swathi JS | FTTN/FTTB | Completed | 2018-01-02 | 2018-01-03 | 2018-01-03 | 2 | 29-Dec : FTTB Active NDD completed. |  |  |  |  | 0 | 0 | 3 | 0 |  |  |  | 4 | 1
2FRE-61 | RFS.104 | M-A-H | BAU | Pre-AT |  | 2017-10-27 | Yes | Pre-AT | Completed | 2017-10-17 | Nayana Anilkumar | Completed | 2017-10-18 | 2017-10-23 |  | 2017-10-23 | 3 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30707 | 0 |  |  |  | 4 | 30711
2PET-68 | RFS.131 | M-M-H | BAU | Design |  | 2017-11-01 | Yes | Design | Completed | 2017-11-13 | NA | Not Applicable |  |  |  |  | 0 | Aswathy Baby |  | FTTN | Completed | 2017-11-16 | 2017-11-23 | 2017-11-23 | 6 | [5 empty] | -30724 | 0 | 3 | 0 |  |  |  | -30723 | -2
2PYM-64 | RFS.136 | M-M-H | BAU | Design |  | 2017-11-09 | Yes | Design | On Hold - Document Unavailability | 2017-12-01 | NA | Not Applicable |  |  |  |  | 0 | Gouri Gopal | Latheefa Ul | FTTN/FTTB | On Hold - Document Unavailability | 2017-12-04 |  |  | -30738 | 04-Dec: FTTN Active NDD started 6-Dec: 3 MPS package are missing in connect MTM so 4 FTTB creation are pending 11-Dec: FTTN part completed. |  |  |  |  | -30738 | 0 | 1 | 0 |  |  |  | -30737 | 0
4FHL-61 | RFS.122 | M-A-Q | HAC | Pre-AT |  | 2017-11-02 | Yes | Design | On Hold – HFC Completed | 2017-11-13 | Sruthi James | Completed | 2017-11-13 | 2017-11-20 |  | 2017-11-20 | 6 |  |  | FTTB | On Hold - Document Unavailability |  |  |  | 0 | 6-Nov: HFC part is pending with DESG team as DESG will be re-running load activities due to duplicate support structure issues.Went on hold. 13 Nov: DESG again released to DSG and restarted HFC execution |  |  |  |  | 0 | 0 | -30724 | 0 |  |  |  | 6 | 30730
4AAR-61 | RFS.103 | M-A-H | BAU | Pre-AT |  | 2017-11-01 | Yes | Design | Completed | 2017-10-30 | Brinson Bovas | Completed | 2017-10-30 | 2017-11-03 |  | 2017-11-03 | 5 |  | Latheefa Ul | FTTB | Completed | 2017-10-30 | 2017-11-02 | 2017-11-02 | 4 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 5 | 5
2STL-66 | RFS.104 | M-A-Q | HAC | Pre-AT |  | 2017-11-02 | Yes | Pre-AT | Completed | 2017-10-26 | Arya PS | Completed | 2017-10-27 | 2017-11-02 |  | 2017-11-02 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30713 | 0 |  |  |  | 6 | 30718
5FLN-60 | RFS.107 | H-B-J | BAU | Pre-AT |  | 2017-11-09 | No |  | Completed | 2017-11-03 | Karishma | Completed | 2017-11-06 | 2017-11-15 |  | 2017-11-15 | 7 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30719 | 0 |  |  |  | 8 | 30726
3TYH-61 | RFS.118 | M-M-H | BAU | Design |  | 2017-11-02 | Yes | Design | Completed | 2017-11-13 | NA | Not Applicable |  |  |  |  | 0 | Arya PS | Midhun RaJ | FTTN/FTTB | Completed | 2017-11-15 | 2017-11-23 | 2017-11-23 | 7 | 15-Nov-2017: Midhun started working on FTTB and Arya on FTTN 16-Nov-2017: FTTB Handover done by Midhun. FTTN part de-deprioritized and put on hold 21-Nov-2017:Arya resumed working on FTTN part 23-Nov-2017: FTTN part handover done |  |  |  |  | -30724 | 0 | 2 | 0 |  |  |  | -30723 | -1
3CLA-68 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-11-03 | No |  | Completed | 2017-10-31 | Divyamol James | Completed | 2017-11-01 | 2017-11-07 |  | 2017-11-07 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30716 | 0 |  |  |  | 5 | 30720
2ING-65 | RFS.130 | M-M-H | BAU | Design |  | 2017-11-02 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2SHA-21 | RFS.137 | M-M-H | BAU | Design |  | 2017-11-02 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2CYS-63 | RFS.105 | M-B-H | BAU | Design |  | 2017-11-02 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4FHL-20 | RFS.108 | M-B-H | BAU | Pre-AT |  | 2017-11-03 | Yes | Pre-AT | Completed | 2017-11-16 | [6 empty] | 0 | Latheefa Ul |  | FTTN | Completed | 2017-11-16 | 2017-11-22 | 2017-11-22 | 5 | [5 empty] | -30727 | 0 | 0 | 0 |  |  |  | -30726 | 1
3HGT-67 | RFS.116 | H-A-Q | HAC | Pre-AT |  | 2017-11-06 | No |  | Completed | 2017-11-06 | Siva kumar | Completed | 2017-11-07 | 2017-11-13 |  | 2017-11-13 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30720 | 0 |  |  |  | 5 | 30725
6SUB-66 | RFS.127 | M-M-H | BAU | Design |  | 2017-11-09 | Yes | Design | Completed | 2017-11-23 | NA | Not Applicable |  |  |  |  | 0 | Aparna Nampoothiri | Shankar Venkatesan | FTTN/FTTB | Completed | 2017-11-28 | 2017-12-06 | 2017-12-06 | 7 | 28 Nov: Awaiting for updated Site design Document and SLD from NA team 4 Dec: Updated SLD and site document got from NA. SAM execution resumed |  |  |  |  | -30732 | 0 | 3 | 0 |  |  |  | -30731 | -2
3WIR-69 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-11-06 | No |  | Completed | 2017-11-03 | Roshni johns | Completed | 2017-11-06 | 2017-11-10 |  | 2017-11-10 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30719 | 0 |  |  |  | 5 | 30723
2ROS-67 | RFS.135 | H-A-Q | HAC | Pre-AT | 2 | 2017-11-13 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
5NRW-63 | RFS.118 | M-A-Q | HAC | Pre-AT |  | 2018-01-30 | Yes | Design | On Hold - HFC Completed | 2017-11-07 | Divyamol James | Completed | 2017-11-08 | 2017-11-14 |  | 2017-11-14 | 5 |  | Latheefa Ul | FTTB | On Hold - Document Unavailability | 2017-11-15 |  |  | -30725 | FTTB paused on 15-Nov-17 due to missing MPS package 5NRW-63-00-MPS-166 |  |  | 2017-11-15 |  | 0 | 0 | 5 | -30725 |  |  |  | 5 | 30725
2PEN-67 | RFS.105 | H-A-Q | HAC | Pre-AT |  | 2017-11-07 | No |  | Completed | 2017-11-06 | Shankar venkatesan | Completed | 2017-11-08 | 2017-11-13 |  | 2017-11-13 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30720 | 0 |  |  |  | 5 | 30724
4CHD-61 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-07 | yes | Design | Completed | 2017-11-13 | Roshni Johns | Completed | 2017-11-13 | 2017-11-20 |  | 2017-11-20 | 6 | Alphy Manuel | Siva Kumar | FTTN/FTTB | Completed | 2017-11-14 | 2017-11-22 | 2017-11-22 | 7 | 14 Nov: DFN termination missing.Issue rasied. 16-Nov: All runsheet activities completed except FAN side splicing. On hold 20-Nov: Got response from DFN team. But new issues found related to FAN side splicing 22-Nov: Raised issue to DFN team and got response. Hnadover done |  |  | 2017-11-16 | 2017-11-22 | 0 | 0 | 1 | 5 |  |  |  | 6 | 0
4CHP-66 | RFS.108 | M-B-H | BAU | Pre-AT |  | 2017-11-07 | Yes | Pre-AT | Completed | 2017-11-08 | [6 empty] | 0 | Nayana Anilkumar |  | FTTN | Completed | 2017-11-09 | 2017-11-15 | 2017-11-15 | 5 | For the SAM 4CHP-66 the data present in integration work book is not accurate. In Serial numbers sheet Node ID column is having DSL instead of FNO. Went on hold on 14-Nov-17. |  |  |  |  | -30721 | 0 | 1 | 0 |  |  |  | -30720 | 0
2HUR-62 | RFS.108 | H-A-Q | HAC | Pre-AT |  | 2017-11-07 | No |  | Completed | 2017-11-07 | Reshma Rajan | Completed | 2017-11-07 | 2017-11-13 |  | 2017-11-13 | 4 | [7 empty] | 0 | [5 empty] | -1 | 0 | -30720 | 0 |  |  |  | 4 | 30725
6WMB-61 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-11-10 | No |  | Completed | 2017-11-13 | Swathi JS | Completed | 2017-11-13 | 2017-11-17 |  | 2017-11-17 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30724 | 0 |  |  |  | 5 | 30729
5BRI-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | 2017-11-07 | No |  | Completed | 2017-11-03 | Sruthi james | Completed | 2017-11-06 | 2017-11-13 |  | 2017-11-13 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30719 | 0 |  |  |  | 6 | 30724
3NES-62 | RFS.124 | H-A-Q | HAC | Pre-AT |  | 2017-11-07 | No |  | Completed | 2017-11-13 | Shankar Venkatesan | Completed | 2017-11-14 | 2017-11-21 |  | 2017-11-21 | 6 | [7 empty] | 0 | 15 Nov: Raised AP issue 17 Nov: Got response after folllow up 20 Nov: Issue was not completely resolved. Rasied again to AP |  |  |  |  | 1 | 0 | -30724 | 0 |  |  |  | 7 | 30730
5NRW-60 | RFS.120 | H-A-Q | HAC | Pre-AT |  | 2017-11-07 | No |  | Completed | 2017-11-13 | Karishma | Completed | 2017-11-13 | 2017-11-21 |  | 2017-11-21 | 7 |  |  |  |  | 2017-11-08 |  |  | -30720 | 17 Nov: AP issues popped up again today. H/o Not done due to this issue. Issue raised to AP team 20 Nov: Got response from AP "The boundary has been locked in BM". Asked for ETA to AP 21 Nov: Got response from AP |  |  |  |  | 0 | 0 | -5 | 0 |  |  |  | 7 | 12
5NRW-64 | RFS.120 | M-A-H | BAU | Pre-AT |  | 2017-11-09 | Yes | Design | Completed | 2017-11-28 | Dona Babu | Completed | 2017-11-28 | 2017-12-04 |  | 2017-12-04 | 5 | Karishma |  | FTTN | Completed | 2017-11-28 | 2017-11-30 | 2017-11-30 | 3 | 28-Nov : More than 1 ON serving for two ADA. Send mail for AP Team 29-Nov : Reminder sent but yet to receive response. 01-Dec:Received response from AP |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 5 | 5
4SOP-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-07 |  |  | Completed | 2017-11-02 | Arya PS | Completed | 2017-11-03 | 2017-11-09 |  | 2017-11-09 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30718 | 0 |  |  |  | 5 | 30722
2PYM-62 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-07 | Yes | Pre-AT | Completed | 2017-11-02 | Geethu Mol AG | Completed | 2017-11-02 | 2017-11-08 |  | 2017-11-08 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30718 | 0 |  |  |  | 4 | 30722
2ING-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-07 | yes | Pre-AT | Completed | 2017-11-02 | Alphy Manuel | Completed | 2017-11-02 | 2017-11-08 |  | 2017-11-08 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30718 | 0 |  |  |  | 4 | 30722
6GIR-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-07 | Yes | Pre-AT | Completed | 2017-11-01 | Haritha | Completed | 2017-11-01 | 2017-11-07 |  | 2017-11-07 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30717 | 0 |  |  |  | 4 | 30721
4BUR-67 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-10 | No |  | Completed | 2017-11-20 | Divyamol James | Completed | 2017-11-20 | 2017-11-24 |  | 2017-11-24 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30729 | 0 |  |  |  | 5 | 30734
4CPR-60 | RFS.108 | M-A-H | BAU | Pre-AT | 1 | 2017-11-08 | yes | Design | On Hold - HFC Completed | 2017-11-13 | Geethu Mol AG | Completed | 2017-11-14 | 2017-11-17 |  | 2017-11-17 | 4 |  | Gouri Gopal | FTTB | On Hold - Document Unavailability | 2017-11-14 |  |  | -30724 | MPS Package misssing |  |  |  |  | 1 | 0 | 1 | 0 |  |  |  | 5 | 3
2PET-64 | RFS.108 | M-M-H | BAU | Pre-AT | 1 | 2017-11-08 | yes | Pre-AT | Completed | 2017-11-10 | Arya PS | Completed | 2017-11-10 | 2017-11-21 |  | 2017-11-21 | 8 |  | Alphy Manuel | FTTB | Completed | 2017-11-13 | 2017-11-21 | 2017-11-21 | 7 | 14-Nov-17 :went on hold sue to TAP upliftment issues. Agreement pending from NA-NEO 21 Nov: NA and NEO agreed upon a solution for the issue | 2017-11-17 | 2017-11-20 |  |  | 0 | 2 | 1 | 0 |  |  |  | 8 | 5
3MIT-60 | RFS.106 | M-M-Q | HAC | Pre-AT | 1 | 2017-11-08 | Yes | Design | Completed | 2017-11-06 | Aswathy Baby | Completed | 2017-11-07 | 2017-11-14 |  | 2017-11-14 | 5 |  | Anju Philip | FTTB | Completed | 2017-11-13 | 2017-11-15 | 2017-11-15 | 3 | [5 empty] | 0 | 0 | 4 | 0 |  |  |  | 6 | 2
2PAR-62 | RFS.125 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-08 | No |  | Completed | 2017-11-17 | Reshma T V | Completed | 2017-11-20 | 2017-11-27 |  | 2017-11-27 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30728 | 0 |  |  |  | 7 | 30734
2PYM-63 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | 2017-11-08 | yes | Design | On Hold - HFC Completed | 2017-11-07 | Midhun RaJ | Completed | 2017-11-08 | 2017-11-14 |  | 2017-11-14 | 5 |  | Alphy Manuel | FTTB | On Hold - Document Unavailability | 2017-11-08 |  |  | -30720 | 09-Nov-2017:FTTB part on hold due to missing MPS file |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 5 | 5
3TYH-69 | RFS.116 | M-M-H | BAU | Design | 1 | 2017-11-09 | Yes | Design | Completed | 2017-11-10 | NA | Not Applicable |  |  |  |  | 0 | Reshma T V |  | FTTN | Completed | 2017-11-15 | 2017-11-17 | 2017-11-17 | 3 | [5 empty] | -30723 | 0 | 3 | 0 |  |  |  | -30722 | -2
4AGV-62 | RFS.107 | M-A-H | BAU | Pre-AT | 1 | 2017-11-09 | Yes | Design | Completed | 2017-11-03 | Reshma T V | Completed | 2017-11-06 | 2017-11-14 |  | 2017-11-14 | 6 | Gouri Gopal | Anju Philip | FTTN/FTTB | Completed | 2017-11-09 | 2017-11-14 | 2017-11-14 | 4 | FTTB part started on 08-Nov-2017 |  |  |  |  | 1 | 0 | 3 | 0 |  |  |  | 7 | 3
2HLS-61 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | 2017-11-09 |  |  | Completed | 2017-11-03 | Swathi JS | Completed | 2017-11-06 | 2017-11-10 |  | 2017-11-10 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30719 | 0 |  |  |  | 5 | 30723
2LIV-66 | RFS.118 | M-M-H | BAU | Design | 1 | 2017-11-09 | Yes | Design | Completed | 2017-11-20 | NA | Not Applicable |  |  |  |  | 0 | Brinson Bovas |  | FTTN | Completed | 2017-11-23 | 2017-11-27 | 2017-11-27 | 3 | [5 empty] | -30729 | 0 | 3 | 0 |  |  |  | -30728 | -2
4ASH-64 | RFS.113 | H-A-H | BAU | Pre-AT | 1 | 2017-11-09 |  |  | Completed | 2017-11-21 | Karishma | Completed | 2017-11-22 | 2017-11-27 |  | 2017-11-27 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30730 | 0 |  |  |  | 5 | 30734
4FHL-62 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-10 | No |  | Completed | 2017-11-17 | Sanjo Lopez | Completed | 2017-11-21 | 2017-11-27 |  | 2017-11-27 | 5 | [7 empty] | 0 | [5 empty] | 2 | 0 | -30728 | 0 |  |  |  | 7 | 30733
6GIR-65 | RFS.143 | M-M-H | BAU | Design | 1 | 2017-11-10 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4SOP-65 | RFS.110 | M-A-H | BAU | Pre-AT |  | 2017-11-21 | No |  | Completed | 2017-11-15 | Haritha | Completed | 2017-11-16 | 2017-11-22 |  | 2017-11-22 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30726 | 0 |  |  |  | 6 | 30731
5NRW-62 | RFS.110 | M-A-H | BAU | Pre-AT |  | 2017-11-14 | Yes | Design | On Hold - HFC Completed | 2017-11-16 | Midhun RaJ | Completed | 2017-11-17 | 2017-11-23 |  | 2017-11-23 | 5 |  | Midhun RaJ | FTTB | On Hold - Awaiting Upstream team Updates |  |  |  | 0 | 17-Nov: Raised issues to AP 20-Nov:Got response from AP "The boundary has been locked in BM" 21-Nov:Got Response from AP 22-Nov: MPS package missing for FTTN Active NDD. |  |  |  |  | 1 | 0 | -30727 | 0 |  |  |  | 6 | 30732
2NEW-63 | RFS.139 | M-M-H | BAU | Design |  | 2017-11-21 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4EMP-25 | RFS.108 | M-B-H | BAU | Pre-AT |  | 2017-11-14 | Yes | Pre-AT | Completed | 2017-11-14 | NA | Not Applicable |  |  |  |  | 0 | Haritha |  | FTTN | Completed | 2017-11-23 | 2017-11-29 | 2017-11-29 | 5 | 16-Nov-17:Incorrect payload version used to promote GML to PNI. Waiting for confirmation from NA and DESG needs to re-promote the latest GML. FTTN put on hold. 23-Nov: Relaunch as BAU has progressed into IAB bucket. |  |  |  |  | -30725 | 0 | 7 | 0 |  |  |  | -30724 | -6
2HUR-64 | RFS.108 | M-M-Q | BAU | Design |  | 2017-11-22 | Yes | Design | [8 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4CUR-60 | RFS.108 | M-A-Q | HAC | Pre-AT |  | 2017-11-15 | Yes | Design | Completed | 2017-11-16 | Nayana Anilkumar | Completed | 2017-11-16 | 2017-11-22 |  | 2017-11-22 | 5 |  | Divyamol James | FTTB | Completed | 2017-11-16 | 2017-11-17 | 2017-11-17 | 2 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 5 | 5
4NDG-62 | RFS.127 | H-A-Q | HAC | Pre-AT |  | 2017-11-15 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4WTF-65 | RFS.136 | M-M-H | BAU | Design |  | 2017-11-23 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
5WES-62 | RFS.108 | H-A-Q | HAC | Pre-AT |  | 2017-11-17 | No |  | Completed | 2017-11-17 | Siva Kumar | Completed | 2017-11-20 | 2017-11-24 |  | 2017-11-24 | 5 | [7 empty] | 0 | 21-Nov: 4 Extra HFC Locations of SC21 present in PNI. Mail sent to LMS team 22-Nov: Got response from LMS |  |  |  |  | 1 | 0 | -30728 | 0 |  |  |  | 6 | 30733
4CHD-21 | RFS.109 | M-A-H | BAU | Pre-AT |  | 2017-11-17 | No |  | Completed | 2017-11-17 | Geethu Mol AG | Completed | 2017-11-24 |  |  | 2017-11-24 | 1 | [7 empty] | 0 | [5 empty] | 5 | 0 | -30728 | 0 |  |  |  | 6 | 30729
5WES-61 | RFS.108 | M-M-H | BAU | Pre-AT |  | 2017-11-17 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4OXE-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | 2017-11-16 | No |  | Completed | 2017-11-16 | Reshma Rajan | Completed | 2017-11-16 | 2017-11-22 |  | 2017-11-22 | 5 | [7 empty] | 0 | There was a rework done by DESG as the completed list sent by LDM was not incorporated. Handed over to DSG on 16-Nov-17 and from then on DSG continued execution of rest of the runsheet activities. |  |  |  |  | 0 | 0 | -30727 | 0 |  |  |  | 5 | 30732
3CAU-67 | RFS.111 | H-A-Q | HAC | Pre-AT |  | 2017-11-09 | No |  | Completed | 2017-11-21 | Swathi JS | Completed | 2017-11-22 | 2017-11-27 |  | 2017-11-27 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30730 | 0 |  |  |  | 5 | 30734
3CAN-64 | RFS.120 | H-A-Q | HAC | Pre-AT |  | 2017-11-23 | No |  | Completed | 2017-11-20 | Roshni Johns | Completed | 2017-11-21 | 2017-11-28 |  | 2017-11-28 | 6 | [7 empty] | 0 | 21 Nov: Extra lcoation issue raised to LM 22 Nov: Got response from LMS |  |  |  |  | 1 | 0 | -30729 | 0 |  |  |  | 7 | 30735
4CHL-70 | RFS.130 | M-A-H | BAU | Pre-AT |  | 2017-11-20 | Yes | Pre-AT | Completed | 2017-11-27 | Reshma T V | Completed | 2017-11-28 | 2017-12-29 |  | 2017-12-29 | 22 | Brinson Bovas |  | FTTN | Completed | 2017-11-28 | 2017-12-07 | 2017-12-07 | 8 | 28-Nov : NDD doc missing in connect MTM for this SAM. Mail has been sent by DESG to Thanh. Waiting for response. 29-Nov: 20% completed. Brinson to take up 4APL-60 on high priority keeping FTTN of 4CHL-70 on hold 30-Nov-17 :Got confirmation from Ray Hart that the latest NDD will be aailable only on 19-Dec, hence putting the HFC part on hold. 6-Dec: ACtive NDD work resumed 27-Dec: NDD made available. Resumed HFC. | 2017-11-30 |  | 2017-11-29 | 2017-12-06 | 1 | -30736 | 1 | 6 |  |  |  | 23 | 30751
2CRR-66 | RFS.116 | M-M-H | BAU | Design |  | 2017-11-20 | Yes | Design | Completed | 2017-11-17 |  | Not Applicable |  |  |  |  | 0 | Dona Babu |  | FTTN | Completed | 2017-11-24 | 2017-11-27 | 2017-11-27 | 2 | [5 empty] | -30728 | 0 | 5 | 0 |  |  |  | -30727 | -4
4OXE-60 | RFS.109 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-21 | No |  | Completed | 2017-11-20 | Sruthi James | Completed | 2017-11-21 | 2017-11-28 |  | 2017-11-28 | 6 | [7 empty] | 0 | 22 Nov: NAT boundary in T18 file and PNI is not matching. Reminder mail sent to AP team by DESG today. |  |  |  |  | 1 | 0 | -30729 | 0 |  |  |  | 7 | 30735
5NRW-66 | RFS.110 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-21 |  |  | Completed | 2017-11-22 | Alphy Manuel | Completed | 2017-11-23 | 2017-11-29 |  | 2017-11-30 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30731 | 0 |  |  |  | 7 | 30737
4OXE-61 | RFS.110 | M-A-H | BAU | Pre-AT | 2 | 2017-11-21 |  |  | Completed | 2017-11-24 | Aswathy Baby | Completed | 2017-11-24 | 2017-11-30 |  | 2017-11-30 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30733 | 0 |  |  |  | 5 | 30738
4FHL-60 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-27 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3SSN-61 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-22 |  |  | Completed | 2017-12-01 | Geethu Mol AG | Completed | 2017-12-04 | 2017-12-07 |  | 2017-12-07 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30738 | 0 |  |  |  | 5 | 30742
2HUR-60 | RFS.135 | M-M-Q | BAU | Design | 1 | 2017-11-29 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3TYH-66 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | 2017-11-22 | Yes | Design | Completed | 2017-12-13 | Dona Babu | Completed | 2017-12-13 | 2017-12-18 |  | 2017-12-18 | 4 | Karishma | Geethu Mol AG | FTTN/FTTB | Completed | 2017-12-13 | 2017-12-18 |  | -30745 | 14-Dec : Self intersecting loop error raised with AP team 15-Dec : FTTN Active NDD Request raised today 18-Dec : Self intersecting loop error resolved |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 4 | 4
4MRA-64 | RFS.113 | M-M-Q | HAC | Pre-AT | 0.2 | 2017-11-30 | No |  | Completed | 2017-11-23 | Nayana Anilkumar | Completed | 2017-11-23 | 2017-11-30 |  | 2017-11-30 | 6 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30732 | 0 |  |  |  | 6 | 30738
6WMB-62 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | 2017-11-24 |  |  | Completed | 2017-11-28 | Swathi JS | Completed | 2017-11-28 | 2017-12-04 |  | 2017-12-04 | 5 | [7 empty] | 0 | Only HFC available for now. Split load with FTTB on hold. 28-Nov : EXTRA ADA (which is NDS area) , mail sent to concerned team (AP Team) 01-Dec : Handover document preparation and mail needs to be sent. Rest all actions completed. 4-Dec: Midhun taking up as Swathi is on leave |  |  |  |  | 0 | 0 | -30735 | 0 |  |  |  | 5 | 30740
2RYD-65 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | 2017-11-24 | Yes | Design | In Progress | 2017-11-26 | Divyamol James | In Progress | 2017-11-27 |  |  |  | -30733 |  | Siva Kumar |  | In Progress | 2018-02-06 |  |  | -30780 | 27-Nov: Optic node ADA boundary mismatch. Awaiting response from AP 28-Nov: Awaiting response from Ahmad regarding extra HFC locations in PNI with copper tap port. Sanjo has responded – NATs are overlapping(similar to 4OXE copper design) and need to attach the email in handover. 01-Dec : To be handed over on 4-Dec after getting confirmation from NA. 04-Dec : Pending for confirmation on the tech type for 96 locations. 05-Feb : Got confirmation to proceed with this SAM as all the existing issues got rectified. | 2017-12-04 | 2018-02-06 | 2018-12-04 | 2018-02-06 | 0 | 43 | 47 | -200 |  |  |  | -30732 | -30622
3OAK-69 | RFS.137 | M-M-H | BAU | Design | 1 | 2017-11-24 | Yes | Design | Completed | 2017-12-13 | NA | Not Applicable |  |  |  |  | 0 |  | Swathi JS | FTTB | Completed | 2017-12-14 | 2017-12-18 | 2017-12-18 | 3 | [5 empty] | -30746 | 0 | 1 | 0 |  |  |  | -30745 | 0
2RYD-66 | RFS.110 | M-A-H | BAU | Pre-AT | 0.1 | 2017-11-24 |  |  | Completed | 2017-11-28 | Reshma Rajan | Completed | 2017-11-28 | 2017-12-04 |  | 2017-12-04 | 5 | [7 empty] | 0 | HFC only for now. Split load with FTTx on hold. 29-Nov:NAT-SAM overlap issue raised to AP 30-Nov:Response received from AP |  |  |  |  | 0 | 0 | -30735 | 0 |  |  |  | 5 | 30740
2PEN-65 | RFS.109 | M-M-H | BAU | Design | 0.1 | 2017-11-27 | Yes | Design | Completed | 2017-11-30 | NA | Not Applicable |  |  |  |  | 0 |  | Midhun RaJ | FTTB | Completed | 2017-11-30 | 2017-12-01 | 2017-12-01 | 2 | [5 empty] | -30737 | 0 | 0 | 0 |  |  |  | -30736 | 1
2HUR-66 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-27 |  |  | Completed | 2017-11-28 | Sanjo Lopez | Completed | 2017-11-29 | 2017-12-06 |  | 2017-12-06 | 6 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30735 | 0 |  |  |  | 7 | 30741
2EAS-69 | RFS.130 | M-M-Q | BAU | Design | 1 | 2017-11-27 | Yes | Design | On Hold - Awaiting Upstream team Updates | 2017-11-29 | [6 empty] | 0 |  | Roshni Johns | FTTB | On Hold - Awaiting Upstream team Updates | 2017-11-29 |  |  | -30735 | 1-Dec: SAM#69 is used by another SAM. Will not be available probably till Apr 2018. Complete all other activities except DFN termination connection, and put on hold. |  |  |  |  | -30736 | 0 | 0 | 0 |  |  |  | -30735 | 1
4EMP-25 | RFS.108 | M-B-H | BAU | Pre-AT | 2 | 2017-11-27 | Yes | Pre-AT | Completed | 2017-11-15 | [6 empty] | 0 | Arya PS |  |  | Completed | 2017-11-23 | 2017-11-29 | 2017-11-29 | 5 | [5 empty] | -30726 | 0 | 6 | 0 |  |  |  | -30725 | -5
4FHL-22 | RFS.141 | M-M-H | BAU | Design | 1 | 2017-11-27 | Yes | Design | Completed | 2017-12-13 | NA | Not Applicable |  |  |  |  | 0 | Divyamol James |  | FTTN | Completed | 2017-12-14 | 2017-12-18 | 2017-12-18 | 3 | 14-Dec : DFN network not fully loaded by DESG (5-DSS cables and 4-DJLs) |  |  |  |  | -30746 | 0 | 1 | 0 |  |  |  | -30745 | 0
2WRO-60 | RFS.139 | M-M-H | BAU | Pre-AT | 1 | 2017-11-27 | No |  | Completed | 2017-12-01 | Karishma | Completed | 2017-12-01 | 2017-12-07 |  | 2017-12-07 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30738 | 0 |  |  |  | 5 | 30743
5HNL-20 | RFS.153 | M-M-H | BAU | Design | 1 | 2017-11-27 | Yes | Design | On Hold - Awaiting Upstream team Updates | 2017-12-04 |  | Not Applicable |  |  |  |  | 0 | Haritha | Swathi JS | FTTN/FTTB | On Hold - Awaiting Upstream team Updates | 2017-12-05 |  |  | -30739 | 8 Dec: Awaiting for DFN termination details 12-Dec: DFN termination details were made available and FTTN active NDD was handed over. |  |  |  |  | -30739 | 0 | 1 | 0 |  |  |  | -30738 | 0
3KGP-20 | RFS.135 | M-M-Q | BAU | Design | 1 | 2017-11-27 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3HDB-68 | RFS.111 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-28 |  | Pre-AT | Completed | 2017-11-28 | Reshma T V | Completed | 2017-12-04 | 2017-12-08 |  | 2017-12-08 | 5 | [7 empty] | 0 | 28-Nov: DESG has issues with demotion of SAM, causing issues with duct-trench-cables associations etc. Awaiting proper Demotion + Promotion activity completion from DESG before taking up. 01-Dec: DESG confirmed that demotion and promotion is completed and good to resume for DSG. |  |  |  |  | 4 | 0 | -30735 | 0 |  |  |  | 9 | 30740
3TNI-62 | RFS.111 | M-A-H | BAU | Pre-AT | 1 | 2017-11-28 | No |  | Completed | 2017-11-30 | Arya PS | Completed | 2017-11-30 | 2017-12-06 |  | 2017-12-06 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30737 | 0 |  |  |  | 5 | 30742
5WES-61 | RFS.111 | M-M-H | BAU | Pre-AT | 1 | 2017-11-29 | Yes | Pre-AT | Completed | 2017-11-29 | Rahul Menon | Completed | 2017-11-30 | 2017-12-07 |  | 2017-12-07 | 6 | Alphy Manuel |  | FTTN | Completed | 2017-11-30 | 2017-12-07 | 2017-12-07 | 6 | [5 empty] | 1 | 0 | 1 | 0 |  |  |  | 7 | 5
3CAU-66 | RFS.125 | M-M-Q | BAU | Design | 3 | 2017-11-02 | Yes | Design | Completed |  | NA | [5 empty] | 0 |  | Anju Philip | FTTB | Completed | 2018-01-01 | 2018-01-04 | 2018-01-04 | 3 | [5 empty] | -1 | 0 | 30754 | 0 |  |  |  | 0 | -30753
2SHA-21 | RFS.137 | M-M-H | BAU | Design | 0.1 | 2017-11-30 | Yes | Design | Completed | 2017-12-04 | NA | Not Applicable |  |  |  |  | 0 | Siva Kumar |  | FTTN | Completed | 2017-12-05 | 2017-12-13 | 2017-12-13 | 7 | 7 Dec: Awaiting for DFN termination details 13-Dec : Response received ,SAM name changed from 2SHA-21 from 66 . DFN details for SHA-66 is availble |  |  |  |  | -30739 | 0 | 1 | 0 |  |  |  | -30738 | 0
2KNS-61 | RFS.111 | M-A-H | BAU | Pre-AT | 0.1 | 2017-12-07 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2LIV-67 | RFS.125 | M-M-H | BAU | Design | 5 | 2017-12-07 | Yes | Design | Completed | 2017-12-11 | NA | Not Applicable |  |  |  |  | 0 | Reshma T V |  | FTTN | Completed | 2017-12-11 | 2017-12-13 | 2017-12-13 | 3 | 11 Dec: DFN Termination details missing. Issue raised. |  |  |  |  | -30744 | 0 | 0 | 0 |  |  |  | -30743 | 1
2SEV-20 | RFS.146 | M-M-H | BAU | Design | 1 | 2017-12-01 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
6SUB-62 | RFS.132 | M-M-H | BAU | Design | 4 | 2017-12-01 | Yes | Design | Completed | 2018-01-11 |  | Not Applicable |  |  |  |  | 0 | Karishma | Nayana Anilkumar | FTTN/FTTB | Completed | 2018-01-11 | 2018-01-22 | 2018-01-22 | 8 | 12 Jan: MPS name issue was raised to NA team 16 Jan: Duplicate HSD present in PNI request raised to NA team for renaming HVMDU FTTB present in SLD document raised request to update SLD 16 Jan: SAM is on Hold since waiting for updates from upstream |  |  | 2018-01-16 | 2018-01-19 | -30764 | 0 | 0 | 4 |  |  |  | -30763 | -3
6MLO-20 | RFS.150 | M-M-H | BAU | Design | 1 | 2017-12-01 | Yes | Design | Completed | 2018-01-09 | [6 empty] | 0 | Sruthi James |  | FTTN | Completed | 2018-01-10 | 2018-01-16 | 2018-01-16 | 5 | [5 empty] | -30762 | 0 | 1 | 0 |  |  |  | -30761 | 0
4NDG-60 | RFS.127 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-08 | No |  | Completed | 2017-12-11 | Anju Philip | Completed | 2017-12-11 | 2017-12-15 |  | 2017-12-15 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30744 | 0 |  |  |  | 5 | 30749
4PDP-63 | RFS.143 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-01 | No |  | Completed | 2017-12-08 | Haritha | Completed | 2017-12-11 | 2017-12-15 |  | 2017-12-15 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30743 | 0 |  |  |  | 6 | 30748
5GLL-20 | RFS.137 | M-M-Q | BAU | Design | 1 | 2018-01-16 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2LIV-63 | RFS.118 | M-M-H | BAU | Design | 3 | 2017-12-04 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3MLN-61 | RFS.125 | M-M-Q | BAU | Design | 3 | 2017-12-04 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2ING-65 | RFS.129 | M-M-H | BAU | Design | 3 | 2017-12-04 | Yes | Design | Completed | 2017-12-07 | NA | Not Applicable |  |  |  |  | 0 | Latheefa Ul |  | FTTN | Completed | 2017-12-07 | 2017-12-08 | 2017-12-08 | 2 | [5 empty] | -30742 | 0 | 0 | 0 |  |  |  | -30741 | 1
2GBE-64 | RFS.112 | M-A-H | BAU | Pre-AT | 1 | 2017-12-05 | No |  | Completed | 2017-12-18 | Reshma T V | Completed | 2017-12-18 | 2017-12-26 |  | 2017-12-26 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30749 | 0 |  |  |  | 5 | 30754
2GBE-65 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-05 |  |  | Completed | 2017-12-07 | Swathi JS | Completed | 2017-12-07 | 2017-12-12 |  | 2017-12-12 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30742 | 0 |  |  |  | 4 | 30746
3KYG-65 | RFS.113 | H-A-H | BAU | Pre-AT | 3 | 2017-12-05 |  |  | Completed | 2017-12-06 | Divyamol James | Completed | 2017-12-07 | 2017-12-13 |  | 2017-12-13 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30741 | 0 |  |  |  | 6 | 30746
6CTO-20 | RFS.133 | M-M-H | BAU | Design | 4 | 2017-12-05 | Yes | Design | Completed | 2018-01-25 | [7 empty] | Divyamol James | Anju Philip | FTTN/FTTB | Completed | 2018-01-25 | 2018-02-02 | 2018-02-02 | 6 | 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. 01-Feb-2018 : Active NDD FTTN is completed. Waiting for FTTB to get completed. 02-Feb-2018 :FTTB Active NDD got completed.
2CRR-20 | RFS.112 | M-B-H | BAU | Pre-AT | 4 | 2017-12-06 | Yes | Pre-AT | Completed | 2017-12-11 | NA | Not Applicable |  |  |  |  | 0 | Latheefa Ul | Brinson Bovas | FTTN/FTTB | Completed | 2017-12-12 | 2017-12-18 | 2017-12-18 | 5 | 15-Dec : FTTB Active NDD requested |  |  |  |  | -30744 | 0 | 1 | 0 |  |  |  | -30743 | 0
2RYD-64 | RFS.110 | H-A-Q | HAC | Pre-AT | 4 | 2017-12-13 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3KYG-69 | RFS.113 | M-A-Q | HAC | Pre-AT | 1 | 2017-12-08 | Yes | Design | Completed | 2017-12-12 | Aswathy Baby | Completed | 2017-12-13 | 2017-12-20 |  | 2017-12-20 | 6 |  | Siva Kumar | FTTB | Completed | 2017-12-13 | 2017-12-15 | 2017-12-15 | 3 | 13-Dec : Self intersecting loop error raised with AP . 14-Dec : Self intersecting loop error resolved via Incident rasied by AP 15-Dec : DFN termination details missing , issue raised and response received |  |  |  |  | 1 | 0 | 1 | 0 |  |  |  | 7 | 5
2RDL-62 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | 2017-12-11 | No |  | Completed | 2017-12-19 | Latheefa Ul | Completed | 2017-12-19 | 2017-12-26 |  | 2017-12-26 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30750 | 0 |  |  |  | 4 | 30754
3NAW-62 | RFS.114 | M-M-Q | HAC | Pre-AT | 0.5 | 2017-12-11 | No |  | Completed | 2017-12-11 | Rahul Menon | Completed | 2017-12-11 | 2017-12-15 |  | 2017-12-15 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30744 | 0 |  |  |  | 5 | 30749
5GNG-60 | RFS.116 | M-A-H | BAU | Pre-AT | 3 | 2017-12-11 | Yes | Design | Completed | 2018-01-09 | Brinson Bovas | Completed | 2018-01-09 | 2018-01-15 |  | 2018-01-15 | 5 | Divyamol James |  | FTTN | Completed | 2018-01-09 | 2018-01-12 | 2018-01-12 | 4 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 5 | 5
6GIR-20 | RFS.151 | M-B-H | BAU | Design | 2 | 2017-12-11 | yes | Design | Completed | 2018-01-09 | [6 empty] | 0 | Siva Kumar | Dona Babu | FTTN/FTTB | Completed | 2018-01-09 | 2018-01-12 | 2018-01-12 | 4 | 11-Jan : FTTN Active NDD requested 12-Jan: Handover completed for both FTTN and FTTB Active NDDs. |  |  |  |  | -30762 | 0 | 0 | 0 |  |  |  | -30761 | 1
4EMP-02 | RFS.110 | M-B-H | BAU | Pre-AT | 0.3 | 2017-12-11 | Yes | Pre-AT | On Hold - Data Issues | 2017-12-11 | NA | Not Applicable |  |  |  |  | 0 | Roshni Johns |  | FTTN | On Hold - Data Issues | 2017-12-12 |  |  | -30744 | 12-Dec:SAM went on hold due to data issues(Redline Sampling issues) 15-Dec : T18 to consider as source of truth . Do not folow Redline . Need to resume work 18-Dec : SAM resumed 21-Dec : SAM on hold due to IFDV changes . Expecting new T18 late Jan-18 |  |  | 2017-12-21 |  | -30744 | 0 | 1 | -30751 |  |  |  | -30743 | 30751
4CHD-63 | RFS.127 | M-M-H | BAU | Design | 2 | 2017-12-11 | Yes | Design | Completed | 2018-01-09 | [6 empty] | 0 |  | Arya PS | FTTB | Completed | 2018-01-10 | 2018-01-12 | 2018-01-12 | 3 | [5 empty] | -30762 | 0 | 1 | 0 |  |  |  | -30761 | 0
4SRW-69 | RFS.149 | M-M-H | BAU | Design | 1 | 2017-12-12 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4CHL-68 | RFS.130 | H-A-Q | HAC | Pre-AT | 3 | 2017-12-12 | No |  | Completed | 2017-12-11 | Midhun RaJ | Completed | 2017-12-12 | 2017-12-18 |  | 2017-12-18 | 5 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30744 | 0 |  |  |  | 6 | 30749
2CAM-60 | RFS.139 | M-M-Q | BAU | Design | 1 | 2017-12-12 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
5NRW-65 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | 2017-12-13 | Yes | Design | Completed | 2017-12-15 | Nayana Anilkumar | Completed | 2017-12-16 | 2017-12-22 |  | 2017-12-22 | 5 | Aparna Nampoothiri |  | FTTN | Completed | 2017-12-15 | 2017-12-18 | 2017-12-18 | 2 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 6 | 6
4RBN-61 | RFS.113 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-13 | No |  | Completed | 2017-12-12 | Reshma Rajan | Completed | 2017-12-13 | 2017-12-18 |  | 2017-12-18 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30745 | 0 |  |  |  | 5 | 30749
4TGP-63 | RFS.135 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-20 | No |  | Completed | 2017-12-23 | Anju Philip | Completed | 2018-01-18 | 2018-01-25 |  | 2018-01-25 | 6 | [7 empty] | 0 | 22-Dec-2017: NDD Not available 18-Jan-2018: NDD is now made available. | 2017-12-22 | 2018-01-18 |  |  | 15 | 17 | -30753 | 0 |  |  |  | 21 | 30742
4CHD-60 | RFS.126 | M-B-H | BAU | Design | 1 | 2017-12-14 | Yes | Design | Completed | 2018-01-11 | [7 empty] | Aparna Nampoothiri |  | FTTN | Completed | 2018-01-11 | 2018-01-12 | 2018-01-12
4ABO-62 | RFS.135 | M-A-Q | HAC | Pre-AT | 1 | 2017-12-21 | Yes | Design | On Hold - Awaiting Upstream team Updates | 2017-12-23 |  | On Hold - Document Unavailability |  |  |  |  | 0 |  | Aswathy Baby | FTTB | Completed | 2018-01-04 | 2018-01-16 | 2018-01-16 | 9 | 22-Dec: NDD Not available. Will be available only on 18 Jan 5-Jan: DFN Termination Issue, awaiting response from DFN Team 16-Jan: All clarifications provided. Site Design document will not be updated right away, but attached confirmation email from Nate and Indika(Network Acceptance Team) that we can proceed with the given address. | 2017-12-22 |  | 2018-01-05 | 2018-01-16 | -30753 | -30752 | 5 | 8 |  |  |  | -30752 | 30740
4TGP-67 | RFS.135 | M-A-H | BAU | Pre-AT | 1 | 2017-12-21 | Yes | Design | Completed | 2017-12-21 | Aparna Nampoothiri | Completed | 2017-12-21 | 2018-01-25 |  | 2018-01-25 | 23 | Reshma Rajan |  | FTTN | Completed | 2017-12-21 | 2017-12-27 | 2017-12-27 | 3 | 21-Dec-2017 : NDD Document is not available 18-Jan-2018 : NDD docs made available. | 2017-12-21 | 2018-01-18 |  |  |  | 18 | 0 | 0 |  |  |  | 23 | 5
4LNH-62 | RFS.142 | H-M-H | BAU | Pre-AT | 1 | 2017-12-14 | No |  | Completed | 2017-12-20 | Roshni Johns | Completed | 2017-12-21 | 2017-12-28 |  | 2017-12-28 | 4 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30751 | 0 |  |  |  | 5 | 30755
3SSN-62 | RFS.132 | M-M-H | BAU | Design | 4 | 2017-12-14 | Yes | Design | Completed | 2017-12-25 | [6 empty] | 0 | Reshma Rajan | Midhun RaJ | FTTN/FTTB | Completed | 2017-12-27 | 2018-01-03 | 2018-01-03 | 5 | 29-Dec : FTTB Active NDD completed, 29 Dec: FTTN - Job lock issue. |  |  | 2017-12-29 | 2017-01-03 | -30753 | -30755 | 0 | #REF! |  |  |  | -30752 | #REF!
4ABC-61 | RFS.113 | M-M-H | BAU | Pre-AT | 0.1 | 2017-12-14 | Yes | Pre-AT | Completed | 2017-12-19 | Alphy Manuel | Completed | 2017-12-19 | 2017-12-27 |  | 2017-12-27 | 5 |  | Aparna Nampoothiri | FTTN | Completed | 2017-12-19 | 2017-12-27 |  | -30749 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 5 | 5
3CTA-65 | RFS.140 | M-M-H | BAU | Design | 1 | 2017-12-15 | Yes | Design | Completed | 2018-01-01 | [6 empty] | 0 | Aparna Nampoothiri |  | FTTN | Completed | 2018-01-03 | 2018-01-22 | 2018-01-22 | 14 | 03-Jan: Awaiting update on Duplicate DSS cable issue & correction in Jumpering Record 08-Jan : Awaiting update from Design team 22-Jan : All artefacts available now | 2018-01-08 | 2018-01-22 | 2018-01-08 | 2018-01-22 | -30756 | 11 | 1 | 11 |  |  |  | -30755 | -22
2MEN-63 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | 2017-12-20 |  |  | Completed | 2018-01-12 | Roshni Johns | Completed | 2018-01-12 | 2018-01-16 |  | 2018-01-16 | 3 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30765 | 0 |  |  |  | 3 | 30768
2PYM-61 | RFS.116 | M-A-H | BAU | Pre-AT | 2 | 2017-12-15 | Yes | Design | Completed | 2017-12-18 | Rahul Menon | Completed | 2017-12-18 | 2017-12-22 |  | 2017-12-22 | 5 | Haritha | Brinson Bovas | FTTN/FTTB | Completed | 2017-12-19 | 2017-12-21 | 2017-12-21 | 3 | 20-Dec : FTTN Active NDD Completed |  |  |  |  | 0 | 0 | 1 | 0 |  |  |  | 5 | 4
3KYG-61 | RFS.147 | M-M-H | BAU | Design | 0.1 | 2017-12-15 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2CHA-62 | RFS.112 | H-A-Q | HAC | Pre-AT | 2 | 2017-12-18 | No |  | Completed | 2017-12-18 | Siva Kumar | Completed | 2017-12-18 | 2017-12-22 |  | 2017-12-22 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30749 | 0 |  |  |  | 5 | 30754
2UND-61 | RFS.117 | H-M-Q | HAC | Pre-AT | 0.1 | 2017-12-22 | No |  | Completed | 2017-12-21 | Aswathy Baby | Completed | 2017-12-22 | 2018-01-03 |  | 2018-01-03 | 6 | [7 empty] | 0 | 28-Dec: ADA boundary issues. |  |  |  |  | 1 | 0 | -30752 | 0 |  |  |  | 7 | 30758
6SUB-66 | RFS.114 | M-A-H | BAU | Pre-AT | 3 | 2017-12-19 | Yes | Design | On Hold - Data Issues | 2017-12-22 | latheefa ul | On Hold - Data Issues | 2017-12-27 |  |  |  | -30753 |  |  |  | In Queue - To be Assigned |  |  |  | 0 | Missing document in NDD Document | 2017-12-28 |  |  |  | 1 | -30754 | -30753 | 0 |  |  |  | -30752 | 30754
2EPP-65 | RFS.114 | H-M-Q | HAC | Pre-AT | 0.1 | 2017-12-19 | No |  | Completed | 2017-12-19 | Haritha | Completed | 2017-12-19 | 2017-12-26 |  | 2017-12-26 | 4 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30750 | 0 |  |  |  | 4 | 30754
3TYH-69 | RFS.114 | M-A-H | BAU | Pre-AT | 1 | 2017-12-19 | No | Design | Completed | 2017-12-20 | Siva Kumar | Completed | 2017-12-26 | 2018-01-08 |  | 2018-01-08 | 8 | [7 empty] | 0 | Unable to update ADA due to self intersecting loop, Unable to create master circuit as the slot and ports are already in use 5-Jan:Resumed work | 2017-12-29 | 2018-01-05 |  |  | 2 | 5 | -30751 | 0 |  |  |  | 11 | 30755
2NEW-23 | RFS.133 | M-M-H | BAU | Design | 3 | 2017-12-19 | Yes | Design | Completed | [7 empty] | 0 | Reshma T V | Brinson Bovas | FTTN/FTTB | Completed | 2017-12-28 | 2018-01-17 | 2018-01-17 | 14 | 4-Jan:FTTN active NDD request has raised 17-Jan:FTTB Creation activities started and FTTB Active NDD request has raised |  |  |  |  | -1 | 0 | 30753 | 0 |  |  |  | 0 | -30752
2CAR-63 | RFS.116 | M-M-H | BAU | Pre-AT | 1 | 2017-12-19 | No |  | Completed | 2017-12-20 | Midhun RaJ | Completed | 2017-12-21 | 2017-12-26 |  | 2017-12-26 | 2 | [7 empty] | 0 | [5 empty] | 1 | 0 | -30751 | 0 |  |  |  | 3 | 30753
2PEN-01 | RFS.134 | M-M-H | BAU | Design | 4.1 | 2017-12-20 | Yes | Design | Completed | 2018-01-02 | [6 empty] | 0 | Arya PS |  | FTTN | Completed | 2018-01-02 | 2018-01-04 | 2018-01-04 | 3 | [5 empty] | -30757 | 0 | 0 | 0 |  |  |  | -30756 | 1
2QUA-63 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | 2017-12-20 | Yes | Design | Completed | 2017-12-22 | Nayana Anilkumar | Completed | 2017-12-22 | 2018-01-10 |  | 2018-01-10 | 11 | Siva Kumar |  | FTTN | Completed | 2018-01-01 | 2018-01-08 | 2018-01-08 | 5 | 27-Dec: ADA Boundary issues. Self Intersecting Loop. 4-Jan:Unable to take Equipment Containment report, pending request with IT Central 3-Jan:Design updates required from upstream 09-Jan:resumed work | 2018-01-04 | 2018-01-09 | 2018-01-04 | 2018-01-08 | 0 | 4 | 3 | 3 |  |  |  | 11 | 1
2CAR-60 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | 2017-12-21 | No |  | Completed | 2017-12-23 | Latheefa Ul | Completed | 2017-12-27 | 2018-01-05 |  | 2018-01-05 | 7 | [7 empty] | 0 | 27-Dec: ADA Boundary issues. Self Intersecting Loop. 2 SDS & PCD not created, pending confirmation from Triage 3-Jan :Resumed working | 2017-12-27 | 2018-01-03 |  |  | 0 | 5 | -30753 | 0 |  |  |  | 7 | 30755
4ALX-67 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | 2017-12-29 | Yes | Design | On Hold - HFC Completed | 2017-12-20 | Rahul Menon | Completed | 2017-12-21 | 2017-12-27 |  | 2017-12-27 | 3 |  | Gouri Gopal | FTTB | On Hold - Document Unavailability |  |  |  | 0 | 22-DEC: MPS package missing. FDDD put on hold. |  |  |  |  | 1 | 0 | -30751 | 0 |  |  |  | 4 | 30754
3HDB-66 | RFS.115 | M-A-H | BAU | Pre-AT | 1 | 2017-12-21 | Yes | Design | Completed |  | Dona Babu | Completed | 2017-12-27 | 2018-01-05 |  | 2018-01-05 | 7 |  |  |  | Not Applicable |  |  |  | 0 | 28-Dec: ADA Boundary issues. Self Intersecting Loop. | 2018-01-01 | 2018-01-04 |  |  | 30752 | 3 | -1 | 0 |  |  |  | 30759 | 5
2CHA-60 | RFS.114 | M-A-H | BAU | Pre-AT | 1 | 2017-12-22 | Yes | Design | Completed | 2017-12-22 | Haritha | Completed | 2017-12-27 | 2018-01-03 |  | 2018-01-03 | 5 |  |  |  | In Queue - To be Assigned |  |  |  | 0 | 28-Dec: Pending confirmation from NA team on MPS Tech Issue |  |  |  |  | 1 | 0 | -30753 | 0 |  |  |  | 6 | 30758
6WMB-60 | RFS.113 | M-A-H | BAU | Pre-AT | 2 | 2017-12-22 | No |  | Completed | 2017-12-26 | Divyamol James | Completed | 2017-12-27 | 2018-01-01 |  | 2018-01-01 | 3 |  |  |  | Not Applicable |  |  |  | 0 | [5 empty] | 0 | 0 | -30753 | 0 |  |  |  | 3 | 30756
4TGP-68 | RFS.134 | M-A-H | BAU | Pre-AT | 1 | 2017-12-25 | Yes | Design | On Hold - Document Unavailability | 2017-12-23 | Divyamol James | Completed | 2018-01-18 | 2018-01-24 |  | 2018-01-24 | 5 | Reshma T V | NA | FTTN/FTTB | On Hold - Document Unavailability | 2018-01-04 | 2018-01-05 |  | -30758 | 22 Dec-2017: Node Split not done for node code WYNM WN04 in T18 and PNI as its not present in NDD document 28-Dec-2017 : FTTB on hold due to Missing MPS package for MPS-001,030,053,125. Expected MPS package to be made available on 01-Feb-2018. 5-Jan-2017 : FTTN handover done. 18-Jan-2018 : NDD made available now. Also FTTB Active NDD is pending for MPS package availability. Expected to get the files on FEB-1, 2018 | 2017-12-22 | 2018-01-18 | 2017-12-28 |  | 15 | 17 | 5 | -30754 |  |  |  | 20 | 30737
4SLA-64 | RFS.119 | M-M-H | BAU | Design | 3 | 2017-12-27 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3RES-68 | RFS.135 | M-M-H | BAU | Design | 1 | 2017-12-28 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4ABO-65 | RFS.134 | M-A-H | BAU | Pre-AT | 1 | 2017-12-28 | Yes | Design | On Hold - Document Unavailability | 2017-12-27 |  | On Hold - Document Unavailability |  |  |  |  | 0 | Swathi JS |  | FTTN | Completed | 2018-01-05 | 2018-01-10 | 2018-01-10 | 4 | NDD document missing and pending DFN load | 2017-12-26 |  |  |  | -30754 | -30752 | 6 | 0 |  |  |  | -30753 | 30747
4ALX-64 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | 2018-01-04 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3KYG-60 | RFS.117 | H-A-H | BAU | Pre-AT | 1 | 2017-12-28 | No | Pre-AT | Completed | 2017-12-28 | Latheefa Ul | Completed | 2018-01-01 | 2017-01-15 |  | 2018-01-15 | 10 | [7 empty] | 0 | 3-Jan:A location is served by two SAM, pending response from NA team 10-Jan: Update received from Telstra | 2018-01-03 | 2018-01-10 |  |  | 1 | 6 | -30755 | 0 |  |  |  | 12 | 30760
3KYG-62 | RFS.117 | H-A-H | BAU | Pre-AT | 1 | 2017-12-28 | No |  | Completed | 2017-12-27 | Nayana Anilkumar | Completed | 2018-01-01 | 2018-01-18 |  | 2018-01-18 | 13 | [7 empty] | 0 | 4-Jan-2018:NDD Document issue. Pending response from upstream 18-Jan-2018 : NDD document made available | 2018-01-04 | 2018-01-18 |  |  | 2 | 11 | -30754 | 0 |  |  |  | 16 | 30757
3BAY-71 | RFS.135 | M-M-H | BAU | Design | 1 | 2017-12-28 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3BLB-65 | RFS.123 | H-M-H | BAU | Pre-AT | 0.1 | 2017-12-29 | No |  | Completed | 2018-01-22 | Roshni Johns | Completed | 2018-01-22 | 2018-01-31 |  | 2018-01-31 | 7 | [7 empty] | 0 | 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. | 2018-01-29 | 2018-01-31 |  |  | 0 | 3 | -30771 | 0 |  |  |  | 7 | 30775
5HNL-61 | RFS.118 | H-M-H | BAU | Pre-AT | 0.2 | 2018-01-01 | No |  | Completed | 2018-01-16 | Haritha | Completed | 2018-01-16 | 2018-01-22 |  | 2018-01-22 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30767 | 0 |  |  |  | 5 | 30772
4BLH-62 | RFS.123 | M-B-H | BAU | Design | 1 | 2018-01-03 | Yes | Design | Completed | 2018-01-23 | [6 empty] | 0 | Geethu Mol AG |  | FTTN | Completed | 2018-01-23 | 2018-01-25 | 2018-01-25 | 3 | [5 empty] | -30772 | 0 | 0 | 0 |  |  |  | -30771 | 1
2HUR-65 | RFS.115 | H-A-H | BAU | Pre-AT | 1 | 2017-12-29 | No |  | Completed | 2018-01-08 | Aswathy Baby | Completed | 2018-01-08 | 2018-01-12 |  | 2018-01-12 | 5 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30761 | 0 |  |  |  | 5 | 30766
4TGP-65 | RFS.135 | H-A-H | BAU | Pre-AT | 1 | 2018-01-09 | No |  | Completed | 2018-01-22 | Arya PS | Completed | 2018-01-22 | 2018-01-31 |  | 2018-01-31 | 7 | [7 empty] | 0 | 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. | 2018-01-29 | 2018-01-31 |  |  | 0 | 3 | -30771 | 0 |  |  |  | 7 | 30775
2CAM-61 | RFS.118 | H-A-H | BAU | Pre-AT | 1 | 2018-01-09 | No |  | Completed | 2018-01-22 | Aswathy Baby | Completed | 2018-01-22 | 2018-02-01 |  | 2018-02-01 | 8 | [7 empty] | 0 | 23-Jan-2018: Missing node split details in NDD Document, Mail sent. SAM-SAM overlap, Mail sent to AP team 24-Jan-2018: Update received from AP 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. | 2018-01-23 | 2018-01-24 |  |  | 0 | 2 | -30771 | 0 |  |  |  | 8 | 30777
2FRE-62 | RFS.119 | M-M-H | BAU | Pre-AT | 0.2 | 2018-01-09 | No |  | Completed | 2018-01-15 | Geethu Mol AG | Completed | 2018-01-15 | 2018-01-18 |  | 2018-01-18 | 4 |  | Latheefa Ul | FTTB | Completed | 2018-01-16 | 2018-01-17 | 2018-01-17 | 2 | [5 empty] | 0 | 0 | 1 | 0 |  |  |  | 4 | 3
2RDL-60 | RFS.142 | M-M-H | BAU | Design | 1 | 2018-01-09 | Yes | Design | Completed | 2018-01-16 | [6 empty] | 0 |  | Aparna Nampoothiri | FTTB | Completed | 2018-01-16 | 2018-01-18 | 2018-01-18 | 3 | [5 empty] | -30767 | 0 | 0 | 0 |  |  |  | -30766 | 1
4MOG-22 | RFS.134 | M-B-H | BAU | Design | 1 | 2018-01-15 | Yes | Design | Completed | 2018-01-17 | [6 empty] | 0 | Dona Babu |  | FTTN | Completed | 2018-01-17 | 2018-01-22 | 2018-01-22 | 4 | 17-Jan : Put on hold as we were awaiting update on the node status in Triage. 19-Jan: DFN termination was missing. Currently it is provided and good to be handed over. |  |  | 2018-01-19 | 2018-01-22 | -30768 | 0 | 0 | 2 |  |  |  | -30767 | -1
3BLB-68 | RFS.144 | M-M-H | BAU | Design | 1 | 2018-01-09 | Yes | Design | Completed | 2018-01-17 | [6 empty] | 0 |  | Aswathy Baby | FTTB | Completed | 2018-01-17 | 2018-01-19 | 2018-01-19 | 3 | [5 empty] | -30768 | 0 | 0 | 0 |  |  |  | -30767 | 1
4SLA-62 | RFS.99 | H-M-H | BAU | Pre-AT | 0.1 | 2018-01-12 |  |  | Completed | 2018-01-22 | Latheefa Ul | Completed | 2018-01-22 | 2018-01-25 |  | 2018-01-25
2NEW-61 | RFS.143 | M-M-H | BAU | Design | 1 | 2018-01-17 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
5GLL-20 | RFS.137 | M-M-Q | BAU | Design | 4 | 2018-01-16 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3DNC-66 | RFS.0 | H-M-H | BAU | Design | 1 | 2018-01-11 | Yes | Design | Rejected | 2018-01-18 | [8 empty] | Nayana Anilkumar | FTTB | In Progress | 2018-01-29 |  |  |  | 22-Jan-2018: Waiting for the SAM variant to change in Appian. | 2018-01-22
2QUA-64 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | 2018-01-15 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
4RBN-60 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | 2018-01-15 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2WRO-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | 2018-01-15 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
5GLL-62 | RFS.141 | M-M-H | BAU | Design | 2 | 2018-01-15 | Yes | Design | Completed | 2018-01-22 | [6 empty] | 0 | Swathi JS |  | FTTN | Completed | 2018-01-22 | 2018-01-23 | 2018-01-23 | 2 | [5 empty] | -30771 | 0 | 0 | 0 |  |  |  | -30770 | 1
3DAD-64 | RFS.128 | M-M-H | BAU | Design | 4 | 2018-01-15 | Yes | Design | Completed | 2018-01-18 | [6 empty] | 0 |  | Siva Kumar | FTTB | Completed | 2018-01-18 | 2018-01-23 | 2018-01-23 | 4 | [5 empty] | -30769 | 0 | 0 | 0 |  |  |  | -30768 | 1
2GBE-62 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | 2018-01-22 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
3RES-70 | RFS.118 | M-M-H | BAU | Design | 0.1 | 2018-01-15 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2PEN-61 | RFS.120 | M-M-H | BAU | Design | 2 | 2018-01-15 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
2PET-62 | RFS.115 | H-A-H | BAU | Pre-AT | 1 | 2017-12-29 | No |  | Completed | 2018-01-08 | Geethu Mol AG | Completed | 2018-01-08 | 2018-01-10 |  | 2018-01-10 | 3 | [7 empty] | 0 | [5 empty] | 0 | 0 | -30761 | 0 |  |  |  | 3 | 30764
2CRR-66 | RFS.118 | M-M-H | BAU | Pre-AT | 0.1 | 2018-01-23 | Yes | Pre-AT | In Progress | 2018-01-29 | Geethu Mol AG | In Progress | 2018-01-29 |  |  |  | -30774 | Geethu Mol AG |  | FTTN | In Progress | 2018-01-29 |  |  | -30774 | Piloting exercise to execute HFC & FTTN by single person 01-Feb-2018 : Update expected from Telstra on the GTDs outside MPS boundaries. NA has sent an email to TLS for feedback. Awaiting the same to proceed, until then the SAM is paused. |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | -30774 | -30774
2HUR-64 | RFS.120 | M-M-H | BAU | Design | 2 | 2017-11-22 | Yes | Design | Completed | 2018-01-23 | [6 empty] | 0 |  | Sruthi James | FTTB | Completed | 2018-01-23 | 2018-01-29 | 2018-01-29 | 4 | [5 empty] | -30772 | 0 | 0 | 0 |  |  |  | -30771 | 1
4NDG-61 | RFS.143 | M-M-H | BAU | Design | 1 | 2018-01-18 | [10 empty] | 0 | [7 empty] | 0 | [5 empty] | -1 | 0 | -1 | 0 |  |  |  | 0 | 2
5HNL-63 | RFS.119 | H-M-H | BAU | Pre-AT | 0.1 | 2018-01-23 | No |  | Completed | 2018-01-25 | Dona Babu | Completed | 2018-01-25 | 2018-02-02 |  | 2018-02-02 | 6 | [7 empty] | 0 | 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. | 2018-01-29 | 2018-01-31 |  |  | 0 | 3 | -30774 | 0 |  |  |  | 6 | 30777
3TYH-61 | RFS.118 | M-M-H | BAU | Pre-AT | 0.2 | 2018-01-19 | No |  | Completed | 2018-01-22 | Brinson Bovas | Completed | 2018-01-22 | 2018-01-31 |  | 2018-01-31 | 7 | [7 empty] | 0 | 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. | 2018-01-29 | 2018-01-31 |  |  | 0 | 3 | -30771 | 0 |  |  |  | 7 | 30775
4ARU-61 | RFS.123 | M-M-H | BAU | Design | 2 | 2018-01-22 | Yes | Design | Completed | 2018-01-23 | [7 empty] | Karishma |  | FTTN | Completed | 2018-01-23 | 2018-01-25 | 2018-01-25
4TGP-64 | RFS.145 | M-M-H | BAU | Design | 1 | 2018-01-22 | Yes | Design | Completed | 2018-01-24 | [7 empty] | Siva Kumar |  | FTTN | Completed | 2018-01-24 | 2018-01-25 | 2018-01-25
3RES-66 | RFS.146 | M-M-H | BAU | Design | 1 | 2018-01-22 | Yes | Design | Completed | 2018-01-23 | [7 empty] | Arya PS |  | FTTN | Completed | 2018-01-23 | 2018-01-25 | 2018-01-25
2ENG-62 | RFS.123 | H-M-H | BAU | Pre-AT | 0.1 | 2018-01-26 | No |  | Completed | 2018-01-24 | Swathi JS | Completed | 2018-01-24 | 2018-02-01 |  | 2018-02-01 | [9 empty] | 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. | 2018-01-29 | 2018-01-31 |  |  |  | 3
5NRW-63 | RFS.114 | M-A-H | BAU | Pre-AT | 2 | 2018-01-30
3HDB-65 | RFS.123 | H-A-H | BAU | Pre-AT | 1 | 2018-01-23
3BAY-71 | RFS.135 | M-M-H | BAU | Design | 3 | 2018-01-23 | Yes | Design | Completed | 2018-01-25 | [7 empty] | Aparna Nampoothiri |  | FTTN | Completed | 2018-01-25 | 2018-02-01 | 2018-02-01 | 5 | 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. | 2018-01-29 | 2018-01-31
2CAR-62 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | 2018-01-23
3WIR-66 | RFS.150 | M-M-Q | BAU | Design | 1 | 2018-01-23
2BAN-60 | RFS.119 | M-B-H | BAU | Pre-AT | 1.1 | 2018-01-25 | Yes | Pre-AT | In Progress | 2018-01-29 | [7 empty] | Latheefa Ul |  | FTTN | In Progress | 2018-01-29
4CHL-61 | RFS.130 | M-A-H | BAU | Pre-AT | 2 | 2018-01-26
2HUR-61 | RFS.133 | M-M-H | BAU | Design | 3 | 2018-01-26
4BEE-64 | RFS.122 | M-A-H | BAU | Pre-AT | 1 | 2018-01-26
2PYM-65 | RFS.118 | M-A-H | BAU | Pre-AT | 6 | 2018-01-24 | Yes | Design | Completed | 2018-01-24 | Siva Kumar | Completed | 2018-01-24 | 2018-01-31 |  | 2018-01-31 |  |  | Nayana Anilkumar | FTTB | Completed | 2018-01-24 | 2018-01-25 | 2018-01-25 |  | 24-Jan-18: Request pending with LMS Team to remove reason code. 29-Jan-18: Received update from LMS 29-Jan-2018 : PNI job posting issue raised. INC000007196503 closed for the same. 30-Jan-2018 : S: drive folders not available issue. INC000007203935 raised for the same. | 2018-01-29 | 2018-01-31
2PNN-63 | RFS.125 | H-M-H | BAU | Pre-AT | 0.1 | 2018-01-29
4BEE-63 | RFS.146 | M-M-H | BAU | Design | 1 | 2018-01-29
2QUA-65 | RFS.121 | M-A-H | BAU | Pre-AT | 1 | 2018-01-30
3RES-60 | RFS.146 | M-M-H | BAU | Design | 1 | 2018-02-06
3SSN-65 | RFS.137 | M-M-H | BAU | Design | 1 | 2018-01-30
4ABO-66 | RFS.138 | H-A-H | BAU | Pre-AT | 2 | 2018-01-30
4FHL-65 | RFS.142 | M-A-Q | HAC | Pre-AT | 3 | 2018-01-30
3RES-63 | RFS.150 | M-M-H | BAU | Design | 1 | 2018-01-31
2EPP-61 | RFS.124 | H-M-H | BAU | Pre-AT | 0.1 | 2018-01-31
3DNC-66 | RFS.0 | M-M-H | BAU | Design | 1 | 2018-02-01 | Yes | Design | On Hold - Awaiting Upstream team Updates | 2018-01-29 | [9 empty] | FTTB | On Hold - Awaiting Upstream team Updates
4SLA-64 | RFS.125 | M-M-H | BAU | Pre-AT | 0.1 | 2018-02-02
3BNT-62 | RFS.123 | H-A-H | BAU | Pre-AT | 1 | 2018-02-02
3BLB-60 | RFS.146 | M-A-H | BAU | Pre-AT | 3 | 2018-02-02
3NBA-70 | RFS.144 | M-M-H | BAU | Design | 3 | 2018-02-02
2QUA-62 | RFS.118 | M-A-H | BAU | Pre-AT | 3 | 2018-02-02
4LNH-60 | RFS.130 | M-A-H | BAU | Pre-AT | 1 | 2018-02-02
3CTA-64 | RFS.150 | M-M-H | BAU | Design | 5 | 2018-02-02
3KGP-66 | RFS.140 | H-A-H | BAU | Pre-AT | 1 | 2018-02-06
2CHA-61 | RFS.121 | M-A-H | BAU | Pre-AT | 1 | 2018-02-06
3BAY-67 | RFS.135 | M-M-H | BAU | Design | 5 | 2018-02-06
3TNB-60 | RFS.143 | M-M-H | BAU | Design | 1 | 2018-02-07
3KYG-67 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | 2018-02-09
4CHL-63 | RFS.137 | M-M-H | BAU | Design | 1 | 2018-02-12
Formulas:
Cycle Time = NETWORKDAYS([Start Date],[NSO/NDQ Handover Date [HFC]],Holiday!$C2:C80)
Cycle Time = NETWORKDAYS([Start Date],[NSO/NDQ/Active Handover Date [FTTx]],Holiday!$C2:C80)
DSG External Waiting Time [HFC] = NETWORKDAYS([On Hold Start Date [HFC]],[Recommencement Date [HFC]],Holiday!$C2:C80)
DSG External Waiting Time [HFC] = NETWORKDAYS([On Hold Start Date [FTTx]],[Recommencement Date [HFC]],Holiday!$C2:C80)
DSG External Waiting Time [FTTx] = NETWORKDAYS([On Hold Start Date [FTTx]],[Recommencement Date [FTTx]],Holiday!$C2:C80)
DSG External Waiting Time [FTTx] = NETWORKDAYS(#REF!,[Recommencement Date [FTTx]],Holiday!$C2:C80)

## NDQ - IAB Allocation
Updated by : | [5 empty] | Expected |  |  |  |  | HFC NDQ Checks |  |  |  |  | MTM NDQ Checks | [6 empty] | Defect Closure Activity |  |  |  | IAB Defect Resolution | [13 empty] | Handover
SAM Name | RFS Group | SAM Code | Program | Gate | Version | Start Date | MTM NDQ Checks Required? | MTM Payload Type | Overall Status | NDQ Input Date | Assigned To | HFC NDQ Checks Status | Start Date | End Date | Cycle Time | MTM Tech | Assigned To | MTM NDQ Checks Status | Start Date | End Date | Overall QI Completion Date | Cycle Time | Assigned To | Start Date | End Date | Defect Closure Status | Assigned To[HFC] | Assigned To[MTM] | Defect Resolution Status | Defect Resolution Start Date | Defect Resolution End Date | Total Number Of Pre RFS Defects | Total Number of Post RFS Defects | Total Major [FTTN] Defects | Total Major (HFC) Defects | Total Minor FTTN Defects | Total Minor HFC Defects | Open (FAB / Other issue) Defects | External Defects (AP/LMS/Design) | Cycle Time | NSO Handover Date | Comments/ Issues/ Blockers | Defects On Hold Start Date | Recommencement Date | NDQ In Queue Time (Internal Waiting Time) | NDQ External Waiting Time | Defects In Queue Time (Internal Waiting Time) | Defects External Waiting Time | Overall Cycle Time DSG Handover to NSO Handover | Overall Processing Time | Sr.No 1 | Sr.No 2 | Names1 | Names2 | Droddown Validation 1 | Dropdown Validation 2
3NBA-71 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Not Applicable | NA | NA | Not Applicable | NA | NA | #VALUE! |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-02-22 | 2017-02-28 |  | 12 | NA | NA | NA |  |  |  | 5 | 2017-02-28 |  |  |  | #VALUE! |  | #VALUE! | 0 | #VALUE! | #VALUE! | 1 | 1 | Pooja Jacob | Arul Dayalan | Pooja Jacob | Arul Dayalan
2CRM-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Not Applicable | NA | NA | Not Applicable | NA | NA | #VALUE! |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-02-22 | 2017-02-28 |  | 12 | NA | NA | NA |  |  |  | 5 | 2017-02-28 |  |  |  | #VALUE! |  | #VALUE! | 0 | #VALUE! | #VALUE! | 2 | 2 | Vinaybhaskar P | Pooja Jacob | Vinaybhaskar P | Pooja Jacob
2CRM-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Not Applicable | 2017-03-02 | NA | Not Applicable | NA | NA | #VALUE! |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-02-24 | 2017-03-02 |  | 12 | NA | NA | NA |  |  |  | 5 | 2017-03-02 |  |  |  | #VALUE! |  | #VALUE! | 0 | 1 | #VALUE! | 3 | 3 | Sree Ram Sundar | Vinaybhaskar P | Sree Ram Sundar | Vinaybhaskar P
2CRM-62 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-03-15 | NA | Completed | 2017-03-15 | 2017-03-20 | 4 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-03-23 | 2017-03-27 |  | 12 | NA | NA | NA |  |  |  | 3 | 2017-03-27 | Pilot SAM |  |  | 0 |  | 3 | 0 | 9 | 7 | 4 | 4 | Sree V | Reenu Treesa Peter | Sree V | Reenu Treesa Peter
2MIL-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-03-16 | NA | Completed | 2017-03-17 | 2017-03-21 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-03-23 | 2017-03-29 |  | 13 | NA | NA | NA |  |  |  | 5 | 2017-03-29 | Pilot SAM |  |  | 1 |  | 2 | 0 | 10 | 8 | 5 | 5 | Anju Lisa | Geethu Mol AG | Anju Lisa | Geethu Mol AG
2ROS-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-03-15 | NA | Completed | 2017-03-15 | 2017-03-20 | 4 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-03-21 | 2017-03-24 |  | 7 | NA | NA | NA |  |  |  | 4 | 2017-04-06 | This is an Advance T18 SAM RFS grp 83. SAM was put-on hold at multiple stages for other high priority SAMs. |  |  | 0 |  | 1 | 0 | 17 | 8 | 6 | 6 | Manjusha M | Alan Babu | Manjusha M | Alan Babu
4SLA-73 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-03-14 | NA | Completed | 2017-03-28 | 2017-03-29 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-03-30 | 2017-03-31 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-03-31 | Pilot SAM |  |  | 10 |  | 1 | 0 | 14 | 4 | 7 | 7 | Jowharulla.M | Sree V | Jowharulla.M | Sree V
2ENG-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-03-28 | NA | Completed | 2017-04-03 | 2017-04-06 | 4 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-03 | 2017-04-13 |  | 16 | NA | NA | NA |  |  |  | 9 | 2017-04-13 | Pilot Wave 3 SAM DF081735 defect raised and resolved |  |  | 4 |  | -5 | 0 | 13 | 13 | 8 | 8 | Lekshmi Balakrishnan | Anju Lisa | Lekshmi Balakrishnan | Anju Lisa
3OAK-62 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-03-29 | NA | Completed | 2017-03-30 | 2017-04-03 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-03 | 2017-04-06 |  | 20 | NA | NA | NA |  |  |  | 4 | 2017-04-13 | 6 defects are raised. Pilot Wave 3 SAM |  |  | 1 |  | 0 | 0 | 12 | 7 | 9 | 9 | Rejitha Retnakaran | Abhishek Ojha | Rejitha Retnakaran | Abhishek Ojha
2EAS-66 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-21 | NA | Completed | 2017-04-24 | 2017-04-25 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-26 | 2017-05-02 |  | 2 | NA | NA | NA |  |  |  | 4 | 2017-05-02 | 2 defects are raised. 1-May is a offshore holiday |  |  | 1 |  | 0 | 0 | 6 | 5 | 10 | 10 | Bastin Joseph | Jowharulla.M | Bastin Joseph | Jowharulla.M
2MOS-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-10 | NA | Completed | 2017-04-07 | 2017-04-11 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-12 | 2017-04-18 |  | 6 | NA | NA | NA |  |  |  | 3 | 2017-04-18 | Easter Weekend |  |  | -3 |  | 1 | 0 | 5 | 6 | 11 | 11 | Pankaj Velavan | Lekshmi Balakrishnan | Pankaj Velavan | Lekshmi Balakrishnan
3RWO-69 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-10 | NA | Completed | 2017-04-07 | 2017-04-11 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-18 | 2017-04-25 |  | 5 | NA | NA | NA |  |  |  | 5 | 2017-04-25 | More than 100 errors in Cable Assosiation Validator |  |  | -3 |  | 3 | 0 | 9 | 8 | 12 | 12 | Mary Ann | Rejitha Retnakaran | Mary Ann | Rejitha Retnakaran
2ASH-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-13 | NA | Completed | 2017-04-13 | 2017-04-13 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-18 | 2017-04-25 |  | 7 | NA | NA | NA |  |  |  | 5 | 2017-05-01 | 7 defects are raised. More than 100 errors in Cable Assosiation Validator |  |  | 0 |  | 1 | 0 | 9 | 6 | 13 | 13 | Nahas Shajahan | Aravind V | Nahas Shajahan | Aravind V
3SOA-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-18 | NA | Completed | 2017-04-12 | 2017-04-13 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-18 | 2017-04-24 |  | 4 | NA | NA | NA |  |  |  | 5 | 2017-04-24 | 4 defects are raised. Easter Weekend |  |  | -4 |  | 1 | 0 | 5 | 7 | 14 | 14 | Naika Arjun | Brinson Bovas | Naika Arjun | Brinson Bovas
3SCO-69 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-18 | NA | Completed | 2017-04-12 | 2017-04-19 | 4 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-20 | 2017-04-24 |  | 5 | NA | NA | NA |  |  |  | 3 | 2017-04-24 | 5 defects are raised. Easter Weekend |  |  | -4 |  | 1 | 0 | 5 | 7 | 15 | 15 | Athul V | Divyamol James | Athul V | Divyamol James
2SHA-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-21 | NA | Completed | 2017-04-24 | 2017-04-25 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-26 | 2017-04-27 |  | 2 | NA | NA | NA |  |  |  | 2 | 2017-05-01 | 2 defects are raised |  |  | 1 |  | 0 | 0 | 5 | 3 | 16 | 16 | Jiya | Gouri Gopal | Jiya | Gouri Gopal
4BLH-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-16 | NA | Completed | 2017-05-16 | 2017-05-17 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-17 | 2017-05-18 |  | 2 | NA | NA | NA |  |  |  | 2 | 2017-05-18 |  |  |  | 0 |  | 0 | 0 | 3 | 4 | 17 | 17 | Jyoti | Jijin Isaac | Jyoti | Jijin Isaac
4IAL-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-26 | NA | Completed | 2017-04-26 | 2017-04-28 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-01 | 2017-05-02 |  | 1 | NA | NA | NA |  |  |  | 1 | 2017-05-05 | NSO release email template was not finalised until 5-May. So sent the final email on 5-May. Completed defect fix and checks on 3-May |  |  | 0 |  | 0 | 0 | 7 | 4 | 18 | 18 | Minu | Krutika Neelak | Minu | Krutika Neelak
2BAN-66 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-20 | NA | Completed | 2017-04-19 | 2017-04-21 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-21 | 2017-04-24 |  | 2 | NA | NA | NA |  |  |  | 2 | 2017-04-24 | 2 defects are raised |  |  | -3 |  | 0 | 0 | 3 | 5 | 19 | 19 | Shahin Basheer | Amalu Manuel | Shahin Basheer | Amalu Manuel
3BAY-69 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-28 | NA | Completed | 2017-04-28 | 2017-05-01 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-02 | 2017-05-02 |  | 1 | NA | NA | NA |  |  |  | 1 | 2017-05-03 |  |  |  | 0 |  | 0 | 0 | 3 | 2 | 20 | 20 | Abhishek Ojha | Sriram Rajendra Kumar | Abhishek Ojha | Sriram Rajendra Kumar
3OAK-70 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-02 | NA | Completed | 2017-05-03 | 2017-05-05 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-08 | 2017-05-11 |  | 4 | NA | NA | NA |  |  |  | 4 | 2017-05-11 |  |  |  | 1 |  | 1 | 0 | 8 | 7 | 21 | 21 | Ashwin Vijayan | Reethu Sebastian | Ashwin Vijayan | Reethu Sebastian
5EDW-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-27 | NA | Completed | 2017-04-28 | 2017-05-02 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-02 | 2017-05-04 |  | 5 | NA | NA | NA |  |  |  | 3 | 2017-05-05 |  |  |  | 1 |  | 0 | 0 | 6 | 5 | 22 | 22 | Vedant | Girish Chandran | Vedant | Girish Chandran
2CAS-61 |  | H-A-Q [P] | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-31 | NA | Completed | 2017-06-01 | 2017-06-01 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-01 | 2017-06-01 |  | 4 | NA | NA | NA |  |  |  | 1 | 2017-06-01 |  |  |  | 1 |  | 0 | 0 | 2 | 2 |  | 23 |  | Selbee Mathew | NA | Selbee Mathew
2CMO-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-02 | NA | Completed | 2017-05-02 | 2017-05-04 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-05 | 2017-05-05 |  | 2 | NA | NA | NA |  |  |  | 1 | 2017-05-08 |  |  |  | 0 |  | 1 | 0 | 5 | 4 |  | 24 |  | Bijeta Biswal |  | Bijeta Biswal
2MEN-60 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-11 | NA | Completed | 2017-05-11 | 2017-05-12 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-15 | 2017-05-16 |  | 3 | NA | NA | NA |  |  |  | 2 | 2017-05-16 |  |  |  | 0 |  | 1 | 0 | 4 | 4 |  | 25 |  | Anpu Susan |  | Anpu Susan
2ROC-60 |  | H-A-Q [P] | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-17 | NA | Completed | 2017-05-17 | 2017-05-18 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-19 | 2017-05-24 |  | 3 | NA | NA | NA |  |  |  | 4 | 2017-05-24 |  |  |  | 0 |  | 1 | 0 | 6 | 6 |  | 26 |  | Nahas Shajahan |  | Nahas Shajahan
3BAY-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-07 | NA | Completed | 2017-06-08 | 2017-06-09 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-09 | 2017-06-14 |  | 4 | NA | NA | NA |  |  |  | 3 | 2017-06-14 |  |  |  | 1 |  | 0 | 0 | 5 | 5 |  | 27 |  | Sahishna Krishna |  | Sahishna Krishna
3DNC-62 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-08 | NA | Completed | 2017-05-08 | 2017-05-09 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-10 | 2017-05-10 |  | 1 | NA | NA | NA |  |  |  | 1 | 2017-05-12 |  |  |  | 0 |  | 1 | 0 | 5 | 3 |  | 28 |  | Nevin Tom |  | Nevin Tom
3KGP-62 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-02 | NA | Completed | 2017-05-03 | 2017-05-05 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-05 | 2017-05-08 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-05-09 |  |  |  | 1 |  | 0 | 0 | 6 | 5 |  | 29 |  | Meera Sudhakumar |  | Meera Sudhakumar
3KGP-67 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-31 | NA | Completed | 2017-06-01 | 2017-06-01 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-02 | 2017-06-08 |  | 3 | NA | NA | NA |  |  |  | 5 | 2017-06-08 |  |  |  | 1 |  | 1 | 0 | 7 | 6 |  | 30 |  | Naika Arjun |  | Naika Arjun
3NBA-68 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-17 | NA | Completed | 2017-05-17 | 2017-05-18 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-19 | 2017-05-23 |  | 2 | NA | NA | NA |  |  |  | 3 | 2017-05-23 |  |  |  | 0 |  | 1 | 0 | 5 | 5 |  | 31 |  | Aleena Johny |  | Aleena Johny
3TYH-65 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-16 | NA | Completed | 2017-05-17 | 2017-05-19 | 3 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-17 | 2017-05-19 |  | 3 | NA | NA | NA |  |  |  | 3 | 2017-05-22 |  |  |  | 1 |  | -4 | 0 | 5 | 6 |  | 32 |  | Jiya |  | Jiya
4CPH-73 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-12 | NA | Completed | 2017-05-15 | 2017-05-16 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-16 | 2017-05-19 |  | 2 | NA | NA | NA |  |  |  | 4 | 2017-05-22 |  |  |  | 1 |  | 0 | 0 | 7 | 6 |  | 33 |  | Shahin Basheer |  | Shahin Basheer
5EZB-60 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-11 | NA | Completed | 2017-05-11 | 2017-05-12 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-15 | 2017-05-17 |  | 2 | NA | NA | NA |  |  |  | 3 | 2017-05-17 |  |  |  | 0 |  | 1 | 0 | 5 | 5 | [5 empty] | NA
6SUB-60 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-31 | NA | Completed | 2017-06-01 | 2017-06-01 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-02 | 2017-06-06 |  | 4 | NA | NA | NA |  |  |  | 3 | 2017-06-06 |  |  |  | 1 |  | 1 | 0 | 5 | 4
3NCO-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-26 | NA | Completed | 2017-05-26 | 2017-05-26 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-26 | 2017-06-01 |  | 2 | NA | NA | NA |  |  |  | 5 | 2017-06-01 |  |  |  | 0 |  | 0 | 0 | 5 | 6
2ASH-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-12 | NA | Completed | 2017-05-15 | 2017-05-16 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-15 | 2017-05-16 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-05-17 |  |  |  | 1 |  | -3 | 0 | 4 | 4
2PET-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-01 | NA | Completed | 2017-06-06 | 2017-06-06 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-07 | 2017-06-14 |  | 3 | NA | NA | NA |  |  |  | 5 | 2017-06-14 | FY17 SAM. Hence parked in queue |  |  | 3 |  | 1 | 0 | 9 | 6
2PET-67 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-19 | NA | Completed | 2017-05-22 | 2017-05-22 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-23 | 2017-05-26 |  | 2 | NA | NA | NA |  |  |  | 4 | 2017-05-26 |  |  |  | 1 |  | 1 | 0 | 6 | 5
3DAD-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-08 | NA | Completed | 2017-06-09 | 2017-06-09 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-13 | 2017-06-14 |  | 3 | NA | NA | NA |  |  |  | 2 | 2017-06-14 |  |  |  | 1 |  | 1 | 0 | 4 | 3
4CPH-62 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-24 | NA | Completed | 2017-05-25 | 2017-05-26 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-26 | 2017-05-30 |  | 3 | NA | NA | NA |  |  |  | 3 | 2017-05-30 |  |  |  | 1 |  | 0 | 0 | 5 | 5
5BRI-68 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-04-21 | NA | Completed | 2017-04-24 | 2017-05-01 | 4 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-27 | 2017-04-28 |  | 2 | NA | NA | NA |  |  |  | 2 | 2017-05-01 |  |  |  | 1 |  | -3 | 0 | 5 | 6
5GLL-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-26 | NA | Completed | 2017-05-29 | 2017-05-29 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-29 | 2017-06-01 |  | 4 | NA | NA | NA |  |  |  | 4 | 2017-06-01 |  |  |  | 1 |  | 0 | 0 | 5 | 5
5GLL-66 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-13 | NA | Completed | 2017-06-13 | 2017-06-13 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-14 | 2017-06-15 |  | 4 | NA | NA | NA |  |  |  | 2 | 2017-06-15 |  |  |  | 0 |  | 1 | 0 | 3 | 3
5HNL-66 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-07 | NA | Completed | 2017-06-08 | 2017-06-08 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-09 | 2017-06-09 |  | 2 | NA | NA | NA |  |  |  | 1 | 2017-06-09 |  |  |  | 1 |  | 1 | 0 | 3 | 2
6MLO-65 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-18 | NA | Completed | 2017-05-18 | 2017-05-19 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-22 | 2017-05-23 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-05-23 |  |  |  | 0 |  | 1 | 0 | 4 | 4
3FNT-66 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-13 | NA | Completed | 2017-06-14 | 2017-06-14 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-15 | 2017-06-26 |  | 3 | NA | NA | NA |  |  |  | 7 | 2017-06-26 | IT tool issue. INC raised and waited for resolution. Pessimistic lock issue delayed it by 2 days. |  |  | 1 |  | 1 | 0 | 9 | 8
3CLA-67 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-18 | NA | Completed | 2017-05-18 | 2017-05-19 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-22 | 2017-05-23 |  | 2 | NA | NA | NA |  |  |  | 2 | 2017-05-23 |  |  |  | 0 |  | 1 | 0 | 4 | 4
3DAD-65 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-15 | NA | Completed | 2017-06-16 | 2017-06-16 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-19 | 2017-06-20 |  | 3 | NA | NA | NA |  |  |  | 2 | 2017-06-20 |  |  |  | 1 |  | 1 | 0 | 4 | 3
3ELT-60 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-06-09 | No |  | Completed | 2017-06-26 | NA | Completed | 2017-06-27 | 2017-06-27 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-28 | 2017-06-29 |  | 3 | NA | NA | NA |  |  |  | 2 | 2017-06-29 |  |  |  | 0 |  | 1 | 0 | 3 | 3
4BUR-68 | RFS.91 | H-A-Q | HAC | Pre-AT |  | 2017-08-04 | No |  | Completed | 2017-08-02 | Abhishek | Completed | 2017-08-03 | 2017-08-03 | 1 | [6 empty] | 0 |  |  |  |  | Abhishek |  | Completed | 2017-08-04 | 2017-08-08 | [8 empty] | 3 | 2017-08-08 |  |  |  | 1 |  | 1 | 0 | 5 | 4
2CMO-60 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-18 | NA | Completed | 2017-05-19 | 2017-05-19 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-22 | 2017-05-24 |  | 2 | NA | NA | NA |  |  |  | 3 | 2017-05-24 |  |  |  | 1 |  | 1 | 0 | 5 | 4
3DAD-60 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-07 | NA | Completed | 2017-06-08 | 2017-06-08 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-09 | 2017-06-14 |  | 3 | NA | NA | NA |  |  |  | 3 | 2017-06-14 |  |  |  | 1 |  | 1 | 0 | 5 | 4
3TYH-68 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-21 | NA | Completed | 2017-06-22 | 2017-06-22 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-23 | 2017-06-26 |  | 3 | NA | NA | NA |  |  |  | 1 | 2017-06-26 |  |  |  | 1 |  | 1 | 0 | 3 | 2
6CTO-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-23 | NA | Completed | 2017-05-24 | 2017-05-24 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-25 | 2017-05-30 |  | 2 | NA | NA | NA |  |  |  | 4 | 2017-05-30 |  |  |  | 1 |  | 1 | 0 | 6 | 5
2ENG-65 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-08 | NA | Completed | 2017-06-09 | 2017-06-09 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-09 | 2017-06-13 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-06-13 |  |  |  | 1 |  | 0 | 0 | 3 | 3
2EPP-60 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-23 | NA | Completed | 2017-06-27 | 2017-06-27 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-28 | 2017-06-30 |  | 3 | NA | NA | NA |  |  |  | 3 | 2017-06-30 |  |  |  | 1 |  | 1 | 0 | 5 | 4
2EPP-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-14 | NA | Completed | 2017-06-15 | 2017-06-15 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-16 | 2017-06-20 |  | 2 | NA | NA | NA |  |  |  | 3 | 2017-06-20 |  |  |  | 1 |  | 1 | 0 | 5 | 4
2SEV-60 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-30 | NA | Completed | 2017-05-31 | 2017-05-31 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-01 | 2017-06-05 |  | 2 | NA | NA | NA |  |  |  | 3 | 2017-06-05 |  |  |  | 1 |  | 1 | 0 | 5 | 4
3MIT-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-31 | NA | Completed | 2017-06-01 | 2017-06-01 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-02 | 2017-06-06 |  | 2 | NA | NA | NA |  |  |  | 3 | 2017-06-06 |  |  |  | 1 |  | 1 | 0 | 5 | 4
3SOA-62 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-06 | NA | Completed | 2017-06-08 | 2017-06-08 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-08 | 2017-06-08 |  | 1 | NA | NA | NA |  |  |  | 1 | 2017-06-08 |  |  |  | 2 |  | 0 | 0 | 3 | 2
3SOA-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-05 | NA | Completed | 2017-06-06 | 2017-06-06 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-06 | 2017-06-07 |  | 2 | NA | NA | NA |  |  |  | 2 | 2017-06-07 |  |  |  | 1 |  | 0 | 0 | 3 | 3
5GNG-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-03-31 | NA | Completed | 2017-04-03 | 2017-04-06 | 4 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-04-03 | 2017-04-06 |  | 0 | NA | NA | NA |  |  |  | 4 | 2017-04-06 | Defects sheet shared to team |  |  | 1 |  | -5 | 0 | 5 | 8
6CTO-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-06 | NA | Completed | 2017-06-07 | 2017-06-07 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-08 | 2017-06-12 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-06-12 |  |  |  | 1 |  | 1 | 0 | 4 | 3
6SUB-63 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-26 | NA | Completed | 2017-06-27 | 2017-06-27 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-28 | 2017-06-30 |  | 1 | NA | NA | NA |  |  |  | 3 | 2017-06-30 |  |  |  | 0 |  | 1 | 0 | 4 | 4
6SUB-68 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-05-30 | NA | Completed | 2017-05-31 | 2017-05-31 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-05-31 | 2017-06-06 |  | 3 | NA | NA | NA |  |  |  | 5 | 2017-06-06 |  |  |  | 1 |  | 0 | 0 | 6 | 6
2NSY-64 |  | H-A-Q [P] | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-14 | NA | Completed | 2017-06-15 | 2017-06-15 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-16 | 2017-06-19 |  | 4 | NA | NA | NA |  |  |  | 2 | 2017-06-19 |  |  |  | 1 |  | 1 | 0 | 4 | 3
2SEV-62 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-21 | NA | Completed | 2017-06-21 | 2017-06-21 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-21 | 2017-06-26 |  | 2 | NA | NA | NA |  |  |  | 3 | 2017-06-26 |  |  |  | 0 |  | 0 | 0 | 3 | 4
2BAN-64 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-22 | NA | Completed | 2017-06-23 | 2017-06-23 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-26 | 2017-06-28 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-06-28 |  |  |  | 1 |  | 0 | 0 | 4 | 3
6GIR-66 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-26 |  | Completed | 2017-06-27 | 2017-06-27 | 1 |  |  | Not Applicable |  |  |  | 0 | [6 empty] | Completed | 2017-06-28 | 2017-06-29 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-06-29 |  |  |  | 0 |  | 1 | 0 | 3 | 3
3RWO-65 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-29 | NA | Completed | 2017-06-30 | 2017-06-30 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-07-03 | 2017-07-03 |  | 2 | NA | NA | NA |  |  |  | 1 | 2017-07-03 |  |  |  | 1 |  | 1 | 0 | 3 | 2
4BLH-67 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-20 | NA | Completed | 2017-06-21 | 2017-06-21 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-21 | 2017-06-22 |  | 2 | NA | NA | NA |  |  |  | 2 | 2017-06-22 |  |  |  | 1 |  | 0 | 0 | 3 | 3
4IAL-62 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-07-10 | NA | Completed | 2017-07-11 | 2017-07-11 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-07-12 | 2017-07-13 |  | 3 | NA | NA | NA |  |  |  | 2 | 2017-07-13 |  |  |  | 1 |  | 1 | 0 | 4 | 3
5SAL-69 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-27 | NA | Completed | 2017-06-28 | 2017-06-28 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-29 | 2017-06-30 |  | 1 | NA | NA | NA |  |  |  | 2 | 2017-06-30 |  |  |  | 1 |  | 1 | 0 | 4 | 3
6GIR-61 |  | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 2017-06-22 | NA | Completed | 2017-06-23 | 2017-06-23 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | NA |  | Completed | 2017-06-27 | 2017-06-28 |  | 2 | NA | NA | NA |  |  |  | 2 | 2017-06-28 |  |  |  | 1 |  | 1 | 0 | 4 | 3
2CRM-61 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-07-19 | No |  | Completed | 2017-07-19 | Lekshmi | Completed | 2017-07-19 | 2017-07-19 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed | 2017-07-19 | 2017-07-20 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-07-20 |  |  |  | 0 |  | 0 | 0 | 2 | 3
5GPC-60 | RFS.90 | H-A-Q | HAC | Pre-AT |  |  | No |  | Completed | 19-Jul-17 |  | Completed | 2017-07-19 | 2017-07-19 | 1 | [6 empty] | 0 | [6 empty] | Completed | 2017-07-20 | 2017-07-25 |  | 1 |  | 1 |  |  |  |  | 4 | 2017-07-25 |  |  |  | #VALUE! |  | 1 | 0 | #VALUE! | 5
2CMO-63 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-07-21 | No |  | Completed | 2017-07-28 | Jyoti | Completed | 2017-07-28 | 2017-07-28 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed | 2017-07-31 | 2017-08-01 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-08-01 |  |  |  | 0 |  | 1 | 0 | 3 | 3
3MLN-63 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-07-24 | No |  | Completed | 2017-07-26 | Lekshmi | Completed | 2017-07-27 | 2017-07-27 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed | 2017-07-28 | 2017-07-31 |  | 2 |  | 2 |  |  |  |  | 2 | 2017-07-31 |  |  |  | 1 |  | 1 | 0 | 4 | 3
2BAL-65 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-07-28 | No |  | Completed | 2017-07-28 | Rejitha | Completed | 2017-07-28 | 2017-07-31 | 2 | [6 empty] | 0 |  |  |  |  | Rejitha Retnakaran |  | Completed | 2017-07-31 | 2017-08-03 |  | 1 |  | 1 |  |  |  |  | 4 | 2017-08-03 |  |  |  | 0 |  | 0 | 0 | 5 | 6
2ENG-62 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2018-02-02 | No | [7 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2EPP-61 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-07-31 | No | [7 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2ROS-65 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-07-31 | No |  | Completed | 2017-08-02 | Ashwin | Completed | 2017-08-02 | 2017-08-02 | 1 | [6 empty] | 0 |  |  |  |  | Ashwin Vijayan |  | Completed | 2017-08-03 | 2017-08-09 |  | 2 |  | 2 |  |  |  |  | 5 | 2017-08-09 |  |  |  | 0 |  | 1 | 0 | 6 | 6
4OXE-63 | RFS.0 | H-A-Q | HAC | Pre-AT |  | 2017-07-31 | No |  | Completed | 2017-07-28 | Jyoti | Completed | 2017-07-28 | 2017-07-28 | 1 | [6 empty] | 0 |  |  |  |  | Jyoti |  | Completed | 2017-07-28 | 2017-07-31 | [8 empty] | 2 | 2017-07-31 |  |  |  | 0 |  | 0 | 0 | 2 | 3
4CPH-69 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-08-02 | No |  | Completed | 2017-08-07 | Abhishek | Completed | 2017-08-07 | 2017-08-07 | 1 | [6 empty] | 0 |  |  |  |  | Abhishek |  | Completed | 2017-08-08 | 2017-08-11 |  | 2 |  | 2 |  |  |  |  | 4 | 2017-08-11 |  |  |  | 0 |  | 1 | 0 | 5 | 5
2PET-60 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-08-03 | No |  | Completed | 2017-08-03 | Shahin | Completed | 2017-09-04 | 2017-09-05 | 0 | [6 empty] | 0 |  |  |  |  | Shahin Basheer |  | Completed | 2017-09-05 | 2017-09-06 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-09-06 |  |  |  | 20 |  | -1 | 0 | 22 | 1 | 23 | 34 | NA | NA
3GLI-61 | RFS.91 | H-A-Q | HAC | Pre-AT |  | 2017-08-04 | No |  | Completed | 2017-08-07 | Shyama | Completed | 2017-08-07 | 2017-08-07 | 1 | [6 empty] | 0 |  |  |  |  | Shyama |  | Completed | 2017-08-08 | 2017-08-10 |  | 1 |  | 1 |  |  |  |  | 3 | 2017-08-10 |  |  |  | 0 |  | 1 | 0 | 4 | 4
3CAU-62 | RFS.92 | H-A-Q | HAC | Pre-AT |  | 2017-08-07 | No |  | Completed | 2017-08-06 | Lekshmi | Completed | 2017-08-06 | 2017-08-06 | 0 | [6 empty] | 0 |  |  |  |  | Jiya |  | Completed | 2017-09-07 | 2017-09-11 |  | 2 |  | 2 |  |  |  |  | 3 | 2017-09-11 |  |  |  | -1 |  | 20 | 0 | 23 | 3
4CHD-65 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-08-08 | No |  | Completed | 2017-08-07 | Shahin | Completed | 2017-08-07 | 2017-08-08 | 2 | [6 empty] | 0 |  |  |  |  | Shahin |  | Completed | 2017-08-08 | 2017-08-10 |  | 1 |  | 1 |  |  |  |  | 3 | 2017-08-10 |  |  |  | 0 |  | 0 | 0 | 4 | 5
3MIT-64 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-08-08 | No |  | Completed | 2017-08-07 | Jyoti | Completed | 2017-08-07 | 2017-08-07 | 1 | [6 empty] | 0 |  |  |  |  | Jyoti |  | Completed | 2017-08-08 | 2017-08-09 | [8 empty] | 2 | 2017-08-09 |  |  |  | 0 |  | 1 | 0 | 3 | 3
2ASH-68 | RFS.0 | H-A-Q | HAC | Pre-AT |  | 2017-08-09 | No |  | Completed | 2017-08-17 | Anju | Completed | 2017-08-17 | 2017-08-17 | 1 | [6 empty] | 0 |  |  |  |  | Anju |  | Completed | 2017-08-18 | 2017-08-21 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-08-21 |  |  |  | 0 |  | 1 | 0 | 3 | 3
2ROS-62 | RFS.94 | H-A-Q | HAC | Pre-AT |  | 2017-08-09 | No |  | Completed | 2017-08-08 | Pooja | Completed | 2017-08-08 | 2017-08-08 | 1 | [6 empty] | 0 |  |  |  |  | Pooja |  | Completed | 2017-08-08 | 2017-08-09 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-08-09 |  |  |  | 0 |  | 0 | 0 | 2 | 3
2SHA-62 | RFS.94 | H-A-Q | HAC | Pre-AT |  | 2017-08-09 | No |  | Completed | 2017-08-11 | Sree | Completed | 2017-08-11 | 2017-08-11 | 1 | [6 empty] | 0 |  |  |  |  | Sree V |  | Completed | 2017-08-11 | 2017-08-14 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-08-14 |  |  |  | 0 |  | 0 | 0 | 2 | 3
3BLB-64 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-08-14 | No |  | Completed | 2017-08-21 | Rejitha | Completed | 2017-08-21 | 2017-08-21 | 1 | [6 empty] | 0 |  |  |  |  | Rejitha Retnakaran |  | Completed | 2017-08-21 | 2017-08-22 | [8 empty] | 2 | 2017-08-22 |  |  |  | 0 |  | 0 | 0 | 2 | 3
6GIR-62 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-08-14 | No |  | Completed | 2017-08-08 | Minu | Completed | 2017-08-08 | 2017-08-08 | 1 | [6 empty] | 0 |  |  |  |  | Minu |  | Completed | 2017-08-08 | 2017-08-09 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-08-09 |  |  |  | 0 |  | 0 | 0 | 2 | 3
5BRI-67 | RFS.100 | H-A-Q | HAC | Pre-AT |  | 2017-08-14 | No |  | Completed | 2017-08-16 | Naika | Completed | 2017-08-16 | 2017-08-16 | 1 | [6 empty] | 0 |  |  |  |  | Naika Arjun |  | Completed | 2017-08-17 | 2017-08-21 |  | 1 |  | 1 |  |  |  |  | 3 | 2017-08-21 |  |  |  | 0 |  | 1 | 0 | 4 | 4
4SLA-68 | RFS.68 | H-A-H | BAU | Pre-AT |  | 2017-08-15 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2PET-63 | RFS.96 | H-M-Q | HAC | Pre-AT |  | 2017-08-15 | No |  | Completed | 2017-08-31 | Anju/Karthika | Completed | 2017-08-31 | 2017-08-31 | 1 | [6 empty] | 0 |  |  |  |  | Karthika V J |  | Completed | 2017-08-31 | 2017-09-07 |  | 2 |  | 2 |  |  |  |  | 4 | 2017-09-07 |  |  |  | 0 |  | 0 | 0 | 4 | 5
3RWO-60 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-08-15 | No |  | Completed | 2017-08-14 | Manjusha | Completed | 2017-08-14 | 2017-08-14 | 1 | [6 empty] | 0 |  |  |  |  | Manjusha M |  | Completed | 2017-08-14 | 2017-08-17 |  | 2 |  | 2 |  |  |  |  | 3 | 2017-08-17 |  |  |  | 0 |  | 0 | 0 | 3 | 4
6KSL-60 | RFS.95 | H-A-Q | HAC | Pre-AT |  | 2017-08-15 | No |  | Completed | 2017-08-14 | Anju | Completed | 2017-08-14 | 2017-08-14 | 1 | [6 empty] | 0 |  |  |  |  | Anju |  | Completed | 2017-08-14 | 2017-08-16 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-08-16 |  |  |  | 0 |  | 0 | 0 | 2 | 3
2SEF-67 | RFS.95 | M-M-H | BAU | Pre-AT |  | 2017-08-17 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
3MIT-63 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-08-18 | No |  | Completed | 2017-08-16 | Minu | Completed | 2017-08-16 | 2017-08-16 | 1 | [6 empty] | 0 |  |  |  |  | Minu |  | Completed | 2017-08-16 | 2017-08-21 |  | 1 |  | 1 |  |  |  |  | 4 | 2017-08-21 |  |  |  | 0 |  | 0 | 0 | 4 | 5
5EDW-68 | RFS.120 | H-A-H | BAU | Pre-AT |  | 2017-08-21 | No |  | Completed | 2017-08-23 | Lekshmi/Naika | Completed | 2017-08-23 | 2017-08-24 | 2 | [6 empty] | 0 | [6 empty] | Completed | 2017-08-24 | 2017-08-29 | 2 |  | 0 | 2 | 0 |  |  |  | 4 | 2017-08-29 |  |  |  | 0 |  | 0 | 0 | 5 | 6
4BUR-62 | RFS.94 | M-M-H | BAU | Pre-AT |  | 2017-08-22 | Yes | Pre-AT | Completed | 2017-08-24 | Jyoti/Ashwin | Completed | 2017-08-24 | 2017-08-24 | 1 |  | Pooja/Minu | Completed | 2017-08-24 | 2017-08-27 |  | 2 | [6 empty] | Completed | 2017-08-28 | 2017-08-31 | 4 |  | 5 | 7 | 2 |  |  |  | 4 | 2017-08-31 |  |  |  | 0 |  | 2 | 0 | 6 | 5
3WIR-62 | RFS.96 | H-A-Q | HAC | Pre-AT |  | 2017-08-23 | No |  | Completed | 2017-08-22 | Jiya/Abhishek | Completed | 2017-08-22 | 2017-08-22 | 1 | [6 empty] | 0 |  |  |  |  | Jiya |  | Completed | 2017-08-23 | 2017-08-24 |  | 3 |  | 3 |  |  |  |  | 2 | 2017-08-24 |  |  |  | 0 |  | 1 | 0 | 3 | 3
2CRR-69 | RFS.93 | M-M-H | BAU | Pre-AT |  | 2017-08-23 | Yes | Pre-AT | Completed | 2017-08-24 | Lekshmi/ Abhishek | Completed | 2017-08-24 | 2017-08-25 | 2 |  | Naika/Anju | Completed | 2017-08-24 | 2017-08-27 |  | 2 | [6 empty] | Completed | 2017-08-28 | 2017-09-05 | 6 |  | 14 | 18 | 2 |  |  |  | 5 | 2017-09-05 |  |  |  | 0 |  | 1 | 0 | 7 | 7
3WER-64 | RFS.100 | M-B-H [P] | BAU | Pre-AT |  | 2017-08-23 | Yes |  | Completed | 2017-10-04 | Abhishek Ojha | Completed | 2017-10-04 | 2017-10-06 | 3 |  | Jyoti | Completed | 2017-10-04 | 2017-10-06 |  | 3 |  |  |  |  | Nahas Shajahan | Nahas Shajahan | Completed | 2017-10-09 | 2017-10-13 | 3 |  | 5 | 3 | 0 | 1 | 0 |  | 5 | 2017-10-13 | Job lock for one defct fix has delayed the task. |  |  | 0 |  | 1 | 0 | 8 | 8
2BAL-66 | RFS.97 | M-A-H | BAU | Pre-AT |  | 2017-08-23 |  |  | Completed | 2017-08-23 | Sree/Rejitha | Completed | 2017-08-23 | 2017-08-24 | 2 | [6 empty] | 0 | [6 empty] | Completed | 2017-08-25 | 2017-08-31 | 4 |  | 0 | 4 | 0 |  |  |  | 5 | 2017-08-31 |  |  |  | 0 |  | 1 | 0 | 7 | 7
2CRR-72 | RFS.95 | M-M-H | BAU | Pre-AT |  | 2017-08-23 | Yes | Pre-AT | Completed | 2017-08-28 | Minu/Shyama | Completed | 2017-08-28 | 2017-08-29 | 2 |  | Anju/Lekshmi | Completed | 2017-08-28 | 2017-08-31 |  | 4 | [6 empty] | Completed | 2017-08-31 | 2017-09-07 | 9 |  | 8 | 15 | 2 |  |  |  | 4 | 2017-09-07 |  |  |  | 0 |  | 2 | 0 | 7 | 6
4MGB-66 | RFS.95 | H-M-Q | BAU | Pre-AT |  | 2017-08-23 | No |  | Completed | 2017-08-22 | Ashwin/Anju | Completed | 2017-08-22 | 2017-08-22 | 1 | [6 empty] | 0 |  |  |  |  | Ashwin Vijayan |  | Completed | 2017-08-23 | 2017-08-23 | [8 empty] | 1 | 2017-08-23 |  |  |  | 0 |  | 1 | 0 | 2 | 2
3SOA-60 | RFS.96 | M-A-H | BAU | Pre-AT |  | 2017-08-24 | No |  | Completed | 2017-08-30 | Minu | Completed | 2017-08-30 | 2017-09-01 | 3 | [6 empty] | 0 | [6 empty] | Completed | 2017-09-05 | 2017-09-07 | 5 |  |  | 5 |  |  |  |  | 2 | 2017-09-07 |  |  |  | 0 |  | 0 | 0 | 5 | 5
2PET-69 | RFS.96 | M-A-H | BAU | Pre-AT |  | 2017-08-24 | No |  | Completed | 2017-08-31 | Rejitha/ Lekshmi | Completed | 2017-08-31 | 2017-09-02 | 2 | [6 empty] | 0 | [6 empty] | Completed | 2017-09-05 | 2017-09-11 | 5 |  | 0 | 5 | 0 |  |  |  | 4 | 2017-09-11 |  |  |  | 0 |  | -1 | 0 | 6 | 6
4MGB-63 | RFS.95 | H-A-Q | HAC | Pre-AT |  | 2017-08-25 | No |  | Completed | 2017-08-25 | Abhishek/Shyama | Completed | 2017-08-25 | 2017-08-25 | 1 | [6 empty] | 0 |  |  |  |  | Abhishek |  | Completed | 2017-08-25 | 2017-08-28 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-08-28 |  |  |  | 0 |  | 0 | 0 | 2 | 3
4ASH-62 | RFS.95 | H-A-Q | HAC | Pre-AT |  | 2017-08-25 | No |  | Completed | 2017-08-22 | Shyama/Minu | Completed | 2017-08-22 | 2017-08-22 | 1 | [6 empty] | 0 |  |  |  |  | Shyama |  | Completed | 2017-08-23 | 2017-08-24 |  | 3 |  | 3 |  |  |  |  | 2 | 2017-08-24 |  |  |  | 0 |  | 1 | 0 | 3 | 3
2EDG-65 |  | M-M-H | BAU | Pre-AT |  | 2017-08-22 | No | Design | Completed | 22-Aug-17 |  | Completed | 2017-08-22 | 2017-08-22 | 1 | [6 empty] | 0 | [6 empty] | Completed | 2017-08-23 | 2017-08-25 | 5 |  |  | 6 | 0 |  |  |  | 3 | 2017-08-25 |  |  |  | #VALUE! |  | 1 | 0 | #VALUE! | 4
3SOA-63 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-06 | No |  | Completed | 2017-07-07 | Lekshmi | Completed | 2017-07-07 | 2017-07-07 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed | 2017-07-10 | 2017-07-11 |  | 3 | [6 empty] | 2 | 2017-07-11 |  |  |  | 0 |  | 1 | 0 | 3 | 3
3NCO-64 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-06-06 | No |  | Completed | 2017-07-11 | Sree | Completed | 2017-07-12 | 2017-07-12 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Sree V |  | Completed | 2017-07-13 | 2017-07-17 |  | 2 | [6 empty] | 3 | 2017-07-17 |  |  |  | 1 |  | 1 | 0 | 5 | 4
2CRM-65 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-16 | No |  | Completed | 2017-06-29 | Lekshmi Balakrishnan | Completed | 2017-06-30 | 2017-06-30 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed | 2017-07-03 | 2017-07-06 |  | 1 | [6 empty] | 4 | 2017-07-06 |  |  |  | 1 |  | 1 | 0 | 6 | 5
3GLI-64 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-22 | No |  | Completed | 2017-07-13 | Jiya | Completed | 2017-07-14 | 2017-07-14 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Rejitha Retnakaran |  | Completed | 2017-07-14 | 2017-07-14 |  | 3 | [6 empty] | 1 | 2017-07-14 |  |  |  | 1 |  | 0 | 0 | 2 | 2
2CAS-62 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-06-23 | No |  | Completed | 2017-07-11 | Sree V | Completed | 2017-07-12 | 2017-07-12 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Sree V |  | Completed | 2017-07-13 | 2017-07-14 |  | 4 | [6 empty] | 2 | 2017-07-14 |  |  |  | 1 |  | 1 | 0 | 4 | 3
3DNC-67 | RFS.93 | H-A-Q | HAC | Pre-AT |  | 2017-06-26 | No |  | Completed | 2017-07-07 | Jowharulla.M | Completed | 2017-07-10 | 2017-07-10 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Jowharulla.M |  | Completed | 2017-07-11 | 2017-07-12 |  | 2 | [6 empty] | 2 | 2017-07-12 |  |  |  | 1 |  | 1 | 0 | 4 | 3
3CTA-62 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-29 | No |  | Completed | 2017-07-03 | Sree V | Completed | 2017-07-03 | 2017-07-03 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Sree V |  | Completed | 2017-07-03 | 2017-07-05 |  | 4 | [6 empty] | 3 | 2017-07-05 |  |  |  | 0 |  | 0 | 0 | 3 | 4
3HGT-74 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-06-29 | No |  | Completed | 2017-07-05 | Rejitha Retnakaran | Completed | 2017-07-05 | 2017-07-06 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Rejitha Retnakaran |  | Completed | 2017-07-06 | 2017-07-06 | [8 empty] | 1 | 2017-07-06 |  |  |  | 0 |  | 0 | 0 | 2 | 3
2CAS-60 | RFS.91 | H-A-Q | HAC | Pre-AT |  | 2017-06-29 | No |  | Completed | 2017-07-10 | Manjusha M | Completed | 2017-07-11 | 2017-07-11 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Manjusha M |  | Completed | 2017-07-12 | 2017-07-14 |  | 2 | [6 empty] | 3 | 2017-07-14 |  |  |  | 1 |  | 1 | 0 | 5 | 4
3KGP-60 | RFS.85 | H-A-Q | HAC | Pre-AT |  | 2017-07-03 | No |  | Completed | 2017-07-10 | Rejitha Retnakaran | Completed | 2017-07-11 | 2017-07-11 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Vinaybhaskar P |  | Completed | 2017-07-11 | 2017-07-12 |  | 4 | [6 empty] | 2 | 2017-07-12 |  |  |  | 1 |  | 0 | 0 | 3 | 3
3NBA-64 | RFS.87 | H-A-Q | HAC | Pre-AT |  | 2017-07-05 | No |  | Completed | 2017-07-06 | Rejitha Retnakaran | Completed | 2017-07-07 | 2017-07-07 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Rejitha Retnakaran |  | Completed | 2017-07-10 | 2017-07-10 |  | 3 | [6 empty] | 1 | 2017-07-10 |  |  |  | 1 |  | 1 | 0 | 3 | 2
2BAN-68 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-07-05 | No |  | Completed | 2017-07-06 | Anju Lisa | Completed | 2017-07-07 | 2017-07-07 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Anju Lisa |  | Completed | 2017-07-10 | 2017-07-10 |  | 2 | [6 empty] | 1 | 2017-07-10 |  |  |  | 1 |  | 1 | 0 | 3 | 2
3BOX-66 | RFS.90 | H-A-Q | HAC | Pre-AT |  | 2017-07-05 | No |  | Completed | 2017-07-12 | Anju Lisa | Completed | 2017-07-13 | 2017-07-13 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Minu |  | Completed | 2017-07-14 | 2017-07-18 |  | 1 | [6 empty] | 3 | 2017-07-18 |  |  |  | 1 |  | 1 | 0 | 5 | 4
2CAS-63 | RFS.90 | H-A-Q | HAC | Pre-AT |  | 2017-07-05 | No |  | Completed | 2017-07-07 |  | Completed | 2017-07-10 | 2017-07-10 | 1 |  |  | Not Applicable |  |  |  | 0 | [6 empty] | Completed | 2017-07-11 | 2017-07-14 |  | 1 | [6 empty] | 4 | 2017-07-14 |  |  |  | 1 |  | 1 | 0 | 6 | 5
3NCO-65 | RFS.86 | H-A-Q | HAC | Pre-AT |  | 2017-07-07 | No |  | Completed | 2017-07-07 | Minu | Completed | 2017-07-10 | 2017-07-10 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Anju Lisa |  | Completed | 2017-07-11 | 2017-07-13 |  | 2 | [6 empty] | 3 | 2017-07-13 |  |  |  | 1 |  | 1 | 0 | 5 | 4
2ROS-60 | RFS.89 | H-A-Q | HAC | Pre-AT |  | 2017-07-07 | No |  | Completed | 2017-07-12 | Lekshmi Balakrishnan | Completed | 2017-07-13 | 2017-07-13 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed | 2017-07-14 | 2017-07-18 |  | 2 | [6 empty] | 3 | 2017-07-18 |  |  |  | 1 |  | 1 | 0 | 5 | 4
3CAU-69 | RFS.91 | H-A-Q | HAC | Pre-AT |  | 2017-07-12 | No |  | Completed | 2017-07-13 | Manjusha M | Completed | 2017-07-14 | 2017-07-14 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Jyoti |  | Completed | 2017-07-17 | 2017-07-19 |  | 1 | [6 empty] | 3 | 2017-07-19 |  |  |  | 1 |  | 1 | 0 | 5 | 4
2MOS-63 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-07-12 | No |  | Completed | 2017-07-21 | Sree V | Completed | 2017-07-21 | 2017-07-21 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Sree V |  | Completed | 2017-07-24 | 2017-07-25 |  | 1 | [6 empty] | 2 | 2017-07-25 |  |  |  | 0 |  | 1 | 0 | 3 | 3
4BLH-60 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-07-12 | No |  | Completed | 2017-07-17 | Rejitha Retnakaran | Completed | 2017-07-17 | 2017-07-17 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Jiya |  | Completed | 2017-07-18 | 2017-07-20 |  | 2 | [6 empty] | 3 | 2017-07-20 |  |  |  | 0 |  | 1 | 0 | 4 | 4
3BGO-60 | RFS.91 | H-A-Q | HAC | Pre-AT |  | 2017-07-13 | No |  | Completed | 2017-07-17 | Sree V | Completed | 2017-07-18 | 2017-07-18 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Jyoti |  | Completed | 2017-07-19 | 2017-07-20 |  | 2 | [6 empty] | 2 | 2017-07-20 |  |  |  | 1 |  | 1 | 0 | 4 | 3
4MGA-66 | RFS.114 | M-A-Q | HAC | Pre-AT |  | 2017-08-08 | No |  | Completed | 2017-10-10 | Rejitha Retnakaran | Completed | 2017-10-10 | 2017-10-10 | 1 | [6 empty] | 0 |  |  |  |  | Rejitha |  | Completed | 2017-10-10 | 2017-10-10 |  | 2 |  | 2 |  |  |  |  | 1 | 2017-10-10 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4MGB-61 | RFS.95 | H-A-H | BAU | Pre-AT |  | 2017-08-29 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2EAS-67 | RFS.96 | M-M-H | BAU | Pre-AT |  | 2017-08-29 | No |  | Completed | 2017-08-28 | Rejitha/Sree | Completed | 2017-08-28 | 2017-08-29 | 2 | [6 empty] | 0 | [6 empty] | Completed | 2017-08-31 | 2017-09-06 | 10 |  | 0 | 10 | 0 |  |  |  | 3 | 2017-09-06 |  |  |  | 0 |  | 2 | 0 | 6 | 5
2EAS-68 | RFS.0 | M-A-H | BAU | Pre-AT |  | 2017-08-29 | No |  | Completed | 2017-09-01 | Rejitha Retnakaran | Completed | 2017-09-01 | 2017-09-05 | 1 | [6 empty] | 0 | [6 empty] | Completed | 2017-09-11 | 2017-09-15 | 3 |  | 0 | 3 | 0 |  |  |  | 5 | 2017-09-15 |  |  |  | 0 |  | 3 | 0 | 9 | 6
4CHP-60 | RFS.95 | M-M-H | BAU | Pre-AT |  | 2017-08-30 | No |  | Completed | 2017-08-30 | Jiya | Completed | 2017-08-30 | 2017-09-01 | 3 | [6 empty] | 0 | [6 empty] | Completed | 2017-09-05 | 2017-09-13 | 5 |  |  | 4 | 1 |  |  |  | 6 | 2017-09-14 |  |  |  | 0 |  | 0 | 0 | 10 | 9
2EAS-65 | RFS.93 | M-M-H | BAU | Pre-AT |  | 2017-08-30 | Yes | Pre-AT | Completed | 2017-08-25 | NA | Completed | NA | NA | #VALUE! |  | Jyoti/Ashwin | Completed | 2017-08-25 | 2017-08-29 |  | 3 | [6 empty] | Completed | 2017-08-30 | 2017-09-05 | 0 | 0 | 5 | 5 | 0 |  |  |  | 3 | 2017-09-05 |  |  |  | #VALUE! |  | #VALUE! | 0 | 6 | #VALUE!
2BON-65 | RFS.99 | H-A-Q | HAC | Pre-AT |  | 2017-08-30 | No |  | Completed | 2017-08-28 | Pooja | Completed | 2017-08-28 | 2017-08-28 | 1 | [6 empty] | 0 |  |  |  |  | Pooja |  | Completed - Handed over to NEO | 2017-08-29 | 2017-08-29 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-08-29 |  |  |  | 0 |  | 1 | 0 | 2 | 2
3SOA-65 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-08-30 | No |  | Completed | 2017-08-31 | Minu | Completed | 2017-08-31 | 2017-09-01 | 2 | [6 empty] | 0 |  |  |  |  | Minu |  | Completed - Handed over to NEO | 2017-09-01 | 2017-09-01 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-09-01 |  |  |  | 0 |  | 0 | 0 | 2 | 3
2EDG-62 | RFS.96 | M-M-H | BAU | Pre-AT |  | 2017-08-31 | Yes | Pre-AT | Completed | 2017-08-29 | Sree V | Completed | 2017-08-29 | 2017-08-30 | 2 |  | Rejitha/Abhishek | Completed | 2017-08-29 | 2017-09-01 |  | 4 | [6 empty] | Completed | 2017-09-01 | 2017-09-07 | 11 |  | 0 | 11 | 0 |  |  |  | 3 | 2017-09-07 |  |  |  | 0 |  | 2 | 0 | 6 | 5
2EAS-62 | RFS.96 | M-M-H | BAU | Pre-AT |  | 2017-08-31 | No |  | Completed | 2017-08-30 |  | Completed | 2017-08-30 | 2017-08-01 | -21 | [6 empty] | 0 | [6 empty] | Completed | 2017-09-05 | 2017-09-12 | 5 |  | 0 | 5 | 0 |  |  |  | 5 | 2017-09-12 |  |  |  | 0 |  | 22 | 0 | 8 | -16
2PEN-63 |  | H-A-Q | HAC | Pre-AT |  | 2017-08-31 | No |  | Completed | 2017-09-14 | Abhishek Ojha | Completed | 2017-09-14 | 2017-09-14 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Abhishek Ojha |  | Completed | 2017-09-14 | 2017-09-18 |  | 2 |  | 2 |  |  |  |  | 3 | 2017-09-18 |  |  |  | 0 |  | 0 | 0 | 3 | 4
5GNG-61 | RFS.95 | M-A-H | BAU | Pre-AT |  | 2017-09-04 | Yes |  | Completed | 2017-09-06 | Jyoti | Completed | 2017-09-06 | 2017-09-06 | 1 |  | Pooja Jacob | Completed | 2017-09-06 | 2017-09-11 |  | 4 | [6 empty] | Completed | 2017-09-11 | 2017-09-14 | 2 |  | 3 | 5 | 0 |  |  |  | 4 | 2017-09-14 |  |  |  | 0 |  | 3 | 0 | 7 | 5
5MOD-63 | RFS.63 | M-A-J | BAU | Pre-AT |  | 2017-09-04 | No |  | Completed | 2017-09-04 | Sree Ram Sundar | Completed | 2017-09-04 | 2017-09-05 | 0 | [6 empty] | 0 | [6 empty] | Completed | 2017-09-07 | 2017-09-18 | 6 |  | 0 | 6 | 0 |  |  |  | 8 | 2017-09-18 |  |  |  | -1 |  | 1 | 0 | 9 | 8
4EMP-63 | RFS.98 | M-B-H | BAU | Pre-AT |  | 2017-09-04 | Yes |  | Completed | 2017-08-31 | Sree Ram Sundar | Completed | 2017-08-31 | 2017-09-01 | 2 |  | Naika Arjun | Completed | 2017-08-30 | 2017-09-01 |  | 3 | [6 empty] | Completed | 2017-09-05 | 2017-09-11 | 8 |  | 5 | 13 | 0 |  |  |  | 4 | 2017-09-11 |  |  |  | 0 |  | 0 | 0 | 6 | 6
2BON-67 | RFS.67 | H-A-Q | HAC | Pre-AT |  | 2017-09-04 | No |  | Completed | 2017-09-06 | Minu | Completed | 2017-09-06 | 2017-09-06 | 1 | [6 empty] | 0 |  |  |  |  | Minu |  | Completed | 2017-09-06 | 2017-09-06 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-09-06 |  |  |  | 0 |  | 0 | 0 | 1 | 2
2STL-64 | RFS.104 | M-M-H | BAU | Pre-AT |  | 2017-09-04 | Yes |  | Completed | 2017-10-17 | Sree V | Completed | 2017-10-19 | 2017-10-20 | 2 |  | Naika | Completed | 2017-10-17 | 2017-10-20 |  | 3 | [5 empty] | Jiya/Bijeta | Completed | 2017-10-23 | 2017-10-26 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 4 | 2017-10-26 | QI Completed and SAM available not in Appian.IT Incident REQ000002947287 raised for LOC Id Count mismatch between Address QA Report and HFC Premise to ON Report DefectResolution: The task is not available in Appian. 1 major defect was incorrectly raised as minor and it is also closed and there were 2 LMS defects to follow-up. The two major defects were for redline mismatches and had many issues in them to correct. |  |  | 1 |  | 1 | 0 | 7 | 6
4CUR-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | 2017-09-04 | No |  | Completed | 2017-09-11 | Minu | Completed | 2017-09-11 | 2017-09-12 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Minu |  | Completed | 2017-09-12 | 2017-09-13 |  | 2 |  | 2 |  |  |  |  | 2 | 2017-09-13 |  |  |  | 0 |  | 0 | 0 | 3 | 4
4CHD-64 | RFS.97 | M-A-H | BAU | Pre-AT |  | 2017-09-06 |  |  | Completed | 2017-09-07 | Abhishek Ojha | Completed | 2017-09-07 | 2017-09-11 | 3 | [6 empty] | 0 | [6 empty] | Completed | 2017-09-11 | 2017-09-11 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2017-09-11 |  |  |  | 0 |  | 0 | 0 | 3 | 4
6MLO-64 | RFS.99 | H-A-Q | HAC | Pre-AT |  | 2017-09-08 | No |  | Completed | 2017-09-06 | Abhishek Ojha | Completed | 2017-09-06 | 2017-09-06 | 1 | [6 empty] | 0 |  |  |  |  | Abhishek Ojha |  | Completed | 2017-09-06 | 2017-09-06 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-09-06 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4CPB-20 | RFS.98 | M-B-H | BAU | Pre-AT |  | 2017-09-12 | Yes |  | Completed | 2017-09-20 |  | Not Applicable |  |  | 0 |  | Vinay | Completed | 2017-09-20 | 2017-09-23 |  | 3 | [6 empty] | Completed | 2017-09-25 | 2017-09-28 | 0 |  | 7 | 0 | 0 | 1 | 0 |  | 4 | 2017-09-28 | Extra 1 day as the SAM is having around 19 FNOs, which is higher than the average of 4-5 FNOs |  |  | -30690 |  | 30691 | 0 | 7 | 4
3DNC-61 | RFS.95 | H-A-Q | HAC | Pre-AT |  | 2017-09-12 | No |  | Completed | 2017-09-11 | Abhishek Ojha | Completed | 2017-09-11 | 2017-09-11 | 1 | [6 empty] | 0 |  |  |  |  | Abhishek Ojha |  | Completed | 2017-09-12 | 2017-09-12 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-09-12 | Extra 1 day as the SAM is having around 10 FNOs, which is higher than the average of 4-5 FNOs |  |  | 0 |  | 1 | 0 | 2 | 2
4BUR-21 | RFS.94 | M-B-H | BAU | Pre-AT |  | 2017-09-12 | Yes |  | Completed | 2017-09-20 |  | Not Applicable |  |  | 0 |  | Sree/Anju | Completed | 2017-09-20 | 2017-09-23 |  | 3 | [6 empty] | Completed | 2017-09-25 | 2017-09-28 | 0 |  | 7 | 0 | 0 | 1 | 0 |  | 4 | 2017-09-28 |  |  |  | -30690 |  | 30691 | 0 | 7 | 4
3NCO-60 | RFS.97 | M-M-H | BAU | Pre-AT |  | 2017-09-13 | No |  | Completed | 2017-09-14 | Lekshmi Balakrishnan | Completed | 2017-09-14 | 2017-09-18 | 3 |  |  | Not Applicable |  |  |  | 0 | [6 empty] | Completed | 2017-09-19 | 2017-09-22 | 5 |  | 0 | 3 | 0 | 0 | 2 |  | 4 | 2017-09-22 |  |  |  | 0 |  | 1 | 0 | 7 | 7
4MGA-62 | RFS.80 | M-A-H | BAU | Pre-AT |  | 2017-09-13 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2CRR-60 | RFS.100 | M-M-H | BAU | Pre-AT |  | 2017-09-13 | No |  | Completed | 2017-09-18 | Jyoti | Completed | 2017-09-18 | 2017-09-20 | 3 |  |  | Not Applicable |  |  |  | 0 | [6 empty] | Completed | 2017-09-21 | 2017-09-25 | 7 |  |  | 4 |  |  | 3 |  | 3 | 2017-09-26 |  |  |  | 0 |  | 1 | 0 | 7 | 6
3BNT-63 | RFS.96 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-07 | Sree V | Completed | 2017-09-07 | 2017-09-07 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Sree V |  | Completed | 2017-09-07 | 2017-09-11 |  | 2 |  | 2 |  |  |  |  | 3 | 2017-09-11 |  |  |  | 0 |  | 0 | 0 | 3 | 4
4SRW-61 | RFS.103 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-15 | Pooja | Completed | 2017-09-15 | 2017-09-15 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Pooja |  | Completed | 2017-09-15 | 2017-09-18 | [8 empty] | 2 | 2017-09-18 |  |  |  | 0 |  | 0 | 0 | 2 | 3
3DAD-67 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-14 | Anju Lisa | Completed | 2017-09-14 | 2017-09-14 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Anju Lisa |  | Completed | 2017-09-14 | 2017-09-18 |  | 1 |  | 1 |  |  |  |  | 3 | 2017-09-18 |  |  |  | 0 |  | 0 | 0 | 3 | 4
2STL-63 | RFS.103 | H-B-Q | BAU | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-14 | Minu | Completed | 2017-09-14 | 2017-09-14 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Minu |  | Completed | 2017-09-14 | 2017-09-15 | 1 |  |  | 1 |  |  |  |  | 2 | 2017-09-15 |  |  |  | 0 |  | 0 | 0 | 2 | 3
3RWO-61 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-14 | Ashwin Vijayan | Completed | 2017-09-14 | 2017-09-14 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Ashwin Vijayan |  | Completed | 2017-09-14 | 2017-09-18 |  | 1 |  | 1 |  |  |  |  | 3 | 2017-09-18 |  |  |  | 0 |  | 0 | 0 | 3 | 4
3DAD-66 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-19 | Minu | Completed | 2017-09-19 | 2017-09-19 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Minu |  | Completed | 2017-09-19 | 2017-09-22 |  | 1 |  | 1 |  |  |  |  | 4 | 2017-09-22 |  |  |  | 0 |  | 0 | 0 | 4 | 5
3DAD-63 | RFS.97 | H-A-Q | HAC | Pre-AT |  | 2017-09-14 | No |  | Completed | 2017-09-18 | Abhishek Ojha | Completed | 2017-09-18 | 2017-09-19 | 2 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Abhishek Ojha |  | Completed | 2017-09-19 | 2017-09-21 |  | 1 |  | 1 |  |  |  |  | 3 | 2017-09-21 |  |  |  | 0 |  | 0 | 0 | 4 | 5
5WES-64 | RFS.108 | H-A-Q | HAC | Pre-AT |  | 2017-09-18 | No |  | Completed | 2017-09-21 | Abhishek Ojha | Completed | 2017-09-21 | 2017-09-21 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Abhishek Ojha |  | Completed | 2017-09-22 | 2017-09-26 |  |  |  | 2 |  |  |  |  | 3 | 2017-09-26 |  |  |  | 0 |  | 1 | 0 | 4 | 4
3BOX-65 | RFS.98 | M-A-H | BAU | Pre-AT |  | 2017-09-18 | No |  | Completed | 2017-09-14 | Jiya | Completed | 2017-09-14 | 2017-09-15 | 2 |  |  | Not Applicable |  |  |  | 0 | [6 empty] | Completed | 2017-09-18 | 2017-09-20 | 3 |  | 0 | 2 | 1 |  |  |  | 3 | 2017-09-20 |  |  |  | 0 |  | 1 | 0 | 5 | 5
3GLI-62 | RFS.100 | M-A-H | BAU | Pre-AT |  | 2017-09-19 | No |  | Completed | 2017-09-22 | Jiya | Completed | 2017-09-22 | 2017-09-26 | 3 | [6 empty] | 0 | [6 empty] | Completed | 2017-09-27 | 2017-09-28 | 5 |  | 0 | 3 | 2 | 0 | 0 |  | 2 | 2017-09-28 |  |  |  | 0 |  | 1 | 0 | 5 | 5
2MIL-60 | RFS.103 | M-M-H | BAU | Pre-AT |  | 2017-09-19 | No |  | Completed | 2017-10-11 | Sree V | Completed | 2017-10-11 | 2017-10-11 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Nahas Shajahan |  | Completed | 2017-10-12 | 2017-10-12 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-10-12 |  |  |  | 0 |  | 1 | 0 | 2 | 2
2PYM-60 | RFS.99 | H-A-Q | HAC | Pre-AT |  | 2017-09-19 | No |  | Completed | 2017-09-25 | Anju Lisa | Completed | 2017-09-25 | 2017-09-25 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Anju Lisa |  | Completed | 2017-09-25 | 2017-09-27 |  | 2 |  | 2 |  |  |  |  | 3 | 2017-09-27 |  |  |  | 0 |  | 0 | 0 | 3 | 4
4MGB-62 | RFS.99 | M-M-H | BAU | Pre-AT |  | 2017-09-20 | Yes |  | Completed - Handed over to NEO | 2017-09-18 | Sree V | Completed | 2017-09-18 | 2017-09-19 | 2 |  | Rejitha Retnakaran | Completed | 2017-12-12 | 2017-12-13 | 2017-12-13 | 2 | [6 empty] | Completed | 2017-09-20 | 2017-09-21 | 2 |  | 3 | 1 | 1 |  |  |  | 2 | 2017-09-21 | QI for FTTN part is completed and is in review with Salah/Carl. |  |  | 0 |  | 1 | 0 | 4 | 4
2PEN-66 | RFS.99 | H-A-Q | HAC | Pre-AT |  | 2017-09-20 | No |  | Completed | 2017-09-18 | Minu | Completed | 2017-09-18 | 2017-09-18 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Minu |  | Completed | 2017-09-18 | 2017-09-18 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-09-18 |  |  |  | 0 |  | 0 | 0 | 1 | 2
3WER-65 | RFS.99 | M-A-H | BAU | Pre-AT |  | 2017-09-20 | No |  | Completed | 2017-09-18 | Lekshmi Balakrishnan | Completed | 2017-09-18 | 2017-09-19 | 2 |  |  | Not Applicable |  |  |  | 0 | [6 empty] | Completed | 2017-09-20 | 2017-09-22 | 5 |  | 0 | 3 | 2 |  |  |  | 3 | 2017-09-22 |  |  |  | 0 |  | 1 | 0 | 5 | 5
3BOX-61 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-09-20 | No |  | Completed | 2017-09-19 | Ashwin Vijayan | Completed | 2017-09-19 | 2017-09-19 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Ashwin Vijayan |  | Completed | 2017-09-20 | 2017-09-21 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-09-21 |  |  |  | 0 |  | 1 | 0 | 3 | 3
2PEN-62 | RFS.100 | H-A-Q | HAC | Pre-AT |  | 2017-09-21 | No |  | Completed | 2017-09-20 | Naika Arjun | Completed | 2017-09-20 | 2017-09-20 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Naika |  | Completed | 2017-09-20 | 2017-09-22 |  | 2 |  | 2 |  |  |  |  | 3 | 2017-09-22 |  |  |  | 0 |  | 0 | 0 | 3 | 4
5GLL-61 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-21 | No |  | Completed | 2017-09-25 | Sree V | Completed | 2017-09-25 | 2017-09-25 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Sree V |  | Completed | 2017-09-26 | 2017-09-28 |  |  |  | 2 |  |  |  |  | 3 | 2017-09-28 | 1 defect went to on hold due to drop cable issue.(Awaited clarification from DSG) |  |  | 0 |  | 1 | 0 | 4 | 4
4BUR-60 | RFS.103 | M-A-Q | HAC | Pre-AT |  | 2017-09-21 | No |  | Completed | 2017-09-21 | Jyoti | Completed | 2017-09-21 | 2017-09-21 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Jyoti |  | Completed | 2017-09-25 | 2017-09-26 |  | 2 |  | 2 |  |  |  |  | 2 | 2017-09-26 |  |  |  | 0 |  | 2 | 0 | 4 | 3
4MGB-20 | RFS.100 | M-B-H | BAU | Pre-AT |  | 2017-09-21 | Yes |  | Completed | 2017-09-22 |  | Not Applicable |  |  | 0 |  | Naika | Completed | 2017-09-22 | 2017-09-26 |  | 3 | [6 empty] | Completed | 2017-09-28 | 2017-10-03 | 0 |  | 3 | 0 | 0 | 0 | 0 |  | 2 | 2017-10-03 |  |  |  | -30692 |  | 30694 | 0 | 6 | 2
4ASH-63 | RFS.134 | H-M-H | BAU | Pre-AT |  | 2017-09-22 |  |  | Completed | 2017-10-03 | Naika Arjun | Completed | 2017-10-03 | 2017-10-04 | 2 | [6 empty] | 0 | [6 empty] | Completed | 2017-10-05 | 2017-10-09 | 2 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | 2017-10-09 |  |  |  | 0 |  | 1 | 0 | 5 | 5
3KYG-64 | RFS.100 | M-A-H | BAU | Pre-AT |  | 2017-09-25 |  |  | Completed | 2017-10-13 | Naika Arjun | Completed | 2017-10-17 | 2017-10-17 | 1 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed | 2017-10-16 | 2017-10-17 | 5 |  | 0 | 5 | 0 | 0 | 3 |  | 2 | 2017-10-17 |  |  |  | 2 |  | -3 | 0 | 3 | 3
2SEV-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-09-25 | No |  | Completed | 2017-09-29 | Minu | Completed | 2017-09-29 | 2017-10-02 | 0 |  |  | Not Applicable |  |  |  | 0 | [6 empty] | Completed | 2017-10-03 | 2017-10-03 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-10-03 |  |  |  | -1 |  | 0 | 0 | 1 | 1
3NCO-66 | RFS.98 | H-A-Q | HAC | Pre-AT |  | 2017-09-21 | No |  | Completed | 2017-09-22 | Minu | Completed | 2017-09-22 | 2017-09-22 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Minu |  | Completed | 2017-09-25 | 2017-09-26 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-09-26 |  |  |  | 0 |  | 1 | 0 | 3 | 3
3CAU-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-25 |  |  | Completed | 2017-09-27 | Minu | Completed | 2017-09-27 | 2017-09-27 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Minu |  | Completed | 2017-09-27 | 2017-09-28 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-09-28 |  |  |  | 0 |  | 0 | 0 | 2 | 3
4CPR-61 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-25 | No |  | Completed | 2017-09-26 | Abhishek Ojha | Completed | 2017-09-26 | 2017-09-26 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Abhishek Ojha |  | Completed | 2017-09-27 | 2017-09-28 |  | 2 |  | 2 |  |  |  |  | 2 | 2017-09-28 |  |  |  | 0 |  | 1 | 0 | 3 | 3
4AGV-20 | RFS.126 | M-A-H | BAU | Pre-AT |  | 2017-10-02 | No |  | Completed | 2017-10-16 | Sree V | Completed | 2017-10-16 | 2017-10-17 | 2 | [6 empty] | 0 |  |  |  |  | Jiya |  | Completed | 2017-10-20 | 2017-10-25 | 5 | 0 | 0 | 5 | 0 | 0 | 0 |  | 4 | 2017-10-25 | DefectResolution: The task is not available in Appian. One defect (DF115294) was with AP team and there was delay in getting the clarification. It was added in Appian on 10-Nov and closed the task on 13-Nov. |  |  | 0 |  | 2 | 0 | 7 | 6
4SUR-62 | RFS.113 | M-A-H | BAU | Pre-AT |  | 2017-09-27 | No |  | Completed | 2017-10-24 | Abhishek Ojha | Completed | 2017-10-24 | 2017-10-25 | 2 | [6 empty] | 0 | [6 empty] | Completed | 2017-10-25 | 2017-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-10-25 | RFS group not marked in Appian. SAM is in Pre-Design in Appian. DefectResolution: Zero defect SAM. |  |  | 0 |  | 0 | 0 | 2 | 3
3TNI-64 | RFS.103 | M-A-H | BAU | Pre-AT |  | 2017-09-27 | No |  | Completed | 2017-09-28 | Ashwin Vijayan | Completed | 2017-09-28 | 2017-09-29 | 1 |  |  | Not Applicable |  |  |  | 0 | [6 empty] | Completed | 2017-10-03 | 2017-10-03 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-10-03 |  |  |  | 0 |  | 0 | 0 | 2 | 2
3MLN-65 | RFS.100 | H-A-Q | HAC | Pre-AT |  | 2017-09-27 |  |  | Completed | 2017-09-28 | Jyoti | Completed | 2017-09-28 | 2017-09-28 | 1 | [6 empty] | 0 |  |  |  |  | Jyoti |  | Completed | 2017-09-29 | 2017-10-03 |  |  |  | 3 |  |  |  |  | 1 | 2017-09-29 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4MGA-70 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-28 |  |  | Completed | 2017-09-27 | Sree V | Completed | 2017-09-27 | 2017-09-27 | 1 | [6 empty] | 0 |  |  |  |  | Sree V |  | Completed | 2017-09-27 | 2017-09-28 |  | 2 |  | 2 |  |  |  |  | 2 | 2017-09-28 |  |  |  | 0 |  | 0 | 0 | 2 | 3
4MGA-72 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-09-28 | No |  | Completed | 2017-09-26 | Ashwin Vijayan | Completed | 2017-09-26 | 2017-09-26 | 1 |  |  | Not Applicable |  |  |  | 0 |  |  |  |  | Ashwin Vijayan |  | Completed | 2017-09-26 | 2017-09-27 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-09-27 |  |  |  | 0 |  | 0 | 0 | 2 | 3
2CAS-66 | RFS.101 | M-A-H | BAU | Pre-AT |  | 2017-10-02 | No |  | Completed | 2017-10-04 | Rejitha Retnakaran | Completed | 2017-10-04 | 2017-10-05 | 2 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed | 2017-10-06 | 2017-10-12 | 6 |  | 0 | 5 | 1 | 0 | 0 |  | 5 | 2017-10-12 | 2 Defects with duplicate design issue have got clarified on the last day only from Design team. |  |  | 0 |  | 1 | 0 | 7 | 7
2WET-65 | RFS.100 | M-M-H | BAU | Pre-AT |  | 2017-10-04 | Yes |  | Completed | 2017-10-06 | Naika Arjun | Completed | 2017-10-06 | 2017-10-09 | 2 |  | Sree/Minu | Completed | 2017-10-06 | 2017-10-10 |  | 3 |  |  |  |  | Nahas Shajahan | Nahas Shajahan | Completed | 2017-10-11 | 2017-10-12 | 0 |  | 8 | 0 | 0 | 0 | 0 |  | 2 | 2017-10-12 |  |  |  | 0 |  | 2 | 0 | 5 | 4
4CPR-65 | RFS.105 | M-A-H | BAU | Pre-AT |  | 2017-10-04 | No |  | Completed | 2017-10-06 | Ashwin Vijayan | Completed | 2017-10-06 | 2017-10-06 | 1 | [6 empty] | 0 | [6 empty] | Completed | 2017-10-09 | 2017-10-09 | 1 |  | 0 | 1 | 0 | 0 | 0 |  | 1 | 2017-10-09 |  |  |  | 0 |  | 1 | 0 | 2 | 2
4CPR-62 | RFS.121 | M-A-H | BAU | Pre-AT |  | 2017-10-04 | No |  | Completed | 2017-10-04 | Anju Lisa | Completed | 2017-10-04 | 2017-10-05 | 2 | [6 empty] | 0 | [6 empty] | Completed | 2017-10-06 | 2017-10-06 | 2 |  | 0 | 0 | 2 | 0 | 0 |  | 1 | 2017-10-06 |  |  |  | 0 |  | 1 | 0 | 3 | 3
3BOX-64 | RFS.100 | H-A-Q | HAC | Pre-AT |  | 2017-10-06 | No |  | Completed | 2017-10-09 | Anju Lisa | Completed | 2017-10-09 | 2017-10-09 | 1 | [6 empty] | 0 |  |  |  |  | Anju |  | Completed | 2017-10-09 | 2017-10-10 |  | 1 | 1 | [5 empty] | 2 | 2017-10-10 |  |  |  | 0 |  | 0 | 0 | 2 | 3
5BRI-61 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-09 | No |  | Completed | 2017-10-09 | Jyoti | Completed | 2017-10-09 | 2017-10-09 | 1 | [6 empty] | 0 |  |  |  |  | Jyoti |  | Completed | 2017-10-09 | 2017-10-10 |  | 2 | [6 empty] | 2 | 2017-10-10 |  |  |  | 0 |  | 0 | 0 | 2 | 3
4ABC-60 | RFS.113 | H-A-Q | HAC | Pre-AT |  | 2017-10-06 | No |  | Completed | 2017-10-09 | Naika Arjun | Completed | 2017-10-09 | 2017-10-09 | 1 | [6 empty] | 0 |  |  |  |  | Naika |  | Completed | 2017-10-09 | 2017-10-10 |  | 2 |  | 2 |  |  |  |  | 2 | 2017-10-10 |  |  |  | 0 |  | 0 | 0 | 2 | 3
4SRW-64 | RFS.105 | H-A-Q | HAC | Pre-AT |  | 2017-10-10 | No |  | Completed | 2017-10-16 | Sree Ram Sundar | Completed | 2017-10-16 | 2017-10-16 | 1 | [6 empty] | 0 |  |  |  |  | Sree Ram Sundar |  | Completed | 2017-10-16 | 2017-10-16 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-10-16 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4CUR-61 | RFS.120 | M-A-H | BAU | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-23 | Minu | Completed | 2017-10-23 | 2017-10-24 | 2 | [6 empty] | 0 |  |  |  |  | Ramcy S |  | Completed | 2017-10-25 | 2017-10-26 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2 | 2017-10-26 | DataCheck: Delay in RPA output - exported the reports manually |  |  | 0 |  | 1 | 0 | 4 | 4
3TYH-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 |  |  | Completed | 2017-10-12 | Rejitha Retnakaran | Completed | 2017-10-12 | 2017-10-12 | 1 | [6 empty] | 0 |  |  |  |  | Rejitha |  | Completed |  |  |  | 0 |  | 0 |  |  |  |  | 0 | 2017-10-12 |  |  |  | 0 |  | -30704 | 0 | 1 | 1
2PEN-60 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-12 | Sree V | Completed | 2017-10-12 | 2017-10-12 | 1 | [6 empty] | 0 |  |  |  |  | Sree V |  | Completed | 2017-10-12 | 2017-10-13 |  | 1 |  | 1 |  |  |  |  | 2 | 2017-10-13 |  |  |  | 0 |  | 0 | 0 | 2 | 3
3CLA-66 | RFS.101 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-30 | Ashwin Vijayan | Completed | 2017-10-30 | 2017-10-30 | 1 | [6 empty] | 0 |  |  |  |  | Ashwin Vijayan |  | Completed - Handed over to NEO | 2017-10-30 | 2017-10-31 |  | 1 | [6 empty] | 2 | 2017-10-31 |  |  |  | 0 |  | 0 | 0 | 2 | 3
5GLL-65 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-16 | Rejitha Retnakaran | Completed | 2017-10-16 | 2017-10-16 | 1 | [6 empty] | 0 |  |  |  |  | Rejitha |  | Completed | 2017-10-16 | 2017-10-16 |  |  | 0 | [5 empty] | 1 | 2017-10-16 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4WTF-63 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-13 | Rejitha Retnakaran | Completed | 2017-10-13 | 2017-10-13 | 1 | [6 empty] | 0 |  |  |  |  | Rejitha |  | Completed | 2017-10-13 | 2017-10-13 |  |  | 0 | [5 empty] | 1 | 2017-10-13 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4AAR-62 | RFS.103 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-12 | Jyoti | Completed | 2017-10-12 | 2017-10-12 | 1 | [6 empty] | 0 |  |  |  |  | Jyoti |  | Completed | 2017-10-12 | 2017-10-13 |  | 1 | [6 empty] | 2 | 2017-10-13 |  |  |  | 0 |  | 0 | 0 | 2 | 3
3BNT-66 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-16 | Sree Ram Sundar | Completed | 2017-10-16 | 2017-10-16 | 1 | [6 empty] | 0 |  |  |  |  | Sree Ram Sundar |  | Completed | 2017-10-16 | 2017-10-16 |  |  | 0 | [5 empty] | 1 | 2017-10-16 |  |  |  | 0 |  | 0 | 0 | 1 | 2
5BRI-63 | RFS.104 | M-A-H | BAU | Pre-AT |  | 2017-10-11 | No |  | Completed | 2017-10-18 | Sree Ram Sundar | Completed | 2017-10-18 | 2017-10-19 | 1 | [6 empty] | 0 |  |  |  |  | Bijeta |  | Completed | 2017-10-20 | 2017-10-26 | 3 | 0 | 0 | 3 | 0 | 0 | 0 |  | 5 | 2017-10-26 | DefectResolution: Two defects are with LMS - DF115661 and DF116243. There was some delay from AP team for clarification for the defect - DF115660. |  |  | -1 |  | 1 | 0 | 6 | 6
4WTF-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-10-24 | No |  | Completed - Handed over to NEO | 2017-10-27 | Abhishek Ojha | Completed | 2017-10-30 | 2017-10-30 | 1 | [6 empty] | 0 | [6 empty] | Completed - Handed over to NEO | 2017-10-30 | 2017-11-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 2017-11-07 | There is only one defect - DF117314 and it is assigned to AP team. FSA-SAM boundary mismatch which affected one location. Informed AP team on 27th October, evening. A CR was raised by AP team on 1st Nov. Issue fixed on 7-Nov |  |  | 1 |  | 0 | 0 | 7 | 7
4ORM-60 | RFS.109 | H-A-Q | HAC | Pre-AT |  | 2017-10-17 | No |  | Completed | 2017-10-20 | Sree Ram Sundar | Completed | 2017-10-20 | 2017-10-20 | 1 | [6 empty] | 0 |  |  |  |  | Sree Ram Sundar |  | Completed | 2017-10-20 | 2017-10-20 | 0 | 0 |  | 0 | 0 |  |  |  | 1 | 2017-10-20 |  |  |  | 0 |  | 0 | 0 | 1 | 2
3CAU-63 | RFS.105 | M-A-H | BAU | Pre-AT |  | 2017-10-17 | No |  | Completed | 2017-10-16 | Naika Arjun | Completed | 2017-10-16 | 2017-10-17 | 2 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed | 2017-10-17 | 2017-10-17 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 2017-10-17 | Task not available in Appian. It was added in Appian on 10-Nov and closed the task on 13-Nov. |  |  | 0 |  | 0 | 0 | 2 | 3
2STL-60 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-17 | No |  | Completed | 2017-10-17 | Lekshmi Balakrishnan | Completed | 2017-10-17 | 2017-10-17 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi |  | Completed | 2017-10-17 | 2017-10-17 | 0 |  | 0 | [5 empty] | 1 | 2017-10-17 |  |  |  | 0 |  | 0 | 0 | 1 | 2
3TNI-63 | RFS.103 | M-A-Q | BAU | Pre-AT |  | 2017-10-17 | No |  | Completed | 2017-10-17 | Minu | Completed | 2017-10-17 | 2017-10-17 | 1 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed | 2017-10-18 | 2017-10-18 | 1 |  | 0 | 1 | 0 | 0 | 0 |  | 0 | 2017-10-18 |  |  |  | 0 |  | 0 | 0 | 1 | 1
6WMB-63 | RFS.120 | M-A-H | BAU | Pre-AT |  | 2017-10-18 | No |  | Completed | 2017-10-24 | Lekshmi Balakrishnan | Completed | 2017-10-24 | 2017-10-24 | 1 | [6 empty] | 0 | [6 empty] | Completed | 2017-10-25 | 2017-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-10-25 | Zero defect |  |  | 0 |  | 1 | 0 | 2 | 2
2MIL-63 | RFS.103 | M-M-H | BAU | Pre-AT |  | 2017-10-18 | No |  | Completed | 2017-10-18 | Sree Ram Sundar | Completed | 2017-10-18 | 2017-10-19 | 1 | [6 empty] | 0 |  |  |  |  | Bijeta |  | Completed | 2017-10-19 | 2017-10-20 | 4 |  | 0 | 3 | 1 | 0 | 0 |  | 2 | 2017-10-20 |  |  |  | -1 |  | 0 | 0 | 2 | 3
3BOX-63 | RFS.105 | H-A-Q | HAC | Pre-AT |  | 2017-10-18 | No |  | Completed | 2017-10-19 | Lekshmi Balakrishnan | Completed | 2017-10-19 | 2017-10-19 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi |  | Completed | 2017-10-19 | 2017-10-19 | 1 | [7 empty] | 1 | 2017-10-19 |  |  |  | 0 |  | 0 | 0 | 1 | 2
3HDB-62 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-18 |  |  | Completed | 2017-10-27 | Rejitha Retnakaran | Completed | 2017-10-27 | 2017-10-27 | 1 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | 2017-10-27 |  |  |  | 0 |  | -30714 | 0 | 1 | 1
2PNN-64 | RFS.80 | H-A-H | BAU | Pre-AT |  | 2017-10-25 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2BAN-69 | RFS.104 | H-M-Q | HAC | Pre-AT |  | 2017-10-18 | No |  | Completed | 2017-10-23 | Lekshmi Balakrishnan | Completed | 2017-10-23 | 2017-10-23 | 1 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | 2017-10-23 |  |  |  | 0 |  | -30710 | 0 | 1 | 1
3BNT-60 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-20 | No |  | Completed | 2017-10-17 | Jiya | Completed | 2017-10-17 | 2017-10-17 | 1 | [6 empty] | 0 |  |  |  |  | Jiya |  | Completed |  |  |  | 0 | [6 empty] | 0 | 2017-10-17 |  |  |  | 0 |  | -30707 | 0 | 1 | 1
3BLB-69 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-10-20 | No |  | Completed | 2017-10-20 | Lekshmi Balakrishnan | Completed | 2017-10-20 | 2017-10-20 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi |  | Completed | 2017-10-20 | 2017-10-20 |  | 0 |  | 0 | 0 |  |  |  | 1 | 2017-10-20 |  |  |  | 0 |  | 0 | 0 | 1 | 2
2PEN-64 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-20 | No |  | Completed | 2017-10-23 | Sree Ram Sundar | Completed | 2017-10-23 | 2017-10-24 | 2 | [6 empty] | 0 |  |  |  |  | Sree ram |  | Completed | 2017-10-24 | 2017-10-26 |  |  |  | 2 |  |  |  |  | 3 | 2017-10-26 | Delay in RPA output - exported the reports manually |  |  | 0 |  | 0 | 0 | 4 | 5
4APL-60 | RFS.125 | M-A-H | BAU | Pre-AT |  | 2017-10-26 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
4MGA-63 | RFS.103 | M-A-Q | HAC | Pre-AT |  | 2017-10-23 | No |  | Completed | 2017-10-23 | Anju Lisa | Completed | 2017-10-23 | 2017-10-24 | 2 | [6 empty] | 0 |  |  |  |  | Anju |  | Completed - Handed over to NEO | 2017-10-24 | 2017-10-25 |  |  | 1 | [5 empty] | 2 | 2017-10-25 |  |  |  | 0 |  | 0 | 0 | 3 | 4
2PNN-68 | RFS.104 | M-A-H | BAU | Pre-AT |  | 2017-10-24 | No |  | Completed | 2017-10-23 | Naika Arjun | Completed | 2017-10-23 | 2017-10-24 | 2 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed | 2017-10-25 | 2017-10-26 | 3 | 0 | 0 | 2 | 1 | 0 | 0 |  | 2 | 2017-10-26 |  |  |  | 0 |  | 1 | 0 | 4 | 4
4CPR-63 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-10-24 | No |  | Completed | 2017-10-24 | Sree Ram Sundar | Completed | 2017-10-24 | 2017-10-25 | 2 | [6 empty] | 0 |  |  |  |  | shahin Basheer |  | Completed | 2017-10-25 | 2017-10-25 | 0 | 2 |  | 2 |  |  |  |  | 1 | 2017-10-26 | Delay in RPA output. |  |  | 0 |  | 0 | 0 | 3 | 3
2STL-61 | RFS.104 | M-M-Q | HAC | Pre-AT |  | 2017-10-31 |  |  | Completed | 2017-10-31 | Naika Arjun | Completed | 2017-10-31 | 2017-10-31 | 1 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | 2017-10-31 |  |  |  | 0 |  | -30716 | 0 | 1 | 1
3OAK-61 | RFS.105 | M-A-H | BAU | Pre-AT |  | 2017-10-26 | No |  | Completed | 2017-10-26 | Abhishek Ojha | Completed | 2017-10-26 | 2017-10-26 | 1 | [6 empty] | 0 |  |  |  |  | Bijeta |  | Completed | 2017-10-27 | 2017-10-27 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 1 | 2017-10-27 |  |  |  | 0 |  | 1 | 0 | 2 | 2
3CAU-64 | RFS.103 | H-A-Q | HAC | Pre-AT |  | 2017-10-27 | No |  | Completed | 2017-10-25 | Lekshmi Balakrishnan | Completed | 2017-10-25 | 2017-10-25 | 1 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | 2017-10-25 |  |  |  | 0 |  | -30712 | 0 | 1 | 1
5BRI-65 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-10-27 | No |  | Completed | 2017-10-24 | Ashwin Vijayan | Completed | 2017-10-24 | 2017-10-25 | 2 | [6 empty] | 0 |  |  |  |  | Ashwin |  | Completed | 2017-10-25 | 2017-10-25 |  | 1 | [6 empty] | 1 | 2017-10-25 |  |  |  | 0 |  | 0 | 0 | 2 | 3
2ROS-66 | RFS.134 | H-A-Q | HAC | Pre-AT |  | 2017-10-27 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2STL-65 | RFS.104 | M-A-H | BAU | Pre-AT |  |  |  |  | Completed | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | Aravind V |  | Completed | 2017-07-13 | 2017-07-13 | 9 |  | 0 | 7 | 2 | 0 | 2 |  | 1 | 2017-07-13 |  |  |  | -1 |  | 30642 | 0 | 30643 | 1
3BAY-65 | RFS.126 | H-A-Q | HAC | Pre-AT |  | 2017-10-30 |  |  | Completed | 2017-10-31 | Abhishek Ojha | Completed | 2017-10-31 | 2017-10-31 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed | 2017-11-01 | 2017-11-01 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-11-01 |  |  |  | 0 |  | 1 | 0 | 2 | 2
4SSB-62 | RFS.126 | H-A-Q | HAC | Pre-AT |  | 2017-10-31 | No |  | Completed | 2017-10-30 | Rejitha Retnakaran | Completed | 2017-10-30 | 2017-10-30 | 1 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | 2017-10-30 |  |  |  | 0 |  | -30715 | 0 | 1 | 1
4ABO-67 |  | H-A-Q | HAC | Pre-AT |  | 2017-11-06 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
3OAK-64 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-11-02 |  |  | Completed - Handed over to NEO | 2017-11-16 | Abhishek Ojha | Completed | 2017-11-16 | 2017-11-16 | 1 | [5 empty] | 2017-11-16 | 0 |  |  |  |  | Abhishek Ojha |  | Completed - Handed over to NEO | 2017-11-17 | 2017-11-17 | 0 | 2 |  | 2 |  |  |  |  | 1 | 2017-11-17 |  |  |  | 0 |  | 1 | 0 | 2 | 2
4SLA-70 | RFS.108 | M-B-H | BAU | Pre-AT |  | 2017-11-02 | Yes |  | Completed - Handed over to NEO | 2017-11-02 |  |  |  |  | 0 | FTTN | Naika Arjun | Completed | 2017-11-02 | 2017-11-03 |  | 2 | [6 empty] | Completed - Handed over to NEO | 2017-11-06 | 2017-11-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-11-06 | Zero DSG defects. |  |  | -30718 |  | 30718 | 0 | 3 | 1
3NBA-67 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-10-25 |  |  | Completed - Handed over to NEO | 2017-11-01 | Ashwin Vijayan | Completed | 2017-11-01 | 2017-11-01 | 1 | [6 empty] | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-02 | 2017-11-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-11-02 | Zero defect SAM |  |  | 0 |  | 1 | 0 | 2 | 2
2CRR-65 | RFS.105 | M-M-H | BAU | Pre-AT |  | 2017-11-02 | Yes |  | Completed - Handed over to NEO | 2017-11-02 | Ashwin Vijayan | Completed | 2017-11-02 | 2017-11-02 | 1 | FTTN | Pooja Jacob | Completed | 2017-11-02 | 2017-11-03 |  | 2 |  |  |  |  | Bijeta Biswal | Bijeta Biswal | Completed - Handed over to NEO | 2017-11-06 | 2017-11-08 | 6 | 0 | 5 | 1 | 0 | 0 | 0 |  | 2 | 2017-11-08 |  |  |  | 0 |  | 2 | 0 | 4 | 3
5FLN-62 | RFS.105 | H-B-J | BAU | Pre-AT |  | 2017-11-03 |  |  | Completed - Handed over to NEO | 2017-11-03 | Rejitha Retnakaran | Completed | 2017-11-03 | 2017-11-06 | 2 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-08 | 2017-11-10 | 4 | 0 | 0 | 2 | 0 | 2 | 0 |  | 3 | 2017-11-10 |  |  |  | 0 |  | 1 | 0 | 5 | 5
2BON-64 | RFS.104 | M-A-H | BAU | Pre-AT |  | 2017-11-03 |  |  | Completed | 2017-10-31 | Rejitha Retnakaran | Completed | 2017-10-31 | 2017-10-31 | 1 | [6 empty] | 0 | [6 empty] | Completed | 2017-11-01 | 2017-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-11-01 |  |  |  | 0 |  | 1 | 0 | 2 | 2
2PNN-62 | RFS.108 | H-M-Q | HAC | Pre-AT |  | 2017-11-03 | No |  | Completed | 2017-10-30 | Abhishek Ojha | Completed | 2017-10-30 | 2017-10-30 | 1 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | 2017-10-30 |  |  |  | 0 |  | -30715 | 0 | 1 | 1
2UND-62 | RFS.108 | H-M-Q | HAC | Pre-AT |  | 2017-11-03 | No |  | Completed - Handed over to NEO | 2017-11-06 | Shahin Basheer | Completed | 2017-11-06 | 2017-11-06 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed - Handed over to NEO | 2017-11-06 | 2017-11-07 |  | 3 |  | 3 |  |  |  |  | 1 | 2017-11-07 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4SSB-60 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-11-03 | No |  | Completed - Handed over to NEO | 2017-11-08 | Anju Lisa | Completed | 2017-11-08 | 2017-11-08 | 1 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-10 | 2017-11-17 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 6 | 2017-11-17 | For the defect - DF118803, we got the clarification from design team on 16-Nov; the issue was for the newly introduced pre-rfs check. |  |  | 0 |  | 2 | 0 | 8 | 7
2PAR-63 | RFS.125 | H-A-Q | HAC | Pre-AT |  | 2017-11-03 |  |  | Completed - Handed over to NEO | 2017-11-16 | Ashwin Vijayan | Completed | 2017-11-16 | 2017-11-16 | 1 | [6 empty] | 0 |  |  |  |  | Naika Arjun |  | Completed - Handed over to NEO | 2017-01-17 | 2017-11-17 |  | 0 |  | 0 |  |  |  |  | 204 | 2017-11-17 |  |  |  | 0 |  | -204 | 0 | 2 | 205
3RWO-66 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-06 | No |  | Completed - Handed over to NEO | 2017-11-08 | Minu | Completed | 2017-11-08 | 2017-11-08 | 1 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-10 | 2017-11-15 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 4 | 2017-11-15 | LDM action was required for the defect - DF118805. |  |  | 0 |  | 2 | 0 | 6 | 5
6GIR-60 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-11-06 |  |  | Completed - Awaiting final Acceptance | 2017-11-03 | Ashwin Vijayan | Completed | 2017-11-03 | 2017-11-03 | 1 | [6 empty] | 0 | [10 empty] | 0 |  | 0 |  |  |  |  | 0 | 2017-11-03 |  |  |  | 0 |  | -30719 | 0 | 1 | 1
6KSL-61 | RFS.104 | H-A-Q | HAC | Pre-AT |  | 2017-11-06 | No |  | Completed - Handed over to NEO | 2017-11-06 | Ashwin Vijayan | Completed | 2017-11-06 | 2017-11-06 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed - Handed over to NEO | 2017-11-06 | 2017-11-06 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-11-06 | DF117761 is open defect(T18 data issue_.Will resolved at FAB stage. |  |  | 0 |  | 0 | 0 | 1 | 2
3KYG-66 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-11-06 | No |  | Completed - Handed over to NEO | 2017-11-08 | Ashwin Vijayan | Completed | 2017-11-08 | 2017-11-08 | 1 | [6 empty] | 0 |  |  |  |  | Ashwin Vijayan |  | Completed - Handed over to NEO | 2017-11-09 | 2017-11-09 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-11-09 |  |  |  | 0 |  | 1 | 0 | 2 | 2
4SRW-66 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-11-06 | No |  | Completed - Handed over to NEO | 2017-11-08 | Abhishek Ojha | Completed | 2017-11-08 | 2017-11-08 | 1 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-09 | 2017-11-09 | 1 | 0 | 0 | 1 | 0 | 0 | 1 |  | 1 | 2017-11-09 | Only one DSG defect and is open on hold with NDQ Desktop. |  |  | 0 |  | 1 | 0 | 2 | 2
3SPL-62 | RFS.120 | M-M-Q | HAC | Pre-AT |  | 2017-11-08 |  |  | Completed - Handed over to NEO | 2017-12-11 | Naika Arjun | Completed | 2017-12-11 | 2017-12-11 | 1 | [5 empty] | 2017-12-11 | 0 |  |  |  |  | Naika Arjun |  | Completed - Handed over to NEO | 2017-12-12 | 2017-12-12 | 2 |  |  | 2 |  |  |  |  | 1 | 2017-12-12 |  |  |  | 0 |  | 1 | 0 | 2 | 2
4SRW-62 | RFS.108 | M-A-Q | HAC | Pre-AT |  | 2017-11-15 | No |  | Completed - Handed over to NEO | 2017-11-28 | Vedant | Completed | 2017-11-28 | 2017-11-28 | 1 | [5 empty] | 2017-11-28 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-28 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-28 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4SSB-61 | RFS.106 | M-A-H | BAU | Pre-AT |  | 2017-11-08 | No |  | Completed - Handed over to NEO | 2017-11-08 | Naika Arjun | Completed | 2017-11-08 | 2017-11-08 | 1 | [6 empty] | 0 |  |  |  |  | Bijeta Biswal |  | Completed - Handed over to NEO | 2017-11-10 | 2017-11-14 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 3 | 2017-11-14 | The defect - DF118800 involved LDM action too. |  |  | 0 |  | 2 | 0 | 5 | 4
4MGB-01 | RFS.106 | M-B-H | BAU | Pre-AT |  | 2017-11-08 | Yes | Pre-AT | Completed - Handed over to NEO | 2017-11-22 |  | Not Applicable |  |  | 0 |  | Pooja Jacob | Completed | 2017-11-22 | 2017-11-23 | 2017-11-23 | 2 | Lekshmi Balakrishnan | 2017-11-28 | 2017-11-29 | Completed |  | Bijeta Biswal | Completed - Handed over to NEO | 2017-11-24 | 2017-11-29 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 1 | 4 | 2017-11-29 | Atlas-MTM sync issue- Defects not reflecting in MTM |  |  | -30731 |  | 30731 | 0 | 6 | 4
2FRE-61 | RFS.104 | M-A-H | BAU | Pre-AT |  | 2017-11-03 | No |  | Completed | 2017-10-24 | Rejitha Retnakaran | Completed | 2017-10-24 | 2017-10-24 | 1 | [6 empty] | 0 | [6 empty] | Completed | 2017-10-26 | 2017-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-10-25 | Zero defect SAM |  |  | 0 |  | 2 | 0 | 2 | 2
4FHL-61 | RFS.122 | M-A-Q | HAC | Pre-AT |  | 2017-11-09 | No |  | Completed - Handed over to NEO | 2017-11-21 | Rejitha Retnakaran | Completed | 2017-11-21 | 2017-11-21 | 1 | [6 empty] | 0 |  |  |  |  | Rejitha Retnakaran |  | Completed - Handed over to NEO | 2017-11-21 | 2017-11-21 |  | 2 |  | 2 |  |  |  |  | 1 | 2017-11-21 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4AAR-61 | RFS.103 | M-A-H | BAU | Pre-AT |  | 2017-11-09 | No | Yes | Completed - Handed over to NEO | 2017-11-06 | Pooja Jacob | Completed | 2017-11-06 | 2017-11-08 | 2 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-09 | 2017-11-20 | 2 | 0 | 0 | 2 | 0 | 0 | 0 |  | 8 | 2017-11-20 | PONSA SAM. Issues while exporting OSP, HFC premise to ON using NAT boundary; DefectResolution: For the defect - DF118801 there was a design issue for a LOC outside MPS boundary and required inputs from Design team and NEO. |  |  | 0 |  | 1 | 0 | 10 | 10
2STL-66 | RFS.104 | M-A-Q | HAC | Pre-AT |  | 2017-11-09 |  |  | Completed - Handed over to NEO | 2017-11-03 | Vedant | Completed | 2017-11-03 | 2017-11-06 | 2 | [6 empty] | 0 |  |  |  |  | Naika Arjun |  | Completed - Handed over to NEO | 2017-11-06 | 2017-11-06 |  | 1 |  | 1 |  |  |  |  | 1 | 2017-11-06 | DF118186 is open defect for T18 issue .Will taking care at FAB stage |  |  | 0 |  | 0 | 0 | 2 | 3
5FLN-60 | RFS.107 | H-B-J | BAU | Pre-AT |  | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-16 | Rejitha Retnakaran | Completed | 2017-11-16 | 2017-11-17 | 2 | [5 empty] | 2017-11-17 | 0 | [6 empty] | Completed - Handed over to NEO |  |  | 0 | 0 | [6 empty] | 0 | 2017-11-17 | Zero defect SAM |  |  | 0 |  | -30728 | 0 | 2 | 2
3CLA-68 | RFS.102 | H-A-Q | HAC | Pre-AT |  | 2017-11-10 | No |  | Completed - Handed over to NEO | 2017-11-08 | Vedant | Completed | 2017-11-08 | 2017-11-09 | 2 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | 2017-11-09 |  |  |  | 0 |  | -30722 | 0 | 2 | 2
4FHL-20 | RFS.108 | M-B-H | BAU | Pre-AT |  | 2017-11-10 | Yes | Pre-AT | Completed - Handed over to NEO | 2017-11-23 |  | Not Applicable |  |  | 0 |  | Minu | Completed | 2017-11-23 | 2017-11-27 | 2017-11-27 | 3 | Anju Lisa | 2017-12-04 | 2017-12-05 | Completed |  | Bijeta Biswal | Completed - Handed over to NEO | 2017-11-29 | 2017-12-05 | 12 | 0 | 11 | 0 | 1 | 0 | 0 | 0 | 5 | 2017-12-05 | Incident raised for Job lock issues due to which resolution for 3 defects were on hold for 3 days, incident# INC000006703250 /REQ000003221540. | 2017-12-01 | 2017-12-05 | -30732 |  | 30734 | 3 | 9 | 5
3HGT-67 | RFS.116 | H-A-Q | HAC | Pre-AT |  | 2017-11-13 | No |  | Completed - Handed over to NEO | 2017-11-14 | Vedant | Completed | 2017-11-14 | 2017-11-14 | 1 | [6 empty] | 0 |  |  |  |  | Vedant |  | Completed - Handed over to NEO | 2017-11-14 | 2017-11-14 |  | 0 | [6 empty] | 1 | 2017-11-14 |  |  |  | 0 |  | 0 | 0 | 1 | 2
3WIR-69 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-11-13 | No |  | Completed - Handed over to NEO | 2017-11-13 | Ashwin Vijayan | Completed | 2017-11-13 | 2017-11-13 | 1 | [6 empty] | 0 |  |  |  |  | Ashwin Vijayan |  | Completed - Handed over to NEO | 2017-11-13 | 2017-11-14 |  | 5 | [6 empty] | 2 | 2017-11-14 |  |  |  | 0 |  | 0 | 0 | 2 | 3
2ROS-67 | RFS.135 | H-A-Q | HAC | Pre-AT | 2 | 2017-11-20 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
5NRW-63 | RFS.118 | M-A-Q | HAC | Pre-AT |  | 2018-02-06 |  |  | Completed - Handed over to NEO | 2017-11-15 | Naika Arjun | Completed | 2017-11-15 | 2017-11-15 | 1 | [6 empty] | 0 |  |  |  |  | Naika Arjun |  | Completed - Handed over to NEO | 2017-11-15 | 2017-11-15 |  | 0 | [6 empty] | 1 | 2017-11-15 |  |  |  | 0 |  | 0 | 0 | 1 | 2
2PEN-67 | RFS.105 | H-A-Q | HAC | Pre-AT |  | 2017-11-14 | No |  | Completed - Handed over to NEO | 2017-11-14 | Abhishek Ojha | Completed | 2017-11-14 | 2017-11-14 | 1 | [6 empty] | 0 |  |  |  |  | Abhishek Ojha |  | Completed - Handed over to NEO | 2017-11-14 | 2017-11-14 |  | 1 | [6 empty] | 1 | 2017-11-14 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4CHD-61 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-14 | No |  | Completed - Handed over to NEO | 2017-11-21 | Abhishek Ojha | Completed | 2017-11-21 | 2017-11-21 | 1 | [6 empty] | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-22 | 2017-11-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-22 | Zero defect SAM |  |  | 0 |  | 1 | 0 | 2 | 2
4CHP-66 | RFS.108 | M-B-H | BAU | Pre-AT |  | 2017-11-14 | yes |  | Completed - Handed over to NEO | 2017-11-16 |  | Not Applicable |  |  | 0 |  | Rejitha Retnakaran | Completed | 2017-11-16 | 2017-11-17 | 2017-11-17 | 2 | Sree Ram Sundar | 2017-11-21 | 2017-11-22 | Completed |  | Bijeta Biswal | Completed - Handed over to NEO | 2017-11-20 | 2017-11-21 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 2017-11-21 |  |  |  | -30727 |  | 30727 | 0 | 4 | 2
2HUR-62 | RFS.108 | H-A-Q | HAC | Pre-AT |  | 2017-11-14 | No |  | Completed - Handed over to NEO | 2017-11-14 | Minu | Completed | 2017-11-14 | 2017-11-14 | 1 | [6 empty] | 0 |  |  |  |  | Minu |  | Completed - Handed over to NEO | 2017-11-14 | 2017-11-15 |  | 1 | [6 empty] | 2 | 2017-11-15 |  |  |  | 0 |  | 0 | 0 | 2 | 3
6WMB-61 | RFS.106 | H-A-Q | HAC | Pre-AT |  | 2017-11-17 | No |  | Completed - Handed over to NEO | 2017-11-20 | Abhishek Ojha | Completed | 2017-11-20 | 2017-11-20 | 1 | [6 empty] | 0 | [6 empty] | Completed - Handed over to NEO |  |  |  | 0 | [6 empty] | 0 | 2017-11-20 |  |  |  | 0 |  | -30729 | 0 | 1 | 1
5BRI-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | 2017-11-14 | No |  | Completed - Handed over to NEO | 2017-11-14 | Bijeta Biswal | Completed | 2017-11-14 | 2017-11-14 | 1 | [6 empty] | 0 |  |  |  |  | Bijeta Biswal |  | Completed - Handed over to NEO | 2017-11-14 | 2017-11-16 |  | 1 | [6 empty] | 3 | 2017-11-16 | The CAV report had a lot many cables(70) to be fixed. |  |  | 0 |  | 0 | 0 | 3 | 4
3NES-62 | RFS.124 | H-A-Q | HAC | Pre-AT |  | 2017-11-14 |  |  | Completed - Handed over to NEO | 2017-11-22 | Anju Lisa | Completed | 2017-11-22 | 2017-11-22 | 1 | [6 empty] | 0 |  |  |  |  | Anju Lisa |  | Completed - Handed over to NEO | 2017-11-22 | 2017-11-22 |  | 1 |  | 1 |  |  | 1 |  | 1 | 2017-11-22 |  |  |  | 0 |  | 0 | 0 | 1 | 2
5NRW-60 | RFS.120 | H-A-Q | HAC | Pre-AT |  | 2017-11-14 |  |  | Completed - Handed over to NEO | 2017-11-22 | Vedant | Completed | 2017-11-22 | 2017-11-22 | 1 | [5 empty] | 2017-11-22 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-22 | 2017-11-22 |  | 1 |  | 1 |  |  | 1 |  | 1 | 2017-11-22 |  |  |  | 0 |  | 0 | 0 | 1 | 2
5NRW-64 | RFS.120 | M-A-H | BAU | Pre-AT |  | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-12-05 | Pooja Jacob | Completed | 2017-12-05 | 2017-12-05 | 1 | [5 empty] | 2017-12-05 | 0 | Shahin Basheer | 2017-12-08 | 2017-12-08 | Completed | Bijeta Biswal |  | Completed - Handed over to NEO | 2017-12-06 | 2017-12-08 | 4 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 3 | 2017-12-08 |  |  |  | 0 |  | 1 | 0 | 4 | 4
4SOP-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-14 | No |  | Completed - Handed over to NEO | 2017-11-10 | Vedant | Completed | 2017-11-10 | 2017-11-10 | 1 | [6 empty] | 0 |  |  |  |  | Naika Arjun |  | Completed - Handed over to NEO | 2017-11-13 | 2017-11-14 | 1 | 0 | 0 | 1 | 0 | 0 | 1 |  | 2 | 2017-11-14 | There is only one defect - DF119253 and it is a T18 data issue. |  |  | 0 |  | 1 | 0 | 3 | 3
2PYM-62 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-14 | No |  | Completed - Handed over to NEO | 2017-11-09 | Anju Lisa | Completed | 2017-11-09 | 2017-11-09 | 1 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-10 | 2017-11-15 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 4 | 2017-11-15 | 1 Defect was with AP team - DF118995 and got the update from them on 3rd day. |  |  | 0 |  | 1 | 0 | 5 | 5
2ING-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-14 | No |  | Completed - Handed over to NEO | 2017-11-09 | Abhishek Ojha | Completed | 2017-11-09 | 2017-11-10 | 2 | [6 empty] | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed - Handed over to NEO | 2017-11-13 | 2017-11-15 | 2 | 0 | 0 | 2 | 0 | 0 | 2 |  | 3 | 2017-11-15 | Both the defects - DF119208 and DF119209 are T18 data issues. |  |  | 0 |  | 1 | 0 | 5 | 5
6GIR-64 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-14 | No |  | Completed - Handed over to NEO | 2017-11-08 | Lekshmi Balakrishnan | Completed | 2017-11-08 | 2017-11-08 | 1 | [6 empty] | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed - Handed over to NEO | 2017-11-09 | 2017-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-11-09 | Zero defect SAM. |  |  | 0 |  | 1 | 0 | 2 | 2
4BUR-67 | RFS.107 | M-A-H | BAU | Pre-AT |  | 2017-11-17 | No |  | Completed - Handed over to NEO | 2017-11-27 | Abhishek Ojha | Completed | 2017-11-27 | 2017-11-27 | 1 | [5 empty] | 2017-11-27 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-27 | 2017-11-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-27 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 1 | 2
4CPR-60 | RFS.108 | M-A-H | BAU | Pre-AT | 1 | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-20 | Vedant | Completed | 2017-11-20 | 2017-11-20 | 1 | [5 empty] | 2017-11-20 | 0 | Sree Ram Sundar | 2017-11-22 | 2017-11-22 | Completed | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-21 | 2017-11-22 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2017-11-22 |  |  |  | 0 |  | 1 | 0 | 3 | 3
2PET-64 | RFS.108 | M-M-H | BAU | Pre-AT | 1 | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-22 | Abhishek Ojha | Completed | 2017-11-22 | 2017-11-22 | 1 | [5 empty] | 2017-11-22 | 0 | Sree Ram Sundar | 2017-11-23 | 2017-11-24 | Completed | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-23 | 2017-11-24 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 2 | 2017-11-24 | DF120984 - has been kept on hold with NDQ after doing DSG part; took clarification from Design team also for this defect resolution. |  |  | 0 |  | 1 | 0 | 3 | 3
3MIT-60 | RFS.106 | M-M-Q | HAC | Pre-AT | 1 | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-15 | Abhishek Ojha | Completed | 2017-11-15 | 2017-11-15 | 1 | [6 empty] | 0 |  |  |  |  | Abhishek Ojha |  | Completed - Handed over to NEO | 2017-11-15 | 2017-11-15 |  | 3 | [6 empty] | 1 | 2017-11-16 | Due to Appian issue couldn't close the task on 15th, though defect resolution was completed on 15th. |  |  | 0 |  | 0 | 0 | 2 | 2
2PAR-62 | RFS.125 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-28 | Ashwin Vijayan | Completed | 2017-11-28 | 2017-11-28 | 1 | [5 empty] | 2017-11-28 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-28 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-28 |  |  |  | 0 |  | 0 | 0 | 1 | 2
2PYM-63 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | 2017-11-16 |  |  | Completed - Handed over to NEO | 2017-11-15 | Ashwin Vijayan | Completed | 2017-11-15 | 2017-11-15 | 1 | [6 empty] | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-16 | 2017-11-16 | 1 |  |  | 1 |  |  | 1 |  | 1 | 2017-11-16 | Zero defect SAM |  |  | 0 |  | 1 | 0 | 2 | 2
4AGV-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-15 | Vedant | Completed | 2017-11-15 | 2017-11-15 | 1 | [6 empty] | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-16 | 2017-11-17 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2 | 2017-11-17 |  |  |  | 0 |  | 1 | 0 | 3 | 3
2HLS-61 | RFS.107 | M-A-H | BAU | Pre-AT | 2 | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-13 | Vedant | Completed | 2017-11-13 | 2017-11-13 | 1 | [6 empty] | 0 |  |  |  |  | Vedant |  | Completed - Handed over to NEO | 2017-11-13 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-11-13 | Zero defect SAM |  |  | 0 |  | 0 | 0 | 1 | 2
4ASH-64 | RFS.113 | H-A-H | BAU | Pre-AT | 1 | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-28 | Abhishek Ojha | Completed | 2017-11-28 | 2017-11-28 | 1 | [5 empty] | 2017-11-28 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-28 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-28 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 1 | 2
4FHL-62 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-16 | No |  | Completed - Handed over to NEO | 2017-11-28 | Pooja Jacob | Completed | 2017-11-28 | 2017-11-28 | 1 | [5 empty] | 2017-11-28 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-28 | 2017-11-28 |  | 3 |  | 3 |  |  | 2 |  | 1 | 2017-11-28 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4SOP-65 | RFS.110 | M-A-H | BAU | Pre-AT |  | 2017-11-28 | No |  | Completed - Handed over to NEO | 2017-11-23 | Vedant | Completed | 2017-11-23 | 2017-11-23 | 1 | [5 empty] | 2017-11-23 | 0 | Lekshmi Balakrishnan | 2017-11-29 | 2017-11-29 | Completed | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-11-27 | 2017-11-29 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 2017-11-29 | Atlas-MTM sync issue- Defects not reflecting in MTM. There was design changes for the defect fix. |  |  | 0 |  | 2 | 0 | 5 | 4
5NRW-62 | RFS.110 | M-A-H | BAU | Pre-AT |  | 2017-11-21 | No |  | Completed - Handed over to NEO | 2017-11-24 | Abhishek Ojha | Completed | 2017-11-24 | 2017-11-24 | 1 | [5 empty] | 2017-11-24 | 0 | Lekshmi Balakrishnan | 2017-11-28 | 2017-11-28 | Completed | Aravind V |  | Completed - Handed over to NEO | 2017-11-27 | 2017-11-28 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 2017-11-28 |  |  |  | 0 |  | 1 | 0 | 3 | 3
4CUR-60 | RFS.108 | M-A-Q | HAC | Pre-AT |  | 2017-11-22 | No |  | Completed - Handed over to NEO | 2017-11-23 | Abhishek Ojha | Completed | 2017-11-23 | 2017-11-23 | 1 | [5 empty] | 2017-11-23 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-24 | 2017-11-24 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | 2017-11-28 | Atlas-MTM sync issue- Defects not reflected in MTM |  |  | 0 |  | 1 | 0 | 4 | 2
4NDG-62 | RFS.127 | H-A-Q | HAC | Pre-AT |  | 2017-11-22 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
5WES-62 | RFS.108 | H-A-Q | HAC | Pre-AT |  | 2017-11-24 | No |  | Completed - Handed over to NEO | 2017-11-27 | Anju Lisa | Completed | 2017-11-27 | 2017-11-27 | 1 | [5 empty] | 2017-11-27 | 0 |  |  |  |  | Anju Lisa |  | Completed - Handed over to NEO | 2017-11-27 | 2017-11-29 |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 2017-11-29 |  |  |  | 0 |  | 0 | 0 | 3 | 4
4CHD-21 | RFS.109 | M-A-H | BAU | Pre-AT |  | 2017-11-24 | No |  | Completed - Handed over to NEO | 2017-11-27 | Vedant | Completed | 2017-11-27 | 2017-11-27 | 1 | [5 empty] | 2017-11-27 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-27 | 2017-11-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-27 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 1 | 2
4OXE-62 | RFS.107 | H-A-Q | HAC | Pre-AT |  | 2017-11-23 | No |  | Completed - Handed over to NEO | 2017-11-23 | Lekshmi Balakrishnan | Completed | 2017-11-23 | 2017-11-23 | 1 | [5 empty] | 2017-11-23 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-24 | 2017-11-24 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 2017-11-28 | Atlas-MTM sync issue- Defects not reflecting in MTM |  |  | 0 |  | 1 | 0 | 4 | 2
3CAU-67 | RFS.111 | H-A-Q | HAC | Pre-AT |  | 2017-11-09 | No |  | Completed - Handed over to NEO | 2017-11-28 | Naika Arjun | Completed | 2017-11-28 | 2017-11-28 | 1 | [5 empty] | 2017-11-28 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-28 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-28 |  |  |  | 0 |  | 0 | 0 | 1 | 2
3CAN-64 | RFS.120 | H-A-Q | HAC | Pre-AT |  | 2017-11-30 | No |  | Completed - Handed over to NEO | 2017-11-29 | Abhishek Ojha | Completed | 2017-11-29 | 2017-11-29 | 1 | [5 empty] | 2017-11-29 | 0 |  |  |  |  | Abhishek Ojha |  | Completed - Handed over to NEO | 2017-11-29 | 2017-11-30 |  | 2 |  | 2 |  |  |  |  | 2 | 2017-11-30 |  |  |  | 0 |  | 0 | 0 | 2 | 3
4CHL-70 | RFS.130 | M-A-H | BAU | Pre-AT |  | 2017-11-27 |  |  | Completed - Handed over to NEO | 2018-01-01 | Vedant | Completed | 2018-01-01 | 2018-01-01 | 0 | [5 empty] | 2018-01-01 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-02 | 2018-01-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-02 | Zero defect SAM. |  |  | -1 |  | 0 | 0 | 1 | 1
4OXE-60 | RFS.109 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-28 | No |  | Completed - Handed over to NEO | 2017-11-29 | Naika Arjun | Completed | 2017-11-29 | 2017-11-29 | 1 | [6 empty] | 0 | [6 empty] | Completed - Handed over to NEO | 2017-11-29 | 2017-11-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-29 |  |  |  | 0 |  | 0 | 0 | 1 | 2
5NRW-66 | RFS.110 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-28 | No |  | Completed - Handed over to NEO | 2017-11-30 | Vedant | Completed | 2017-11-30 | 2017-11-30 | 1 | [5 empty] | 2017-11-30 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-01 | 2017-12-01 |  | 1 | 0 | 1 |  |  |  |  | 1 | 2017-12-01 |  |  |  | 0 |  | 1 | 0 | 2 | 2
4OXE-61 | RFS.110 | M-A-H | BAU | Pre-AT | 2 | 2017-11-28 | No |  | Completed - Handed over to NEO | 2017-12-01 | Abhishek Ojha | Completed | 2017-12-01 | 2017-12-01 | 1 | [5 empty] | 2017-12-01 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-01 | 2017-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-12-01 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 1 | 2
4FHL-60 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-04 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
3SSN-61 | RFS.122 | H-A-Q | HAC | Pre-AT | 1 | 2017-11-29 | No |  | Completed - Handed over to NEO | 2017-12-12 | Vedant | Completed | 2017-12-12 | 2017-12-12 | 1 | [5 empty] | 2017-12-12 | 0 | [7 empty] | 2017-12-12 | 2017-12-12 |  | 2 |  | 2 |  |  |  |  | 1 | 2017-12-12 |  |  |  | 0 |  | 0 | 0 | 1 | 2
3TYH-66 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | 2017-11-29 |  |  | Completed - Handed over to NEO | 2017-12-20 | Rejitha Retnakaran | Completed | 2017-12-20 | 2017-12-20 | 1 | [5 empty] | 2017-12-20 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-21 | 2017-12-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-12-21 | Zero defect SAM. |  |  | 0 |  | 1 | 0 | 2 | 2
4MRA-64 | RFS.113 | M-M-Q | HAC | Pre-AT | 0.2 | 2017-12-07 | No |  | Completed - Handed over to NEO | 2017-12-01 | Shahin Basheer | Completed | 2017-12-01 | 2017-12-01 | 1 | [5 empty] | 2017-12-01 | 0 |  |  |  |  | Shahin Basheer |  | Completed - Handed over to NEO | 2017-12-01 | 2017-12-01 | 0 | 3 | 0 | 3 | 0 | 0 | 1 | 0 | 1 | 2017-12-01 |  |  |  | 0 |  | 0 | 0 | 1 | 2
6WMB-62 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | 2017-12-01 | No |  | Completed - Handed over to NEO | 2017-12-05 | Abhishek Ojha | Completed | 2017-12-05 | 2017-12-05 | 1 | [5 empty] | 2017-12-05 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-06 | 2017-12-06 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 2017-12-06 | Zero defect |  |  | 0 |  | 1 | 0 | 2 | 2
2RYD-65 | RFS.110 | M-A-H | BAU | Pre-AT | 1 | 2017-12-01 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2RYD-66 | RFS.110 | M-A-H | BAU | Pre-AT | 0.1 | 2017-12-01 | No |  | Completed - Handed over to NEO | 2017-12-05 | Vedant | Completed | 2017-12-05 | 2017-12-05 | 1 | [5 empty] | 2017-12-05 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-05 | 2017-12-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-12-06 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 2 | 2
2HUR-66 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-04 | No |  | Completed - Handed over to NEO | 2017-12-07 | Abhishek Ojha | Completed | 2017-12-07 | 2017-12-07 | 1 | [5 empty] | 2017-12-08 | 0 | Abhishek Ojha | 2017-12-08 | 2017-12-08 | Completed | [13 empty] | 0 | 2017-12-08 |  |  |  | 0 |  | -30742 | 0 | 2 | 1
4EMP-25 | RFS.108 | M-B-H | BAU | Pre-AT | 2 | 2017-12-04 | Yes | Pre-AT | On Hold | 2017-11-30 |  | Not Applicable |  |  | 0 |  | Anju Lisa | Completed | 2017-11-30 | 2017-12-01 | 2017-12-01 | 2 | Anju Lisa | 2017-12-05 | 2017-12-05 | Completed |  | Nahas Shajahan | DSG Completed - with External Team for update | 2017-12-04 | 2017-12-05 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 |  | SAM has been put on hold with the following comments: "Removed from RFS Group 109 at AT-R as TLS advised on 04-Dec-17 the FAB Ver 2 T18 did not reflect the correct construction status of the copper based on the issued IFDV." |  |  | -30737 |  | 30737 | 0 | -30736 | 2
3HDB-68 | RFS.111 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-05 |  |  | Completed - Handed over to NEO | 2017-12-11 | Anju Lisa | Completed | 2017-12-11 | 2017-12-11 | 1 | [5 empty] | 2017-12-11 | 0 |  |  |  |  | Anju Lisa |  | Completed - Handed over to NEO | 2017-12-12 | 2017-12-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-12-12 | Zero defect SAM |  |  | 0 |  | 1 | 0 | 2 | 2
3TNI-62 | RFS.111 | M-A-H | BAU | Pre-AT | 1 | 2017-12-05 | No |  | Completed - Handed over to NEO | 2017-12-07 | Rejitha Retnakaran | Completed | 2017-12-07 | 2017-12-07 | 1 | [5 empty] | 2017-12-07 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-08 | 2017-12-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2017-12-08 | Zero defect SAM |  |  | 0 |  | 1 | 0 | 2 | 2
5WES-61 | RFS.111 | M-M-H | BAU | Pre-AT | 1 | 2017-12-06 | Yes |  | Completed - Handed over to NEO | 2017-12-08 | Rejitha Retnakaran | Completed | 2017-12-08 | 2017-12-11 | 2 |  | Pooja Jacob | Completed | 2017-12-08 | 2017-12-11 | 2017-12-11 | 2 | Lekshmi Balakrishnan | 2017-12-13 | 2017-12-14 | Completed | Nahas Shajahan | Bijeta Biswal | Completed - Handed over to NEO | 2017-12-12 | 2017-12-14 | 9 | 0 | 6 | 2 | 0 | 1 | 1 | 0 | 3 | 2017-12-14 |  |  |  | 0 |  | 1 | 0 | 5 | 5
2KNS-61 | RFS.111 | M-A-H | BAU | Pre-AT | 0.1 | 2017-12-14 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
4NDG-60 | RFS.127 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-15 |  |  | Completed - Handed over to NEO | 2017-12-18 | Rejitha Retnakaran | Completed | 2017-12-18 | 2017-12-18 | 1 | [5 empty] | 2017-12-18 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-18 | 2017-12-18 | 0 | 0 |  | 0 | 0 |  | 0 |  | 1 | 2017-12-18 | Zero defect SAM |  |  | 0 |  | 0 | 0 | 1 | 2
4PDP-63 | RFS.143 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-08 |  |  | Completed - Handed over to NEO | 2017-12-18 | Abhishek Ojha | Completed | 2017-12-18 | 2017-12-18 | 1 | [5 empty] | 2017-12-18 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-18 | 2017-12-18 | 0 | 0 |  | 1 |  | 0 |  | 1 | 1 | 2017-12-18 |  |  |  | 0 |  | 0 | 0 | 1 | 2
2GBE-64 | RFS.112 | M-A-H | BAU | Pre-AT | 1 | 2017-12-12 |  |  | Completed - Handed over to NEO | 2017-12-27 | Abhishek Ojha | Completed | 2017-12-27 | 2017-12-27 | 1 | [5 empty] | 2017-12-27 | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-12-28 | 2017-12-28 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2017-12-28 | Only one major defect and is due to T18 data issue. |  |  | 0 |  | 1 | 0 | 2 | 2
2GBE-65 | RFS.112 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-12 |  |  | Completed - Handed over to NEO | 2017-12-13 | Vedant | Completed | 2017-12-13 | 2017-12-13 | 1 | [5 empty] | 2017-12-13 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-13 | 2017-12-13 | 0 | 0 | 0 | [5 empty] | 1 | 2017-12-13 | Zero defect SAM |  |  | 0 |  | 0 | 0 | 1 | 2
3KYG-65 | RFS.113 | H-A-H | BAU | Pre-AT | 3 | 2017-12-12 |  |  | Completed - Handed over to NEO | 2017-12-14 | Vedant | Completed | 2017-12-14 | 2017-12-14 | 1 | [5 empty] | 2017-12-14 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-15 | 2017-12-15 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 1 | 2017-12-15 |  |  |  | 0 |  | 1 | 0 | 2 | 2
2CRR-20 | RFS.112 | M-B-H | BAU | Pre-AT | 4 | 2017-12-13 | Yes |  | Completed - Handed over to NEO | 2017-12-19 |  |  |  |  | 0 |  | Vedant | Completed | 2017-12-19 | 2017-12-21 | 2017-12-21 | 3 | Shahin Basheer | 2017-12-27 | 2017-12-27 | Completed |  | Bijeta Biswal | Completed - Handed over to NEO | 2017-12-22 | 2018-01-04 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 7 | 2018-01-04 | Out of the 2 DSG defects, actually only one defect(DF125365) required correction from DSG team, for the other defect(DF125365) we had intimated to transit team on 22-Dec-17, but due to Embargo period it was on hold without any response and we got it fixed by them on 4-Jan-18. | 2017-12-22 | 2018-01-02 | -30750 |  | 30751 | 5 | 10 | 7
2RYD-64 | RFS.110 | H-A-Q | HAC | Pre-AT | 4 | 2017-12-20 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
3KYG-69 | RFS.113 | M-A-Q | HAC | Pre-AT | 1 | 2017-12-15 |  |  | Completed - Handed over to NEO | 2017-12-21 | Abhishek Ojha | Completed | 2017-12-21 | 2017-12-21 | 1 | [5 empty] | 2017-12-21 | 0 | [7 empty] | 2017-12-21 | 2017-12-21 |  | 1 | [5 empty] | 1 | 1 | 2017-12-22 |  |  |  | 0 |  | 0 | 0 | 2 | 2
2RDL-62 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | 2017-12-18 |  |  | Completed - Handed over to NEO | 2017-12-27 | Vedant | Completed | 2017-12-28 | 2017-12-28 | 1 | [5 empty] | 2017-12-28 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-29 | 2017-12-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-12-29 | Zero defect SAM |  |  | 1 |  | 1 | 0 | 3 | 2
3NAW-62 | RFS.114 | M-M-Q | HAC | Pre-AT | 0.5 | 2017-12-18 |  |  | Completed - Handed over to NEO | 2017-12-18 | Vedant | Completed | 2017-12-18 | 2017-12-18 | 1 | [5 empty] | 2017-12-18 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-18 | 2017-12-18 | 0 | 0 |  | 0 |  | 0 |  |  | 1 | 2017-12-18 | Zero defect SAM |  |  | 0 |  | 0 | 0 | 1 | 2
5GNG-60 | RFS.116 | M-A-H | BAU | Pre-AT | 3 | 2017-12-18 |  |  | Completed - Handed over to NEO | 2018-01-16 | Abhishek Ojha | Completed | 2018-01-16 | 2018-01-16 | 1 | [5 empty] | 2018-01-17 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-17 | 2018-01-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-17 | Zero defect SAM. |  |  | 0 |  | 1 | 0 | 2 | 2
4EMP-02 | RFS.110 | M-B-H | BAU | Pre-AT | 0.3 | 2017-12-18 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
4CHL-68 | RFS.130 | H-A-Q | HAC | Pre-AT | 3 | 2017-12-19 |  |  | Completed - Handed over to NEO | 2017-12-19 | Abhishek Ojha | Completed | 2017-12-19 | 2017-12-19 | 1 | [5 empty] | 2017-12-19 | 0 |  |  |  |  | Abhishek Ojha |  | Completed - Handed over to NEO | 2017-12-20 | 2017-12-20 |  | 2 |  | 2 |  |  | 2 |  | 1 | 2017-12-20 |  |  |  | 0 |  | 1 | 0 | 2 | 2
5NRW-65 | RFS.113 | M-A-H | BAU | Pre-AT | 1 | 2017-12-20 | No |  | Completed - Handed over to NEO | 2017-12-26 | Abhishek Ojha | Completed | 2017-12-26 | 2017-12-26 | 0 | [5 empty] | 2017-12-26 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-27 | 2017-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-12-27 | Zero defect SAM. |  |  | -1 |  | 0 | 0 | 1 | 1
4RBN-61 | RFS.113 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-20 |  |  | Completed - Handed over to NEO | 2017-12-20 | Lekshmi Balakrishnan | Completed | 2017-12-20 | 2017-12-20 | 1 | [5 empty] | 2017-12-20 | 0 | [7 empty] | 2017-12-20 | 2017-12-20 |  |  |  | 0 |  |  |  |  | 1 | 2017-12-20 |  |  |  | 0 |  | 0 | 0 | 1 | 2
4TGP-63 | RFS.135 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-28 |  |  | Completed - Handed over to NEO | 2018-01-29 | Anju Lisa | Completed | 2018-01-29 | 2018-01-30 | 2 | [5 empty] | 2018-01-30 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-30 | 2018-01-30 | 0 | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 2018-01-30 | QI extended to second day due to the SpatialNet issue(Database error) on 29th Jan. |  |  | 0 |  | 0 | 0 | 2 | 3
4ABO-62 | RFS.135 | M-A-Q | HAC | Pre-AT | 1 | 2017-12-29 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
4TGP-67 | RFS.135 | M-A-H | BAU | Pre-AT | 1 | 2017-12-29 |  |  | Completed - Handed over to NEO | 2018-01-29 | Abhishek Ojha | Completed | 2018-01-29 | 2018-01-30 | 2 | [5 empty] | 2018-01-30 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-30 | 2018-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-30 | Zero defect SAM. QI extended to second day due to the SpatialNet issue(Database error) on 29th Jan. |  |  | 0 |  | 0 | 0 | 2 | 3
4LNH-62 | RFS.142 | H-M-H | BAU | Pre-AT | 1 | 2017-12-21 | No |  | Completed - Handed over to NEO | 2017-12-28 | Abhishek Ojha | Completed | 2017-12-29 | 2017-12-29 | 1 | [5 empty] | 2017-12-29 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-01 | 2018-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-01-01 | Zero defect SAM.
4ABC-61 | RFS.113 | M-M-H | BAU | Pre-AT | 0.1 | 2017-12-21 | Yes | Pre-AT | Completed - Handed over to NEO | 2017-12-28 | Lekshmi Balakrishnan | Completed | 2017-12-28 | 2017-12-28 | 1 |  | Anju Lisa | Completed | 2017-12-28 | 2017-12-29 | 2017-12-29 | 2 |  |  |  |  | Nahas Shajahan | Bijeta Biswal | Completed - Handed over to NEO | 2018-01-01 | 2018-01-02 | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 2018-01-02 |  |  |  | 0 |  | 1 | 0 | 3 | 2
2MEN-63 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | 2017-12-28 |  |  | Completed - Handed over to NEO | 2018-01-17 | Abhishek Ojha | Completed | 2018-01-17 | 2018-01-17 | 1 | [5 empty] | 2018-01-17 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-17 | 2018-01-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-17 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 1 | 2
2PYM-61 | RFS.116 | M-A-H | BAU | Pre-AT | 2 | 2017-12-22 | No |  | Completed - Handed over to NEO | 2017-12-26 | Vedant | Completed | 2017-12-26 | 2017-12-26 | 0 | [5 empty] | 2017-12-26 | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-12-27 | 2017-12-27 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 2017-12-27 | There is only one defect and it is a T18 data issue. SAM is tracked outside Appian. |  |  | -1 |  | 0 | 0 | 1 | 1
2CHA-62 | RFS.112 | H-A-Q | HAC | Pre-AT | 2 | 2017-12-25 |  |  | Completed - Handed over to NEO | 2017-12-26 | Nahas Shajahan | Completed | 2017-12-26 | 2017-12-27 | 1 | [5 empty] | 2017-12-27 | -30753 |  |  |  |  | Bijeta Biswal |  | Completed - Handed over to NEO | 2017-12-27 | 2017-12-27 |  | 2 |  | 2 |  |  |  | 1 | 1 | 2017-12-27 |  |  |  | -1 |  | 0 | 0 | 1 | 2
2WRO-60 | RFS.139 | H-A-Q | HAC | Pre-AT | 1 | 2017-12-08 |  |  | Completed - Handed over to NEO | 2017-12-08 | Vedant | Completed | 2017-12-08 | 2017-12-08 | 1 | [5 empty] | 2017-12-08 | 0 |  |  |  |  | Anju Lisa |  | Completed - Handed over to NEO | 2017-12-11 | 2017-12-11 |  | 2 |  | 2 |  |  |  |  | 1 | 2017-12-12 |  |  |  | 0 |  | 1 | 0 | 3 | 2
2UND-61 | RFS.117 | H-M-Q | HAC | Pre-AT | 0.1 | 2018-01-01 |  |  | Completed - Handed over to NEO | 2018-01-03 | Abhishek Ojha | Completed | 2018-01-04 | 2018-01-04 | 1 | [5 empty] | 2018-01-04 | 0 |  |  |  |  | Abhishek Ojha |  | Completed - Handed over to NEO | 2018-01-05 | 2018-01-08 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2018-01-08 | Exceeded 2 days due to count of defects to be fixed. |  |  | 1 |  | 1 | 0 | 4 | 3
6SUB-66 | RFS.114 | M-A-H | BAU | Pre-AT | 3 | 2017-12-27 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
2EPP-65 | RFS.114 | H-M-Q | HAC | Pre-AT | 0.1 | 2017-12-27 |  |  | Completed - Handed over to NEO | 2017-12-27 | Pooja Jacob | Completed | 2017-12-27 | 2017-12-27 | 1 | [5 empty] | 2017-12-27 | 0 | [7 empty] | 2017-12-27 | 2017-12-27 | 0 |  |  | 0 |  | 0 |  |  | 1 | 2017-12-27 |  |  |  | 0 |  | 0 | 0 | 1 | 2
3TYH-69 | RFS.114 | M-A-H | BAU | Pre-AT | 1 | 2017-12-27 |  |  | Completed - Handed over to NEO | 2018-01-09 | Anju Lisa | Completed | 2018-01-09 | 2018-01-09 | 1 | [5 empty] | 2018-01-09 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-09 | 2018-01-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-09 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 1 | 2
2QUA-63 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | 2017-12-28 |  |  | Completed - Handed over to NEO | 2018-01-11 | Abhishek Ojha | Completed | 2018-01-11 | 2018-01-11 | 1 | [5 empty] | 2018-01-11 | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed - Handed over to NEO | 2018-01-12 | 2018-01-12 | 3 | 0 | 0 | 3 | 0 | 0 | 2 | 0 | 1 | 2018-01-12 | All 3 defects are due to T18 data issues. |  |  | 0 |  | 1 | 0 | 2 | 2
2CAR-60 | RFS.116 | M-A-H | BAU | Pre-AT | 1 | 2017-12-29 |  |  | Completed - Handed over to NEO | 2018-01-08 | Abhishek Ojha | Completed | 2018-01-08 | 2018-01-09 | 2 | [5 empty] | 2018-01-09 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-09 | 2018-01-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-09 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 2 | 3
4ALX-67 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | 2018-01-05 |  |  | Completed - Handed over to NEO | 2017-12-28 | Abhishek Ojha | Completed | 2017-12-28 | 2017-12-28 | 1 | [5 empty] | 2017-12-28 | 0 | [6 empty] | Completed - Handed over to NEO | 2017-12-29 | 2017-12-29 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 2017-12-29 | One major defect and is due to T18 data issue. |  |  | 0 |  | 1 | 0 | 2 | 2
3HDB-66 | RFS.115 | M-A-H | BAU | Pre-AT | 1 | 2017-12-29 |  |  | Completed - Handed over to NEO | 2018-01-08 | Lekshmi Balakrishnan | Completed | 2018-01-08 | 2018-01-08 | 1 | [5 empty] | 2018-01-08 | 0 | Nahas Shajahan | 2018-01-09 | 2018-01-09 | Completed | Nahas Shajahan |  | Completed - Handed over to NEO | 2018-01-09 | 2018-01-09 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2018-01-09 |  |  |  | 0 |  | 1 | 0 | 2 | 2
2CHA-60 | RFS.114 | M-A-H | BAU | Pre-AT | 1 | 2018-01-01 |  |  | Completed - Handed over to NEO | 2018-01-03 | Anju Lisa | Completed | 2018-01-04 | 2018-01-04 | 1 | [5 empty] | 2018-01-04 | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2018-01-05 | 2018-01-05 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 2018-01-05 | Only one defect due to T18 data issue. |  |  | 1 |  | 1 | 0 | 3 | 2
6WMB-60 | RFS.113 | M-A-H | BAU | Pre-AT | 2 | 2018-01-01 |  |  | Completed - Handed over to NEO | 2018-01-02 | Lekshmi Balakrishnan | Completed | 2018-01-02 | 2018-01-02 | 1 | [5 empty] | 2018-01-02 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-03 | 2018-01-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-03 | Zero defect SAM. |  |  | 0 |  | 1 | 0 | 2 | 2
4TGP-68 | RFS.134 | M-A-H | BAU | Pre-AT | 1 | 2018-01-02 |  |  | Completed - Handed over to NEO | 2018-01-25 | Anju Lisa | Completed | 2018-01-25 | 2018-01-25 | 1 | [5 empty] | 2018-01-25 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-25 | Zero defect SAM. |  |  | 0 |  | 0 | 0 | 1 | 2
4ABO-65 | RFS.134 | M-A-H | BAU | Pre-AT | 1 | 2018-01-04 | [8 empty] | 0 | [6 empty] | 0 | [17 empty] | 0 |  |  |  |  | -1 |  | -1 | 0 | 0 | 0
4ALX-64 | RFS.126 | M-A-H | BAU | Pre-AT | 1 | 2018-01-11 | [8 empty] | 0
3KYG-60 | RFS.117 | H-A-H | BAU | Pre-AT | 1 | 2018-01-04 |  |  | Completed - Handed over to NEO | 2018-01-16 | Vedant | Completed | 2018-01-16 | 2018-01-16 | 1 | [5 empty] | 2018-01-16 | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2018-01-17 | 2018-01-17 | 4 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 1 | 2018-01-17 | Out of 4 defects, 3 defects are due to T18 data issues.
3KYG-62 | RFS.117 | H-A-H | BAU | Pre-AT | 1 | 2018-01-04 |  |  | Completed - Handed over to NEO | 2018-01-19 | Abhishek Ojha | Completed | 2018-01-19 | 2018-01-19 | 1 | [5 empty] | 2018-01-19 | 0 |  |  |  |  | Lekshmi Balakrishnan |  | Completed - Handed over to NEO | 2018-01-22 | 2018-01-22 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 |  | 2018-01-22 | There are 2 defects and are due to T18 data issues.
3BLB-65 | RFS.123 | H-M-H | BAU | Pre-AT | 0.1 | 2018-01-05 |  |  | Completed - Handed over to NEO | 2018-02-01 | Naika Arjun | Completed | 2018-02-01 | 2018-02-01 | 1 | [5 empty] | 2018-02-01 | [7 empty] | Completed - Handed over to NEO | 2018-02-01 | 2018-02-01 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 2018-02-01 | Only one defect and is due to T18 data issue.
5HNL-61 | RFS.118 | H-M-H | BAU | Pre-AT | 0.2 | 2018-01-08 | No |  | Completed - Handed over to NEO | 2018-01-23 | Rejitha Retnakaran | Completed | 2018-01-23 | 2018-01-23 | 1 |  |  | Not Applicable |  |  | 2018-01-23 | [5 empty] | Bijeta Biswal |  | Completed - Handed over to NEO | 2018-01-24 | 2018-01-24 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 2018-01-24
2CAR-63 | RFS.116 | M-M-H | BAU | Pre-AT | 1 | 2017-12-26 |  |  | Completed - Handed over to NEO | 2017-12-27 | Vedant | Completed | 2017-12-27 | 2017-12-27 | 1 | [5 empty] | 2017-12-27 | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2017-12-28 | 2017-12-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-12-28 | Zero defect SAM. |  |  | 0 |  | 1 | 0 | 2 | 2
2HUR-65 | RFS.115 | H-A-H | BAU | Pre-AT | 2 | 2018-01-05 |  |  | Completed - Handed over to NEO | 2018-01-15 | Abhishek Ojha | Completed | 2018-01-15 | 2018-01-16 | 2 | [5 empty] | 2018-01-16 | 0 |  |  |  |  | Nahas Shajahan |  | Completed - Handed over to NEO | 2018-01-17 | 2018-01-19 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 2018-01-19 | The defect - DF126906(LOC000028304609 has a tech type mismatch between T18(HFC) and PNI(FIBRE)), we received clarification from Nathan on 19th Jan. | 2018-01-17 | 2018-01-19
4TGP-65 | RFS.135 | H-A-H | BAU | Pre-AT | 1 | 2018-01-16 |  |  | Completed - Handed over to NEO | 2018-02-01 | Abhishek Ojha | Completed | 2018-02-01 | 2018-02-01 | 1 | [5 empty] | 2018-02-01 | [7 empty] | Completed - Handed over to NEO | 2018-02-01 | 2018-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01 | Zero defect SAM.
2CAM-61 | RFS.118 | H-A-H | BAU | Pre-AT | 1 | 2018-01-16 |  |  | Completed - Handed over to NEO | 2018-02-02 | Anju Lisa | Completed | 2018-02-02 | 2018-02-02 | 1 | [5 empty] | 2018-02-02 | [7 empty] | Completed - Handed over to NEO | 2018-02-02 | 2018-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-02 | Zero defect SAM.
2FRE-62 | RFS.119 | M-M-H | BAU | Pre-AT | 0.2 | 2018-01-16 |  |  | Completed - Handed over to NEO | 2018-01-19 | Vedant | Completed | 2018-01-19 | 2018-01-19 | 1 | [5 empty] | 2018-01-19 | [7 empty] | Completed - Handed over to NEO | 2018-01-19 | 2018-01-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-19 | Zero defect SAM.
6GIR-68 | RFS.116 | M-A-H | BAU | Pre-AT |  | 2018-01-03 |  |  | Completed - Handed over to NEO | 2018-01-02 | Abhishek Ojha | Completed | 2018-01-03 | 2018-01-03 | 1 | [5 empty] | 2018-01-03 | 1 | [6 empty] | Completed - Handed over to NEO | 2018-01-04 | 2018-01-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-04 | Zero defect SAM.
4SLA-62 | RFS.99 | H-M-H | BAU | Pre-AT | 0.1 | 2018-01-19 |  |  | Completed - Handed over to NEO | 2018-01-29 | Lekshmi Balakrishnan | Completed | 2018-01-29 | 2018-01-30 | 2 | [5 empty] | 2018-01-30 | 0 | [6 empty] | Completed - Handed over to NEO | 2018-01-30 | 2018-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-30 | Zero defect SAM. QI extended to second day due to the SpatialNet issue(Database error) on 29th Jan.
2QUA-64 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | 2018-01-22 | [8 empty] | 0
4RBN-60 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | 2018-01-22 | [8 empty] | 0
2WRO-62 | RFS.118 | M-A-H | BAU | Pre-AT | 1 | 2018-01-22 | [8 empty] | 0
2GBE-62 | RFS.117 | M-A-H | BAU | Pre-AT | 1 | 2018-01-29 | [8 empty] | 0
2PET-62 | RFS.115 | H-A-H | BAU | Pre-AT | 1 | 2018-01-05 |  |  | Completed - Handed over to NEO | 2018-01-11 | Anju | Completed | 2018-01-11 | 2018-01-11 | 1 | [5 empty] | 2018-01-11 | [7 empty] | Completed - Handed over to NEO | 2018-01-11 | 2018-01-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-01-11 | Zero defect SAM
2CRR-66 | RFS.118 | M-M-H | BAU | Pre-AT | 0.1 | 2018-01-30 | [8 empty] | 0
5HNL-63 | RFS.119 | H-M-H | BAU | Pre-AT | 0.1 | 2018-01-30 |  |  | In Progress | 2018-02-05 | Naika Arjun | Completed | 2018-02-05 | 2018-02-05 | 1 | [5 empty] | 2018-02-05
3TYH-61 | RFS.118 | M-M-H | BAU | Pre-AT | 0.2 | 2018-01-26 |  |  | Completed - Handed over to NEO | 2018-02-01 | Anju Lisa | Completed | 2018-02-01 | 2018-02-01 | 1 | [5 empty] | 2018-02-01 | [7 empty] | Completed - Handed over to NEO | 2018-02-01 | 2018-02-01 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 2018-02-01 | Only one defect and is due to T18 data issue.
2ENG-62 | RFS.123 | H-M-H | BAU | Pre-AT | 0.1 | 2018-02-02 |  |  | Completed - Handed over to NEO | 2018-02-02 | Rejitha Retnakaran | Completed | 2018-02-02 | 2018-02-02 | 1 | [13 empty] | Completed - Handed over to NEO | 2018-02-02 | 2018-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2018-02-02 | Zero defect SAM.
5NRW-63 | RFS.114 | M-A-H | BAU | Pre-AT | 2 | 2018-02-06 | [8 empty] | 0
3HDB-65 | RFS.123 | H-A-H | BAU | Pre-AT | 1 | 2018-01-30 | [8 empty] | 0
2CAR-62 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | 2018-01-30 | [8 empty] | 0
2BAN-60 | RFS.119 | M-B-H | BAU | Pre-AT | 1.1 | 2018-02-01 | [8 empty] | 0
4CHL-61 | RFS.130 | M-A-H | BAU | Pre-AT | 2 | 2018-02-02 | [8 empty] | 0
4BEE-64 | RFS.122 | M-A-H | BAU | Pre-AT | 1 | 2018-02-02 | [8 empty] | 0
2PYM-65 | RFS.118 | M-A-H | BAU | Pre-AT | 6 | 2018-01-31 |  |  | Completed - Handed over to NEO | 2018-02-01 | Vedant | Completed | 2018-02-01 | 2018-02-01 | 1 | [5 empty] | 2018-02-01 | [7 empty] | Completed - Handed over to NEO | 2018-02-01 | 2018-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01 | Zero defect SAM.
2PNN-63 | RFS.125 | H-M-H | BAU | Pre-AT | 0.1 | 2018-02-05 | [8 empty] | 0
2QUA-65 | RFS.121 | M-A-H | BAU | Pre-AT | 1 | 2018-02-06 | [8 empty] | 0
4ABO-66 | RFS.138 | H-A-H | BAU | Pre-AT | 2 | 2018-02-06 | [8 empty] | 0
4FHL-65 | RFS.142 | M-A-Q | HAC | Pre-AT | 3 | 2018-02-06 | [8 empty] | 0
2EPP-61 | RFS.124 | H-M-H | BAU | Pre-AT | 0.1 | 2018-02-07 | [8 empty] | 0
4SLA-64 | RFS.125 | M-M-H | BAU | Pre-AT | 0.1 | 2018-02-09 | [8 empty] | 0
3BNT-62 | RFS.123 | H-A-H | BAU | Pre-AT | 1 | 2018-02-09 | [8 empty] | 0
3BLB-60 | RFS.146 | M-A-H | BAU | Pre-AT | 3 | 2018-02-09 | [8 empty] | 0
2QUA-62 | RFS.118 | M-A-H | BAU | Pre-AT | 3 | 2018-02-09 | [8 empty] | 0
4LNH-60 | RFS.130 | M-A-H | BAU | Pre-AT | 1 | 2018-02-09 | [8 empty] | 0
3KGP-66 | RFS.140 | H-A-H | BAU | Pre-AT | 1 | 2018-02-13 | [8 empty] | 0
2CHA-61 | RFS.121 | M-A-H | BAU | Pre-AT | 1 | 2018-02-13 | [8 empty] | 0
3KYG-67 | RFS.123 | M-A-H | BAU | Pre-AT | 1 | 2018-02-16 | [8 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Cycle Time = NETWORKDAYS([Start Date],[End Date],Holiday!$C2:C80)
Cycle Time = NETWORKDAYS([Defect Resolution Start Date],[Defect Resolution End Date],Holiday!$C2:C80)
Defects External Waiting Time = NETWORKDAYS([Defects On Hold Start Date],[Recommencement Date],Holiday!$C2:C80)

## DSG - FAB Allocation
Updated by : | sriram rajendra kumar | Updated on : | 2017-10-23 | [8 empty] | FAB HFC Data Load | [5 empty] | FAB FTTx Data Load | [10 empty] | Internal Tracking
SAM Name | RFS Group | SAM Code | Program | Gate | Version | FAB Backlog? | Expected Input Date | MTM Load Required? | MTM Payload Type FAB/Dlite | Overall Status | T18 Input Received Date | Assigned To | Start Date | End Date | NDQ Handover Date | FAB HFC Data Load Status | Cycle Time | Assigned To | Start Date | End Date | NDQ Handover Date | FAB FTTx Data Load Status | Cycle Time | Comments/ Issues/ Blockers | On Hold Start Date [HFC] | Recommnecement Date [HFC] | On Hold Start Date [FTTx] | Recommencement Date [FTTx] | FAB In Queue Time (Internal waiting time) [HFC] | FAB Waiting Time (External waiting time) [HFC] | FAB In Queue Time (Internal waiting time) [FTTx] | FAB Waiting Time (External waiting time) [FTTx] | Overall Cycle Time | Overall Processing Time | Entry Type | DSG Input Date [Appian] | Sr.No | Names | Droddown validation
3NAW-63 | RFS.59 | H-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-04-10 | Aravind | 2017-04-10 | 2017-04-13 | 2017-04-13 | Completed | 4 |  |  |  |  | Not Applicable | 0 | Reverse KT SAM |  |  |  |  | 0 | 0 |  | 0 | 4 | 4 |  |  | 1 | Arul Dayalan | Arul Dayalan
6JTS-61 | RFS.51 | M-M-J | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-04-18 | Shenita | 2017-04-18 | 2017-05-01 | 2017-05-01 | Completed | 8 |  |  |  |  | Not Applicable | 0 | Reverse KT SAM |  |  |  |  | 0 | 0 |  | 0 | 8 | 8 |  |  | 2 | Vinaybhaskar P | Vinaybhaskar P
4CPB-62 | RFS.60 | M-M-J | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-05-17 | Shenita | 2017-05-17 | 2017-05-22 | 2017-05-22 | Completed | 4 |  |  |  |  | Not Applicable | 0 | [5 empty] | 0 | 0 |  | 0 | 4 | 4 |  |  | 3 | Devika Kala | Devika Kala
4CHP-67 | RFS.68 | H-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-05-23 | Shenita | 2017-05-23 | 2017-05-30 | 2017-05-30 | Completed | 6 |  |  |  |  | Not Applicable | 0 | [5 empty] | 0 | 0 |  | 0 | 6 | 6 |  |  | 4 | Ramcy S | Ramcy S
4ASH-60 | RFS.55 | H-A-J | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-05-30 | Shenita | 2017-05-30 | 2017-06-23 | 2017-06-23 | Completed | 18 |  |  |  |  | Not Applicable | 0 | Incident- INC000004918503. |  |  |  |  | 0 | 0 |  | 0 | 18 | 18 |  |  | 5 | Brinson Bovas | Brinson Bovas
2ESP-62 | RFS.57 | H-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-02 | Shenita | 2017-06-02 | 2017-06-16 | 2017-06-16 | Completed | 10 |  |  |  |  | Not Applicable | 0 | Pilot SAM |  |  |  |  | 0 | 0 |  | 0 | 10 | 10 |  |  | 6 | Anju Shaji | Anju Shaji
3DRP-64 | RFS.57 | H-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-05 | Shenita | 2017-06-05 | 2017-06-16 | 2017-06-16 | Completed | 9 |  |  |  |  | Not Applicable | 0 | Pilot SAM |  |  |  |  | 0 | 0 |  | 0 | 9 | 9 |  |  | 7 | Geethu Gilbert | Geethu Gilbert
4ASH-65 | RFS.55 | H-A-J | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-05 | Jijin | 2017-06-05 | 2017-06-24 | 2017-06-24 | Completed | 14 |  |  |  |  | Not Applicable | 0 | Issue highlighted in FBR. LOCID issue mailed to LMS |  |  |  |  | 0 | 0 |  | 0 | 14 | 14 |  |  | 8 | Naveen Kumar Nagaraj | Naveen Kumar Nagaraj
3DAN-62 | RFS.55 | H-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-08 | Shenita | 2017-06-08 | 2017-06-22 | 2017-06-22 | Completed | 10 |  |  |  |  | Not Applicable | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10 |  |  | 9 | Saranya Geetha | Saranya Geetha
3CAN-60 | RFS.61 | H-M-J | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-08 | Reethu | 2017-06-08 | 2017-06-27 | 2017-06-27 | Completed | 12 |  |  |  |  | Not Applicable | 0 | [5 empty] | 0 | 0 |  | 0 | 12 | 12 |  |  | 10 | Aravind V | Aravind V
2ESP-60 | RFS.52 | H-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-09 | Shenita | 2017-06-09 | 2017-06-26 | 2017-06-26 | Completed | 10 |  |  |  |  | Not Applicable | 0 | Script Error. IT request number: REQ000002217389 |  |  |  |  | 0 | 0 |  | 0 | 10 | 10 |  |  | 11 | Jijin Isaac | Jijin Isaac
2ESP-61 | RFS.56 | M-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-09 | Kruthika | 2017-06-09 | 2017-06-26 | 2017-06-26 | Completed | 10 |  |  |  |  | Not Applicable | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10 |  |  | 12 | Krutika Neelak | Krutika Neelak
3CAN-62 | RFS.61 | H-M-J | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-14 | Kruthika | 2017-06-14 | 2017-07-03 | 2017-07-03 | Completed | 13 |  |  |  |  | Not Applicable | 0 | Pilot SAM |  |  |  |  | 0 | 0 |  | 0 | 13 | 13 |  |  | 13 | Shenita | Shenita
3CAN-61 | RFS.63 | H-M-J | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-15 | Reethu | 2017-06-15 | 2017-06-29 | 2017-06-29 | Completed | 10 |  |  |  |  | Not Applicable | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10 |  |  | 14 | Bhagyalekshmi | Bhagyalekshmi
3FNT-65 | RFS.60 | H-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-23 | Nevin | 2017-06-23 | 2017-07-03 | 2017-07-03 | Completed | 6 |  |  |  |  | Not Applicable | 0 | [5 empty] | 0 | 0 |  | 0 | 6 | 6 |  |  | 15 | Karthika V J | Karthika V J
3DAN-60 | RFS.52 | H-A-H | BAU | Post RFS | 1 | FY17 |  | No |  | Completed | 2017-06-29 | Ashok | 2017-06-29 | 2017-07-07 | 2017-07-07 | Completed | 7 |  |  |  |  | Not Applicable | 0 | [5 empty] | 0 | 0 |  | 0 | 7 | 7 |  |  | 16 | Shyama P | Shyama P
5BRI-69 | RFS.80 | H-M-H | BAU | Post RFS |  | Backlog | 2017-07-10 |  |  | Completed | 2017-07-21 | Nevin | 2017-07-21 | 2017-07-28 | 2017-07-28 | Completed | 6 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 6 | 6 |  |  | 17 | Sreelekha K | Sreelekha K
2LIV-62 | RFS.65 | H-A-H | BAU | Post RFS |  | Backlog | 2017-07-18 |  |  | Completed | 2017-07-21 | Reethu | 2017-07-21 | 2017-07-28 | 2017-07-28 | Completed | 6 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 6 | 6 |  |  | 18 | Aswathy T | Aswathy T
3FNT-67 | RFS.66 | H-A-H | BAU | Post RFS |  | Backlog | 2017-07-18 |  |  | Completed | 2017-07-21 | Sahishna | 2017-07-21 | 2017-07-28 | 2017-07-28 | Completed | 6 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 6 | 6 |  |  | 19 | Amalu Manuel | Amalu Manuel
4MRA-62 | RFS.58 | H-A-H | BAU | Post RFS |  | Backlog | 2017-07-19 |  |  | Completed | 2017-07-24 | Ashok | 2017-07-24 | 2017-07-31 | 2017-07-31 | Completed | 6 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 6 | 6 |  |  | 20 | Sriram Rajendra Kumar | Sriram Rajendra Kumar
4ASH-67 | RFS.70 | M-M-J | BAU | Post RFS |  | Backlog | 2017-07-27 |  |  | Completed | 2017-07-28 | Sriram | 2017-07-28 | 2017-08-03 | 2017-08-07 | Completed | 7 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 7 | 7 |  |  | 21 | Nevin Tom | Nevin Tom
4SLA-69 | RFS.66 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-07-28 |  |  | Completed | 2017-08-01 | Nevin | 2017-08-01 | 2017-08-07 | 2017-08-07 | Completed | 5 | [5 empty] | 0 | First T18 lite SAM |  |  |  |  | 0 | 0 |  | 0 | 5 | 5 |  |  | 22 | Meera Sudhakumar | Meera Sudhakumar
3HGT-68 | RFS.74 | M-M-J | BAU | Post RFS | 1 | Backlog | 2017-07-27 |  |  | Completed | 2017-08-07 | Karthika | 2017-08-07 | 2017-08-10 | 2017-08-10 | Completed | 4 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 4 | 4 |  |  | 23 | Anju shaji | Anju shaji
5HNL-60 | RFS.77 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-08-02 |  |  | Completed | 2017-08-07 | Nevin | 2017-08-07 | 2017-08-11 | 2017-08-11 | Completed | 5 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 5 | 5 |  |  | 24 | Jyoti | Jyoti
3END-62 | RFS.81 | M-A-J | BAU | Post RFS | 1 | Backlog | 2017-08-07 |  |  | Completed | 2017-08-09 | Ashok | 2017-08-09 | 2017-08-16 | 2017-08-16 | Completed | 5 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 5 | 5 |  |  |  |  | Reethu Sebastian
4BUR-65 | RFS.77 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-08-11 |  |  | Completed | 2017-08-15 | Sahishna | 2017-08-15 | 2017-08-21 | 2017-08-21 | Completed | 4 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 4 | 5 |  |  |  |  | Akash Raja
4SLA-72 | RFS.68 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-08-18 |  |  | Completed | 2017-08-21 | Amalu | 2017-08-21 | 2017-08-25 | 2017-08-25 | Completed | 5 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 5 | 5 |  |  |  |  | Aleena Johny
5SAL-62 | RFS.82 | M-M-H | BAU | Post RFS | 1 | Backlog | 2017-08-17 |  |  | Completed | 2017-08-23 | Ashok | 2017-08-23 | 2017-09-05 | 2017-08-31 | Completed | 7 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 7 | 7 |  |  |  |  | Reshma Rajan
3NAW-64 | RFS.66 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-08-22 |  |  | Completed | 2017-08-24 | Shenita | 2017-08-25 | 2017-09-13 | 2017-09-13 | Completed | 12 | [5 empty] | 0 | [5 empty] | 1 | 0 |  | 0 | 13 | 12 |  |  |  |  | NA
3SPL-63 | RFS.66 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-07-26 |  |  | Completed | 2017-08-26 | Nevin | 2017-08-29 | 2017-09-12 | 2017-09-13 | Completed | 10 | [5 empty] | 0 | Sam was kept on hold for RFS 95- 96 IAB tasks |  |  |  |  | 1 | 0 |  | 0 | 11 | 10 |  |  | 25 | Reethu Sebastian | Sahishna Krishna
2CRR-70 | RFS.63 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-08-01 |  |  | Completed | 2017-08-28 | Amalu | 2017-08-30 | 2017-09-22 | 2017-09-22 | Completed | 16 | [5 empty] | 0 | New T18 lite was generated on 29-Aug-17. Also was kept onhold due to RFS 95-96 priority SAM taskstill 11-Sep-17 |  |  |  |  | 2 | 0 |  | 0 | 18 | 16 |  |  | 26 | Akash Raja | Jiya
2SEF-65 | RFS.57 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-08-22 |  |  | Completed | 2017-08-24 | Reethu | 2017-08-30 | 2017-09-14 | 2017-09-14 | Completed | 10 | [5 empty] | 0 | Sam was kept on hold due to RFS 95-96 IAB tasks |  |  |  |  | 4 | 0 |  | 0 | 14 | 10 |  |  |  |  | Ashok Hariharamoni
4EMP-61 | RFS.75 | M-M-H | BAU | Post RFS | 1 | Backlog | 2017-09-08 |  |  | Completed | 2017-09-07 | Sahishna Krishna | 2017-09-07 | 2017-09-22 | 2017-09-25 | Completed | 13 | [5 empty] | 0 | SAM was kept on hold due to RFS 95-96 IAB tasks from 28-Aug-17 till 11-Sep-2017.Also Incident was raised for the issue faced in Asset Comparison generation using T18 lite. |  |  |  |  | 0 | 0 |  | 0 | 13 | 13
4BUR-69 | RFS.77 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-08-31 |  |  | Completed | 2017-08-31 | Sriram Rajendra Kumar | 2017-09-12 | 2017-09-25 | 2017-09-25 | Completed | 10 | [5 empty] | 0 | SAM was kept on hold for RFS 95-96 IAB tasks |  |  |  |  | 6 | 0 |  | 0 | 16 | 10
3CTA-67 | RFS.66 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-09-12 |  |  | Completed | 2017-09-13 | Ashok Hariharamoni | 2017-09-15 | 2017-09-27 | 2017-09-27 | Completed | 9 | [5 empty] | 0 | [5 empty] | 2 | 0 |  | 0 | 11 | 9
3HGT-66 | RFS.66 | H-A-H | BAU | Post RFS |  | Backlog | 2017-09-18 |  |  | Completed | 2017-09-20 | Karthika V J | 2017-09-20 | 2017-10-04 | 2017-10-03 | Completed | 8 | [5 empty] | 0 | 19-Sep : Requested for T18 Lite |  |  |  |  | 0 | 0 |  | 0 | 8 | 8
2WET-61 | RFS.63 | H-A-H | BAU | Post RFS |  | Backlog | 2017-09-13 |  |  | Completed | 2017-09-21 | Ashok Hariharamoni | 2017-09-25 | 2017-10-10 | 2017-10-10 | Completed | 10 | [5 empty] | 0 | [5 empty] | 2 | 0 |  | 0 | 12 | 10
3CAU-61 | RFS.78 | H-A-H | BAU | Post RFS |  | Backlog | 2017-09-20 |  |  | Completed | 2017-09-21 | Nevin Tom | 2017-09-25 | 2017-10-09 | 2017-10-07 | Completed | 8 | [5 empty] | 0 | [5 empty] | 2 | 0 |  | 0 | 10 | 8
4ASH-67 | RFS.70 | M-M-J | BAU | Post RFS | 1 | FY17 |  | No |  | Rejected | 2017-06-06 | Sriram | 2017-09-26 |  |  | On Hold | -30693 |  |  |  |  | Not Applicable | 0 | Pilot SAM - ON HOLD |  |  |  |  | 75 | 0 |  | 0 | -30618 | -30693 |  |  | 27 | Aleena Johny
5GUG-63 | RFS.47 | H-M-J | BAU | Post RFS | 1 | FY17 |  | No |  | On Hold | 2017-06-14 | Jijin | 2017-09-26 |  |  | On Hold | -30693 |  |  |  |  | Not Applicable | 0 | Pilot SAM - ON HOLD |  |  |  |  | 70 | 0 |  | 0 | -30623 | -30693 |  |  | 28 | Reshma Rajan
4BUR-61 | RFS.77 | H-A-H | BAU | Post RFS |  | Backlog | 2017-09-11 |  |  | Completed | 2017-10-02 | Reethu Sebastian | 2017-10-03 | 2017-10-16 | 2017-10-16 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
2ING-61 | RFS.63 | H-A-H | BAU | Post RFS |  | Backlog | 2017-10-05 |  |  | On Hold | 2017-10-06 | Shyama P | 2017-10-06 |  |  | On Hold | -30699 | [5 empty] | 0 | Due to some design issue the SAM was paused in Appian on 9th Oct and re-trigged again from beginning on 13th Oct. |  |  |  |  | 0 | 0 |  | 0 | -30699 | -30699
3CTA-61 | RFS.64 | M-A-H | BAU | Post RFS |  | Backlog | 2017-09-25 |  |  | Completed | 2017-10-10 | Aleena Johny | 2017-10-10 | 2017-10-24 | 2017-10-24 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
4MRA-63 | RFS.78 | H-M-H | BAU | Post RFS |  | Backlog | 2017-10-06 |  |  | Completed | 2017-10-10 | Amalu Manuel | 2017-10-10 | 2017-10-24 | 2017-10-24 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
2EDG-61 | RFS.55 | H-A-H | BAU | Post RFS |  |  | 2017-10-06 |  |  | Completed | 2017-10-12 | Sahishna Krishna | 2017-10-12 | 2017-10-26 | 2017-10-26 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
4BUR-68 | RFS.91 | H-M-Q | BAU | Post RFS |  |  | 2017-10-05 |  |  | Completed | 2017-10-13 | Karthika V J | 2017-10-13 | 2017-10-27 | 2017-10-27 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
2PNN-66 | RFS.80 | H-A-H | BAU | Post RFS |  | Backlog | 2017-10-11 |  |  | Completed | 2017-10-13 | Ashok Hariharamoni | 2017-10-16 | 2017-10-26 | 2017-10-26 | Completed | 8 | [5 empty] | 0 | [5 empty] | 1 | 0 |  | 0 | 9 | 8
2LIV-68 | RFS.97 | M-M-H | BAU | Post RFS |  | FY18 | 2017-10-06 |  |  | Completed | 2017-10-17 | Shenita | 2017-10-19 | 2017-10-31 | 2017-10-31 | Completed | 9 | [5 empty] | 0 | [5 empty] | 1 | 0 |  | 0 | 10 | 9
3WHL-65 | RFS.63 | M-A-J | BAU | Post RFS |  | Backlog | 2017-10-10 | Yes | Dlite | Completed | 2017-10-18 | Shyama P | 2017-10-19 | 2017-11-02 | 2017-11-02 | Completed | 11 | Reshma TV | 2017-10-23 | 2017-10-26 | 2017-10-26 | Completed | 4 | One day delay - due to testing perfomed on Create Asset Import Tool in asset comparison. |  |  |  |  | 0 | 0 |  | 0 | 11 | 11
2WET-64 | RFS.65 | H-A-H | BAU | Post RFS |  | Backlog | 2017-10-10 |  |  | Completed | 2017-10-19 | Reethu Sebastian | 2017-10-19 | 2017-11-01 | 2017-11-01 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
3NES-61 | RFS.65 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-10-12 |  |  | Completed | 2017-10-25 | Sriram Rajendra Kumar | 2017-10-25 | 2017-11-07 | 2017-11-07 | Completed | 9 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 9 | 9 |  |  | 29 | NA
2ING-61 | RFS.63 | H-A-H | BAU | Post RFS | 2 | Backlog | 2017-10-20 |  |  | Completed | 2017-10-25 | Amalu Manuel | 2017-10-25 | 2017-11-03 | 2017-11-03 | Completed | 8 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 8 | 8
5SAL-63 | RFS.51 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-10-24 |  |  | Completed | 2017-10-27 | Sahishna Krishna | 2017-10-27 | 2017-11-09 | 2017-11-09 | Completed | 9 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 9 | 9
2WET-63 | RFS.58 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-10-24 |  |  | Completed | 2017-10-27 | Aleena Johny | 2017-10-27 | 2017-11-09 | 2017-11-09 | Completed | 9 | [5 empty] | 0 | The post RFS SAM spatial net load was on hold from 2-Nov-17 to 3-Nov-17 as facing issues with Asset comparison tool using T18 lite as input - Incident raised - INC000006414484 |  |  |  |  | 0 | 0 |  | 0 | 9 | 9
2ENG-63 | RFS.72 | H-A-Q | BAU | Post RFS | 1 | Backlog | 2017-10-24 |  |  | Completed | 2017-10-27 | Ashok Hariharamoni | 2017-10-27 | 2017-11-07 | 2017-11-07 | Completed | 7 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 7 | 7
4BUR-63 | RFS.80 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-10-24 |  |  | Completed | 2017-10-27 | Vinaybhaskar P | 2017-10-30 | 2017-11-10 | 2017-11-10 | Completed | 9 | [5 empty] | 0 | Resources were working on priority task. Sam was taken up by next available resource on 30-Oct-17 |  |  |  |  | 1 | 0 |  | 0 | 10 | 9
4ASH-62 | RFS.95 | H-A-Q | BAU | Post RFS | 1 | FY18 | 2017-10-09 |  |  | Completed | 2017-10-31 | Jyoti | 2017-10-31 | 2017-11-13 | 2017-11-13 | Completed | 9 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 9 | 9
5GUG-63 | RFS.48 | H-M-J | BAU | Post RFS | 2 | Backlog | 2017-10-18 |  |  | On Hold | 2017-10-31 | Meera Sudhakumar | 2017-10-31 |  |  | On Hold | -30715 | [5 empty] | 0 | Onhold with NA team for discussion with NEO |  |  |  |  | 0 | 0 |  | 0 | -30715 | -30715
2EDG-65 | RFS.95 | M-M-H | BAU | Post RFS | 1 | FY18 | 2017-10-18 |  |  | Completed | 2017-11-02 | Naveen Kumar | 2017-11-01 | 2017-11-14 | 2017-11-14 | Completed | 9 | [5 empty] | 0 | [5 empty] | -3 | 0 |  | 0 | 8 | 11
5GNG-61 | RFS.99 | M-M-H | BAU | Post RFS | 1 | FY18 | 2017-10-24 |  |  | Completed | 2017-11-01 | Bhagyalekshmi | 2017-11-01 | 2017-11-14 | 2017-11-14 | Completed | 9 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 9 | 9
2CRM-62 | RFS.72 | H-A-Q | BAU | Post RFS | 1 | Backlog | 2017-10-30 |  |  | Completed | 2017-11-02 | Devika Kala | 2017-11-01 | 2017-11-13 | 2017-11-13 | Completed | 8 | [5 empty] | 0 | [5 empty] | -3 | 0 |  | 0 | 7 | 10
2WET-60 | RFS.63 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-10-31 |  |  | Completed | 2017-11-03 | Nevin Tom | 2017-11-03 | 2017-11-16 | 2017-11-16 | Completed | 9 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 9 | 9
3WHL-60 | RFS.66 | H-M-H | BAU | Post RFS | 1 | Backlog | 2017-10-31 |  |  | Completed | 2017-11-03 | Reethu Sebastian | 2017-11-03 | 2017-12-04 | 2017-12-04 | Completed | 21 | [6 empty] | 3-Nov-17 -- SAM allocated and reported issues which needed clarification from Onshore. 10-Nov-17-- Got clarification on the issue. More than 500 GTD mismatces to be rectified. 3 DAYs delayed -Performing UAT for LIU tool/Client Visit at offshore |  |  |  |  | 5 | 0 |  | 0 | 21 | 16
4MGA-64 | RFS.79 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-01 |  |  | Completed | 2017-11-03 | Jiya | 2017-11-06 | 2017-11-15 | 2017-11-15 | Completed | 7 | [5 empty] | 0 | Resources were working on priority task. Sam was taken up by next available resource on 6-Nov-17 |  |  |  |  | 1 | 0 |  | 0 | 8 | 7
4CPB-60 | RFS.65 | M-M-J | BAU | Post RFS | 0.6 |  | 2017-11-06 |  |  | Completed | 2018-01-22 | Devika Kala | 2018-01-22 | 2018-02-05 | 2018-02-05 | Completed | 10 | [6 empty] | 29-01-2018 - PNI issues faced for which incident was raised 30-01-2018 - S Drive access issue for which incident was raised | 2018-01-29 | 2018-01-30 |  |  |  | 2 | [5 empty] | 2018-01-19
2PNN-67 | RFS.80 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-10-20 |  |  | Completed | 2017-11-08 | Karthika V J | 2017-11-08 | 2017-11-17 | 2017-11-17 | Completed | 8 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 8 | 8
5GUG-66 | RFS.78 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-11-02 |  |  | Completed | 2017-11-06 | Shenita | 2017-11-08 | 2017-11-23 | 2017-11-23 | Completed | 12 | [5 empty] | 0 | All resources were assigned with priority tasks.Sam was taken up by next available resource on 8-Nov-17 |  |  |  |  | 1 | 0 |  | 0 | 13 | 12
2PNN-65 | RFS.80 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-02 |  |  | Completed | 2017-11-08 | Ashok Hariharamoni | 2017-11-08 | 2017-11-17 | 2017-11-17 | Completed | 8 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 8 | 8
2NSY-60 | RFS.84 | H-M-H | BAU | Post RFS | 0.2 | FY18 | 2017-11-03 |  |  | Completed | 2017-11-09 | Amalu Manuel | 2017-11-09 | 2017-11-22 | 2017-11-22 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
4FHL-64 | RFS.80 | M-M-H | BAU | Post RFS | 1 | FY18 | 2017-11-01 |  |  | Completed | 2017-11-09 | Sriram Rajendra Kumar | 2017-11-10 | 2017-11-23 | 2017-11-23 | Completed | 10 | [5 empty] | 0 | Sam was taken up from the queue by the next available resource on 10-Nov-17 |  |  |  |  | 1 | 0 |  | 0 | 11 | 10
5EDW-60 | RFS.78 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-11-02 |  |  | Completed | 2017-11-10 | Aleena Johny | 2017-11-10 | 2017-11-23 | 2017-11-23 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
2PNN-64 | RFS.80 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-10-25 |  |  | Completed | 2017-11-20 | Devika Kala | 2017-11-15 | 2017-11-29 | 2017-11-29 | Completed | 11 | [5 empty] | 0 | SAM execution delayed as the T18 lite genartion was delayed |  |  |  |  | -5 | 0 |  | 0 | 8 | 13
4MGB-62 | RFS.101 | M-M-H | BAU | Post RFS | 1 | Backlog | 2017-11-07 |  |  | Completed | 2017-11-14 | Bhagyalekshmi | 2017-11-15 | 2017-11-24 | 2017-11-24 | Completed | 8 | [5 empty] | 0 | SAM was in queue for 1 day and it was assigned to next available resource on 2nd day. |  |  |  |  | 1 | 0 |  | 0 | 9 | 8
4BLH-61 | RFS.80 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-09 |  |  | Completed | 2017-11-14 | Anju Shaji | 2017-11-15 | 2017-11-28 | 2017-11-28 | Completed | 10 | [5 empty] | 0 | [5 empty] | 1 | 0 |  | 0 | 11 | 10
4MRA-60 | RFS.70 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-11-07 |  |  | Completed | 2017-11-16 | Jyoti | 2017-11-16 | 2017-11-30 | 2017-11-30 | Completed | 11 | [5 empty] | 0 | 28-11-17 - incident raised for Job posting issue-REQ000003205402 |  |  |  |  | 0 | 0 |  | 0 | 11 | 11
2PNN-69 | RFS.76 | M-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-02 |  |  | Completed | 2017-11-16 | Nevin Tom | 2017-11-17 | 2017-12-01 | 2017-12-01 | Completed | 11 | [5 empty] | 0 | 17-11-17 - Sam was assigned to next available resource 30-11-17 -Due to VDI issues |  |  |  |  | 1 | 0 |  | 0 | 12 | 11
2CRM-60 | RFS.80 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-02 |  |  | Completed | 2017-11-09 | Reethu Sebastian | 2017-11-17 | 2017-11-30 | 2017-11-30 | Completed | 10 | [5 empty] | 0 | Paused in Appian til resources were available for allocation.Also Reethu was allocated to LIU Tool UAT |  |  |  |  | 5 | 0 |  | 0 | 16 | 11
3FNT-61 | RFS.63 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-11-13 | No |  | Completed | 2017-11-17 | Jiya | 2017-11-20 | 2017-11-30 | 2017-11-30 | Completed | 9 | [5 empty] | 0 | Sam was taken by next available resource on 20-11-17 |  |  |  |  | 3 | 0 |  | 0 | 10 | 7 |  | 2017-11-15
2SHA-60 | RFS.80 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-10 |  |  | Completed | 2017-11-17 | Shyama P | 2017-11-22 | 2017-12-05 | 2017-12-05 | Completed | 10 | [5 empty] | 0 | Was taken for execution on 22-11-17 by next available resources |  |  |  |  | 3 | 0 |  | 0 | 13 | 10
4MRA-65 | RFS.84 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-10 |  |  | On Hold | 2017-11-17 | Sriram Rajendra Kumar | 2017-11-23 |  |  | On Hold | -30731 | [5 empty] | 0 | All Resources were assigned with priority tasks.Sam was taken up by next available resource on 23-11-17. SAM onhold from 21-12-17, due to huge no of GTD renaming issues. |  |  |  |  | 4 | 0 |  | 0 | -30727 | -30731
5EDW-65 | RFS.80 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-14 |  |  | Completed | 2017-11-20 | Karthika V J | 2017-11-23 | 2017-12-06 | 2017-12-06 | Completed | 10 | [5 empty] | 0 | All Resources were assigned with priority tasks. Sam was taken up bu next available resource on 23-11-17 |  |  |  |  | 3 | 0 |  | 0 | 13 | 10
2MOS-64 | RFS.75 | H-A-Q | BAU | Post RFS | 1 | Backlog | 2017-11-17 |  |  | Completed | 2017-11-21 | Sahishna Krishna | 2017-11-23 | 2017-12-05 | 2017-12-05 | Completed | 9 | [5 empty] | 0 | All Resources were assigned with priority tasks.Sam was taken up by next available resource on 23-11-17 |  |  |  |  | 2 | 0 |  | 0 | 11 | 9
3GLI-60 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 | Backlog | 2017-11-20 |  |  | Completed | 2017-11-21 | Amalu Manuel | 2017-11-23 | 2017-12-06 | 2017-12-06 | Completed | 10 | [5 empty] | 0 | All Resources were assigned with priority tasks.Sam was taken up by next available resource on 23-11-17 |  |  |  |  | 2 | 0 |  | 0 | 12 | 10
4BNP-62 | RFS.83 | H-A-H | BAU | Post RFS | 1 | FY18 | 2017-11-17 |  |  | Completed | 2017-11-22 | Aleena Johny | 2017-11-24 | 2017-12-07 | 2017-12-07 | Completed | 10 | [5 empty] | 0 | All Resources are assigned with priority tasks |  |  |  |  | 2 | 0 |  | 0 | 12 | 10
3HGT-73 | RFS.66 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-08-14 |  |  | Completed | 2017-11-27 | Bhagyalekshmi | 2017-11-27 | 2017-12-22 | 2017-12-20 | Completed | 18 | [5 empty] | 0 | Onhold in Appian with comments ON HOLD (DCD): Issue with PNI-asset comparison/T18-Lite REQ000003232606 till 22-12-17 SAM execution resumed on 18-12-17 and handed over on 20-DEC-17 | 2017-12-13 | 2017-12-18 |  |  | 0 | 4 |  | 0 | 18 | 14 |  | 2017-11-26
4FHL-63 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 | Backlog | 2017-11-27 |  |  | Completed | 2017-11-30 | Jiya | 2017-11-30 | 2017-12-13 | 2017-12-13 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10
4BNP-61 | RFS.83 | H-A-H | BAU | Post RFS | 0.1 | FY18 | 2017-11-21 |  |  | Completed | 2017-11-24 | Jyoti | 2017-12-01 | 2017-12-14 | 2017-12-14 | Completed | 10 | [5 empty] | 0 | 24-11-17 -SAM paused in Appian as, there are no free resources |  |  |  |  | 5 | 0 |  | 0 | 15 | 10
3DNC-64 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 | Backlog | 2017-11-21 |  |  | Completed | 2017-11-27 | Shyama P | 2017-12-01 | 2017-12-14 | 2017-12-14 | Completed | 10 | [5 empty] | 0 | 24-11-17 -SAM paused in Appian as, there are no free resources |  |  |  |  | 4 | 0 |  | 0 | 14 | 10 |  | 2017-11-24
2CRR-71 | RFS.58 | H-A-H | BAU | Post RFS | 1 | Backlog | 2017-10-06 |  |  | Completed | 2017-12-01 | Nevin Tom | 2017-12-04 | 2017-12-20 | 2017-12-20 | Completed | 13 | [5 empty] | 0 | 4-Dec-17 - Sam assigned to next available resource Extra days due to 1 day leave and manual effort took in creating and removal of equipments/cables/trenches/ducts and fixing trace issues |  |  |  |  | 1 | 0 |  | 0 | 14 | 13
6MLO-62 | 1 | H-A-H | BAU | Post RFS | 0.1 | FY18 | 2017-11-29 |  |  | Completed | 2017-12-01 | Naveen Kumar Nagaraj | 2017-12-05 | 2017-12-18 | 2017-12-18 | Completed | 10 | [5 empty] | 0 | [5 empty] | 2 | 0 |  | 0 | 12 | 10 |  | 2017-11-29
3CAU-65 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-10-02 |  |  | Completed | 2017-12-06 | Ashok Hariharamoni | 2017-12-06 | 2017-12-15 | 2017-12-15 | Completed | 8 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 8 | 8 |  | 2017-12-05
4MGB-63 | RFS.95 | H-A-Q | BAU | Post RFS | 1.1 | Backlog | 2017-11-21 |  |  | Completed | 2017-11-24 | Anju Shaji | 2017-12-07 | 2017-12-22 | 2017-12-22 | Completed | 12 | [5 empty] | 0 | 24-11-17 -SAM paused in Appian as, there are no free resources |  |  |  |  | 9 | 0 |  | 0 | 21 | 12 |  | 2017-11-23
4MRA-61 | RFS.58 | M-A-H | BAU | Post RFS | 0.1 |  | 2017-11-30 |  |  | Completed | 2017-12-07 | Aleena Johny | 2017-12-08 | 2017-12-28 | 2017-12-28 | Completed | 13 | [5 empty] | 0 | 8-12-17 - Asset comparison export with T18 lite is getting failed More than 50 GTD renaming issues and more Assets to create and Remove |  |  |  |  | 1 | 0 |  | 0 | 14 | 13 |  | 2017-12-06
3NBA-63 | RFS.97 | H-A-Q | BAU | Post RFS | 0.1 |  | 2017-12-05 |  |  | Completed | 2017-12-07 | Ramcy S | 2017-12-11 | 2017-12-22 | 2017-12-22 | Completed | 10 | [5 empty] | 0 | [5 empty] | 2 | 0 |  | 0 | 12 | 10 |  | 2017-12-06
2STL-64 | RFS.104 | M-M-H | BAU | Post RFS | 0.1 |  | 2017-12-06 |  |  | On Hold | 2017-12-11 | Sahishna Krishna | 2017-12-11 |  |  | On Hold | -30743 | [5 empty] | 0 | 21- DEC-17 -2STL-64 rejected due to 54 PLANNED PCDs in T18/LIL. |  |  |  |  | 0 | 0 |  | 0 | -30743 | -30743
4FHL-66 | RFS.78 | M-M-H | BAU | Post RFS | 1.1 |  | 2017-11-30 |  |  | Completed | 2017-12-12 | Ashok Hariharamoni | 2017-12-12 | 2018-01-01 | 2018-01-01 | Completed | 12 | [5 empty] | 0 | Incident raised for PNI error REQ000003350439 |  |  |  |  | 0 | 0 |  | 0 | 12 | 12 |  | 2017-12-11
4SLA-73 | RFS.73 | H-A-H | BAU | Post RFS |  | Backlog | 2017-08-10 |  |  | Completed | 2017-12-14 | Jiya | 2017-12-14 | 2017-12-22 | 2017-12-22 | Completed | 7 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 7 | 7 |  | 2017-12-13
4AAR-64 | RFS.63 | H-A-H | BAU | Post RFS | 0.2 |  | 2017-12-12 |  |  | Completed | 2017-12-15 | Jyoti | 2017-12-15 | 2017-12-27 | 2017-12-27 | Completed | 7 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 7 | 7 |  | 2017-12-13
3SPL-66 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-14 |  |  | On Hold | 2017-12-18 | Ashok Hariharamoni | 2017-12-18 |  |  |  | -30748 | [5 empty] | 0 | Onhold as a new payload is requested |  |  |  |  | 0 | 0 |  | 0 | -30748 | -30748 |  | 2017-12-15
2CRR-67 | RFS.83 | H-M-H | BAU | Post RFS | 0.1 |  | 2017-12-13 |  |  | Completed | 2017-12-15 | Naveen Kumar Nagaraj | 2017-12-19 | 2018-01-02 | 2018-01-02 | Completed | 8 | [5 empty] | 0 | [5 empty] | 2 | 0 |  | 0 | 10 | 8 |  | 2017-12-14
4EMP-66 | RFS.56 | H-A-H | BAU | Post RFS |  |  | 2017-10-11 |  |  | Completed | 2017-12-19 | devika Kala | 2017-12-20 | 2018-01-04 | 2018-01-04 | Completed | 9 | [5 empty] | 0 | There were 37 equipment structure id mismatches and 80+ cable start/end structure id mismatches which is a higher volume to be completed in stipulated time frame. |  |  |  |  | 1 | 0 |  | 0 | 10 | 9 |  | 2017-12-18
5SAL-68 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-14 |  |  | Completed | 2017-12-20 | Amalu Manuel | 2017-12-20 | 2018-01-02 | 2018-01-02 | Completed | 7 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 7 | 7 |  | 2017-12-18
2STL-66 | RFS.105 | M-A-Q | BAU | Post RFS | 0.1 |  | 2017-12-15 |  |  | Completed | 2017-12-20 | Sriram Rajendra Kumar | 2017-12-22 | 2018-01-09 | 2018-01-09 | Completed | 10 | [5 empty] | 0 | SAM used for Cross training |  |  |  |  | 2 | 0 |  | 0 | 12 | 10 |  | 2017-12-19
4FHL-68 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-14 |  |  | Completed | 2017-12-19 | Geethu Gilbert | 2017-12-19 | 2018-01-05 | 2018-01-05 | Completed | 11 | [5 empty] | 0 | Around 100 assets to be created and 200 assets to be removed along with 40 structure id mismatch corrections.Due to High manual effort, failed to release the SAM on stipulated time |  |  |  |  | 0 | 0 |  | 0 | 11 | 11 |  | 2017-12-18
5FLN-60 | RFS.104 | H-B-J | BAU | Post RFS |  |  | 2017-07-27 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1 |  |  | 30 | Sahishna Krishna
4BUR-21 | RFS.94 | M-B-H | BAU | Post RFS |  |  | 2017-08-02 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1 |  |  | 31 | Jiya
4SLA-66 | RFS.94 | M-B-H | BAU | Post RFS |  |  | 2017-08-02 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1 |  |  | 32 | Ashok Hariharamoni
3DRP-63 | RFS.80 | M-M-H | BAU | Post RFS |  |  | 2017-08-10 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
3FNT-63 | RFS.87 | M-M-H | BAU | Post RFS |  |  | 2017-08-17 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
4MGA-62 | RFS.80 | M-A-H | BAU | Post RFS | 2 | Backlog | 2017-08-30 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
4BUR-66 | RFS.87 | M-M-H | BAU | Post RFS |  |  | 2017-10-05 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
3DRP-62 | RFS.63 | H-A-H | BAU | Post RFS |  |  | 2017-10-06 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
2FRE-63 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-11-14 |  |  | Completed | 2018-01-08 | Sriram Rajendra Kumar | 2018-01-08 | 2018-01-23 | 2018-01-23 | Completed | 12 | [5 empty] | 0 | SAM used for cross training |  |  |  |  | 0 | 0 |  | 0 | 12 | 12 |  | 2018-01-05
6JDL-21 | RFS.80 | M-M-J | BAU | Post RFS | 0.5 |  | 2017-11-27 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
4ASH-66 | RFS.70 | H-M-J | BAU | Post RFS | 1 |  | 2017-12-11 | Yes | Dlite | Completed | 2017-12-14 | Sahishna Krishna | 2017-12-21 | 2018-01-12 | 2018-01-12 | Completed | 14 | Nevin Tom | 2017-12-27 | 2018-01-12 | 2018-01-12 | Completed | 12 | HFC part -As the FTTN demotion and promotion affected the HFC cable attachment and supports, it took around 4 days for clearing CAV errors for around 1000 cables. FTTN Part-Also T18 data was incorrect, had to recreate 2 FNOS and the associated connections |  |  |  |  | 5 | 0 |  | 0 | 19 | 14 |  | 2017-12-13
3DNC-65 | RFS.70 | H-A-H | BAU | Post RFS | 0.2 |  | 2017-12-11 |  |  | Completed | 2017-12-13 | Bhagyalekshmi | 2017-12-14 | 2017-12-29 | 2017-12-29 | Completed | 10 | [5 empty] | 0 | [5 empty] | 1 | 0 |  | 0 | 11 | 10 |  | 2017-12-12
4SLA-73 | RFS.73 | H-A-H | BAU | Post RFS | 0.1 | Backlog | 2017-12-11 |  |  | Completed | 2017-12-14 | Jiya | 2017-12-14 | 2017-12-22 | 2017-12-22 | Completed | 7 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 7 | 7 |  | 2017-12-13
4MGB-66 | RFS.95 | H-M-Q | BAU | Post RFS | 0.1 |  | 2017-12-12 |  |  | Completed | 2017-12-13 | Karthika V J | 2017-12-14 | 2017-12-28 | 2017-12-28 | Completed | 9 | [5 empty] | 0 | [5 empty] | 1 | 0 |  | 0 | 10 | 9 |  | 2017-12-12
3FNT-63 | RFS.87 | M-M-H | BAU | Post RFS | 0.2 |  | 2017-12-12 |  |  | Completed | 2017-12-21 | Anju shaji | 2017-12-22 | 2018-01-04 | 2018-01-04 | Completed | 7 | [5 empty] | 0 | [5 empty] | 1 | 0 |  | 0 | 8 | 7 |  | 2017-12-20
3DAN-61 | RFS.49 | M-A-H | BAU | Post RFS | 2.1 |  | 2017-12-13 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
2SHA-60 | RFS.80 | H-A-H | BAU | Post RFS | 1.1 |  | 2017-12-14 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
3CTA-60 | RFS.58 | H-A-H | BAU | Post RFS | 2 |  | 2017-12-14 |  |  | Completed | 2018-01-10 | Naveen Kumar Nagaraj | 2018-01-10 | 2018-01-23 | 2018-01-23 | Completed | 10 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 10 | 10 |  | 2018-01-09
4EMP-62 | RFS.80 | H-M-H | BAU | Post RFS | 0.1 |  | 2017-12-14 |  |  | Completed | 2018-01-18 | Reshma Rajan | 2018-01-18 | 2018-02-01 | 2018-02-01 | Completed | 10 | [5 empty] | 0 | 29-01-2018 - PNI issues faced for which incident was raised 30-01-2018 - S Drive access issue for which incident was raised | 2018-01-29 | 2018-01-30 |  |  | 0 | 2 |  | 0 | 10 | 8 |  | 2018-01-17
3CTA-63 | RFS.78 | H-A-H | BAU | Post RFS | 1.1 |  | 2011-12-15 |  |  | Completed | 2018-01-04 | Ramcy S | 2018-01-04 | 2018-01-18 | 2018-01-18 | Completed | 11 | [5 empty] | 0 | manual effort spent on analyising and removing around 50 assets present in remove sheet |  |  |  |  | 0 | 0 |  | 0 | 11 | 11 |  | 2018-01-03
4BNP-63 | RFS.83 | M-A-H | BAU | Post RFS | 0.1 |  | 2017-12-14 | Yes | Dlite | Completed | 2018-01-16 | Shyama P | 2018-01-16 | 2018-01-31 | 2018-01-31 | Completed | 11 |  |  |  |  | On Hold | 0 | FTTN part for DLITE onhold as confirmed from onshore till the process to be followed is finalized 29-01-2018 - PNI issues faced for which incident was raised 30-01-2018 - S Drive access issue for which incident was raised | 2018-01-29 | 2018-01-30 |  |  | 0 | 2 |  | 0 | 11 | 9 |  | 2018-01-15
5EDW-61 | RFS.58 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-20 |  |  | Completed | 2018-01-09 | Akash Raja | 2018-01-09 | 2018-01-29 | 2018-01-29 | Completed | 14 | [5 empty] | 0 | Around 100 Assets to be created manually.Also faced intermittent job lock issues with other teams |  |  |  |  | 0 | 0 |  | 0 | 14 | 14 |  | 2018-01-05
5SAL-67 | RFS.58 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-20 |  |  | Completed | 2017-12-22 | Brinson Bovas | 2017-12-22 | 2018-01-08 | 2018-01-08 | Completed | 9 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 9 | 9 |  | 2017-12-21
4CHP-64 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-25 |  |  | Completed | 2018-01-04 | Ashok Hariharamoni | 2018-01-04 | 2018-02-05 | 2018-02-05 | Completed | 22 | [5 empty] | 0 | Awaiting Telstra response | 2018-01-17 | 2018-02-02 |  |  | 0 | 12 |  | 0 | 22 | 10 |  | 2018-01-03
3DAN-61 | RFS.49 | M-A-H | BAU | Post RFS | 2.1 |  | 2018-01-11 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
5SAL-65 | RFS.78 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-11 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
4DRR-62 | RFS.57 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-12 |  |  | Completed | 2018-01-17 | Jyoti | 2018-01-17 | 2018-01-31 |  | Completed | -30767 | [5 empty] | 0 | 29-01-2018 - PNI issues faced for which incident was raised 30-01-2018 - S Drive access issue for which incident was raised | 2018-01-29 | 2018-01-30 |  |  | 0 | 2 |  | 0 | -30767 | -30769 |  | 2018-01-16
6MLO-63 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-15 |  |  | Completed | 2018-01-18 | Karthika V J | 2018-01-18 | 2018-02-01 | 2018-02-01 | In Progress | 10 | [5 empty] | 0 | 29-01-2018 - PNI issues faced for which incident was raised 30-01-2018 - S Drive access issue for which incident was raised | 2018-01-29 | 2018-01-30 |  |  | 0 | 2 |  | 0 | 10 | 8 |  | 2018-01-17
3KGP-64 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-16 |  |  | In Progress | 2018-02-02 | Ramcy S | 2018-02-02 |  |  | In Progress | -30778 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | -30778 | -30778 |  | 2018-02-01
5SAL-69 | RFS.87 | H-A-Q | BAU | Post RFS | 0.1 |  | 2018-01-17 |  |  | Completed | 2018-01-19 | Bhagyalekshmi | 2018-01-19 | 2018-01-31 | 2018-01-31 | Completed | 8 | [5 empty] | 0 | 29-01-2018 - PNI issues faced for which incident was raised 30-01-2018 - S Drive access issue for which incident was raised | 2018-01-29 | 2018-01-30 |  |  | 0 | 2 |  | 0 | 8 | 6 |  | 2018-01-18
3DRP-60 | RFS.59 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-18 |  |  | Completed | 2018-01-19 | Sahishna Krishna | 2018-01-19 | 2018-02-02 | 2018-02-02 | Completed | 10 | [5 empty] | 0 | 29-01-2018 - PNI issues faced for which incident was raised 30-01-2018 - S Drive access issue for which incident was raised | 2018-01-29 | 2018-01-30 |  |  | 0 | 2 |  | 0 | 10 | 8 |  | 2018-01-18
3SOA-62 | RFS.85 | H-A-Q | BAU | Post RFS | 0.1 |  | 2018-01-25 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
3NBA-71 | RFS.70 | H-A-Q | BAU | Post RFS | 0.1 |  | 2018-01-25 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
3SCO-68 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-25 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
3HGT-60 | RFS.63 | M-A-J | BAU | Post RFS | 2.1 |  | 2018-01-30 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
4ABC-62 | RFS.115 | M-A-H | BAU | Post RFS | 0.1 |  | 2018-01-30 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
2ENG-60 | RFS.78 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-30 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
5SAL-64 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-02-01 | No |  | In Progress | 2018-02-01 | Sriram Rajendra Kumar | 2018-02-01 |  |  | In Progress | -30777 | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | -30777 | -30777 |  | 2018-01-31
2ENG-61 | RFS.74 | H-A-H | BAU | Post RFS | 0.2 |  | 2018-02-05 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
3SCO-64 | RFS.77 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-02-06 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
2STL-60 | RFS.104 | H-M-Q | BAU | Post RFS | 0.1 |  | 2018-02-06 | [9 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
[17 empty] | 0 | [5 empty] | 0 | [5 empty] | -1 | 0 |  | 0 | 0 | 1
Formulas:
Cycle Time = NETWORKDAYS([Start Date],[NDQ Handover Date],Holiday!$C2:C80)
Cycle Time = NETWORKDAYS([Start Date],[End Date],Holiday!$C2:C80)
Internal Tracking = NETWORKDAYS([T18 Input Received Date],[Start Date],Holiday!$C2:C80)-1
Overall Cycle Time = NETWORKDAYS([T18 Input Received Date],[NDQ Handover Date],Holiday!$C2:C80)

## NDQ - FAB Allocation
Updated by : |  | Updated on : | [9 empty] | FAB HFC NDQ Checks |  |  |  |  | FAB FTTx NDQ Checks | [5 empty] | Defect Closure Activity |  |  |  | FAB Defect Resolution | [20 empty] | Internal Tracking
SAM Name | RFS Group | SAM Code | Program | Gate | Version | FAB Backlog? | Expected Input Date | MTM Checks Required? | MTM Payload Type FAB/ Dlite | Overall Status | DSG Handover Date | Assigned To | Start Date | End Date | FAB HFC NDQ Checks Status | Cycle Time | Assigned To | Start Date | End Date | FAB MTM NDQ Checks Status | Cycle Time | Overall QI Completion Date | Assigned To | Start Date | End Date | Defect Closure Status | Assigned To 1 [HFC] | Assigned To 2 [HFC] | Assigned To 1 [MTM] | Assigned To 2 [MTM] | Defect Resolution Status | Defect Resolution Start Date | Defect Resolution End Date | Total No of FAB Defects | Total No of Non-FAB Defects | Total Major [FTTN] Defects | Total Major (HFC) Defects | Total Minor FTTN Defects | Total Minor HFC Defects | Open (FAB/Other issue) Defects | External Defects (AP/LMS/Design) | NSO H/O Date | NSO Acceptance Date | Cycle Time | Comments/ Issues/ Blockers | Defects On Hold Start Date | Recommencement Date | NDQ FAB In Queue Time (Internal Waiting Time) | NDQ FAB External Waiting Time | FAB Defects In Queue Time (Internal waiting time) | FAB Defects Waiting Time (External waiting time) | Overall Cycle Time | Overall Processing Time | Sr.No | Sr.No | Names1 | Names2 | Dropdown Validation1 | DropdownValidation2
4ASH-65 | RFS.55 | H-A-J | BAU | Post RFS | [5 empty] | Completed | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-07-07 | 2017-08-21 | 0 | 6 | 0 | 1 |  |  |  |  | 2017-08-21 |  | 31 |  |  |  | -1 |  | 30638 | 0 | 30669 | 32 | 1 | 1 | Pooja Jacob | Vinaybhaskar P | Pooja Jacob | Vinaybhaskar P
3CAN-60 | RFS.61 | H-M-J | BAU | Post RFS | [5 empty] | Completed | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-07-07 | 2017-07-13 |  |  |  | 2 |  |  |  |  | 2017-07-13 |  | 5 |  |  |  | -1 |  | 30638 | 0 | 30643 | 6 | 2 | 2 | Vinaybhaskar P | Naveen Kumar Nagaraj | Vinaybhaskar P | Naveen Kumar Nagaraj
2ESP-61 | RFS.56 | M-A-H | BAU | Post RFS | [5 empty] | Completed | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-07-07 | 2017-07-13 |  |  |  | 2 |  |  |  |  | 2017-07-13 |  | 5 |  |  |  | -1 |  | 30638 | 0 | 30643 | 6 | 3 | 3 | Sree Ram Sundar | Renjini R | Sree Ram Sundar | Renjini R
3CAN-62 | RFS.61 | H-M-J | BAU | Post RFS | [5 empty] | Completed | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-07-07 | 2017-07-13 |  |  |  | 1 |  |  |  |  | 2017-07-13 |  | 5 |  |  |  | -1 |  | 30638 | 0 | 30643 | 6 | 4 | 4 | Sree V | Saranya Geetha | Sree V | Saranya Geetha
3FNT-65 | RFS.60 | H-A-H | BAU | Post RFS | [5 empty] | Completed | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-07-07 | 2017-07-13 |  |  |  | 6 |  |  |  |  | 2017-07-13 |  | 5 |  |  |  | -1 |  | 30638 | 0 | 30643 | 6 | 5 | 5 | Anju Lisa | Aravind V | Anju Lisa | Meera Sudhakumar
3DAN-60 | RFS.52 | H-A-H | BAU | Post RFS | [5 empty] | Completed | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-07-24 | 2017-07-28 |  |  |  | 3 |  |  |  |  | 2017-07-28 |  | 5 |  |  |  | -1 |  | 30649 | 0 | 30654 | 6 | 6 | 6 | Lekshmi Balakrishnan | Jijin Isaac | Lekshmi Balakrishnan | Karthika
5BRI-69 | RFS.80 | H-M-H | BAU | Post RFS |  |  | 2017-07-17 | [8 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-08-02 | 2017-08-09 | 0 | 11 | 0 | 0 |  |  |  |  | 2017-08-09 |  | 6 |  |  |  | -1 |  | 30656 | 0 | 30662 | 7 | 7 | 7 | Rejitha Retnakaran | Shenita | Rejitha Retnakaran | Shenita
2LIV-62 | RFS.65 | H-A-H | BAU | Post RFS |  |  | 2017-07-25 | [8 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-08-03 | 2017-08-09 | 2 | 6 | 0 | 2 |  |  |  |  | 2017-08-09 |  | 5 |  |  |  | -1 |  | 30657 | 0 | 30662 | 6 | 8 | 8 | Aravind V | Reshma Rajan | Aravind V | Sahishna
3FNT-67 | RFS.66 | H-A-H | BAU | Post RFS |  |  | 2017-07-25 |  |  | Completed - Accepted by NEO | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-08-03 | 2017-08-09 | [8 empty] | 2017-08-09 | 2017-09-29 | 5 |  |  |  | -1 |  | 30657 | 0 | 30662 | 6 | 9 | 9 | Bastin Joseph | Bhagyalekshmi | Bastin Joseph | Bhagyalekshmi
4MRA-62 | RFS.58 | H-A-H | BAU | Post RFS |  |  | 2017-07-26 | [8 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-08-04 | 2017-08-09 | [8 empty] | 2017-08-09 |  | 4 |  |  |  | -1 |  | 30658 | 0 | 30662 | 5 | 10 | 10 | Naika Arjun | Shyama P | Naika Arjun | Shyama P
3SPL-63 | RFS.66 | H-A-H | BAU | Post RFS |  |  | 2017-08-02 |  |  | Completed - Accepted by NEO |  |  | 2017-09-14 | 2017-09-16 | Completed | 2 |  |  |  |  | 0 | 2017-09-16 | [8 empty] | Completed - Handed over to NEO | 2017-09-19 | 2017-09-29 | 9 | 2 | 0 | 9 | 0 | 0 | 0 | 2 | 2017-09-29 | 2017-10-06 | 8 |  |  |  | 30684 |  | 30687 | 0 | 30695 | -30676 | 11 | 11 | Jiya | Amalu Manuel | Jiya | Amalu Manuel
3HGT-68 | RFS.74 | M-M-J | BAU | Post RFS |  |  | 2017-08-03 |  |  | Completed - Accepted by NEO | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-08-17 | 2017-09-20 | [8 empty] | 2017-09-21 | 2017-09-29 | 24 |  |  |  | -1 |  | 30666 | 0 | 30690 | 25 | 12 | 12 | Jyoti | Sriram Rajendra Kumar | Jyoti | Sriram Rajendra Kumar
5FLN-60 | RFS.104 | H-B-J | BAU | Post RFS |  |  | 2017-07-24 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2 | 13 | 13 | Shahin Basheer | Reethu Sebastian | Shahin Basheer | Reethu Sebastian
4SLA-69 | RFS.66 | H-A-H | BAU | Post RFS |  |  | 2017-08-04 |  |  | Completed - Accepted by NEO | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-08-11 | 2017-09-12 | [8 empty] | 2017-09-14 | 2017-09-22 | 22 |  |  |  | -1 |  | 30663 | 0 | 30685 | 23 | 14 | 14 | Vedant | Nevin Tom | Vedant | Nevin Tom
2CRR-70 | RFS.63 | H-A-H | BAU | Post RFS |  |  | 2017-08-08 |  |  | Completed - Accepted by NEO |  |  | 2017-09-25 | 2017-09-27 | Completed | 3 |  |  |  |  | 0 | 2017-09-27 | [8 empty] | Completed - Handed over to NEO | 2017-09-28 | 2017-10-04 | 13 | 1 | 0 | 13 | 0 | 1 | 0 | 2 | 2017-10-09 | 2017-10-16 | 6 |  |  |  | 30691 |  | 30694 | 0 | 30700 | -30685 |  | 15 |  | Jiya | Ashwin | Jiya
4BUR-21 | RFS.94 | M-B-H | BAU | Post RFS |  |  | 2017-07-28 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2 |  | 16 |  | Ashok Hariharamoni |  | Ashok Hariharamoni
4SLA-66 | RFS.94 | M-B-H | BAU | Post RFS |  |  | 2017-07-28 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2 |  | 17 |  | Jyoti |  | Jyoti
5HNL-60 | RFS.77 | H-A-H | BAU | Post RFS |  |  | 2017-08-09 |  |  | Completed - Accepted by NEO | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-08-17 | 2017-09-18 | [8 empty] | 2017-09-18 | 2017-09-27 | 21 |  |  |  | -1 |  | 30666 | 0 | 30687 | 22 | [5 empty] | Ramcy S
3END-62 | RFS.81 | M-A-J | BAU | Post RFS |  |  | 2017-08-14 |  |  | Completed - Accepted by NEO | [5 empty] | 0 |  |  |  |  | 0 | [9 empty] | Completed - Handed over to NEO | 2017-08-21 | 2017-09-17 | [8 empty] | 2017-09-19 | 2017-09-28 | 20 |  |  |  | -1 |  | 30668 | 0 | 30688 | 21
3DRP-63 | RFS.80 | M-M-H | BAU | Post RFS |  |  | 2017-08-18 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
4BUR-65 | RFS.77 | H-A-H | BAU | Post RFS |  |  | 2017-08-21 |  |  | Completed - Accepted by NEO |  |  | 2017-08-22 | 2017-08-22 | Completed | 1 |  |  |  |  | 0 | 2017-08-22 | [8 empty] | Completed - Handed over to NEO | 2017-09-15 | 2017-09-21 | 12 | 4 | 0 | 8 | 0 | 1 | 0 | 0 | 2017-10-12 | 2017-10-20 | 18 |  |  |  | 30669 |  | 30685 | 0 | 30703 | -30651
3HGT-73 | RFS.66 | H-A-H | BAU | Post RFS |  |  | 2017-08-22 |  |  | Completed - Awaiting final Acceptance | 2017-12-20 | Naika Arjun | 2017-12-21 | 2017-12-22 | Completed | 2 |  |  |  |  | 0 | 2017-12-22 |  |  |  |  | Jyoti |  |  |  | Completed - Handed over to NEO | 2017-12-27 | 2018-01-04 | 1 | 0 | 0 | 1 |  |  |  | 1 | 2018-01-05 |  | 7 | DF125517 was raised with Telstra | 2018-01-02 | 2018-01-04 | 1 |  | 30752 | 3 | 10 | -30746
5SAL-62 | RFS.82 | M-M-H | BAU | Post RFS |  |  | 2017-08-24 |  |  | Completed - Accepted by NEO |  |  | 2017-09-11 | 2017-09-14 | Completed | 4 |  |  |  |  | 0 | 2017-09-14 | [8 empty] | Completed - Handed over to NEO | 2017-09-15 | 2017-09-21 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2017-10-05 | 2017-10-10 | 13 |  |  |  | 30681 |  | 30685 | 0 | 30698 | -30668
4SLA-72 | RFS.68 | H-A-H | BAU | Post RFS |  |  | 2017-08-25 |  |  | Completed - Accepted by NEO |  |  | 2017-08-28 | 2017-08-28 | Completed | 1 |  |  |  |  | 0 | 2017-08-28 | [8 empty] | Completed - Handed over to NEO | 2017-09-15 | 2017-09-18 | 4 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 2017-09-18 | 2017-09-29 | 2 |  |  |  | 30673 |  | 30685 | 0 | 30687 | -30671
3NAW-64 | RFS.66 | H-A-H | BAU | Post RFS |  |  | 2017-08-29 |  |  | Completed - Accepted by NEO |  |  | 2017-09-14 | 2017-09-18 | Completed | 3 |  |  |  |  | 0 | 2017-09-18 | [8 empty] | Completed - Handed over to NEO | 2017-09-19 | 2017-09-26 | 10 | 1 | 0 | 10 | 0 | 0 | 0 | 1 | 2017-09-27 | 2017-10-06 | 7 |  |  |  | 30684 |  | 30687 | 0 | 30694 | -30677
2SEF-65 | RFS.57 | H-A-H | BAU | Post RFS |  |  | 2017-08-29 |  |  | Completed - Accepted by NEO |  |  | 2017-09-15 | 2017-09-20 | Completed | 4 |  |  |  |  | 0 | 2017-09-20 | [8 empty] | Completed - Handed over to NEO | 2017-09-25 | 2017-09-29 | 6 | 4 | 0 | 6 | 0 | 0 | 0 | 1 | 2017-10-04 | 2017-10-06 | 6 |  |  |  | 30685 |  | 30691 | 0 | 30697 | -30679
4MGA-62 | RFS.80 | M-A-H | BAU | Post RFS | 2 |  | 2017-09-08 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
4BUR-69 | RFS.77 | H-A-H | BAU | Post RFS |  |  | 2017-09-11 |  |  | Completed - Accepted by NEO |  |  | 2017-09-26 | 2017-09-28 | Completed | 3 |  |  |  |  | 0 | 2017-09-28 | [8 empty] | Completed - Handed over to NEO | 2017-09-29 | 2017-10-03 | 4 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 2017-10-09 | 2017-10-17 | 5 |  |  |  | 30692 |  | 30694 | 0 | 30700 | -30686
4EMP-61 | RFS.75 | M-M-H | BAU | Post RFS |  |  | 2017-09-15 |  |  | Completed - Accepted by NEO |  |  | 2017-09-26 | 2017-09-28 | Completed | 3 |  |  |  |  | 0 | 2017-09-28 | [8 empty] | Completed - Handed over to NEO | 2017-09-29 | 2017-10-03 | 7 | 0 | 0 | 7 | 0 | 2 | 0 | 0 | 2017-10-10 | 2017-10-25 | 6 |  |  |  | 30692 |  | 30694 | 0 | 30701 | -30685
4BUR-61 | RFS.77 | H-A-H | BAU | Post RFS |  |  | 2017-09-18 |  |  | Completed - Accepted by NEO |  |  | 2017-10-17 | 2017-10-17 | Completed | 1 |  |  |  |  | 0 | 2017-10-17 | [8 empty] | Completed - Handed over to NEO | 2017-10-19 | 2017-10-19 | 4 | 2 | 0 | 4 | 0 | 1 | 0 | 1 | 2017-10-20 | 2017-10-24 | 2 |  |  |  | 30705 |  | 30706 | 0 | 30708 | -30703
3CTA-67 | RFS.66 | H-A-H | BAU | Post RFS |  |  | 2017-09-19 |  |  | Completed - Accepted by NEO |  |  | 2017-09-28 | 2017-10-04 | Completed | 3 |  |  |  |  | 0 | 2017-10-04 | [8 empty] | Completed - Handed over to NEO | 2017-10-04 | 2017-10-06 | 8 | 2 | 0 | 8 | 0 | 2 | 0 | 1 | 2017-10-11 | 2017-10-20 | 6 | Unable to close the task on 3rd Oct due to Appian issue |  |  | 30694 |  | 30696 | 0 | 30702 | -30688
2WET-61 | RFS.63 | H-A-H | BAU | Post RFS |  |  | 2017-09-20 |  |  | Completed - Accepted by NEO |  |  | 2017-10-11 | 2017-10-12 | Completed | 2 |  |  |  |  | 0 | 2017-10-12 | [8 empty] | Completed - Handed over to NEO | 2017-10-13 | 2017-10-17 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 1 | 2017-10-18 | 2017-10-25 | 3 |  |  |  | 30701 |  | 30703 | 0 | 30706 | -30698
3HGT-66 | RFS.66 | H-A-H | BAU | Post RFS |  |  | 2017-09-25 |  |  | Completed - Accepted by NEO |  |  | 2017-10-04 | 2017-10-06 | Completed | 3 |  |  |  |  | 0 | 2017-10-06 | [8 empty] | Completed - Handed over to NEO | 2017-10-09 | 2017-10-12 | 5 | 1 | 0 | 5 | 0 | 2 | 0 | 1 | 2017-10-13 | 2017-10-19 | 5 |  |  |  | 30696 |  | 30699 | 0 | 30704 | -30691
3CAU-61 | RFS.78 | H-A-H | BAU | Post RFS |  |  | 2017-09-27 |  |  | Completed - Accepted by NEO |  |  | 2017-10-09 | 2017-10-10 | Completed | 2 |  |  |  |  | 0 | 2017-10-10 | [8 empty] | Completed - Handed over to NEO | 2017-10-11 | 2017-10-12 | 11 | 1 | 0 | 11 | 0 | 1 | 0 | 1 | 2017-10-13 | 2017-10-19 | 3 |  |  |  | 30699 |  | 30701 | 0 | 30704 | -30696
3CTA-61 | RFS.64 | M-A-H | BAU | Post RFS |  |  | 2017-10-02 |  |  | Completed - Accepted by NEO |  |  | 2017-10-25 | 2017-10-26 | Completed | 2 |  |  |  |  | 0 | 2017-10-26 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-10-27 | 2017-10-30 | 6 | 1 | 0 | 6 | 0 | 0 | 0 | 1 | 2017-11-01 | 2017-11-13 | 4 |  |  |  | 30710 |  | 30712 | 0 | 30716 | -30706
3CAU-65 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-10-10 |  |  | Completed - Awaiting final Acceptance | 2017-12-15 | Lekshmi Balakrishnan | 2017-12-18 | 2017-12-19 | Completed | 2 |  |  |  |  | 0 | 2017-12-19 | Sree Ram Sundar | 2017-12-22 |  | In Progress | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-20 | 2017-12-22 | 2 | 0 | 0 | 2 |  |  |  | 2 | 2018-01-02 |  | 7 |  |  |  | 1 |  | 30749 | 0 | 10 | -30740
4BUR-66 | RFS.87 | M-M-H | BAU | Post RFS |  |  | 2017-10-12 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
4BUR-68 | RFS.91 | H-M-Q | BAU | Post RFS |  |  | 2017-10-12 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-10-30 | 2017-10-31 | Completed | 2 |  |  |  |  | 0 | 2017-10-31 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-02 | 2017-11-07 | 8 | 1 | 0 | 8 | 0 | 0 | 0 | 1 | 2017-11-15 |  | 9 |  |  |  | 30713 |  | 30716 | 0 | 30725 | -30704
2CRR-71 | RFS.58 | H-A-H | BAU | Post RFS |  |  | 2017-10-13 |  |  | Completed - Awaiting final Acceptance | 2017-12-20 | Rejitha Retnakaran | 2017-12-21 | 2017-12-22 | Completed | 2 |  |  |  |  | 0 | 2017-12-22 |  |  |  |  | Ramcy S |  |  |  | Completed - Handed over to NEO | 2017-12-26 | 2018-01-04 | 4 | 0 | 0 | 4 |  |  |  | 2 | 2018-01-05 |  | 7 | DF125524-mail has been sent to AP team to rectify the boundary to make the locations and associated tasp inside same ADAs, which will correct the service class mismatches. | 2017-12-27 | 2018-01-03 | 1 |  | 30751 | 5 | 10 | -30747
3DRP-62 | RFS.63 | H-A-H | BAU | Post RFS |  |  | 2017-10-13 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
4MRA-63 | RFS.78 | H-M-H | BAU | Post RFS |  |  | 2017-10-13 |  |  | Completed - Accepted by NEO |  |  | 2017-10-25 | 2017-10-26 | Completed | 2 |  |  |  |  | 0 | 2017-10-26 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-10-27 | 2017-11-01 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 1 | 2017-11-02 | 2017-11-06 | 5 |  |  |  | 30710 |  | 30712 | 0 | 30717 | -30705
2EDG-61 | RFS.55 | H-A-H | BAU | Post RFS |  |  | 2017-10-13 |  |  | Completed - Accepted by NEO |  |  | 2017-10-27 | 2017-10-30 | Completed | 2 |  |  |  |  | 0 | [5 empty] | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-01 | 2017-11-09 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 3 | 2017-11-14 | 2017-11-17 | 9 |  |  |  | 30712 |  | 30715 | 0 | 30724 | -30703
2LIV-68 | RFS.97 | M-M-H | BAU | Post RFS |  |  | 2017-10-13 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-01 | 2017-11-02 | Completed | 2 |  |  |  |  | 0 | 2017-11-02 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-06 | 2017-11-14 | 2 | 0 | 0 | 2 | 0 | 1 | 0 | 2 | 2017-11-15 |  | 7 |  |  |  | 30715 |  | 30718 | 0 | 30725 | -30708
4ASH-62 | RFS.95 | H-A-Q | BAU | Post RFS |  |  | 2017-10-16 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-14 | 2017-11-15 | Completed | 2 |  |  |  |  | 0 | 2017-11-15 | Sree Ram Sundar | 2017-11-21 | 2017-11-23 | Completed | Karthika |  |  |  | Completed - Handed over to NEO | 2017-11-20 | 2017-11-22 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2017-11-23 |  | 4 |  |  |  | 30723 |  | 30727 | 0 | 30731 | -30719
3WHL-65 | RFS.63 | M-A-J | BAU | Post RFS |  |  | 2017-10-17 | Yes | Yes | Completed - Awaiting final Acceptance | 2017-11-02 |  | 2017-11-03 | 2017-11-06 | Completed | 2 | Minu | 2017-11-03 | 2017-11-07 | Completed | 2 | 2017-11-07 | Shahin Basheer | 2017-11-20 | 2017-12-15 | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-08 | 2017-12-13 | 19 | 2 | 10 | 9 | 0 | 0 | 1 | 1 | 2017-12-19 |  | 30 | More number of defects to be validated as it’s a D-Lite SAM (FTTN+FTTB+CSD) Waiting for update from Downstream Design team for the defect - DF118249. Two issues with Design team has been pending since 16th November. | 2017-11-16 | 2017-12-13 | 1 |  | 30719 | 20 | 33 | -30707
2WET-64 | RFS.65 | H-A-H | BAU | Post RFS |  |  | 2017-10-17 | No |  | Completed - Awaiting final Acceptance |  |  | 2017-11-02 | 2017-11-03 | Completed | 2 |  |  |  |  | 0 | 2017-11-03 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-07 | 2017-11-17 | 5 | 1 | 0 | 5 | 0 | 0 | 0 | 1 | 2017-11-20 |  | 9 |  |  |  | 30716 |  | 30718 | 0 | 30728 | -30706
2PNN-66 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-10-18 |  |  | Completed - Accepted by NEO |  |  | 2017-10-27 | 2017-10-30 | Completed | 2 |  |  |  |  | 0 | 2017-10-30 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-10-31 | 2017-11-02 | 10 | 1 | 0 | 10 | 0 | 0 | 0 | 0 | 2017-11-06 | 2017-11-09 | 5 |  |  |  | 30712 |  | 30714 | 0 | 30719 | -30707
4EMP-66 | RFS.56 | H-A-H | BAU | Post RFS |  |  | 2017-10-18 |  |  | Completed - Awaiting final Acceptance | 2018-01-04 | Vedant | 2018-01-05 | 2018-01-09 | Completed | 3 |  |  |  |  | 0 | 2018-01-09 |  |  |  |  | Amalu Manuel |  |  |  | Completed - Handed over to NEO | 2018-01-10 | 2018-01-12 | 3 | 0 | 0 | 3 |  |  |  | 1 | 2018-01-16 |  | 5 |  |  |  | 1 |  | 30761 | 0 | 9 | -30753
3NES-61 | RFS.65 | H-A-H | BAU | Post RFS |  |  | 2017-10-20 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-08 | 2017-11-09 | Completed | 2 |  |  |  |  | 0 |  | Sree Ram Sundar | 2017-11-20 | 2017-11-23 | Completed | Shyama P |  |  |  | Completed - Handed over to NEO | 2017-11-14 | 2017-11-20 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 2 | 2017-11-23 |  | 8 | For the defect - DF119005, waiting for confirmation from NEO, which is under discussion. | 2017-11-15 | 2017-11-23 | 30719 | 6 | 30723 | 7 | 30731 | -30724
2EDG-65 | RFS.95 | M-M-H | BAU | Post RFS |  |  | 2017-10-26 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-15 | 2017-11-16 | Completed | 2 |  |  |  |  | 0 | 2017-11-16 | Sree Ram Sundar | 2017-11-21 | 2017-11-29 | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-20 | 2017-11-29 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 2017-11-30 |  | 9 |  | 2017-11-16 | 2017-11-24 | 30724 |  | 30727 | 7 | 30736 | -30722
5GUG-63 | RFS.48 | H-M-J | BAU | Post RFS |  |  | 2017-10-26 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
2ING-61 | RFS.63 | H-A-H | BAU | Post RFS |  |  | 2017-10-27 |  |  | On Hold | 2017-11-06 |  | 2017-11-06 | 2017-11-07 | Completed | 1 |  |  |  |  | 0 | 2017-11-07 | Sree Ram Sundar | 2017-11-20 | 2017-11-20 | Completed | Meera Sudhakumar |  |  |  | On Hold | 2017-11-13 |  | 9 | 1 | 0 | 9 | 0 | 0 | 1 | 1 |  |  | -30723 | For the defect - DF118519, waiting for confirmation from NEO, which is under discussion. | 2017-11-27 |  | 0 |  | 30722 | -30733 | -30719 | -30708
2PNN-67 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-10-27 | No | Pre-AT | Completed - Awaiting final Acceptance | 2017-11-20 | Naika Arjun | 2017-11-20 | 2017-11-21 | Completed | 2 |  |  |  |  | 0 | 2017-11-21 | Sree Ram Sundar | 2017-11-23 |  |  | Ashok Hariharamoni |  |  |  | Completed - Handed over to NEO | 2017-11-22 | 2017-11-27 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 2017-11-28 |  | 5 | Onhold in Appian due to planned PCDs | 2017-12-19 |  | 0 |  | 30729 | -30749 | 7 | 27
4BUR-63 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-10-31 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-13 | 2017-11-14 | Completed | 2 |  |  |  |  | 0 | 2017-11-14 | Sree Ram Sundar | 2017-11-21 | 2017-11-23 | Completed | Ashok Hariharamoni |  |  |  | Completed - Handed over to NEO | 2017-11-17 | 2017-11-22 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-11-23 |  | 5 | DF124792 : rasied with Testra for clarification | 2017-12-18 |  | 30722 |  | 30726 | -30748 | 30731 | 31
5GNG-61 | RFS.99 | M-M-H | BAU | Post RFS |  |  | 2017-10-31 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-15 | 2017-11-16 | Completed | 2 |  |  |  |  | 0 | 2017-11-16 | Sree Ram Sundar | 2017-11-22 | 2017-11-24 | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-21 | 2017-11-27 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 1 | 2017-11-27 |  | 5 | DF125594 ; raised with Tesltra | 2018-01-02 |  | 30724 |  | 30728 | -30756 | 30733 | 37
5SAL-63 | RFS.51 | H-A-H | BAU | Post RFS |  |  | 2017-10-31 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-10 | 2017-11-13 | Completed | 2 |  |  |  |  | 0 | 2017-11-13 | Sree Ram Sundar | 2017-11-20 | 2017-11-23 | Completed | Jyoti |  |  |  | Completed - Handed over to NEO | 2017-11-15 | 2017-11-23 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 2017-11-24 |  | 8 | DF126585 - Location to be validated by LMS.Mail sent on 12-01-2018 MPS boundary to be validated by Design team. Mail sent on 15-01-2018 | 2018-01-12 |  | 30721 |  | 30724 | -30764 | 30732 | 51
2WET-63 | RFS.58 | H-A-H | BAU | Post RFS |  |  | 2017-10-31 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-10 | 2017-11-13 | Completed | 2 |  |  |  |  | 0 | 2017-11-13 | Sree Ram Sundar | 2017-11-20 | 2017-11-27 | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-17 | 2017-11-27 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 2017-11-27 |  | 7 | DF119488 - was with LMS team to be resolved |  |  | 30721 |  | 30726 | 0 | 30733 | -30714
2ENG-63 | RFS.72 | H-A-Q | BAU | Post RFS |  |  | 2017-10-31 |  |  | Completed - Awaiting final Acceptance |  |  | 2017-11-08 | 2017-11-09 | Completed | 2 |  |  |  |  | 0 | 2017-11-09 | Lekshmi Balakrishnan | 2017-11-20 | 2017-11-20 | Completed | Sriram Rajendra Kumar |  |  |  | Completed - Handed over to NEO | 2017-11-15 | 2017-11-17 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 2017-11-20 |  | 4 |  |  |  | 30719 |  | 30724 | 0 | 30728 | -30715
2PNN-64 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-11-01 | No |  | Completed - Awaiting final Acceptance | 2017-11-30 | Rejitha Retnakaran | 2017-11-30 | 2017-12-01 | Completed | 2 |  |  |  |  | 0 | 2017-12-01 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-12-05 |  | 30739 |  |  |  | 0 |  | -1 | 0 | 4 | 5
2CRM-62 | RFS.72 | H-A-Q | BAU | Post RFS |  |  | 2017-11-06 |  |  | Completed - Accepted by NEO |  |  | 2017-11-14 | 2017-11-15 | Completed | 2 |  |  |  |  | 0 | 2017-11-15 | Sree Ram Sundar | 2017-11-21 | 2017-11-22 | Completed | Shyama P |  |  |  | Completed - Handed over to NEO | 2017-11-20 | 2017-11-22 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 2017-11-22 | 2017-11-27 | 3 |  |  |  | 30723 |  | 30727 | 0 | 30730 | -30720
2WET-60 | RFS.63 | H-A-H | BAU | Post RFS |  |  | 2017-11-07 | No |  | Completed - Handed over to NEO | 2017-11-17 | Anju Lisa | 2017-11-17 | 2017-11-20 | Completed | 2 |  |  |  |  | 0 | 2017-11-20 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-22 | 2017-11-27 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 2017-11-28 |  | 5 |  |  |  | 0 |  | 30729 | 0 | 8 | -30721
3WHL-60 | RFS.66 | H-M-H | BAU | Post RFS |  |  | 2017-11-07 | No |  | Completed - Awaiting final Acceptance | 2017-12-05 | Naika Arjun | 2017-12-05 | 2017-12-07 | Completed | 3 |  |  |  |  | 0 | 2017-12-07 | Sree Ram Sundar | 2017-12-11 | 2017-12-11 | Completed | Amalu Manuel |  |  |  | Completed - Handed over to NEO | 2017-12-07 | 2017-12-21 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 2 | 2017-12-22 |  | 12 | Due to ATLAS issue,raised defect on 7th Dec eventhogh QI completed on 6th Dec Due to the high no of GTD mismatches, defect resolution and closure activities took much effort. Ho prepared on 22-12-17 |  |  | 0 |  | 30740 | 0 | 14 | -30726
4FHL-64 | RFS.80 | M-M-H | BAU | Post RFS |  |  | 2017-11-08 | No |  | Completed - Awaiting final Acceptance |  | Naika Arjun | 2017-11-24 | 2017-11-27 | Completed | 2 |  |  |  |  | 0 | 2017-11-27 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-29 | 2017-12-07 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 2017-12-07 |  | 7 |  | 2017-11-30 | 2017-12-05 | 30731 |  | 30734 | 4 | 30741 | -30728
4MGA-64 | RFS.79 | H-A-H | BAU | Post RFS |  |  | 2017-11-08 |  |  | Completed - Accepted by NEO |  |  | 2017-11-16 | 2017-11-17 | Completed | 2 |  |  |  |  | 0 | 2017-11-17 |  |  |  |  | NA |  |  |  | Completed - Handed over to NEO |  |  | 0 | 0 | 0 | [5 empty] | 2017-11-20 | 2017-11-22 | 30728 | This is a Zero Defect SAM |  |  | 30725 |  | -1 | 0 | 30728 | 4
4CPB-60 | RFS.65 | M-M-J | BAU | Post RFS |  |  | 2017-11-20
2PNN-69 | RFS.76 | M-A-H | BAU | Post RFS |  |  | 2017-11-09 | No |  | Completed - Awaiting final Acceptance | 2017-12-04 | Rejitha Retnakaran | 2017-12-04 | 2017-12-05 | Completed | 2 |  |  |  |  | 0 | 2017-12-05 | Sree Ram Sundar | 2017-12-08 | 2017-12-08 | Completed | Sahishna |  |  |  | Completed - Handed over to NEO | 2017-12-06 | 2017-12-07 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 2017-12-11 |  | 4 |  |  |  | 0 |  | 30739 | 0 | 6 | -30733
5GUG-66 | RFS.78 | H-A-H | BAU | Post RFS |  |  | 2017-11-09 | No |  | Completed - Awaiting final Acceptance |  | Pooja Jacob | 2017-11-24 | 2017-11-27 | Completed | 2 |  |  |  |  | 0 | 2017-11-27 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-29 | 2017-12-01 | 7 | 0 | 0 | 6 | 0 | 1 | 0 | 1 | 2017-12-04 |  | 4 |  |  |  | 30731 |  | 30734 | 0 | 30738 | -30727
5EDW-60 | RFS.78 | H-A-H | BAU | Post RFS |  |  | 2017-11-09 | No |  | Completed - Awaiting final Acceptance |  | Lekshmi Balakrishnan | 2017-11-24 | 2017-11-27 | Completed | 2 |  |  |  |  | 0 | 2017-11-27 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-11-29 | 2017-12-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2017-12-05 |  | 5 |  | 2017-11-30 | 2017-12-05 | 30731 |  | 30734 | 4 | 30739 | -30730
2CRM-60 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-11-09 | No |  | Completed - Awaiting final Acceptance | 2017-12-01 | Naika Arjun | 2017-12-01 | 2017-12-04 | Completed | 2 |  |  |  |  | 0 | 2017-12-04 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-05 | 2017-12-08 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 2017-12-08 |  | 4 |  |  |  | 0 |  | 30738 | 0 | 6 | -30732
2PNN-65 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-11-09 | No | Pre-AT | Completed - Awaiting final Acceptance | 2017-11-20 | Pooja Jacob | 2017-11-20 | 2017-11-21 | Completed | 2 |  |  |  |  | 0 | 2017-11-21 | Sree Ram Sundar | 2017-11-23 | 2017-11-28 | Completed | Ashok Hariharamoni |  |  |  | Completed - Handed over to NEO | 2017-11-22 | 2017-11-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-11-28 |  | 5 | There was an LMS issue |  |  | 0 |  | 30729 | 0 | 7 | -30722
2NSY-60 | RFS.84 | H-M-H | BAU | Post RFS | 0.2 |  | 2017-11-13 | No | Pre-AT | Completed - Awaiting final Acceptance | 2017-11-23 | Rejitha Retnakaran | 2017-11-23 | 2017-11-24 | Completed | 2 |  |  |  |  | 0 | 2017-11-24 |  |  |  |  | Ashok Hariharamoni |  |  |  | Completed - Handed over to NEO | 2017-11-27 | 2017-12-05 | 4 | 1 | 0 | 4 | 0 | 0 | 0 | 2 | 2017-12-06 |  | 8 |  | 2017-11-30 | 2017-12-04 | 0 |  | 30732 | 7 | 10 | -30729
4MRA-60 | RFS.70 | H-A-H | BAU | Post RFS | 1 |  | 2017-11-13 | No |  | Completed - Awaiting final Acceptance | 2017-12-01 | Pooja Jacob | 2017-12-01 | 2017-12-04 | Completed | 2 |  |  |  |  | 0 | 2017-12-04 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-11 | 2017-12-19 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 2 | 2017-12-22 |  | 10 | Defect resolution started on 11-12-17 due to resource availability.2 defects were with LMS team.NEO HO was prepared on 22-Dec-17 | 2017-12-05 | 2017-12-08 | 0 |  | 30742 | 4 | 16 | -30730
4MGB-62 | RFS.101 | M-M-H | BAU | Post RFS | 1 |  | 2017-11-13 | No |  | Completed - Awaiting final Acceptance | 2017-11-27 | Rejitha Retnakaran | 2017-11-28 | 2017-11-29 | Completed | 2 |  |  |  |  | 0 | 2017-11-29 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-01 | 2017-12-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-12-05 |  | 3 |  |  |  | 1 |  | 30736 | 0 | 7 | -30730
4BLH-61 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-11-16 | No |  | Completed - Awaiting final Acceptance | 2017-11-29 | Pooja Jacob | 2017-11-29 | 2017-11-30 | Completed | 2 |  |  |  |  | 0 | 2017-11-30 | Sree Ram Sundar | 2017-12-01 |  | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-01 | 2017-12-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2017-12-06 |  | 4 |  |  |  | 0 |  | 30736 | 0 | 6 | -30730
4MRA-65 | RFS.84 | H-A-H | BAU | Post RFS |  |  | 2017-11-17 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
2SHA-60 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-11-17 |  |  | On Hold | 2017-12-06 | Vedant | 2017-12-06 | 2017-12-08 | Completed | 3 |  |  |  | 2017-12-08 | 0 | 2017-12-08 |  |  |  |  | Meera Sudhakumar |  |  |  | On Hold | 2017-12-13 |  | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 1 |  |  | -30745 | Onhold in Appian due to planned PCDs | 2017-12-19 |  | 0 |  | 30744 | -30749 | -30740 | -30735
3FNT-61 | RFS.63 | H-A-H | BAU | Post RFS |  |  | 2017-11-20 | No |  | Completed - Awaiting final Acceptance | 2017-12-01 | Lekshmi Balakrishnan | 2017-12-04 | 2017-12-05 | Completed | 2 |  |  |  |  | 0 | 2017-12-05 | Shahin Basheer | 2017-12-11 |  | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-07 | 2018-01-04 | 5 | 0 | 0 | 5 | 0 | 1 | 0 | 1 | 2018-01-04 |  | 18 | Sam delayed by 1 day due to priority SAM 4EMP_25 being worked upon by 2 folks. One issue sent to LMS on 6/12/2017. Issue to be addressed by TELSTRA. Query sent on 12/12/2017. Awaiting response 4-01-2018-Defect resolved after confirmation from telstra.Could not complete the task in Appian as the same is paused. | 2017-12-12 | 2018-01-04 | 1 |  | 30740 | 15 | 22 | -30734
2FRE-63 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-11-21 |  |  | Completed - Awaiting final Acceptance | 2018-01-23 | Naika Arjun | 2018-01-24 | 2018-01-25 | Completed | 2 |  |  |  |  | 0 | 2018-01-25 |  |  |  |  | Sriram Rajendra Kumar |  |  |  | Completed - Handed over to NEO | 2018-01-29 | 2018-01-31 | 0 | 0 | 0 | 0 |  |  |  | 2 | 2018-01-31 |  | 3 |  |  |  | 1 |  | 30773 | 0 | 6 | -30768
5EDW-65 | RFS.80 | H-A-H | BAU | Post RFS |  |  | 2017-11-21 | No |  | Completed - Awaiting final Acceptance | 2017-12-07 | Naika Arjun | 2017-12-07 | 2017-12-08 | Completed | 2 |  |  |  | 2017-12-08 | 0 | 2017-12-08 |  |  |  |  | Karthika |  |  |  | Completed - Handed over to NEO | 2017-12-08 | 2017-12-11 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2017-12-11 |  | 2 |  |  |  | 0 |  | 30741 | 0 | 3 | -30738
4BNP-62 | RFS.83 | H-A-H | BAU | Post RFS | 1 |  | 2017-12-01 |  |  | Completed - Awaiting final Acceptance | 2017-12-08 | Shahin Basheer | 2017-12-08 | 2017-12-11 | Completed | 2 |  |  |  |  | 0 | 2017-12-11 |  |  |  | Completed | Vinaybhaskar P |  |  |  | Completed - Handed over to NEO | 2017-12-12 | 2017-12-12 | 4 | 0 | 0 | 4 | 0 | 0 |  | 1 | 2017-12-18 |  | 5 |  |  |  | 0 |  | 30743 | 0 | 7 | -30736
2MOS-64 | RFS.75 | H-A-Q | BAU | Post RFS | 1 |  | 2017-12-01 |  |  | Completed - Awaiting final Acceptance | 2017-12-06 | Pooja Jacob | 2017-12-06 | 2017-12-07 | Completed | 2 |  |  |  |  | 0 | 2017-12-07 |  |  |  |  | Vinaybhaskar P |  |  |  | Completed - Handed over to NEO | 2017-12-08 | 2017-12-08 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 2017-12-08 |  | 1 |  |  |  | 0 |  | 30741 | 0 | 3 | -30738
3GLI-60 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-04 | No |  | Completed - Awaiting final Acceptance | 2017-12-07 | Lekshmi Balakrishnan | 2017-12-07 | 2017-12-08 | Completed | 2 |  |  |  |  | 0 | 2017-12-08 |  |  |  |  | Shyama P |  |  |  | Completed - Handed over to NEO | 2017-12-12 | 2017-12-19 | 5 | 0 | 0 | 5 |  |  |  | 1 | 2017-12-21 |  | 8 | Defect resolution started on 12-12-17 due to resource availability.3 defects were with LMS team.NEO HO was prepared on 22-Dec-17 |  |  | 0 |  | 30743 | 0 | 11 | -30732 | 15 | 18 | NA | NA
4BNP-61 | RFS.83 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-05 |  |  | Completed - Awaiting final Acceptance | 2017-12-14 | Pooja Jacob | 2017-12-15 | 2017-12-19 | Completed | 3 |  |  |  |  | 0 | 2017-12-19 | Pooja Jacob | 2017-12-22 | 2017-12-26 | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-20 | 2017-12-22 | 3 | 0 | 0 | 3 |  |  |  | 2 | 2017-12-28 |  | 5 |  |  |  | 1 |  | 30749 | 0 | 9 | -30741
3DNC-64 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-05 |  |  | Completed - Awaiting final Acceptance | 2017-12-14 | Naika Arjun | 2017-12-15 | 2017-12-18 | Completed | 2 |  |  |  |  | 0 | 2017-12-18 | Lekshmi Balakrishnan | 2017-12-22 | 2017-12-26 | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-20 | 2017-12-22 | 1 | 0 | 0 | 1 |  |  |  | 1 | 2018-01-05 |  | 10 | INC000006974223 - was raised for job lock issue - resolved on 5-01-2018 | 2017-12-22 | 2018-01-05 | 1 |  | 30749 | 8 | 14 | -30744
4MGB-63 | RFS.95 | H-A-Q | BAU | Post RFS | 1.1 |  | 2017-12-05 |  |  | Completed - Awaiting final Acceptance | 2017-12-22 | Lekshmi Balakrishnan | 2017-12-26 | 2017-12-27 | Completed | 1 |  |  |  |  | 0 | 2017-12-27 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-28 |  | 2 | 0 | 0 | 2 |  |  |  | 1 |  |  | -30754 | DF125597 - was raised with telstra for clarification | 2017-12-28 | 2018-01-03 | 0 |  | 30753 | 4 | -30752 | -61509
4FHL-63 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-11 |  |  | On Hold | 2017-12-13 | Rejitha Retnakaran | 2017-12-14 | 2017-12-15 | Completed | 2 |  |  |  |  | 0 | 2017-12-15 | Shahin Basheer | 2017-12-20 |  | Completed | Meera Sudhakumar |  |  |  | On Hold | 2017-12-18 |  | 2 | 1 | 0 | 2 | 0 | 0 |  | 1 |  |  | -30748 | DF124792 : rasied with Testra for clarification | 2017-12-18 |  | 1 |  | 30747 | -30748 | -30745 | -30745
6JDL-21 | RFS.80 | M-M-J | BAU | Post RFS | 0.5 |  | 2017-12-11 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
6MLO-62 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-13 |  |  | Completed - Awaiting final Acceptance | 2017-12-18 | Naika Arjun | 2017-12-19 | 2017-12-20 | Completed | 2 |  |  |  |  | 0 | 2017-12-20 | Vedant | 2017-12-22 | 2017-12-26 | Completed | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-22 | 2017-12-26 | 1 | 0 | 0 | 1 |  |  |  | 2 | 2018-01-04 |  | 7 |  |  |  | 1 |  | 30751 | 0 | 11 | -30741
4MRA-61 | RFS.58 | M-A-H | BAU | Post RFS | 0.1 |  | 2017-12-14 |  |  | Completed - Awaiting final Acceptance | 2017-12-28 | Naika Arjun | 2017-12-29 | 2018-01-02 | Completed | 2 |  |  |  |  | 0 | 2018-01-02 |  |  |  |  | Karthika |  |  |  | Completed - Handed over to NEO | 2018-01-03 | 2018-01-10 | 6 | 0 | 0 | 6 |  |  |  | 2 | 2018-01-11 |  | 7 | DF125767 : Query has been sent to AP team to modify the boundary on 27-12-2017 during SAM execution | 2017-12-27 | 2018-01-10 | 1 |  | 30756 | 10 | 10 | -30757
4FHL-66 | RFS.78 | M-M-H | BAU | Post RFS | 1.1 |  | 2017-12-14 |  |  | Completed - Awaiting final Acceptance | 2018-01-01 | Vedant | 2018-01-02 | 2018-01-03 | Completed | 2 |  |  |  |  | 0 | 2018-01-03 |  |  |  |  | Karthika |  |  |  | Completed - Handed over to NEO | 2018-01-04 | 2018-01-12 | 2 | 0 | 0 | 2 |  |  |  |  | 2018-01-16 |  | 9 | DF125928 waiting for resolutio of Incident raised for PNI error REQ000003350439 during SAM execution. | 2018-01-04 | 2018-01-11 | 0 |  | 30757 | 6 | 11 | -30752
3NBA-63 | RFS.97 | H-A-Q | BAU | Post RFS | 0.1 |  | 2017-12-19 |  |  | Completed - Awaiting final Acceptance | 2017-12-22 | Naika Arjun | 2017-12-27 | 2017-12-28 | Completed | 2 |  |  |  |  | 0 | 2017-12-28 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2017-12-29 | 2018-01-01 | 1 | 0 | 0 | 1 |  |  |  |  | 2018-01-04 |  | 4 |  |  |  | 1 |  | 30754 | 0 | 7 | -30748
2STL-64 | RFS.104 | M-M-H | BAU | Post RFS | 0.1 |  | 2017-12-20 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
4ASH-66 | RFS.70 | H-M-J | BAU | Post RFS | 1 |  | 2017-12-25 | Yes | Dlite | Completed - Handed over to NEO | 2018-01-12 | Lekshmi Balakrishnan | 2018-01-15 | 2018-01-18 | Completed | 4 | Lekshmi Balakrishnan | 2018-01-15 | 2018-01-18 | Completed | 4 | 2018-01-18 |  |  |  |  | Nevin Tom | Ramcy S |  |  | Completed - Handed over to NEO | 2018-01-19 | 2018-01-24 | 4 | 0 | 2 | 2 |  |  |  | 2 | 2018-01-25 |  | 5 | QI completed for HFC,FTTn and CSD by same person |  |  | 1 |  | 30768 | 0 | 10 | -30759
3DNC-65 | RFS.70 | H-A-H | BAU | Post RFS | 0.2 |  | 2017-12-25 |  |  | Completed - Awaiting final Acceptance | 2017-12-29 | Anju Lisa | 2018-01-01 | 2018-01-02 | Completed | 1 |  |  |  |  | 0 | 2018-01-02 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2018-01-03 | 2018-01-05 | 1 | 0 | 0 | 1 |  |  |  | 1 | 2018-01-05 |  | 3 |  |  |  | 0 |  | 30756 | 0 | 5 | -30751
4SLA-73 | RFS.73 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-25 |  |  | On Hold | 2017-12-22 | Rejitha Retnakaran | 2017-12-26 | 2017-12-27 | Completed | 1 |  |  |  |  | 0 | 2017-12-27 |  |  |  |  | Meera Sudhakumar |  |  |  | On Hold | 2017-12-28 |  | 3 | 0 | 0 | 3 |  |  |  | 1 |  |  | -30754 | DF125594 ; raised with Tesltra | 2018-01-02 |  | 0 |  | 30753 | -30756 | -30752 | -30749
4AAR-64 | RFS.63 | H-A-H | BAU | Post RFS | 0.2 |  | 2017-12-27 |  |  | Completed - Awaiting final Acceptance | 2017-12-27 | Pooja Jacob | 2017-12-28 | 2017-12-29 | Completed | 2 |  |  |  |  | 0 | 2017-12-29 |  |  |  |  | Karthika |  |  |  | Completed - Handed over to NEO | 2017-12-29 | 2017-12-29 | 0 | 0 | 0 | 0 |  |  |  |  | 2018-01-07 |  | 5 |  |  |  | 1 |  | 30754 | 0 | 7 | -30748
4MGB-66 | RFS.95 | H-M-Q | BAU | Post RFS | 0.1 |  | 2017-12-27 |  |  | Completed - Awaiting final Acceptance | 2017-12-28 | Lekshmi Balakrishnan | 2017-12-29 | 2018-01-01 | Completed | 1 |  |  |  |  | 0 | 2018-01-01 |  |  |  |  | Karthika |  |  |  | Completed - Handed over to NEO | 2018-01-02 | 2018-01-10 | 3 | 0 | 0 | 3 |  |  |  |  | 2018-01-11 |  | 8 | Query was sent to telstra for planned objects-27-12-17 Got response from telstra and resolved the defect - 10-01-2018 | 2017-12-27 | 2018-01-10 | 1 |  | 30755 | 10 | 10 | -30756
3FNT-63 | RFS.87 | M-M-H | BAU | Post RFS | 0.2 |  | 2017-12-27 |  |  | Completed - Awaiting final Acceptance | 2018-01-04 | Anju Lisa | 2018-01-05 | 2018-01-08 | Completed | 2 |  |  |  |  | 0 | 2018-01-08 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2018-01-09 | 2018-01-12 | 3 | 0 | 0 | 3 |  |  |  | 1 | 2018-01-17 |  | 7 | Sam was kept hold for the clarification on FTTN part execution as this is a DLITE SAM. | 2018-01-15 | 2018-01-16 | 1 |  | 30760 | 2 | 10 | -30753
3DAN-61 | RFS.49 | M-A-H | BAU | Post RFS | 2.1 |  | 2017-12-28 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
2CRR-67 | RFS.83 | H-M-H | BAU | Post RFS | 0.1 |  | 2017-12-28 |  |  | Completed - Awaiting final Acceptance | 2018-01-02 | Anju Lisa | 2018-01-03 | 2018-01-03 | Completed | 1 |  |  |  |  | 0 | 2018-01-03 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2018-01-04 | 2018-01-05 | 2 | 0 | 0 | 2 |  |  |  |  | 2018-01-08 |  | 3 |  |  |  | 1 |  | 30757 | 0 | 5 | -30753
4FHL-68 | RFS.63 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-29 |  |  | Completed - Awaiting final Acceptance | 2018-01-05 | Rejitha Retnakaran | 2018-01-08 | 2018-01-09 | Completed | 2 |  |  |  |  | 0 | 2018-01-09 |  |  |  |  | Jyoti |  |  |  | Completed - Handed over to NEO | 2018-01-10 | 2018-01-16 | 5 | 0 | 0 | 6 |  |  |  | 1 | 2018-01-17 |  | 6 | DF126494 - was seeked for design team clarification |  |  | 1 |  | 30761 | 0 | 9 | -30753
3SPL-66 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-29 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
2SHA-60 | RFS.80 | H-A-H | BAU | Post RFS | 1.1 |  | 2017-12-29 | [8 empty] | 0 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | -1 |  | -1 | 0 | 0 | 2
3CTA-60 | RFS.58 | H-A-H | BAU | Post RFS | 2 |  | 2017-12-29 |  |  | Completed - Awaiting final Acceptance | 2018-01-23 | Lekshmi Balakrishnan | 2018-01-24 | 2018-01-25 | Completed | 2 |  |  |  |  | 0 | 2018-01-25 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 |  |  |  |  | 2018-01-31 |  | 4 |  |  |  | 1 |  | 30772 | 0 | 6 | -30767
4EMP-62 | RFS.80 | H-M-H | BAU | Post RFS | 0.1 |  | 2017-12-29 |  |  | In Progress | 2018-02-01 | Naika Arjun | 2018-02-02 |  | In Progress | -30778 |  |  |  |  | 0 | [22 empty] | 0 |  |  |  | 1 |  | -1 | 0 | -30777 | -30777
3CTA-63 | RFS.78 | H-A-H | BAU | Post RFS | 1.1 |  | 2011-12-29 |  |  | Completed - Handed over to NEO | 2018-01-18 | Lekshmi Balakrishnan | 2018-01-19 | 2018-01-19 | Completed | 1 |  |  |  |  | 0 | 2018-01-19 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2018-01-22 | 2018-01-24 | 2 | 0 | 0 | 2 |  |  |  | 1 | 2018-01-25 |  | 4 |  |  |  | 1 |  | 30769 | 0 | 6 | -30764
4BNP-63 | RFS.83 | M-A-H | BAU | Post RFS | 0.1 |  | 2017-12-29 |  |  | In Progress | 2018-01-31 | Lekshmi Balakrishnan | 2018-02-01 | 2018-02-01 | Completed | 1 |  |  |  |  | 0 | 2018-02-01 |  |  |  |  | Shyama P |  |  |  | In Progress | 2018-02-01 | 2018-02-01 | 3 | 0 | 0 | 3 |  |  |  | 1 |  |  | -30777 |  |  |  | 1 |  | 30776 | 0 | -30776 | -61553
5SAL-68 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 |  | 2017-12-29 |  |  | Completed - Awaiting final Acceptance | 2018-01-02 | Vedant | 2018-01-03 | 2018-01-04 | Completed | 2 |  |  |  |  | 0 | 2018-01-04 |  |  |  |  | Meera Sudhakumar |  |  |  | Completed - Handed over to NEO | 2018-01-05 | 2018-01-08 | 0 | 0 | 0 | 0 |  |  |  | 1 | 2018-01-10 |  | 4 |  |  |  | 1 |  | 30758 | 0 | 7 | -30752
2STL-66 | RFS.105 | M-A-Q | BAU | Post RFS | 0.1 |  | 2018-01-01 |  |  | Completed - Awaiting final Acceptance | 2018-01-09 | Rejitha Retnakaran | 2018-01-10 | 2018-01-12 | Completed | 3 |  |  |  |  | 0 | 2018-01-12 |  |  |  |  | Sahishna |  |  |  | Completed - Handed over to NEO | 2018-01-15 | 2018-01-17 | 2 | 0 | 0 | 2 |  |  |  | 1 | 2018-01-17 |  | 3 |  |  |  | 1 |  | 30764 | 0 | 7 | -30758
5EDW-61 | RFS.58 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-04 |  |  | Completed - Awaiting final Acceptance | 2018-01-29 | Lekshmi Balakrishnan | 2018-01-30 | 2018-01-31 | Completed | 2 |  |  |  |  | 0 | 2018-01-31 |  |  |  |  | Naveen Kumar Nagaraj |  |  |  | Completed - Handed over to NEO | 2018-02-01 | 2018-02-01 | 1 | 0 | 0 | 1 |  |  |  | 1 | 2018-02-05 |  | 3 | QI extended to second day due to the S drive folder missing issue on 30th Jan. | 2018-01-30 | 2018-01-30 | 1 |  | 30776 | 1 | 6 | -30772
5SAL-67 | RFS.58 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-04 |  |  | On Hold | 2018-01-08 | Lekshmi Balakrishnan | 2018-01-09 | 2018-01-10 | Completed | 2 |  |  |  |  | 0 | 2018-01-10 |  |  |  |  | Meera Sudhakumar |  |  |  | On Hold | 2018-01-11 |  | 2 | 0 | 0 | 2 |  |  |  | 1 |  |  | -30763 | DF126585 - Location to be validated by LMS.Mail sent on 12-01-2018 MPS boundary to be validated by Design team. Mail sent on 15-01-2018 | 2018-01-12 |  | 1 |  | 30762 | -30764 | -30760 | -30759
4CHP-64 | RFS.70 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-09
3DAN-61 | RFS.49 | M-A-H | BAU | Post RFS | 2.1 |  | 2018-01-25
5SAL-65 | RFS.78 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-25
4DRR-62 | RFS.57 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-26 |  |  | In Progress | 2018-01-31 | Naika Arjun | 2018-02-01 | 2018-02-01 | Completed | 1 |  |  |  |  | 0 | 2018-02-01 |  |  |  |  | Jyoti |  |  |  | In Progress | 2018-02-01 | 2018-02-01 | 0 | 0 | 0 | 0 |  |  |  | 1 |  |  | -30777 | Zero Defect SAM
6MLO-63 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-29 |  |  | In Progress | 2018-02-01 | Vedant | 2018-02-02 | 2018-02-02 | Completed | 1 |  |  |  |  | 0 | 2018-02-02 |  |  |  |  | Meera Sudhakumar |  |  |  | In Progress | 2018-02-05 |  | 0 | 0 | 0 | 0 |  |  |  | 1
3KGP-64 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-01-30
5SAL-69 | RFS.87 | H-A-Q | BAU | Post RFS | 0.1 |  | 2018-01-31 |  |  | Completed - Awaiting final Acceptance | 2018-01-31 | Rejitha Retnakaran | 2018-02-01 | 2018-02-01 | Completed | 1 |  |  |  |  | 0 | 2018-02-01 |  |  |  |  | Bhagyalekshmi |  |  |  | Completed - Handed over to NEO | 2018-02-01 | 2018-02-01 | 0 | 0 | 0 | 0 |  |  |  | 0 | 2018-02-05 |  | 3 | Zero Defect SAM
3DRP-60 | RFS.59 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-02-01 |  |  | In Progress | 2018-02-05 | Rejitha Retnakaran | 2018-02-05 | 2018-02-05 | Completed | 1 | [5 empty] | 2018-02-05
3SOA-62 | RFS.85 | H-A-Q | BAU | Post RFS | 0.1 |  | 2018-02-08
3NBA-71 | RFS.70 | H-A-Q | BAU | Post RFS | 0.1 |  | 2018-02-08
3SCO-68 | RFS.80 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-02-08
3HGT-60 | RFS.63 | M-A-J | BAU | Post RFS | 2.1 |  | 2018-02-13
4ABC-62 | RFS.115 | M-A-H | BAU | Post RFS | 0.1 |  | 2018-02-13
2ENG-60 | RFS.78 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-02-13
5SAL-64 | RFS.66 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-02-15
2ENG-61 | RFS.74 | H-A-H | BAU | Post RFS | 0.2 |  | 2018-02-19
3SCO-64 | RFS.77 | H-A-H | BAU | Post RFS | 0.1 |  | 2018-02-20
2STL-60 | RFS.104 | H-M-Q | BAU | Post RFS | 0.1 |  | 2018-02-20
Formulas:
Cycle Time = NETWORKDAYS([Start Date],[End Date],Holiday!$C2:C80)
Cycle Time = NETWORKDAYS([Defect Resolution Start Date],[NSO H/O Date],Holiday!$C2:C80)
Internal Tracking = NETWORKDAYS([DSG Handover Date],[Start Date],Holiday!$C2:C80)-1
Overall Cycle Time = NETWORKDAYS([DSG Handover Date],[NSO H/O Date],Holiday!$C2:C80)

## Transit Allocation
Updated by : |  | Updated on : |  | PNI Load |  |  | Defect Resolution
Transit ID | State | Overall Status | Input Date | Assigned to (PNI Load) | Load Start Date | Load Completion Date | Defects Input Date | Assigned to (Defects) | Defect Resolution Start Date | Defect Resolution End Date | Number of Defects in ConnectMTM | Number of Actual Defects | Final Acceptance | Comments/Issues
3END | VIC | Completed - Final Acceptance Received | 2017-01-28 | Sridhar | 2017-01-28 | 2017-02-01 | 2017-02-01 |  | 2017-08-11 | 2017-08-18 |  |  | 2017-08-23 |  | Ratish Radhakrishnan
2BAN | NSW | Completed - Final Acceptance Received | 2017-01-30 | Sridhar | 2017-01-30 | 2017-02-01 | 2017-02-01 | [5 empty] | 2017-03-12 |  | Nayana Anilkumar
3OAK | VIC | Completed - Final Acceptance Received | 2017-02-01 | Sridhar | 2017-02-01 | 2017-02-02 | 2017-02-02 | [5 empty] | 2017-03-16 |  | Sridhar
4IAL | QLD | Completed - Final Acceptance Received | 2017-03-06 | Sridhar | 2017-03-06 | 2017-03-14 | 2017-03-14 | [5 empty] | 2017-04-07 |  | Rikku
4MGA | QLD | Completed - Final Acceptance Received | 2017-03-06 | Sridhar | 2017-03-06 | 2017-03-17 | 2017-03-17 | [5 empty] | 2017-04-07
5MOD-5GWT | SA | Completed - Final Acceptance Received | 2017-04-08 | Sridhar | 2017-04-08 | 2017-05-09 | 2017-05-09 |  |  |  | 2 | 2 | 2017-06-16
3BAL | VIC | Completed - Final Acceptance Received | 2017-05-01 | Sridhar | 2017-05-01 | 2017-06-15 | 2017-06-15 | [5 empty] | 2017-06-17
3DAN | VIC | Completed - Final Acceptance Received | 2017-05-16 | Sridhar | 2017-05-16 | 2017-07-26 | 2017-07-26 | [5 empty] | 2017-06-21
3FNT | VIC | Completed - Final Acceptance Received | 2017-07-04 | Rikku | 2017-07-14 | 2017-07-26 | 2017-07-26 | [5 empty] | 2017-07-26
3HTL | VIC | Completed - Final Acceptance Received | 2017-07-06 | Rikku | 2017-07-18 | 2017-07-25 | 2017-07-25 | Sridhar |  |  | 38 | 5 | 2017-07-16
4BNP | QLD | Completed - Final Acceptance Received | 2017-07-10 | Krishnan | 2017-07-14 | 2017-07-19 | 2017-07-19 | Sridhar | 2017-07-21 | 2017-07-25 | 1 | 1 | 2017-07-31
3SCO | VIC | Completed - Final Acceptance Received | 2017-07-17 | Krishnan | 2017-07-18 | 2017-08-09 | 2017-08-09 | Sridhar | 2017-08-21 | 2017-08-22 | 1 | 1 | 2017-08-23
3BEA | VIC | Completed - Final Acceptance Received | 2017-07-20 | Rikku | 2017-07-22 | 2017-08-18 | 2017-08-12 |  | 2017-08-23 | 2017-08-25 | 0 | 0 | 2017-08-29
3SPL | VIC | Completed - Final Acceptance Received | 2017-07-20 | Rikku | 2017-07-22 | 2017-08-11 | 2017-08-11 | Sridhar | 2017-08-14 | 2017-08-25 | 3 | 3 | 2017-09-01
6BLA | WA | Completed - Final Acceptance Received | 2017-08-03 |  | 2017-08-28 | 2017-09-04 |  |  |  |  | 0 | 0 | 2017-08-29
2INL | NSW | Completed - Final Acceptance Received | 2017-08-04 | Swathy | 2017-08-10 | 2017-08-14 | 2017-08-15 | Sridhar |  |  | 0 | 0 | 2017-08-15
5NRW | SA | Completed - Final Acceptance Received | 2017-08-08 | Rikku | 2017-08-10 | 2017-08-29 |  |  |  |  | 0 | 0 | 2017-08-18
2ASH | NSW | Completed - Final Acceptance Received | 2017-08-08 | Rikku | 2017-08-22 | 2017-09-08 | 2017-09-26 | Rikku | 2017-09-26 | 2017-09-26 | 1 | 1 | 2017-09-26
2MEN | NSW | Completed - Final Acceptance Received | 2017-08-08 |  | 2017-08-22 | 2017-08-24 | 2017-08-25 |  |  |  | 0 | 0 | 2017-08-28
2ING | NSW | Completed - Final Acceptance Received | 2017-08-11 | Swathy | 2017-08-11 | 2017-08-25 | 2017-08-17 | Rikku | 2017-08-17 | 2017-08-19 | 2 | 2 | 2017-08-31
3WES | VIC | Completed - Final Acceptance Received | 2017-08-22 | Rikku | 2017-08-30 | 2017-09-11 |  |  |  |  | 0 | 0 | 2017-09-15
3BGO | VIC | Completed - Final Acceptance Received | 2017-08-28 |  | 2017-09-11 | 2017-09-15 | 2017-09-19 | Sridhar | 2017-09-19 | 2017-09-19 | 1 | 0 | 2017-09-19
3ELS | VIC | Completed - Final Acceptance Received | 2017-09-08 | Sridhar | 2017-09-11 | 2017-09-11 | 2017-09-15 | Sridhar | 2017-09-15 | 2017-09-19 | 1 | 0 | 2017-09-18
2CMO | NSW | Completed - Final Acceptance Received | 2017-09-11 | Rikku | 2017-09-15 | 2017-09-21 | 2017-09-25 | Rikku | 2017-09-25 | 2017-09-25 | 2 | 2 | 2017-09-25
3WRN | VIC | Completed - Final Acceptance Received | 2017-09-13 | Swathy | 2017-09-15 | 2017-09-21 | 2017-09-25 | Rikku | 2017-09-25 | 2017-09-25 | 8 | 0 | 2017-09-25
3BUL | VIC | Completed - Final Acceptance Received | 2017-09-21 | Sridhar | 2017-09-22 | 2017-09-22 | 2017-09-26 | Sridhar | 2017-09-27 | 2017-09-27 | 3 | 0 | 2017-10-19
2UND | NSW | Completed - Final Acceptance Received | 2017-09-26 | Swathy | 2017-09-26 | 2017-10-02 | 2017-10-27 | Rikku | 2017-10-31 | 2017-10-31 | 4 | 3 | 2017-11-02
2HUR | NSW | Completed - Final Acceptance Received | 2017-10-05 | Swathy | 2017-10-05 | 2017-10-12 |  |  |  |  | 0 | 0 | 2017-10-18
3SND | VIC | Completed - Final Acceptance Received | 2017-10-05 | Sridhar | 2017-10-06 | 2017-10-09 | 2017-10-27 | Sridhar | 2017-11-01 | 2017-11-01 | 1 | 1 | 2017-11-02
2PET | NSW | Completed - Final Acceptance Received | 2017-10-23 | Sridhar | 2017-10-23 | 2017-10-24 | 2017-10-27 |  |  |  | 1 | 0 | 2017-11-02
3SOA | VIC | Completed - Final Acceptance Received | 2017-10-26 | Rikku | 2017-10-27 | 2017-11-01 | 2017-11-02 | Rikku | 2017-11-03 | 2017-11-03 | 2 | 2 | 2017-11-14
4YRG | QLD | Completed - Final Acceptance Received | 2017-11-03 | Rikku | 2017-11-06 | 2017-11-09 | 2017-11-14 | Rikku | 2017-11-17 | 2017-11-20 | 3 | 3 | 2017-11-14
4SYB | QLD | Completed - Final Acceptance Received | 2017-11-08 | Rikku | 2017-11-10 | 2017-11-16 |  |  |  |  | 0 | 0 | 2017-11-20
3ELT | VIC | Completed - Handed over to NDQ | 2017-11-08 | Swathy | 2017-12-19 | 2018-01-02 | 2018-01-08 | Rikku | 2018-01-10 |  | 9 | 9 |  | 9-Nov : Awaiting new payload Ver 3 Load. 17/1: Defect fix in progress
3BNT | VIC | Completed - Final Acceptance Received | 2017-11-16 | Swathy | 2017-11-17 | 2017-11-24 | 2017-11-28 | Rikku | 2017-12-04 | 2017-12-04 | 9 | 9 | 2018-02-05 | 17/1: Defect fix in progress. Resolved
6SUB | WA | Completed - Final Acceptance Received | 2017-11-20 | Rikku | 2017-11-23 | 2017-11-29 | 2018-01-04 | Rikku | 2017-12-04 | 2017-12-05 | 8 | 8 | 2017-12-06 | 16-Nov :Awaiting new payload Ver 2 Payload
6NDL | WA | Completed - Final Acceptance Received | 2017-11-28 | Swathy | 2017-11-29 | 2017-12-15 | 2017-12-20 | Rikku | 2018-01-17 | 2018-01-17 | 2 | 2 | 2018-02-02 | 30-Nov : Rack termination issue [resolved]
6WMB | WA | Completed - Final Acceptance Received | 2017-11-28 | Swathy | 2017-11-29 | 2017-12-06 | 2017-12-11 |  | 2017-12-13 | 2017-12-13 | 4 | 4 | 2018-01-02 | 30-Nov : Rack termination issue Resolved
3IVA | VIC | Completed - Final Acceptance Received | 2017-12-01 | Rikku | 2017-12-04 | 2017-12-12 | 2017-12-20 | Rikku | 2017-12-20 | 2017-12-21 | 4 | 0 | 2018-01-31
6CTO | WA | Completed - Final Acceptance Received | 2017-12-05 | Rikku | 2017-12-05 | 2017-12-08 | 2017-12-12 | Rikku | 2017-12-20 | 2017-12-21 | 3 | 3 | 2018-01-17
3BLB | VIC | Completed - Final Acceptance Received | 2017-12-19 | Rikku | 2017-12-21 | 2017-12-27 | 2018-01-09 | Rikku | 2018-01-09 | 2018-01-12 | 6 | 6 | 2018-01-17
3DCT | VIC | Completed - Final Acceptance Received | 2017-12-21 | Rikku | 2017-12-28 | 2018-01-02 | 2018-01-10 | Rikku | 2018-01-10 | 2018-01-12 | 6 | 4 | 2018-01-15
3GAL | VIC | Completed - Final Acceptance Received | 2017-12-21 | Swathy | 2017-12-28 | 2018-01-09 |  |  |  |  | 0 | 0 | 2018-01-16 | Placed on hold. Boundary table missing in T18. (Resolved)
4CHP | QLD | Completed - Handed over to NDQ | 2018-01-03 | Rikku | 2018-01-03 | 2018-01-09 | 2018-01-31 | Rikku | 2018-01-31 | 2018-01-31 | 3 | 3
2SHA | NSW | On Hold - PNI Load | 2018-01-24 | Rikku | 2018-01-24

## skillset (hidden)
| Skill Set | LDM | DESG - T18 | DESG-PDC | NDQ - IAB | NDQ- FAB | DSG - IAB - HFC | DSG - IAB | DSG - IAB - FTTx | DSG - IAB - Defects | DSG - FAB | DSG - FAB - Defects | Transit Fibre | Aerial AS Built | Sweeper SAMs | Location
Name | Service Line Allocation
Sanjo Lopez | DSG-IAB |  | Y |  |  |  | Y | Y | [7 empty] | Onsite | HDA Program Overall Resource View | DESG-PDC | DESG - T18 | LDM | NDQ - IAB | NDQ- FAB | DSG - IAB - HFC | DSG - IAB | DSG - IAB - FTTx | DSG - IAB - Defects | DSG - FAB | DSG - FAB - Defects | Transit Fiber | Aerial As Built | Sweeper SAMs
Saravanan Kannan | Governance | [14 empty] | Onsite | Total Resources | 16 | 20 | 21 | 17 | 17 |  | 29 |  |  | 18 | 18 | 0 | 1 | 0
Arun Krishna | DESG |  | Y | [12 empty] | Onsite | Allocated Resources | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Arul Dayalan | DSG-IAB | [5 empty] | Y | Y |  | Y | Y |  |  |  |  | Onsite | Available Resources | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Eldhose Joy | LDM | Y | [13 empty] | Onsite | Unavailable Resources | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Pooja Jacob | NDQ |  |  |  | Y | Y | Y | Y |  | Y | [6 empty] | Required resources | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Vinaybhaskar P | NDQ |  |  |  | Y | Y |  |  |  | Y | Y | Y |  |  |  | Onsite | Cross Skilled | 6 | 18 | 6 | 6 | 1 | 0 | 37 |  |  | 6 |  | 4 | 1 | 2
Sree Ram Sundar | NDQ |  |  |  | Y | Y | [9 empty] | Onsite
Jainy Joseph | PDC |  |  | Y
Asha Jacob | PDC |  |  | Y
Lisha Manuel | PDC |  |  | Y
Nina Sebastian | PDC |  |  | Y
Sheeba C | PDC |  |  | Y
Anusa Moottoolikandy | DESG |  | Y
Arunika Joy | LDM | Y | Y
S Shilpa | LDM | Y | Y
Deepa M04 | DESG |  | Y
Dhanya A | PDC |  | Y | Y
Devika Kala | DSG-FAB | Y |  |  |  |  | Y | Y |  |  | Y
SanjanaKrishnan | LDM | Y | Y
Reenu Treesa Peter | DSG-FAB | Y |  |  |  |  | Y | Y |  | Y | Y
Aswathy Baby | DSG-IAB | [5 empty] | Y | Y | Y
Geethu Mol AG | DSG-IAB | [5 empty] | Y | Y | Y | Y
Swathy Mohan | DESG |  | Y |  |  |  | Y | Y |  |  | Y
Abhay Arora | DESG |  | Y |  |  |  | Y | Y |  |  | Y
Shambhavi Chandra | DSG-FAB | Y |  |  |  |  | Y | Y |  |  | Y
Latheefa Ul | DSG-IAB | [5 empty] | Y | Y | Y
Naveen Kumar Nagaraj | DSG-FAB |  | Y |  |  |  | Y | Y |  |  | Y | Y
Renjini R | Automation | Y |  |  |  |  | Y | Y |  |  | Y | Y
Saranya Geetha | LDM | Y |  |  |  |  | Y | Y |  |  | Y | Y
Selva Shobana | Leave | [5 empty] | Y | Y | Y
Sruthi James | DSG-IAB | [5 empty] | Y | Y | Y
Kishore KI | LDM | Y
Revathy A | LDM | Y
Anet Jose | LDM | Y
Saiju Xavier | LDM | Y
Jumana.M | LDM | Y |  | Y
Alan Babu | DESG |  | Y |  |  |  | Y | Y |  | Y
Sree V | NDQ |  |  |  | Y | Y | Y | Y |  | Y
Anju Lisa | NDQ |  |  |  | Y | Y |  |  |  | Y
Manjusha M | LDM | Y |  |  | Y |  |  |  |  | Y
Jowharulla.M | LDM | Y |  |  | Y |  |  |  |  | Y
Lekshmi Balakrishnan | NDQ |  |  |  | Y | Y |  |  |  | Y
Rejitha Retnakaran | NDQ |  |  |  | Y | Y |  |  |  | Y
Hemanth B | Automation
Debjyoti Choudhury | Automation
Chitra VS | Automation
Sushant Jain | Automation
Aravind V | DSG-FAB |  |  |  |  | Y |  | Y |  | Y | Y | Y |  |  |  | Onsite
Bastin Joseph | NDQ |  |  |  | Y | Y |  | Y | Y | [6 empty] | Onsite
Brinson Bovas | DSG-IAB |  |  | Y |  |  |  | Y | Y | Y
Divyamol James | DSG-IAB | [6 empty] | Y | Y | Y
Gouri Gopal | DSG-IAB | [6 empty] | Y | Y | Y | [5 empty] | Onsite
Jijin Isaac | DSG-FAB | [6 empty] | Y | Y | Y | Y | Y |  |  |  | Onsite
Krutika Neelak | DSG-IAB | [6 empty] | Y |  | Y | Y |  |  |  |  | Onsite
Shankar Venkatesan | DSG-IAB | [6 empty] | Y | Y | [6 empty] | Onsite
Shenita | DSG-FAB | [9 empty] | Y | Y |  |  |  | Onsite
Swathy Mohandas | LDM | Y | [13 empty] | Onsite
Tajinder Kaur | LDM | Y | [13 empty] | Onsite
Goutham A S | LDM | Y
ShabeenaShamsudin | LDM | Y
VishnuS | LDM | Y
ChristieThomas | LDM | Y
JadeeraKT | LDM | Y
George | LDM | Y
Ratish Radhakrishnan | DSG-IAB | [6 empty] | Y | Y |  |  |  | Y | Y | Y
Nayana Anilkumar | Aerial-SAM | [6 empty] | Y | Y |  |  |  | Y | Y | Y
Reshma T V | DSG-IAB | [6 empty] | Y | Y
Alphy Manuel | DSG-IAB | [6 empty] | Y | Y
Swathi JS | DSG-IAB | [6 empty] | Y | Y
Midhun RaJ | DSG-IAB |  | Y |  |  |  |  | Y | Y
Reshma Rajan | DSG-FAB | Y | [5 empty] | Y | Y |  | Y | Y
Bhagyalekshmi | DESG |  | Y |  |  |  |  | Y | Y |  | Y | Y
Haritha | DSG-IAB | [6 empty] | Y | Y
Arya PS | DSG-IAB |  | Y |  |  |  |  | Y | Y
Karishma | DSG-IAB | [6 empty] | Y | Y
Karthika V J | DSG-FAB | [6 empty] | Y | Y |  | Y
Roshni Johns | DSG-IAB | [6 empty] | Y | Y
Siva Kumar | DSG-IAB | [6 empty] | Y | Y
Dona Babu | DSG-IAB | [6 empty] | Y | Y
Pankaj Velavan | Backlog |  |  |  | Y |  |  | Y | Y
Shyama P | DSG-FAB | [6 empty] | Y |  |  | Y | Y
Sreelekha K | Backlog | [6 empty] | Y |  |  | Y
Aswathy T | Backlog | [6 empty] | Y |  |  | Y
Nimi Mol | DSG-IAB | [6 empty] | Y | Y
Mary Ann | Backlog |  |  |  | Y |  |  | Y
Amalu Manuel | DSG-FAB | [6 empty] | Y |  | Y | Y | Y
Sriram Rajendra Kumar | DSG-FAB | [6 empty] | Y |  | Y | Y | Y
Reethu Sebastian | DSG-FAB | [6 empty] | Y |  | Y | Y | Y
Girish Chandran | Automation | [6 empty] | Y | Y | Y
Selbee Mathew | Backlog | [6 empty] | Y |  | Y | Y
Bijeta Biswal | DSG-IAB | [6 empty] | Y | Y | Y
Anpu Susan | DSG-IAB | [6 empty] | Y | Y | Y
Nahas Shajahan | DSG-IAB |  |  |  | Y |  |  | Y | Y | Y
Sahishna Krishna | DSG-FAB | [6 empty] | Y |  | Y | Y
Nevin Tom | DSG-FAB | [6 empty] | Y |  | Y | Y | Y
Meera Sudhakumar | DSG-FAB | [6 empty] | Y |  | Y | Y
Naika Arjun | NDQ |  |  |  | Y | Y |  | Y |  | Y
Aleena Johny | DSG-FAB | Y | [5 empty] | Y |  | Y | Y
Athul V | Backlog |  |  |  | Y |  |  | Y
Jiya | NDQ |  |  |  | Y | Y |  | Y |  | Y | Y | Y
Ashok Hariharamoni | DSG-FAB |  | Y | [7 empty] | Y | Y
Varun | PDC |  |  | Y |  |  | Y | Y | Y | [6 empty] | Onsite
Jyothish | NDQ |  |  | Y
Rupesh | Governance |  | Y | [12 empty] | Onsite
Sridhar | Transit |  | Y | [9 empty] | Y |  |  | Onsite
Midhun | DESG |  | Y | [12 empty] | Onsite
Fausia | PDC |  |  | Y
Jyoti | NDQ |  |  | Y | Y | Y |  |  |  |  | Y | Y
Joshlee | PDC |  | Y | Y
Linda | PDC |  | Y | Y
Anila | PDC |  |  | Y
Mythili S | PDC |  |  | Y
Minu | NDQ |  |  | Y | Y
Anuja | PDC |  |  | Y
Parth | DESG |  | Y
Gaurav | DESG |  | Y
Rikku | Transit |  | Y | [9 empty] | Y
Sangeetha | DESG |  | Y
Krishnan | DESG |  | Y
Mohith | DESG |  | Y
Aravind | DESG |  | Y
Mani | DESG |  | Y | Y
Joju | PDC |  | Y | Y
Visakh | Automation |  | Y
Devi Vidyadharan | Automation |  | Y
Nisha | DESG |  | Y
Mahalakshmi | DESG |  | Y
Salil | Governance |  | Y | [12 empty] | Onsite
Kiran | Governance | [14 empty] | Onsite
Rajeev | Governance | [14 empty] | Onsite
Mini | Governance | [14 empty] | Onsite
Nirmal | Governance
Bijesh | Governance
Charles | Governance
Venkatesh H | Governance
Doyle Wilson | Automation
Aneesh Radhakrishnan | Automation
Amritha Praveen | Automation
Shahin Basheer | NDQ |  |  |  | Y | Y |  |  |  | Y | [5 empty] | Onsite
Abhishek Ojha | NDQ |  |  |  | Y
Ashwin Vijayan | NDQ |  |  |  | Y
Janani Murugesan | Leave | [14 empty] | Onsite
Rijo Sunny | DESG |  | Y
Keerthi | PDC |  |  | Y
Sree Lekshmi | PDC |  |  | Y
Reshma Menon | DESG |  | Y
Maria Joy | DESG |  | Y
Vedant | NDQ |  |  |  | Y | Y
Kavya Methil | LDM | Y
Rahul Menon | DSG-IAB | [5 empty] | Y | Y | Y
Aparna Nampoothiri | DSG-IAB | [5 empty] | Y | Y | Y
Anju Philip | DSG-IAB | [5 empty] | Y | Y | Y

## Configurations (hidden)
Effort Matrix (This is used for effort estimation across service lines)
Design Load Iteration
SAM Code | DESG-T18 |  | DESG-PDC |  |  | LDM | DSG |  | NDQ + Defect | DESG-T18(PC) | DESG-T18(GD)
H-B-x | 5 |  | 5 |  |  | 4.5 | 0 |  | 0 | 3 | 2
M-B-x | 5 |  | 5 |  |  | 4.5 | 3 |  | 0 | 3 | 2
H-M-x | 5 |  | 5 |  |  | 4.5 | 0 |  | 0 | 3 | 2
M-M-x | 5 |  | 5 |  |  | 4.5 | 3 |  | 0 | 3 | 2
[10 empty] | 3 | 2
Pre-AT Iteration
SAM Code | DESG |  | DESG-PDC |  |  | LDM | DSG |  | NDQ + Defect | DESG-T18(PC) | DESG-T18(GD)
H-A-x | 6 |  | 5 |  |  | 4.5 | 6 |  | 4 | 3 | 3
M-A-x | 6 |  | 5 |  |  | 4.5 | 9 |  | 8 | 3 | 3
H-M-x | 6 |  | 0 |  |  | 4.5 | 6 |  | 4 | 3 | 3
M-M-x | 6 |  | 0 |  |  | 4.5 | 9 |  | 8 | 3 | 3
H-B-x | 6 |  | 0 |  |  | 4.5 | 6 |  | 5 | 3 | 3
M-B-x | 6 |  | 0 |  |  | 4.5 | 9 |  | 8 | 3 | 3
FAB - Iteration
SAM Code | DESG |  | DESG-PDC |  |  | LDM | DSG |  | NDQ + Defect | DESG-T18(PC) | DESG-T18(GD)
H-A-x | 0 |  | 0 |  |  | 2 | 6 |  | 4 | 0 | 0
M-A-x | 0 |  | 0 |  |  | 2 | 9 |  | 7 | 0 | 0
H-M-x | 0 |  | 0 |  |  | 2 | 6 |  | 4 | 0 | 0
M-M-x | 0 |  | 0 |  |  | 2 | 9 |  | 7 | 0 | 0
Non-RFS Tracks
| PNI Load | Defect Fix
Transit Loads | 4 | 2
Sweeper SAMs | 4 | 0
Aerial Asbuild Loads | 4 | 2
Others
No: of working days per month | 21
Cycle Time Matrix (This is used for shifting the inflow volume across service lines)
Pre-Design Iteration
PDC Expected Date | -30 | T18-30 BD
PDC Cycle Time | 5
Design Load Iteration
SAM Code | DESG-T18(PC) | DESG-T18(GD) | DESG-PDC | DESG-PDC(QA) | DESG-PDC(AFR) | LDM | DSG | NDQ-QA | NDQ-Defect
H-B-x | 3 | 3 | 3 | 3 | 3 | 4 | 0 | 0 | 0
M-B-x | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 0 | 0
H-M-x | 3 | 3 | 3 | 3 | 3 | 4 | 0 | 0 | 0
M-M-x | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 0 | 0
M-A-x | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 0 | 0
Pre-AT Iteration
SAM Code | DESG-T18(PC) | DESG-T18(GD) | DESG-PDC | DESG-PDC(QA) | DESG-PDC(AFR) | LDM | DSG | NDQ-QA | NDQ + Defect
H-A-x | 3 | 3 | 4 | 1 | 1 | 4 | 5 | 2 | 3
M-A-x | 3 | 3 | 4 | 1 | 1 | 4 | 5 | 2 | 3
H-M-x | 3 | 3 | 0 | 0 | 0 | 4 | 5 | 2 | 3
M-M-x | 3 | 3 | 0 | 0 | 0 | 4 | 5 | 2 | 3
H-B-x | 3 | 3 | 0 | 0 | 0 | 4 | 5 | 2 | 3
M-B-x | 3 | 3 | 0 | 0 | 0 | 4 | 5 | 2 | 3
FAB - Iteration
SAM Code | DESG-T18(PC) | DESG-T18(GD) | DESG-PDC | DESG-PDC(QA) | DESG-PDC(AFR) | LDM | DSG | NDQ-QA | NDQ + Defect
H-A-x | 0 | 0 | 0 | 0 | 0 | 2 | 10 | 2 | 3
M-A-x | 0 | 0 | 0 | 0 | 0 | 2 | 10 | 2 | 3
H-M-x | 0 | 0 | 0 | 0 | 0 | 2 | 10 | 2 | 3
M-M-x | 0 | 0 | 0 | 0 | 0 | 2 | 10 | 2 | 3
Non-RFS Tracks
| PNI Load | Defect Fix
Transit Loads | 4 | 2
Sweeper SAMs | 4 | 0
Aerial Asbuild Loads | 4 | 2
Post-RFS LDM+Triage time | 3
Pre-Design Iteration
PDC Expected Date | -30 | T18-30 BD
SAM CODE | DESG-PDC | DESG-PDC(QA) | DESG-PDC(AFR)
H-A-x | 4 | 1 | 1
M-A-x | 4 | 1 | 1
H-M-x | 4 | 1 | 1
M-M-x | 4 | 1 | 1
H-B-x | 4 | 1 | 1
M-B-x | 4 | 1 | 1
|  |  | DESG-PDC | DESG-PDC(QA) | DESG-PDC(AFR)
|  |  | 4 | 1 | 1
|  |  | 4 | 1 | 1
|  |  | 4 | 1 | 1
|  |  | 4 | 1 | 1
|  |  | 4 | 1 | 1
|  |  | 4 | 1 | 1

## Dropdowns
SAMCodes | Program | Gating | Version | FlagValue | Financial Year | Week Start Date | Week End Date | RFS Grp Name | MTM Payload Type | PDC Cleansing type | Entry type | PDC Overall Status | PDC Status | AFR Load Status | LDM Status | DESG Status | DSG-IAB | NDQ-IAB | Defect Resolution IAB | DSG-FAB Status | NDQ-FAB Status | Defect Resolution FAB | Overall Status - NDQ FAB sheet | Transit Fiber
H-A-H | HAC | Design | V1 | Yes | FY 17 | 2016-07-01 | 2017-06-30 | RFS.83 | Design | PDC | Manual | In Queue - To be Assigned | In Progress - Buffering | Not Applicable(Blank AFR) | In Queue - FBR Completed | In Queue - [PC] To be Assigned | In Queue - To be Assigned | In Queue - To be Assigned | In Queue - To be Assigned | In Queue - To be Assigned | In Queue - To be Assigned | In Queue - To be Assigned | In Queue - To be Assigned (QI) | In Queue - To be Assigned (PNI Load)
H-A-J | BAU | Pre-AT | V2 | No | FY 18 | 2017-07-01 | 2017-07-07 | RFS.84 | Pre-AT | Delta PDC |  | In Progress - PDC | In Progress - Buffering Completed | In Queue - To be Assigned | In Queue - To be Assigned | In Progress - [PC] Perform Validation of T18 | In Queue - HFC Completed | In Progress | In Progress | In Queue - Awaiting T18 Lite | In Progress | In Progress | In Queue - To be Assigned (Defect Resolution) | In Progress - PNI Load
H-A-Q |  | Post RFS | V3 |  |  | 2017-07-08 | 2017-07-14 | RFS.85 | Dlite |  |  | In Progress - AFR Load | In Progress - Self QA in Progress | In Progress - AFR Load | In Progress - LocID Matching | In Progress - [PC] Load PNI | In Progress | On Hold | DSG Completed - with External Team for update | In Progress | On Hold | On Hold | In Progress | In Progress - Asset Remediation
M-A-H |  |  | V4 |  |  | 2017-07-15 | 2017-07-21 | RFS.86 |  |  |  | Not Applicable | In Progress - Self QA Completed | On Hold | In Progress - LocID Matching Completed | Not Applicable | In Progress - HFC Completed | Completed | On Hold - Boundary updates | On Hold | Completed | Completed - Handed over to NEO | On Hold | Completed - Handed over to NDQ
M-A-J |  |  | V5 |  |  | 2017-07-22 | 2017-07-28 | RFS.87 |  |  |  | QA Completed - Ready for submission | In Progress - QA In Progress | AFR Load Completed - Ready to Post | In Progress - Repurposing | Completed [PC] - Trigger Triage | On Hold - HFC Completed | Not Applicable | On Hold - LMS updates | Completed | Not Applicable | Completed - Awaiting final Acceptance | Completed - Handed over to NEO | In Queue - To be Assigned (Defects)
M-A-Q | [5 empty] | 2017-07-29 | 2017-08-04 | RFS.88 |  |  |  | PDC completed & AFR Submitted | In Progress - QA Pending | AFR Load Completed & Posted | Not Applicable | On Hold - Awaiting Address File | On Hold - PNI Issues |  | On Hold - Awaiting Design team updates | Rejected |  | In Queue - Awaiting T18 Lite | Completed - Awaiting final Acceptance | In Progress - Defect Fix
H-A-H [P] | [5 empty] | 2017-08-05 | 2017-08-11 | RFS.89 |  |  |  | AFR Load Completed - Ready to Post | QA Completed - Ready for submission |  | In Progress - Repurposing Completed | On Hold - [PC] Data Issues | On Hold - Data Issues |  | Completed - Handed over to NEO | Not Applicable |  |  | Completed - Accepted by NEO | Completed - Defects fixed & notified NDQ
H-A-J [P] | [5 empty] | 2017-08-12 | 2017-08-18 | RFS.90 |  |  |  | AFR Load Completed & Posted | Not Applicable |  | In Progress - Address Alignment | On Hold - [PC] NDD not available | On Hold - Document Unavailability | [6 empty] | Completed - Final Acceptance Received
H-A-Q [P] | [5 empty] | 2017-08-19 | 2017-08-25 | RFS.91 |  |  |  | Rejected | On Hold |  | In Progress - Address Alignment Completed | On Hold - [PC] Awaiting Boundary Update | On Hold - Awaiting Upstream team Updates | [6 empty] | On Hold - PNI Load
M-A-H [P] | [5 empty] | 2017-08-26 | 2017-09-01 | RFS.92 |  |  |  | On Hold | PDC completed & AFR Submitted |  | In Progress - Final Validations | On Hold - [PC] Issues - NBN Internal | Completed | [6 empty] | On Hold - Asset Remediation
M-A-J [P] | [5 empty] | 2017-09-02 | 2017-09-08 | RFS.93 |  |  |  | In Progress-Delta | Rejected |  | Completed - Handover done | On Hold - [PC] GDSS/PNI Issue | Rejected | [6 empty] | On Hold - Defect Fix
M-A-Q [P] |  |  |  | FTTN |  | 2017-09-09 | 2017-09-15 | RFS.94 |  |  |  | Delta completed-Ready for submission | In Progress-Delta |  | On Hold | Rejected - [PC] Sent Back to Telstra (DESG) | Not Applicable
H-B-H |  |  |  | FTTB |  | 2017-09-16 | 2017-09-22 | RFS.95 |  |  |  | Delta completed & AFR submitted | In Progress-Delta completed |  | Rejected | Rejected - [PC] Sent Back to Telstra (LDM)
H-B-J |  |  |  | FTTC |  | 2017-09-23 | 2017-09-29 | RFS.96 |  |  |  |  | In Progress-Delta review |  |  | Rejected - [PC] Sent Back to Telstra (AP) | In Queue - To be Assigned
H-B-Q | [5 empty] | 2017-09-30 | 2017-10-06 | RFS.97 |  |  |  |  | Delta completed-Ready for Submission |  |  | Rejected - [PC] Sent Back to Telstra (Design/NA) | In Progress
M-B-H | [5 empty] | 2017-10-07 | 2017-10-13 | RFS.98 |  |  |  |  | Delta completed & AFR submitted |  |  | In Queue - [GML] To be Assigned | On Hold - PNI Issues
M-B-J | [5 empty] | 2017-10-14 | 2017-10-20 | RFS.99 | [7 empty] | On Hold - [GML] Issues - NBN Internal | On Hold - Data Issues
M-B-Q | [5 empty] | 2017-10-21 | 2017-10-27 | RFS.100 | [7 empty] | On Hold - [GML] PNI Issue | On Hold - Document Unavailability
H-B-H [P] | [5 empty] | 2017-10-28 | 2017-11-03 | RFS.101 | [7 empty] | On Hold - [GML] Awaiting Boundary Update | On Hold - Awaiting Upstream team Updates
H-B-J [P] | [5 empty] | 2017-11-04 | 2017-11-10 | RFS.102 | [7 empty] | In Progress - [GML] PNI Load - Complete Run | Completed
H-B-Q [P] | [5 empty] | 2017-11-11 | 2017-11-17 | RFS.103 | [7 empty] | In Progress - [GML] Generate Trace Report | Rejected
M-B-H [P] | [5 empty] | 2017-11-18 | 2017-11-24 | RFS.104 | [7 empty] | Completed - [GML] Handover to DSG | Not Applicable
M-B-J [P] | [5 empty] | 2017-11-25 | 2017-12-01 | RFS.105 | [7 empty] | Rejected - [GML] Sent Back to Telstra (DESG)
M-B-Q [P] | [5 empty] | 2017-12-02 | 2017-12-08 | RFS.106 | [7 empty] | On Hold - Paused in Triage
H-M-H | [5 empty] | 2017-12-09 | 2017-12-15 | RFS.107 | [7 empty] | Completed - [PC] GDSS Notification
H-M-J | [5 empty] | 2017-12-16 | 2017-12-22 | RFS.108
H-M-Q | [5 empty] | 2017-12-23 | 2017-12-29 | RFS.109
M-M-H | [5 empty] | 2017-12-30 | 2018-01-05 | RFS.110
M-M-J | [5 empty] | 2018-01-06 | 2018-01-12 | RFS.111
M-M-Q | [5 empty] | 2018-01-13 | 2018-01-19 | RFS.112
H-M-H [P] | [5 empty] | 2018-01-20 | 2018-01-26 | RFS.113
H-M-J [P] | [5 empty] | 2018-01-27 | 2018-02-02 | RFS.114
H-M-Q [P] | [5 empty] | 2018-02-03 | 2018-02-09 | RFS.115
M-M-H [P] | [5 empty] | 2018-02-10 | 2018-02-16 | RFS.116
M-M-J [P] | [5 empty] | 2018-02-17 | 2018-02-23 | RFS.117
M-M-Q [P] | [5 empty] | 2018-02-24 | 2018-03-02 | RFS.118
[6 empty] | 2018-03-03 | 2018-03-09 | RFS.119
[6 empty] | 2018-03-10 | 2018-03-16 | RFS.120
[6 empty] | 2018-03-17 | 2018-03-23 | RFS.121
[6 empty] | 2018-03-24 | 2018-03-30 | RFS.122
[6 empty] | 2018-03-31 | 2018-04-06 | RFS.123
[6 empty] | 2018-04-07 | 2018-04-13 | RFS.124
[6 empty] | 2018-04-14 | 2018-04-20 | RFS.125
[6 empty] | 2018-04-21 | 2018-04-27 | RFS.126
[6 empty] | 2018-04-28 | 2018-05-04 | RFS.127
[6 empty] | 2018-05-05 | 2018-05-11 | RFS.128
[6 empty] | 2018-05-12 | 2018-05-18 | RFS.129
[6 empty] | 2018-05-19 | 2018-05-25 | RFS.130
[6 empty] | 2018-05-26 | 2018-06-01 | RFS.131
[6 empty] | 2018-06-02 | 2018-06-08 | RFS.132
[6 empty] | 2018-06-09 | 2018-06-15 | RFS.133
[6 empty] | 2018-06-16 | 2018-06-22 | RFS.134
[6 empty] | 2018-06-23 | 2018-06-29 | RFS.135
[5 empty] | FY 19 | 2018-06-30 | 2018-07-06 | RFS.136
[6 empty] | 2018-07-07 | 2018-07-13 | RFS.137
[6 empty] | 2018-07-14 | 2018-07-20 | RFS.138
[6 empty] | 2018-07-21 | 2018-07-27 | RFS.139
[6 empty] | 2018-07-28 | 2018-08-03 | RFS.140
[6 empty] | 2018-08-04 | 2018-08-10 | RFS.141
[6 empty] | 2018-08-11 | 2018-08-17 | RFS.142
[6 empty] | 2018-08-18 | 2018-08-24 | RFS.143
[6 empty] | 2018-08-25 | 2018-08-31 | RFS.144
[6 empty] | 2018-09-01 | 2018-09-07 | RFS.145
[6 empty] | 2018-09-08 | 2018-09-14 | RFS.146
[6 empty] | 2018-09-15 | 2018-09-21 | RFS.147
[6 empty] | 2018-09-22 | 2018-09-28 | RFS.148
[6 empty] | 2018-09-29 | 2018-10-05 | RFS.149
[6 empty] | 2018-10-06 | 2018-10-12 | RFS.150
[6 empty] | 2018-10-13 | 2018-10-19 | RFS.151
[6 empty] | 2018-10-20 | 2018-10-26 | RFS.152
[6 empty] | 2018-10-27 | 2018-11-02 | RFS.153
[6 empty] | 2018-11-03 | 2018-11-09 | RFS.154
[6 empty] | 2018-11-10 | 2018-11-16 | RFS.155
[6 empty] | 2018-11-17 | 2018-11-23 | RFS.156
[6 empty] | 2018-11-24 | 2018-11-30 | RFS.157
[6 empty] | 2018-12-01 | 2018-12-07 | RFS.158
[6 empty] | 2018-12-08 | 2018-12-14 | RFS.159
[6 empty] | 2018-12-15 | 2018-12-21 | RFS.160
[6 empty] | 2018-12-22 | 2018-12-28 | RFS.161
[6 empty] | 2018-12-29 | 2019-01-04 | RFS.162
[6 empty] | 2019-01-05 | 2019-01-11 | RFS.163
[6 empty] | 2019-01-12 | 2019-01-18 | RFS.164
[6 empty] | 2019-01-19 | 2019-01-25 | RFS.165
[6 empty] | 2019-01-26 | 2019-02-01 | RFS.166
[6 empty] | 2019-02-02 | 2019-02-08 | RFS.167
[6 empty] | 2019-02-09 | 2019-02-15 | RFS.168
[6 empty] | 2019-02-16 | 2019-02-22 | RFS.169
[6 empty] | 2019-02-23 | 2019-03-01 | RFS.170
[6 empty] | 2019-03-02 | 2019-03-08 | RFS.171
[6 empty] | 2019-03-09 | 2019-03-15 | RFS.172
[6 empty] | 2019-03-16 | 2019-03-22 | RFS.173
[6 empty] | 2019-03-23 | 2019-03-29 | RFS.174
[6 empty] | 2019-03-30 | 2019-04-05 | RFS.175
[6 empty] | 2019-04-06 | 2019-04-12 | RFS.176
[6 empty] | 2019-04-13 | 2019-04-19 | RFS.177
[6 empty] | 2019-04-20 | 2019-04-26 | RFS.178
[6 empty] | 2019-04-27 | 2019-05-03 | RFS.179
[6 empty] | 2019-05-04 | 2019-05-10 | RFS.180
[6 empty] | 2019-05-11 | 2019-05-17 | RFS.181
[6 empty] | 2019-05-18 | 2019-05-24 | RFS.182
[6 empty] | 2019-05-25 | 2019-05-31 | RFS.183
[6 empty] | 2019-06-01 | 2019-06-07 | RFS.184
[6 empty] | 2019-06-08 | 2019-06-14 | RFS.185
[6 empty] | 2019-06-15 | 2019-06-21 | RFS.186
[6 empty] | 2019-06-22 | 2019-06-28 | RFS.187
[6 empty] | 2019-06-29 | 2019-07-05 | RFS.188
[5 empty] | FY 20 | 2019-07-06 | 2019-07-12 | RFS.189
[6 empty] | 2019-07-13 | 2019-07-19 | RFS.190
[6 empty] | 2019-07-20 | 2019-07-26 | RFS.191
[6 empty] | 2019-07-27 | 2019-08-02 | RFS.192
[6 empty] | 2019-08-03 | 2019-08-09 | RFS.193
[6 empty] | 2019-08-10 | 2019-08-16 | RFS.194
[6 empty] | 2019-08-17 | 2019-08-23 | RFS.195
[6 empty] | 2019-08-24 | 2019-08-30 | RFS.196
[6 empty] | 2019-08-31 | 2019-09-06 | RFS.197
[6 empty] | 2019-09-07 | 2019-09-13 | RFS.198
[6 empty] | 2019-09-14 | 2019-09-20 | RFS.199
[6 empty] | 2019-09-21 | 2019-09-27 | RFS.200
[6 empty] | 2019-09-28 | 2019-10-04 | RFS.201
[6 empty] | 2019-10-05 | 2019-10-11 | RFS.202

## Holiday (hidden)
| NSW and VIC Holidays | Date | Offshore Holidays | Financial Year | Week Start Date | Week End Date | RFS Grp Name
2016 | New Year's Day | 2016-01-01 | 2017-01-26 | FY 17 | 2016-07-01 | 2017-06-30 | RFS.83
| Australia Day | 2016-01-26 | 2017-04-14 | FY 18 | 2017-07-01 | 2017-07-07 | RFS.84
| Labour Day (Vic) | 2016-03-14 | 2017-05-01 |  | 2017-07-08 | 2017-07-14 | RFS.85
| Good Friday | 2016-03-25 | 2017-06-26 |  | 2017-07-15 | 2017-07-21 | RFS.86
| Easter Monday | 2016-03-28 | 2017-08-15 |  | 2017-07-22 | 2017-07-28 | RFS.87
| Anzac Day | 2016-04-25 | 2017-09-04 |  | 2017-07-29 | 2017-08-04 | RFS.88
| Queen's Birthday | 2016-06-13 | 2017-09-05 |  | 2017-08-05 | 2017-08-11 | RFS.89
| Friday before Grand Final (Vic) | 2016-09-30 | 2017-10-02 |  | 2017-08-12 | 2017-08-18 | RFS.90
| Labour Day (NSW) | 2016-10-03 | 2017-10-18 |  | 2017-08-19 | 2017-08-25 | RFS.91
| Melbourne Cup | 2016-11-01 | 2017-12-25 |  | 2017-08-26 | 2017-09-01 | RFS.92
| Boxing Day | 2016-12-26 |  |  | 2017-09-02 | 2017-09-08 | RFS.93
| Christmas Day (In Lieu) | 2016-12-27 |  |  | 2017-09-09 | 2017-09-15 | RFS.94
2017 | New Year's Day | 2017-01-02 |  |  | 2017-09-16 | 2017-09-22 | RFS.95
| Australia Day | 2017-01-26 |  |  | 2017-09-23 | 2017-09-29 | RFS.96
| Labour Day (Vic) | 2017-03-13 |  |  | 2017-09-30 | 2017-10-06 | RFS.97
| Good Friday | 2017-04-14 |  |  | 2017-10-07 | 2017-10-13 | RFS.98
| Easter Monday | 2017-04-17 |  |  | 2017-10-14 | 2017-10-20 | RFS.99
| Anzac Day | 2017-04-25 |  |  | 2017-10-21 | 2017-10-27 | RFS.100
| Queen's Birthday | 2017-06-12 |  |  | 2017-10-28 | 2017-11-03 | RFS.101
| Friday before Grand Final (Vic) | 2017-09-29 |  |  | 2017-11-04 | 2017-11-10 | RFS.102
| Labour Day (NSW) | 2017-10-02 |  |  | 2017-11-11 | 2017-11-17 | RFS.103
| Melbourne Cup | 2017-11-07 |  |  | 2017-11-18 | 2017-11-24 | RFS.104
| Christmas Day | 2017-12-25 |  |  | 2017-11-25 | 2017-12-01 | RFS.105
| Boxing Day (In Lieu) | 2017-12-26 |  |  | 2017-12-02 | 2017-12-08 | RFS.106
| Offshore Holidays | 2017-01-26 |  |  | 2017-12-09 | 2017-12-15 | RFS.107
| Offshore Holidays | 2017-04-14 |  |  | 2017-12-16 | 2017-12-22 | RFS.108
| Offshore Holidays | 2017-05-01 |  |  | 2017-12-23 | 2017-12-29 | RFS.109
| Offshore Holidays | 2017-06-26 |  |  | 2017-12-30 | 2018-01-05 | RFS.110
| Offshore Holidays | 2017-08-15 |  |  | 2018-01-06 | 2018-01-12 | RFS.111
| Offshore Holidays | 2017-09-04 |  |  | 2018-01-13 | 2018-01-19 | RFS.112
| Offshore Holidays | 2017-09-05 |  |  | 2018-01-20 | 2018-01-25 | RFS.113
| Offshore Holidays | 2017-10-02 |  |  | 2018-01-27 | 2018-02-02 | RFS.114
| Offshore Holidays | 2017-10-18 |  |  | 2018-02-03 | 2018-02-09 | RFS.115
| Offshore Holidays | 2017-12-25 |  |  | 2018-02-10 | 2018-02-16 | RFS.116
2018 | New Year's Day | 2018-01-01 |  |  | 2018-02-17 | 2018-02-23 | RFS.117
| Australia Day | 2018-01-26 |  |  | 2018-02-24 | 2018-03-02 | RFS.118
| Labour Day (Vic) | 2018-03-12 |  |  | 2018-03-03 | 2018-03-09 | RFS.119
| Good Friday | 2018-03-30 |  |  | 2018-03-10 | 2018-03-16 | RFS.120
| Easter Monday | 2018-04-02 |  |  | 2018-03-17 | 2018-03-23 | RFS.121
| Anzac Day | 2018-04-25 |  |  | 2018-03-24 | 2018-03-29 | RFS.122
| Queen's Birthday | 2018-06-11 |  |  | 2018-03-31 | 2018-04-06 | RFS.123
| Friday before Grand Final (Vic) | 2018-09-28 |  |  | 2018-04-07 | 2018-04-13 | RFS.124
| Labour Day (NSW) | 2018-10-01 |  |  | 2018-04-14 | 2018-04-20 | RFS.125
| Melbourne Cup | 2018-11-06 |  |  | 2018-04-21 | 2018-04-27 | RFS.126
| Boxing Day | 2018-12-26 |  |  | 2018-04-28 | 2018-05-04 | RFS.127
| Christmas Day (In Lieu) | 2018-12-25 |  |  | 2018-05-05 | 2018-05-11 | RFS.128
| Offshore Holidays (Holi) | 2018-03-02 |  |  | 2018-05-12 | 2018-05-18 | RFS.129
| Offshore Holidays(May Day) | 2018-05-01 |  |  | 2018-05-19 | 2018-05-25 | RFS.130
| Offshore Holidays(Id) | 2018-06-15 |  |  | 2018-05-26 | 2018-06-01 | RFS.131
| Offshore Holidays(Independence) | 2018-08-15 |  |  | 2018-06-02 | 2018-06-08 | RFS.132
| Offshore Holidays(1st Onam) | 2018-08-24 |  |  | 2018-06-09 | 2018-06-15 | RFS.133
| Offshore Holidays(4th Onam) | 2018-08-27 |  |  | 2018-06-16 | 2018-06-22 | RFS.134
| Offshore Holidays(Gandhi Jayanti) | 2018-10-02 |  |  | 2018-06-23 | 2018-06-29 | RFS.135
| Offshore Holidays(Vijayadashami) | 2018-10-19 |  | FY 19 | 2018-06-30 | 2018-07-06 | RFS.136
| Offshore Holidays(Deepavali) | 2018-12-06 |  |  | 2018-07-07 | 2018-07-13 | RFS.137
[5 empty] | 2018-07-14 | 2018-07-20 | RFS.138
[5 empty] | 2018-07-21 | 2018-07-27 | RFS.139
[5 empty] | 2018-07-28 | 2018-08-03 | RFS.140
[5 empty] | 2018-08-04 | 2018-08-10 | RFS.141
[5 empty] | 2018-08-11 | 2018-08-17 | RFS.142
[5 empty] | 2018-08-18 | 2018-08-24 | RFS.143
[5 empty] | 2018-08-25 | 2018-08-31 | RFS.144
[5 empty] | 2018-09-01 | 2018-09-07 | RFS.145
[5 empty] | 2018-09-08 | 2018-09-14 | RFS.146
[5 empty] | 2018-09-15 | 2018-09-21 | RFS.147
[5 empty] | 2018-09-22 | 2018-09-28 | RFS.148
[5 empty] | 2018-09-29 | 2018-10-05 | RFS.149
[5 empty] | 2018-10-06 | 2018-10-12 | RFS.150
[5 empty] | 2018-10-13 | 2018-10-19 | RFS.151
[5 empty] | 2018-10-20 | 2018-10-26 | RFS.152
[5 empty] | 2018-10-27 | 2018-11-02 | RFS.153
[5 empty] | 2018-11-03 | 2018-11-09 | RFS.154
[5 empty] | 2018-11-10 | 2018-11-16 | RFS.155
[5 empty] | 2018-11-17 | 2018-11-23 | RFS.156
[5 empty] | 2018-11-24 | 2018-11-30 | RFS.157
[5 empty] | 2018-12-01 | 2018-12-07 | RFS.158
[5 empty] | 2018-12-08 | 2018-12-14 | RFS.159
[5 empty] | 2018-12-15 | 2018-12-21 | RFS.160
[5 empty] | 2018-12-22 | 2018-12-28 | RFS.161
[5 empty] | 2018-12-29 | 2019-01-04 | RFS.162
[5 empty] | 2019-01-05 | 2019-01-11 | RFS.163
[5 empty] | 2019-01-12 | 2019-01-18 | RFS.164
[5 empty] | 2019-01-19 | 2019-01-25 | RFS.165
[5 empty] | 2019-01-26 | 2019-02-01 | RFS.166
[5 empty] | 2019-02-02 | 2019-02-08 | RFS.167
[5 empty] | 2019-02-09 | 2019-02-15 | RFS.168
[5 empty] | 2019-02-16 | 2019-02-22 | RFS.169
[5 empty] | 2019-02-23 | 2019-03-01 | RFS.170
[5 empty] | 2019-03-02 | 2019-03-08 | RFS.171
[5 empty] | 2019-03-09 | 2019-03-15 | RFS.172
[5 empty] | 2019-03-16 | 2019-03-22 | RFS.173
[5 empty] | 2019-03-23 | 2019-03-29 | RFS.174
[5 empty] | 2019-03-30 | 2019-04-05 | RFS.175
[5 empty] | 2019-04-06 | 2019-04-12 | RFS.176
[5 empty] | 2019-04-13 | 2019-04-19 | RFS.177
[5 empty] | 2019-04-20 | 2019-04-26 | RFS.178
[5 empty] | 2019-04-27 | 2019-05-03 | RFS.179
[5 empty] | 2019-05-04 | 2019-05-10 | RFS.180
[5 empty] | 2019-05-11 | 2019-05-17 | RFS.181
[5 empty] | 2019-05-18 | 2019-05-24 | RFS.182
[5 empty] | 2019-05-25 | 2019-05-31 | RFS.183
[5 empty] | 2019-06-01 | 2019-06-07 | RFS.184
[5 empty] | 2019-06-08 | 2019-06-14 | RFS.185
[5 empty] | 2019-06-15 | 2019-06-21 | RFS.186
[5 empty] | 2019-06-22 | 2019-06-28 | RFS.187
[5 empty] | 2019-06-29 | 2019-07-05 | RFS.188
|  |  |  | FY 20 | 2019-07-06 | 2019-07-12 | RFS.189
[5 empty] | 2019-07-13 | 2019-07-19 | RFS.190
[5 empty] | 2019-07-20 | 2019-07-26 | RFS.191
[5 empty] | 2019-07-27 | 2019-08-02 | RFS.192
[5 empty] | 2019-08-03 | 2019-08-09 | RFS.193
[5 empty] | 2019-08-10 | 2019-08-16 | RFS.194
[5 empty] | 2019-08-17 | 2019-08-23 | RFS.195
[5 empty] | 2019-08-24 | 2019-08-30 | RFS.196
[5 empty] | 2019-08-31 | 2019-09-06 | RFS.197
[5 empty] | 2019-09-07 | 2019-09-13 | RFS.198
[5 empty] | 2019-09-14 | 2019-09-20 | RFS.199
[5 empty] | 2019-09-21 | 2019-09-27 | RFS.200
[5 empty] | 2019-09-28 | 2019-10-04 | RFS.201
[5 empty] | 2019-10-05 | 2019-10-11 | RFS.202

## TEMP (hidden)
PRE-AT/DESIGN -Rejected SAMs | Post RFS -Rejected SAMs | DSG IAB Rejected SAMs | DSG FAB Rejected SAMs
2ASH-63 | 3WER-64 |  |  | 5WES-63
2BAM-64 | 4CPB-61 |  |  | 4ASH-61
4SRW-60 | 5FLN-62 |  |  | 4SRW-60
5WES-65 | 2SEF-61 |  |  | 2RDL-61
5WES-63 | 4SLA-67 |  |  | 2CAS-65
2CAS-65 | 3DRP-61 |  |  | 2MEN-61
2MEN-61 | 5MOD-63 |  |  | 4CHL-66
4CHL-66 | 4SUR-61 |  |  | 4CHL-66
2RDL-61 | 4EMP-64 |  |  | 3CTA-64
4SUR-61 | 2NSY-64 |  |  | 2PET-66
4EMP-64 | 3DNC-62 |  |  | 2PET-66
2CAS-65 | 3DNC-62
2NSY-64 | 3DNC-62
2MEN-61 | 3DNC-62
3DNC-62 | 5SAL-64
4CHL-66 | 3CTA-63
4CHL-66
2PET-66
3DNC-62
3CTA-64
2PET-66
2PET-66
2PET-66

## D-Lite Allocation
[6 empty] | LDM Track | [7 empty] | DESG Track | [7 empty] | DSG Track |  |  |  |  | NDQ | [5 empty] | DEFECT MANAGEMENt
[6 empty] | Temp ID creation |  |  |  | Address Alignment and Validations |  |  |  | Performance Checks[PC] |  |  |  | PNI Load [GML] |  |  |  | MTM Data Load | [5 empty] | MTM Data Checks |  |  |  |  | Defect Resolution
SAM | Type | Program | Gate | Version | T18 Input | Assigned To | Status | Start Date | End Date | Start Date | End Date | EUP Count | Actual LDM Handover Date | Assigned To | Status | PC Start Date | PC End Date | Assigned To | GML Start Date | GML End Date | DSG H/O date | Assigned To | Status | Start Date | End Date | NEO/NDQ H/o date /NDD Reuested | NDQ Input Date | Assigned To | Status | Start Date | End Date | Overall QI Completion Date | Assigned To | Status | Start Date | End Date | No. of Pre RFS Defects | No. of Post RFS Defects | Major FTTN | Minor FTTN | Open/FAB Defects | External Defects | NSO H/o Date | Remarks
3WHL-65 | (M-A-J) | BAU | Post RFS |  | 2017-10-05 | Saiju Xavier | Completed | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-16 |  | 2017-10-16 | [8 empty] | Reshma TV | Completed | 2017-10-23 | 2017-10-26 | 2017-10-26 | [6 empty] | Sriram rajendrakumar | Completed | 2017-11-08 | 2017-11-14 |  | 10 | 10 |  |  |  | 2017-12-18
4CPB-61 | (M-A-J) | BAU | Post RFS
3HGT-60 | (M-A-J) | BAU | Post RFS |  | 2018-01-25 | Arunika Joy | In Progress | 2018-01-25 | 2018-01-30 | 2018-01-30 | 2018-01-30 |  | 2018-01-30
4ASH-66 | (M-M-J) | BAU | Post RFS |  | 2017-10-06 | Saiju Xavier | Completed | 2017-10-06 | 2017-10-08 | 2017-10-08 | 2017-10-08 |  | 2017-10-08 | Aravind | Handed over to FAB | 2017-12-19 | 2017-12-20 | Aravind | 2017-12-20 | 2017-12-21 | 2017-12-21 | Nevin Tom | Inprogress | 2017-12-27 | 2018-01-12 | 2018-01-12
3DRP-63 | (M-M-H) | BAU | Post RFS
3FNT-63 | (M-M-H) | BAU | Post RFS |  | 2017-10-07 | ChristieThomas | Completed | 2017-10-08 | 2017-10-11 | 2017-10-11 | 2017-10-11 |  | 2017-10-11
4EMP-61 | (M-M-H) | BAU | Post RFS |  | 2017-09-01 | George | Completed | 2017-09-01 | 2017-09-06 | 2017-09-06 | 2017-09-06 |  | 2017-09-06
4SLA-67 | (M-A-H) | BAU | Post RFS
3DRP-61 | (M-A-H) | BAU | Post RFS
2ING-63 | (M-A-H) | BAU | Post RFS
4BNP-63 | (M-A-H) | BAU | Post RFS |  | 2017-12-11 | Anet | Completed | 2017-12-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 |  | 2018-01-12
5SAL-60 | (M-A-H) | BAU | Post RFS
5SAL-61 | (M-A-H) | BAU | Post RFS
3DAN-63 | (M-A-H) | BAU | Post RFS
3WER-65 | (M-A-H) | BAU | Post RFS
2FRE-65 | (M-A-H) | BAU | Post RFS
2EDG-66 | (M-A-H) | BAU | Post RFS
4BUR-67 |  | BAU | Post RFS
3TNI-62 |  | BAU | Post RFS
6SUB-65 | (M-A-H) | BAU | Post RFS
6SUB-64 | (M-A-H) | BAU | Post RFS
2FRE-61 |  | BAU | Post RFS
5EDW-67 | (M-A-H) | BAU | Post RFS
2PNN-68 |  | BAU | Post RFS
3NCO-60 | (M-A-H) | BAU | Post RFS
4OXE-61 |  | BAU | Post RFS
4MGB-62 | (M-M-H) | BAU | Post RFS |  | 2017-10-06 | ChristieThomas | Completed | 2017-10-06 | 2017-10-07 | 2017-10-07 | 2017-10-07 |  | 2017-10-07
3NAW-65 | (M-A-H) | BAU | Post RFS
2MEN-63 | (M-A-H) | BAU | Post RFS
5MOD-63 | (M-A-J) | BAU | Post RFS
3NAW-61 | (M-A-H) | BAU | Post RFS
2MIL-63 |  | BAU | Post RFS
3TNI-64 |  | BAU | Post RFS
2CAS-66 |  | BAU | Post RFS
2MIL-60 |  | BAU | Post RFS
5EDW-63 | (M-A-H) | BAU | Post RFS
2BAL-64 |  | BAU | Post RFS
2ING-64 |  | BAU | Post RFS
4SSB-61 |  | BAU | Post RFS
4WTF-61 |  | BAU | Post RFS
6GIR-64 |  | BAU | Post RFS
2HLS-61 |  | BAU | Post RFS
2PYM-62 |  | BAU | Post RFS
3NBA-67 |  | BAU | Post RFS
4SOP-64 |  | BAU | Post RFS
4CHD-61 |  | BAU | Post RFS
4CUR-61 |  | BAU | Post RFS
2CRR-60 | (M-M-H) | BAU | Post RFS
4CHD-21 |  | BAU | Post RFS
4CUR-63 |  | BAU | Post RFS
3NBA-65 | (M-A-H) | BAU | Post RFS
4SLA-60 | (M-A-H) | BAU | Post RFS